## 基站数据
基站数据
Physical Plan Site ID | Longitude | Latitude | Area Type | Site Type | New Site Type | Year | Bands | Region | Province | City/Municipality | Barangay | Area | brgy_code | brgy_pop | Height (m) | Tower Type | CO Homing | Distance (km) | S/N | Priority | Phase(baseline) | Phase (2020_v1) | Phase (2020_v2) | Friendly Site | Cluster | SAQ Vendor | SAQ PO Number | SAQ PO Batch | TSS/DDD Vendor | TSS/DDD PO Number | CME Vendor | CME PO Number | SARF Issued | Survey Done Plan | Survery Done Actual | Submitted Plan | Submitted Option A | Submitted Option B | Submitted Option C | Submitted Option D | Submitted Actual | Reviewed Option A | Reviewed Option B | Reviewed Option C | Reviewed Option D | Reviewed Actual | SAR Remarks | 1st Revision | 2nd Revision | Approved Plan | Approved Option A | Approved Option B | Approved Option C | Approved Option D | Approved Actual | MOC Signed Option A | MOC Signed Option B | MOC Signed Option C | MOC Signed Option D | MOC Signed Actual | MOC Submitted Actual | MOC Approved Plan | MOC Approved Actual | MOC for Renego | MOC Remarks | NRAF Submitted Actual | NRAF Approved Actual | Approved Option | Lessor Name | Site Address | Province | ACT Longitude | ACT Latitude | Site Type | Altitude(m) | Building Height (RT)(m) | Period of Lease | Monthly Rent | Payment | Lease Area | Advance Rental | Security Deposit | Escalation Rate | Neighbors Actual | No Neighbors Actual | Name of Subdivision/HOA | Name of HOA President | HOA President Contact No. | HOA Clearance Secured | BrgyClearance Plan | BrgyClearance Applied | BrgyClearance Actual | BrgyResolution Applied | BrgyResolution Plan | BrgyResolution Actual | Property Docs Plan | Tax Declaration Secured | Tax Clearance Secured | TCT Secured | Segregation Plan Signed | Conceptual Drawing Signed | Other Documents | TIN | Bank Details (Account Name & Number) | Lessor Contact | Lessor Address | Lessor Information Sheet Signed by Lessor | Land Classification | Existing Building Permit for RT site | As-Built Plan for RT Site | TPCA / SPCA | Lease Package Plan | Lessor ID | Lease Package Submitted | Draft COL Plan | Draft COL Signed by Lessor | COL Approved by Legal | CRAF Submitted Actual | CRAF Approved Actual | COL Signed by DITO | COL Signed by Lessor | COL Signed Plan | COL Signed Actual | RFP Submitted by Vendor | RFP Approved | Rental Paid Plan | Released Cheque to Vendor | Released Cheque to Lessor | AR/OR Submitted to Dito | Remarks | SBT/SI Done Plan | SBT/SI Done Actual | SBT/SI Report Plan | SBT/SI Report Submitted | SBT/SI Report Approved | TSS Done Plan | TSS Done Actual | TSSR Submitted Plan | TSSR Submitted Actual | TSSR Approved Actual | DDD Submitted Plan | Prelim DDD Submitted | Prelim DDD Approved | DDD Submitted Actual | DDD Approved Plan | DDD Approved Actual | Tower Type | Tower (m) | Tower Ordering | Tower Delivery on Site_Plan | Tower Delivery on Site_Actual | Telecom Equipment Delivery On Site_Actual | Facility Telecom Delivery On Site_Actual | National Permit Plan | DENR-CNC Applied | DENR-CNC Acquired | DOH Applied | DOH Acquired | ATO/CAAP Applied | ATO/CAAP Acquired | Natl Completed Plan | LGU Permit Plan | Zoning Applied | Zoning Acquired | Locational Applied | Locational Acquired | SB/SP Resolution Applied | SB/SP Resolution Acquired | Mayors Permit Secured | Building Permit Applied | Building Permit Secured | Electrical Permit Applied | Electrical Permit Secured | Mechanical Permit Applied | Mechanical Permit Secured | Electronics Permit Applied | Electronics Permit Secured | Fencing Permit Applied | Fencing Permit Secured | Sanitary Permit Applied | Sanitary Permit Secured | Sanitary Permit Secured | FSEC Acquired | LGU Completed Plan | BOM | Copy of BP OR | Remarks | RTB Declared Plan | RTB Declared Actual | CFEI Applied | CFEI Acquired | Occupancy Permit Applied | Occupancy Permit Secured | FSIC Applied | FSIC Acquired | SKOM Actual | Mobilization Plan | Mobilization Actual | Excavation Plan | Excavation Actual | Lean Concrete Completion | Rebars Plan | Rebar Installation | Rebar Testing | Rebar Inspection | Concrete Plan | Concrete Pouring Completed | Concrete Testing | Back Filling Plan | Back Filling Actual | ODU Pad Started | ODU Pad Completed | Electrical Grounding Plan | Electrical Works Actual | Tower Erection Started | Tower Erection Plan | Tower Erection Completed | Tower Verticality | Site Dev Works Completed (RFI) | Tempo Power Plan | Tempo Power Connected | RFTI Plan | RFTI Actual | Pre-PAT Actual | PAT Plan | PAT Passed Actual | TX Solution | TX Installed Actual | MOS Plan | MOS Actual | BTS Installation Completed | Integrated Plan | Integrated Actual | RFS Plan | RFS Actual | Permanent Power Applied | Joint Inspection Survey with COOP | Charge Letter Acquired | Power Payment RFP Submitted | Power Payment RFP Released | Line Construction | Energized Plan | Energized Actual | Electrical PAT | Site Utility Contract Submitted | Meter Serial Number | Electric Cooperative | Remarks
Physical Plan Site ID | LONG | LAT | Area Type | Site Type | New Site Type | Year | Bands | Region | Province | City/Municipality | Barangay | Area | brgy_code | brgy_pop | Height (m) | Tower Type | CO Homing | Distance (km) | S/N | Priority | Phase (baseline) | Phase (2020_v1) | Phase (2020_v2) | Friendly Site | SAQ Clustering | SAQ Vendor | SAQ PO Number | SAQ PO Batch | TSS/DDD Vendor | TSS/DDD PO Number | CME Vendor | CME PO Number | SARF Issued | Survey Done_ Plan | Survery Done_ Actual | Submitted_ Plan | Submitted_ Option A | Submitted_ Option B | Submitted_ Option C | Submitted_ Option D | Submitted_ Actual | Reviewed_ Option A | Reviewed_ Option B | Reviewed_ Option C | Reviewed_ Option D | Reviewed_ Actual | SAR Remarks | 1st Revision | 2nd Revision | Approved_ Plan | Approved_ Option A | Approved_ Option B | Approved_ Option C | Approved_ Option D | Approved_ Actual | MOC Signed_ Option A | MOC Signed_ Option B | MOC Signed_ Option C | MOC Signed_ Option D | MOC Signed_ Actual | MOC Submitted_ Actual | MOC Approved_ Plan | MOC Approved_ Actual | MOC for Renego | MOC Remarks | NRAF Submitted_ Actual | NRAF Approved_ Actual | Approved Option | Lessor Name | Site Address | Province | LONG | LAT | Site Type | Altitude | Building Height (RT) | Period of Lease | Monthly Rent | Payment | Lease Area | Advance Rental | Security Deposit | Escalation Rate | Neighbor's_ Actual | No Neighbors_ Actual | Name of Subdivision/HOA | Name of HOA President | HOA President Contact No. | HOA Clearance_ Secured | BrgyClearance_ Plan | BrgyResolution_ Applied | BrgyClearance_ Actual | BrgyResolution_ Plan | BrgyResolution_ Actual | Property Docs_ Plan | Tax Declaration_ Secured | Tax Clearance_ Secured | TCT_ Secured | Segregation Plan Signed | Conceptual Drawing Signed | Lessor Information Sheet Signed by Lessor | TPCA / SPCA | TIN | Bank Account Name | Bank Name/Branch | Bank Account Number | Lessor Contact | Lessor Address | Land Classification | Existing Building Permit for RT site | As-Built Plan for RT Site | Lease Package_ Plan | Lessor ID | Property Docs Completed | Draft COL_ Plan | Draft COL Signed | COL Approved | CRAF Submitted_ Actual | CRAF Approved_ Actual | COL Signed by DITO | COL Signed by Lessor | COL Signed_ Plan | COL Signed_ Actual | RFP Submitted to DITO | RFP Approved | Rental Paid_ Plan | Released Cheque to Vendor | Cheque Received by Lessor | AR Submitted to DITO | Remarks | SBT/SI Done_ Plan | SBT/SI Done_ Actual | SBT/SI Report_ Plan | SBT/SI Report Submitted | SBT/SI Report Approved | TSS Done_ Plan | TSS Done_ Actual | TSSR Submitted_ Plan | TSSR Submitted_ Actual | TSSR Approved_ Actual | DDD Submitted_ Plan | TE DDD Submitted | TE DDD Approved | CW DDD Submitted | DDD Approved_ Plan | CW DDD Approved | Tower Type | Tower (m) | Tower Ordering | Tower Delivery on Site_Plan | Tower Delivery on Site_Actual |  |  | National Permit_ Plan | DENR-CNC_ Applied | DENR-CNC_ Acquired | DOH_ Applied | DOH_ Acquired | ATO/CAAP_ Applied | ATO/CAAP_ Acquired | Natl Completed_ Plan | LGU Permit_ Plan | SB/SP Resolution Applied | SB/SP Resolution Acquired | Mayor's Permit _Secured | LC/Zoning_ Applied | Zoning_ Acquired | Locational_ Acquired | Building Permit_Applied | Building Permit_Secured | Electrical Permit_Applied | Electrical Permit_Secured | Mechanical Permit_Applied | Mechanical Permit_Secured | Electronics Permit_Applied | Electronics Permit_Secured | Fencing Permit_Applied | Fencing Permit_Secured | Sanitary Permit_Applied | Sanitary Permit_Secured | FSEC_ Applied | FSEC_ Acquired | LGU Completed_ Plan | BOM | Copy of BP OR | Remarks | RTB Declared_ Plan | RTB Declared_ Actual | CFEI_Applied | CFEI_Acquired | Occupancy Permit_Applied | Occupancy Permit_Secured | FSIC_Applied | FSIC_Acquired | SKOM_ Actual | Mobilization_ Plan | Mobilization_ Actual | Excavation_ Plan | Excavation_ Actual | Lean Concrete Completion | Rebars_ Plan | Rebar Installation | Rebar Testing | Rebar Inspection | Concrete_ Plan | Concrete Pouring Completed | Concrete Testing | Back Filling_ Plan | Back Filling_ Actual | ODU Pad Started | ODU Pad Completed | Electrical/ Grounding_Plan | Electrical Works_Actual | Tower Erection Started | Tower Erection_ Plan | Tower Erection Completed | Tower Verticality | Site Dev Works Completed (RFI) | Tempo Power_ Plan | Tempo Power Connected | RFTI_ Plan | RFTI_ Actual | Pre-PAT_ Actual | PAT_ Plan | PAT Passed_ Actual | TX Solution | TX Installed_ Actual | MOS_ Plan | MOS_ Actual | BTS Installation Completed | Integrated_ Plan | Integrated_ Actual |  | RFS_ Plan | RFS_ Actual | PAT_ Actual | SSV_ Actual | On-Aired_ Actual | PAC_ Actual | FAC_ Actual | Permanent Power Applied | Joint Inspection Survey with COOP | Charge Letter Acquired | Power Payment RFP Submitted | Power Payment RFP Released | Line Construction | Energized_ Plan | Energized_ Actual | Electrical PAT | Site Utility Contract Submitted | Meter Serial Number | Electric Cooperative | Remarks | DITO Phase | New POOL | UIC - Private Site | CME Priority | RFP Priority | FINAL PRIORITIZATION
PH0900001 | 122.05 | 6.9285 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Campo Islam | MIN | PH097332072 | 27889 | 30 | Three Legged Tubular Tower | CO69 | 3.395 | MIN-0900001 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | JXD |  | Proposed PO 1 |  |  |  |  | 2020-02-05 | 2020-02-01 | 2020-02-03 | 2020-02-03 | 2020-02-04 |  |  |  | 2020-02-04 | [8 empty] | 2020-02-08 | [11 empty] | 2020-03-09 | [27 empty] | 2020-03-16 |  |  | 2020-04-15 |  | 2020-03-23 | [16 empty] | 2020-04-13 |  |  | 2020-04-22 | [6 empty] | 2020-05-06 |  |  |  | 2020-05-06 |  |  |  |  | 2020-03-30 | 2020-02-04 | 2020-04-09 |  |  | 2020-04-13 |  | 2020-04-16 |  |  | 2020-04-30 |  |  |  | 2020-05-07 |  | 3GT-30-280C-2NPT |  |  | 2020-05-19 |  | 2020-04-27 | [6 empty] | 2020-05-27 | 2020-06-03 | [20 empty] | 2020-07-03 |  |  |  | 2020-07-06 | [8 empty] | 2020-05-12 |  | 2020-05-15 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-06 |  |  |  | 2020-06-09 |  |  | 2020-06-24 |  |  |  | 2020-07-06 |  | 2020-07-09
PH0900002 | 122.0468 | 6.9198 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Campo Islam | MIN | PH097332071 | 16723 | 15 | Pole | CO69 | 3.7028 | MIN-0900002 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | AFP_61 | Cluster M27 | Richworld | PO2019122101PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-20 | 2020-01-28 | 2020-01-22 | 2020-01-31 |  |  |  | 2020-01-31 | 2020-02-03 |  |  |  | 2020-02-03 |  |  |  | 2020-01-27 | 2020-02-03 |  |  |  | 2020-02-03 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-02-25 | 2020-02-26 | [5 empty] | A | Amir Hawari | AH Bldg., Block 1 Lot 10, Suterville, Brgy. San Jose, Gusu, Zamboanga City | Zamboanga Sibugay | 122.0466 | 6.9204 | Rooftop |  |  | 10 years | P22,000 exclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-04 | 2020-03-02 |  | 2020-04-03 |  | 2020-03-11 | [16 empty] | 2020-04-01 |  |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  |  | 2020-03-18 |  | 2020-03-28 |  |  | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-18 |  |  |  | 2020-04-25 |  | ZCG-12-280C-1NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH0900003 | 122.056 | 6.9251 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Canelar | MIN | PH097332071 | 16723 | 30 | Three Legged Tubular Tower | CO69 | 2.6878 | MIN-0900003 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | JXD |  | Proposed PO 1 |  |  |  |  | 2020-02-05 | 2020-02-04 | 2020-02-04 | 2020-02-06 | 2020-02-05 |  |  |  | 2020-02-05 | 2020-02-07 |  |  |  | 2020-02-07 |  |  |  | 2020-02-11 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-03-02 |  |  |  | 2020-03-02 | 2020-02-24 | 2020-03-12 | [5 empty] | A | Jovino P. Atilano | San Roque, Zamboanga City | Zamboanga Sibugay | 122.0574 | 6.9311 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-19 |  |  | 2020-04-18 |  | 2020-03-26 | [16 empty] | 2020-04-16 |  |  | 2020-04-25 | [6 empty] | 2020-05-09 |  |  |  | 2020-05-09 |  |  |  |  | 2020-04-02 |  | 2020-04-12 |  |  | 2020-04-16 |  | 2020-04-19 |  |  | 2020-05-03 |  |  |  | 2020-05-10 |  | 3GT-30-280C-2NPT |  |  | 2020-05-22 |  | 2020-04-30 | [6 empty] | 2020-05-30 | 2020-06-06 | [20 empty] | 2020-07-06 |  |  |  | 2020-07-09 | [8 empty] | 2020-05-15 |  | 2020-05-18 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-09 |  |  |  | 2020-06-12 |  |  | 2020-06-27 |  |  |  | 2020-07-09 |  | 2020-07-12
PH0900006 | 122.0632 | 6.9186 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Canelar | MIN | PH097332021 | 11100 | 30 | Monopole Tower | CO69 | 1.9284 | MIN-0900004 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-02-07 |  | 2020-02-09 | [13 empty] | 2020-02-14 | [11 empty] | 2020-03-15 | [27 empty] | 2020-03-22 |  |  | 2020-04-21 |  | 2020-03-29 | [16 empty] | 2020-04-19 |  |  | 2020-04-28 | [6 empty] | 2020-05-12 |  |  |  | 2020-05-12 |  |  |  |  | 2020-04-05 |  | 2020-04-15 |  |  | 2020-04-19 |  | 2020-04-22 |  |  | 2020-05-06 |  |  |  | 2020-05-13 |  | 3GT-30-280C-2NPT |  |  | 2020-05-25 |  | 2020-05-03 | [6 empty] | 2020-06-02 | 2020-06-09 | [20 empty] | 2020-07-09 |  |  |  | 2020-07-12 | [8 empty] | 2020-05-18 |  | 2020-05-21 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-12 |  |  |  | 2020-06-15 |  |  | 2020-06-30 |  |  |  | 2020-07-12 |  | 2020-07-15
PH0900008 | 122.0688 | 6.9248 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Camino Nuevo | MIN | PH097332076 | 25185 | 30 | Monopole Tower | CO69 | 1.2795 | MIN-0900005 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-02-10 |  | 2020-02-12 | [13 empty] | 2020-02-17 | [11 empty] | 2020-03-18 | [27 empty] | 2020-03-25 |  |  | 2020-04-24 |  | 2020-04-01 | [16 empty] | 2020-04-22 |  |  | 2020-05-01 | [6 empty] | 2020-05-15 |  |  |  | 2020-05-15 |  |  |  |  | 2020-04-08 |  | 2020-04-18 |  |  | 2020-04-22 |  | 2020-04-25 |  |  | 2020-05-09 |  |  |  | 2020-05-16 |  | 3GT-30-280C-2NPT |  |  | 2020-05-28 |  | 2020-05-06 | [6 empty] | 2020-06-05 | 2020-06-12 | [20 empty] | 2020-07-12 |  |  |  | 2020-07-15 | [8 empty] | 2020-05-21 |  | 2020-05-24 |  |  | 2020-06-05 |  |  |  | 2020-06-08 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-07-03 |  |  |  | 2020-07-15 |  | 2020-07-18
PH0900009 | 122.0688 | 6.9175 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Barangay Zone II | MIN | PH097332021 | 11100 | 30 | Monopole Tower | CO69 | 1.3781 | MIN-0900006 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-02-13 |  | 2020-02-15 | [13 empty] | 2020-02-20 | [11 empty] | 2020-03-21 | [27 empty] | 2020-03-28 |  |  | 2020-04-27 |  | 2020-04-04 | [16 empty] | 2020-04-25 |  |  | 2020-05-04 | [6 empty] | 2020-05-18 |  |  |  | 2020-05-18 |  |  |  |  | 2020-04-11 |  | 2020-04-21 |  |  | 2020-04-25 |  | 2020-04-28 |  |  | 2020-05-12 |  |  |  | 2020-05-19 |  | 3GT-30-280C-2NPT |  |  | 2020-05-31 |  | 2020-05-09 | [6 empty] | 2020-06-08 | 2020-06-15 | [20 empty] | 2020-07-15 |  |  |  | 2020-07-18 | [8 empty] | 2020-05-24 |  | 2020-05-27 |  |  | 2020-06-08 |  |  |  | 2020-06-11 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-07-06 |  |  |  | 2020-07-18 |  | 2020-07-21
PH0900010 | 122.0688 | 6.9103 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Santo Nino | MIN | PH097332077 | 4129 | 30 | Monopole Tower | CO69 | 1.8599 | MIN-0900007 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-02-16 |  | 2020-02-18 | [13 empty] | 2020-02-23 | [11 empty] | 2020-03-24 | [27 empty] | 2020-03-31 |  |  | 2020-04-30 |  | 2020-04-07 | [16 empty] | 2020-04-28 |  |  | 2020-05-07 | [6 empty] | 2020-05-21 |  |  |  | 2020-05-21 |  |  |  |  | 2020-04-14 |  | 2020-04-24 |  |  | 2020-04-28 |  | 2020-05-01 |  |  | 2020-05-15 |  |  |  | 2020-05-22 |  | ZCG-12-280C-1NPT |  |  | 2020-06-03 |  | 2020-05-12 | [6 empty] | 2020-06-11 | 2020-06-18 | [20 empty] | 2020-07-18 |  |  |  | 2020-07-21 | [8 empty] | 2020-05-27 |  | 2020-05-30 |  |  | 2020-06-11 |  |  |  | 2020-06-14 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-09 |  |  |  | 2020-07-21 |  | 2020-07-24
PH0900016 | 122.0813 | 6.9248 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Tetuan | MIN | PH097332087 | 29785 | 30 | Monopole Tower | CO69 | 0.27002 | MIN-0900008 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M27 | Richworld | PO2019122101PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-22 | 2020-02-03 | 2020-01-24 | 2020-02-04 | 2020-02-05 |  |  | 2020-02-04 |  | 2020-02-07 |  |  | 2020-02-07 |  |  |  | 2020-01-29 |  | 2020-02-07 |  |  | 2020-02-07 | 2020-02-04 | 2020-02-05 |  |  | 2020-02-04 | 2020-02-25 | 2020-02-28 | [5 empty] | A | Roger Fernandez | Blue Gym Bldg., Cabato Rd., Brgy. Tetuan, Zamboanga City | Zamboanga Sibugay | 122.0835 | 6.9262 | Rooftop |  |  | 10 years | P17,000 exclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-06 |  |  | 2020-04-05 |  | 2020-03-13 | [16 empty] | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 |  | 2020-03-30 |  |  | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-20 |  |  |  | 2020-04-27 |  | 3GT-30-280C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH0900018 | 122.0814 | 6.9103 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Santa Barbara | MIN | PH097332075 | 17294 | 30 | Monopole Tower | CO69 | 1.3776 | MIN-0900009 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-02-19 |  | 2020-02-21 | [13 empty] | 2020-02-26 | [11 empty] | 2020-03-27 | [27 empty] | 2020-04-03 |  |  | 2020-05-03 |  | 2020-04-10 | [16 empty] | 2020-05-01 |  |  | 2020-05-10 | [6 empty] | 2020-05-24 |  |  |  | 2020-05-24 |  |  |  |  | 2020-04-17 |  | 2020-04-27 |  |  | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-18 |  |  |  | 2020-05-25 |  | DGT-30-280C-2NPT |  |  | 2020-06-06 |  | 2020-05-15 | [6 empty] | 2020-06-14 | 2020-06-21 | [20 empty] | 2020-07-21 |  |  |  | 2020-07-24 | [8 empty] | 2020-05-30 |  | 2020-06-02 |  |  | 2020-06-14 |  |  |  | 2020-06-17 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-12 |  |  |  | 2020-07-24 |  | 2020-07-27
PH0900021 | 122.0876 | 6.9211 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Tetuan | MIN | PH097332087 | 29785 | 30 | Monopole Tower | CO69 | 0.83217 | MIN-0900010 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-02-22 |  | 2020-02-24 | [13 empty] | 2020-02-29 | [11 empty] | 2020-03-30 | [27 empty] | 2020-04-06 |  |  | 2020-05-06 |  | 2020-04-13 | [16 empty] | 2020-05-04 |  |  | 2020-05-13 | [6 empty] | 2020-05-27 |  |  |  | 2020-05-27 |  |  |  |  | 2020-04-20 |  | 2020-04-30 |  |  | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-21 |  |  |  | 2020-05-28 |  | DGT-30-280C-2NPT |  |  | 2020-06-09 |  | 2020-05-18 | [6 empty] | 2020-06-17 | 2020-06-24 | [20 empty] | 2020-07-24 |  |  |  | 2020-07-27 | [8 empty] | 2020-06-02 |  | 2020-06-05 |  |  | 2020-06-17 |  |  |  | 2020-06-20 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-15 |  |  |  | 2020-07-27 |  | 2020-07-30
PH0900024 | 122.0922 | 6.9325 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Tetuan | MIN | PH097332065 | 19681 | 30 | Monopole Tower | CO69 | 1.726 | MIN-0900011 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-02-25 |  | 2020-02-27 | [13 empty] | 2020-03-03 | [11 empty] | 2020-04-02 | [27 empty] | 2020-04-09 |  |  | 2020-05-09 |  | 2020-04-16 | [16 empty] | 2020-05-07 |  |  | 2020-05-16 | [6 empty] | 2020-05-30 |  |  |  | 2020-05-30 |  |  |  |  | 2020-04-23 |  | 2020-05-03 |  |  | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-24 |  |  |  | 2020-05-31 |  | DGT-30-280C-2NPT |  |  | 2020-06-12 |  | 2020-05-21 | [6 empty] | 2020-06-20 | 2020-06-27 | [20 empty] | 2020-07-27 |  |  |  | 2020-07-30 | [8 empty] | 2020-06-05 |  | 2020-06-08 |  |  | 2020-06-20 |  |  |  | 2020-06-23 |  |  | 2020-06-30 |  |  |  | 2020-07-03 |  |  | 2020-07-18 |  |  |  | 2020-07-30 |  | 2020-08-02
PH0900026 | 122.0939 | 6.9103 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Santa Catalina | MIN | PH097332101 | 14114 | 30 | Three Legged Tubular Tower | CO69 | 2.042 | MIN-0900012 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-02-28 |  | 2020-03-01 | [13 empty] | 2020-03-06 | [11 empty] | 2020-04-05 | [27 empty] | 2020-04-12 |  |  | 2020-05-12 |  | 2020-04-19 | [16 empty] | 2020-05-10 |  |  | 2020-05-19 | [6 empty] | 2020-06-02 |  |  |  | 2020-06-02 |  |  |  |  | 2020-04-26 |  | 2020-05-06 |  |  | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-27 |  |  |  | 2020-06-03 |  | DGT-30-280C-2NPT |  |  | 2020-06-15 |  | 2020-05-24 | [6 empty] | 2020-06-23 | 2020-06-30 | [20 empty] | 2020-07-30 |  |  |  | 2020-08-02 | [8 empty] | 2020-06-08 |  | 2020-06-11 |  |  | 2020-06-23 |  |  |  | 2020-06-26 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-21 |  |  |  | 2020-08-02 |  | 2020-08-05
PH0900027 | 123.4306 | 7.8264 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Sur | Pagadian City | Santo Nino | MIN | PH097322002 | 14384 | 15 | Pole | CO68 | 112.4785 | MIN-0900013 | Level 6 | phase2_add | phase3 |  | DepEd_2876 | Cluster M25 | TBD | [6 empty] | 2020-02-12 | 2020-07-01 |  | 2020-07-03 | [13 empty] | 2020-07-08 | [11 empty] | 2020-08-07 | [27 empty] | 2020-08-14 |  |  | 2020-09-13 |  | 2020-08-21 | [16 empty] | 2020-09-11 |  |  | 2020-09-20 | [6 empty] | 2020-10-04 |  |  |  | 2020-10-04 |  |  |  |  | 2020-08-28 |  | 2020-09-07 |  |  | 2020-09-11 |  | 2020-09-14 |  |  | 2020-09-28 |  |  |  | 2020-10-05 |  | ZCG-12-280C-1NPT |  |  | 2020-10-17 |  | 2020-09-25 | [6 empty] | 2020-10-25 | 2020-11-01 | [20 empty] | 2020-12-01 |  |  |  | 2020-12-04 | [8 empty] | 2020-10-10 |  | 2020-10-13 |  |  | 2020-10-25 |  |  |  | 2020-10-28 |  |  | 2020-11-04 |  |  |  | 2020-11-07 |  |  | 2020-11-22 |  |  |  | 2020-12-04 |  | 2020-12-07
PH0900029 | 123.4369 | 7.83 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Sur | Pagadian City | San Jose | MIN | PH097322040 | 7443 | 30 | Monopole Tower | CO68 | 112.1642 | MIN-0900014 | Level 6 | phase2_add | phase3 |  | DICT_64 | Cluster M25 | TBD | [6 empty] | 2020-02-12 | 2020-07-02 |  | 2020-07-04 | [13 empty] | 2020-07-09 | [11 empty] | 2020-08-08 | [27 empty] | 2020-08-15 |  |  | 2020-09-14 |  | 2020-08-22 | [16 empty] | 2020-09-12 |  |  | 2020-09-21 | [6 empty] | 2020-10-05 |  |  |  | 2020-10-05 |  |  |  |  | 2020-08-29 |  | 2020-09-08 |  |  | 2020-09-12 |  | 2020-09-15 |  |  | 2020-09-29 |  |  |  | 2020-10-06 |  | 3GT-30-280C-2NPT |  |  | 2020-10-18 |  | 2020-09-26 | [6 empty] | 2020-10-26 | 2020-11-02 | [20 empty] | 2020-12-02 |  |  |  | 2020-12-05 | [8 empty] | 2020-10-11 |  | 2020-10-14 |  |  | 2020-10-26 |  |  |  | 2020-10-29 |  |  | 2020-11-05 |  |  |  | 2020-11-08 |  |  | 2020-11-23 |  |  |  | 2020-12-05 |  | 2020-12-08
PH0900030 | 123.4369 | 7.8228 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Sur | Pagadian City | Gatas | MIN | PH097322042 | 8553 | 30 | Monopole Tower | CO68 | 111.6828 | MIN-0900015 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [6 empty] | 2020-02-12 | 2020-07-03 |  | 2020-07-05 | [13 empty] | 2020-07-10 | [11 empty] | 2020-08-09 | [27 empty] | 2020-08-16 |  |  | 2020-09-15 |  | 2020-08-23 | [16 empty] | 2020-09-13 |  |  | 2020-09-22 | [6 empty] | 2020-10-06 |  |  |  | 2020-10-06 |  |  |  |  | 2020-08-30 |  | 2020-09-09 |  |  | 2020-09-13 |  | 2020-09-16 |  |  | 2020-09-30 |  |  |  | 2020-10-07 |  | ZCG-12-280C-1NPT |  |  | 2020-10-19 |  | 2020-09-27 | [6 empty] | 2020-10-27 | 2020-11-03 | [20 empty] | 2020-12-03 |  |  |  | 2020-12-06 | [8 empty] | 2020-10-12 |  | 2020-10-15 |  |  | 2020-10-27 |  |  |  | 2020-10-30 |  |  | 2020-11-06 |  |  |  | 2020-11-09 |  |  | 2020-11-24 |  |  |  | 2020-12-06 |  | 2020-12-09
PH0900051 | 121.9221 | 6.9954 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Talisayan | MIN | PH097332084 | 8220 | 40 | Three Legged Tubular Tower | CO69 | 19.2407 | MIN-0900016 | Level 6 | phase2_add | phase3 |  |  | Cluster M27 | JXD |  | Proposed PO 1 |  |  |  |  | 2020-02-05 | 2020-03-02 | 2020-02-04 | 2020-03-04 | 2020-02-05 |  |  |  | 2020-02-05 | 2020-02-07 |  |  |  | 2020-02-07 |  |  |  | 2020-03-09 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-03-02 |  |  |  | 2020-03-02 | 2020-03-02 | 2020-04-08 | 2020-03-04 |  |  | 2020-03-03 | 2020-03-03 | A | Esther Riveral Yasin | Purok 5, Talisay, Zamboanga City | Zamboanga Sibugay | 121.9293 | 6.9877 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-15 |  |  | 2020-05-15 |  | 2020-04-22 | [16 empty] | 2020-05-13 |  |  | 2020-05-22 | [6 empty] | 2020-06-05 |  |  |  | 2020-06-05 |  |  |  |  | 2020-04-29 |  | 2020-05-09 |  |  | 2020-05-13 |  | 2020-05-16 |  |  | 2020-05-30 |  |  |  | 2020-06-06 |  | JGT-36-280C-2NPT |  |  | 2020-06-18 |  | 2020-05-27 | [6 empty] | 2020-06-26 | 2020-07-03 | [20 empty] | 2020-08-02 |  |  |  | 2020-08-05 | [8 empty] | 2020-06-11 |  | 2020-06-14 |  |  | 2020-06-26 |  |  |  | 2020-06-29 |  |  | 2020-07-06 |  |  |  | 2020-07-09 |  |  | 2020-07-24 |  |  |  | 2020-08-05 |  | 2020-08-08
PH0900054 | 121.9513 | 6.9787 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Talisayan | MIN | PH097332032 | 7557 | 40 | Three Legged Tubular Tower | CO69 | 15.5367 | MIN-0900017 | Level 6 | phase2_add | phase3 |  |  | Cluster M27 | JXD |  | Proposed PO 1 |  |  |  |  | 2020-02-05 | 2020-03-05 | 2020-02-03 | 2020-03-07 | 2020-02-04 |  |  |  | 2020-02-04 | 2020-02-09 |  |  |  | 2020-02-09 |  |  |  | 2020-03-12 | 2020-02-09 |  |  |  | 2020-02-09 | 2020-02-05 |  |  |  | 2020-02-05 | 2020-03-02 | 2020-04-11 | 2020-03-12 |  |  | 2020-03-12 |  | A | Archie Paculan | Zone 1, Ayala and La Paz Boundary, Zamboanga City | Zamboanga Sibugay | 121.9514 | 6.9782 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-18 |  |  | 2020-05-18 |  | 2020-04-25 | [16 empty] | 2020-05-16 |  |  | 2020-05-25 | [6 empty] | 2020-06-08 |  |  |  | 2020-06-08 |  |  |  |  | 2020-05-02 |  | 2020-05-12 |  |  | 2020-05-16 |  | 2020-05-19 |  |  | 2020-06-02 |  |  |  | 2020-06-09 |  | JGT-36-280C-2NPT |  |  | 2020-06-21 |  | 2020-05-30 | [6 empty] | 2020-06-29 | 2020-07-06 | [20 empty] | 2020-08-05 |  |  |  | 2020-08-08 | [8 empty] | 2020-06-14 |  | 2020-06-17 |  |  | 2020-06-29 |  |  |  | 2020-07-02 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-27 |  |  |  | 2020-08-08 |  | 2020-08-11
PH0900060 | 121.9805 | 6.9518 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Sinunoc | MIN | PH097332046 | 8958 | 40 | Monopole Tower | CO69 | 11.4705 | MIN-0900018 | Level 6 | phase2_add | phase3 |  | DepEd_2947 | Cluster M27 | JXD |  | Proposed PO 1 |  |  |  |  | 2020-02-05 | 2020-03-08 | 2020-02-03 | 2020-03-10 | 2020-02-04 |  |  |  | 2020-02-04 | 2020-02-08 |  |  |  | 2020-02-08 |  |  |  | 2020-03-15 | 2020-02-08 |  |  |  | 2020-02-08 | 2020-03-02 |  |  |  | 2020-03-02 |  | 2020-04-14 | [5 empty] | A |  |  |  | 121.9802 | 6.9539 | [16 empty] | 2020-04-21 |  |  | 2020-05-21 |  | 2020-04-28 | [16 empty] | 2020-05-19 |  |  | 2020-05-28 | [6 empty] | 2020-06-11 |  |  |  | 2020-06-11 |  |  |  |  | 2020-05-05 |  | 2020-05-15 |  |  | 2020-05-19 |  | 2020-05-22 |  |  | 2020-06-05 |  |  |  | 2020-06-12 |  | JGT-36-280C-2NPT |  |  | 2020-06-24 |  | 2020-06-02 | [6 empty] | 2020-07-02 | 2020-07-09 | [20 empty] | 2020-08-08 |  |  |  | 2020-08-11 | [8 empty] | 2020-06-17 |  | 2020-06-20 |  |  | 2020-07-02 |  |  |  | 2020-07-05 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-30 |  |  |  | 2020-08-11 |  | 2020-08-14
PH0900062 | 122.0036 | 6.9345 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Sinunoc | MIN | PH097332080 | 16507 | 40 | Three Legged Tubular Tower | CO69 | 8.553 | MIN-0900019 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-03-11 |  | 2020-03-13 | [13 empty] | 2020-03-18 | [11 empty] | 2020-04-17 | [27 empty] | 2020-04-24 |  |  | 2020-05-24 |  | 2020-05-01 | [16 empty] | 2020-05-22 |  |  | 2020-05-31 | [6 empty] | 2020-06-14 |  |  |  | 2020-06-14 |  |  |  |  | 2020-05-08 |  | 2020-05-18 |  |  | 2020-05-22 |  | 2020-05-25 |  |  | 2020-06-08 |  |  |  | 2020-06-15 |  | JGT-36-280C-2NPT |  |  | 2020-06-27 |  | 2020-06-05 | [6 empty] | 2020-07-05 | 2020-07-12 | [20 empty] | 2020-08-11 |  |  |  | 2020-08-14 | [8 empty] | 2020-06-20 |  | 2020-06-23 |  |  | 2020-07-05 |  |  |  | 2020-07-08 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-08-02 |  |  |  | 2020-08-14 |  | 2020-08-17
PH0900065 | 122.0494 | 6.9401 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | San Roque | MIN | PH097332016 | 13680 | 40 | Three Legged Tubular Tower | CO69 | 3.9151 | MIN-0900020 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-03-14 |  | 2020-03-16 | [13 empty] | 2020-03-21 | [11 empty] | 2020-04-20 | [27 empty] | 2020-04-27 |  |  | 2020-05-27 |  | 2020-05-04 | [16 empty] | 2020-05-25 |  |  | 2020-06-03 | [6 empty] | 2020-06-17 |  |  |  | 2020-06-17 |  |  |  |  | 2020-05-11 |  | 2020-05-21 |  |  | 2020-05-25 |  | 2020-05-28 |  |  | 2020-06-11 |  |  |  | 2020-06-18 |  | JGT-36-280C-2NPT |  |  | 2020-06-30 |  | 2020-06-08 | [6 empty] | 2020-07-08 | 2020-07-15 | [20 empty] | 2020-08-14 |  |  |  | 2020-08-17 | [8 empty] | 2020-06-23 |  | 2020-06-26 |  |  | 2020-07-08 |  |  |  | 2020-07-11 |  |  | 2020-07-18 |  |  |  | 2020-07-21 |  |  | 2020-08-05 |  |  |  | 2020-08-17 |  | 2020-08-20
PH0900066 | 122.0719 | 6.9366 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Santa Maria | MIN | PH097332076 | 25185 | 40 | Three Legged Tubular Tower | CO69 | 1.8027 | MIN-0900021 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-03-17 |  | 2020-03-19 | [13 empty] | 2020-03-24 | [11 empty] | 2020-04-23 | [27 empty] | 2020-04-30 |  |  | 2020-05-30 |  | 2020-05-07 | [16 empty] | 2020-05-28 |  |  | 2020-06-06 | [6 empty] | 2020-06-20 |  |  |  | 2020-06-20 |  |  |  |  | 2020-05-14 |  | 2020-05-24 |  |  | 2020-05-28 |  | 2020-05-31 |  |  | 2020-06-14 |  |  |  | 2020-06-21 |  | JGT-36-280C-2NPT |  |  | 2020-07-03 |  | 2020-06-11 | [6 empty] | 2020-07-11 | 2020-07-18 | [20 empty] | 2020-08-17 |  |  |  | 2020-08-20 | [8 empty] | 2020-06-26 |  | 2020-06-29 |  |  | 2020-07-11 |  |  |  | 2020-07-14 |  |  | 2020-07-21 |  |  |  | 2020-07-24 |  |  | 2020-08-08 |  |  |  | 2020-08-20 |  | 2020-08-23
PH0900070 | 122.0816 | 6.9539 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Lunzuran | MIN | PH097332059 | 27374 | 40 | Monopole Tower | CO69 | 3.4805 | MIN-0900022 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-03-20 |  | 2020-03-22 | [13 empty] | 2020-03-27 | [11 empty] | 2020-04-26 | [27 empty] | 2020-05-03 |  |  | 2020-06-02 |  | 2020-05-10 | [16 empty] | 2020-05-31 |  |  | 2020-06-09 | [6 empty] | 2020-06-23 |  |  |  | 2020-06-23 |  |  |  |  | 2020-05-17 |  | 2020-05-27 |  |  | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-17 |  |  |  | 2020-06-24 |  | JGT-36-280C-2NPT |  |  | 2020-07-06 |  | 2020-06-14 | [6 empty] | 2020-07-14 | 2020-07-21 | [20 empty] | 2020-08-20 |  |  |  | 2020-08-23 | [8 empty] | 2020-06-29 |  | 2020-07-02 |  |  | 2020-07-14 |  |  |  | 2020-07-17 |  |  | 2020-07-24 |  |  |  | 2020-07-27 |  |  | 2020-08-11 |  |  |  | 2020-08-23 |  | 2020-08-26
PH0900073 | 122.093 | 6.9412 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Putik | MIN | PH097332065 | 19681 | 40 | Monopole Tower | CO69 | 2.5089 | MIN-0900023 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-03-23 |  | 2020-03-25 | [13 empty] | 2020-03-30 | [11 empty] | 2020-04-29 | [27 empty] | 2020-05-06 |  |  | 2020-06-05 |  | 2020-05-13 | [16 empty] | 2020-06-03 |  |  | 2020-06-12 | [6 empty] | 2020-06-26 |  |  |  | 2020-06-26 |  |  |  |  | 2020-05-20 |  | 2020-05-30 |  |  | 2020-06-03 |  | 2020-06-06 |  |  | 2020-06-20 |  |  |  | 2020-06-27 |  | JGT-36-280C-2NPT |  |  | 2020-07-09 |  | 2020-06-17 | [6 empty] | 2020-07-17 | 2020-07-24 | [20 empty] | 2020-08-23 |  |  |  | 2020-08-26 | [8 empty] | 2020-07-02 |  | 2020-07-05 |  |  | 2020-07-17 |  |  |  | 2020-07-20 |  |  | 2020-07-27 |  |  |  | 2020-07-30 |  |  | 2020-08-14 |  |  |  | 2020-08-26 |  | 2020-08-29
PH0900074 | 122.1027 | 6.9469 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Boalan | MIN | PH097332026 | 9218 | 40 | Monopole Tower | CO69 | 3.669 | MIN-0900024 | Level 6 | phase2_add | phase2_1231 |  | DepEd_2912 | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-03-26 |  | 2020-03-28 | [13 empty] | 2020-04-02 | [11 empty] | 2020-05-02 | [27 empty] | 2020-05-09 |  |  | 2020-06-08 |  | 2020-05-16 | [16 empty] | 2020-06-06 |  |  | 2020-06-15 | [6 empty] | 2020-06-29 |  |  |  | 2020-06-29 |  |  |  |  | 2020-05-23 |  | 2020-06-02 |  |  | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-23 |  |  |  | 2020-06-30 |  | JGT-36-280C-2NPT |  |  | 2020-07-12 |  | 2020-06-20 | [6 empty] | 2020-07-20 | 2020-07-27 | [20 empty] | 2020-08-26 |  |  |  | 2020-08-29 | [8 empty] | 2020-07-05 |  | 2020-07-08 |  |  | 2020-07-20 |  |  |  | 2020-07-23 |  |  | 2020-07-30 |  |  |  | 2020-08-02 |  |  | 2020-08-17 |  |  |  | 2020-08-29 |  | 2020-09-01
PH0900075 | 122.1028 | 6.9357 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Putik | MIN | PH097332065 | 19681 | 40 | Three Legged Tubular Tower | CO69 | 2.8816 | MIN-0900025 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M27 | Richworld | PO2019122101PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-24 | 2020-01-30 | 2020-01-26 | 2020-01-31 |  |  |  | 2020-01-31 | 2020-02-02 |  |  |  | 2020-02-02 |  |  |  | 2020-01-31 | 2020-02-02 |  |  |  | 2020-02-02 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-02-25 | 2020-03-01 | [5 empty] | A | Meilin Lim | Brgy. Caputatan, Putik, Zamboanga City | Zamboanga Sibugay | 122.1032 | 6.9356 | Greenfield |  |  | 10 years | P18,000 exclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-08 |  |  | 2020-04-07 |  | 2020-03-15 | [16 empty] | 2020-04-05 |  |  | 2020-04-14 | [6 empty] | 2020-04-28 |  |  |  | 2020-04-28 |  |  |  |  | 2020-03-22 |  | 2020-04-01 |  |  | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-22 |  |  |  | 2020-04-29 |  | JGT-36-280C-2NPT |  |  | 2020-05-11 |  | 2020-04-19 | [6 empty] | 2020-05-19 | 2020-05-26 | [20 empty] | 2020-06-25 |  |  |  | 2020-06-28 | [8 empty] | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-05-29 |  |  |  | 2020-06-01 |  |  | 2020-06-16 |  |  |  | 2020-06-28 |  | 2020-07-01
PH0900077 | 122.1028 | 6.9132 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Kasanyangan | MIN | PH097332085 | 34916 | 40 | Three Legged Tubular Tower | CO69 | 2.7054 | MIN-0900026 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-03-29 |  | 2020-03-31 | [13 empty] | 2020-04-05 | [11 empty] | 2020-05-05 | [27 empty] | 2020-05-12 |  |  | 2020-06-11 |  | 2020-05-19 | [16 empty] | 2020-06-09 |  |  | 2020-06-18 | [6 empty] | 2020-07-02 |  |  |  | 2020-07-02 |  |  |  |  | 2020-05-26 |  | 2020-06-05 |  |  | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-26 |  |  |  | 2020-07-03 |  | JGT-36-280C-2NPT |  |  | 2020-07-15 |  | 2020-06-23 | [6 empty] | 2020-07-23 | 2020-07-30 | [20 empty] | 2020-08-29 |  |  |  | 2020-09-01 | [8 empty] | 2020-07-08 |  | 2020-07-11 |  |  | 2020-07-23 |  |  |  | 2020-07-26 |  |  | 2020-08-02 |  |  |  | 2020-08-05 |  |  | 2020-08-20 |  |  |  | 2020-09-01 |  | 2020-09-04
PH0900082 | 122.1222 | 6.9133 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Kasanyangan | MIN | PH097332048 | 34312 | 40 | Three Legged Tubular Tower | CO69 | 4.7564 | MIN-0900027 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-04-01 |  | 2020-04-03 | [13 empty] | 2020-04-08 | [11 empty] | 2020-05-08 | [27 empty] | 2020-05-15 |  |  | 2020-06-14 |  | 2020-05-22 | [16 empty] | 2020-06-12 |  |  | 2020-06-21 | [6 empty] | 2020-07-05 |  |  |  | 2020-07-05 |  |  |  |  | 2020-05-29 |  | 2020-06-08 |  |  | 2020-06-12 |  | 2020-06-15 |  |  | 2020-06-29 |  |  |  | 2020-07-06 |  | JGT-36-280C-2NPT |  |  | 2020-07-18 |  | 2020-06-26 | [6 empty] | 2020-07-26 | 2020-08-02 | [20 empty] | 2020-09-01 |  |  |  | 2020-09-04 | [8 empty] | 2020-07-11 |  | 2020-07-14 |  |  | 2020-07-26 |  |  |  | 2020-07-29 |  |  | 2020-08-05 |  |  |  | 2020-08-08 |  |  | 2020-08-23 |  |  |  | 2020-09-04 |  | 2020-09-07
PH0900085 | 122.1319 | 6.9413 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Zambowood | MIN | PH097332104 | 10166 | 40 | Three Legged Tubular Tower | CO69 | 6.075 | MIN-0900028 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_3026 | Cluster M27 | Richworld | PO2019122101PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-26 | 2020-01-28 | 2020-01-28 | 2020-01-31 |  |  |  | 2020-01-31 | [8 empty] | 2020-02-02 | [5 empty] | 2020-01-29 |  |  |  | 2020-01-29 |  | 2020-03-03 | [27 empty] | 2020-03-10 |  |  | 2020-04-09 |  | 2020-03-17 | [16 empty] | 2020-04-07 |  |  | 2020-04-16 | [6 empty] | 2020-04-30 |  |  |  | 2020-04-30 |  |  |  |  | 2020-03-24 |  | 2020-04-03 |  |  | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-24 |  |  |  | 2020-05-01 |  | JGT-36-280C-2NPT |  |  | 2020-05-13 |  | 2020-04-21 | [6 empty] | 2020-05-21 | 2020-05-28 | [20 empty] | 2020-06-27 |  |  |  | 2020-06-30 | [8 empty] | 2020-05-06 |  | 2020-05-09 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-18 |  |  |  | 2020-06-30 |  | 2020-07-03
PH0900088 | 122.1416 | 6.9582 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Mercedes | MIN | PH097332053 | 14721 | 40 | Three Legged Tubular Tower | CO69 | 7.8455 | MIN-0900029 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M27 | Richworld | PO2019122101PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-20 | 2020-01-28 | 2020-01-22 | 2020-02-07 |  |  |  | 2020-02-07 | [8 empty] | 2020-01-27 | [5 empty] | 2020-01-29 | 2020-01-31 |  |  | 2020-01-29 |  | 2020-02-26 | [27 empty] | 2020-03-04 |  |  | 2020-04-03 |  | 2020-03-11 | [16 empty] | 2020-04-01 |  |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  |  | 2020-03-18 |  | 2020-03-28 |  |  | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-18 |  |  |  | 2020-04-25 |  | JGT-36-280C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH0900091 | 122.1514 | 6.9189 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Mampang | MIN | PH097332001 | 12589 | 40 | Three Legged Tubular Tower | CO69 | 7.8695 | MIN-0900030 | Level 6 | phase2_add | phase2_1231 |  | DepEd_2870 | Cluster M27 | Richworld | [6 empty] | 2020-02-12 | 2020-04-04 |  | 2020-04-06 | [13 empty] | 2020-04-11 | [11 empty] | 2020-05-11 | [27 empty] | 2020-05-18 |  |  | 2020-06-17 |  | 2020-05-25 | [16 empty] | 2020-06-15 |  |  | 2020-06-24 | [6 empty] | 2020-07-08 |  |  |  | 2020-07-08 |  |  |  |  | 2020-06-01 |  | 2020-06-11 |  |  | 2020-06-15 |  | 2020-06-18 |  |  | 2020-07-02 |  |  |  | 2020-07-09 |  | JGT-36-280C-2NPT |  |  | 2020-07-21 |  | 2020-06-29 | [6 empty] | 2020-07-29 | 2020-08-05 | [20 empty] | 2020-09-04 |  |  |  | 2020-09-07 | [8 empty] | 2020-07-14 |  | 2020-07-17 |  |  | 2020-07-29 |  |  |  | 2020-08-01 |  |  | 2020-08-08 |  |  |  | 2020-08-11 |  |  | 2020-08-26 |  |  |  | 2020-09-07 |  | 2020-09-10
PH0900095 | 122.5987 | 7.7914 | [20 empty] | OA_1231_no BTS | [102 empty] | 1900-01-11
PH0900101 | 123.3288 | 8.5516 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Norte | Dipolog City | Galas | MIN | PH097202004 | 17540 | 40 | Three Legged Tubular Tower | CO68 | 179.2022 | MIN-0900031 | Level 6 | phase3 | phase3 |  |  | Cluster M18 | TBD | [7 empty] | 2020-07-01 |  | 2020-07-03 | [13 empty] | 2020-07-08 | [11 empty] | 2020-08-07 | [27 empty] | 2020-08-14 |  |  | 2020-09-13 |  | 2020-08-21 | [16 empty] | 2020-09-11 |  |  | 2020-09-20 | [6 empty] | 2020-10-04 |  |  |  | 2020-10-04 |  |  |  |  | 2020-08-28 |  | 2020-09-07 |  |  | 2020-09-11 |  | 2020-09-14 |  |  | 2020-09-28 |  |  |  | 2020-10-05 |  | JGT-36-280C-2NPT |  |  | 2020-10-17 |  | 2020-09-25 | [6 empty] | 2020-10-25 | 2020-11-01 | [20 empty] | 2020-12-01 |  |  |  | 2020-12-04 | [8 empty] | 2020-10-10 |  | 2020-10-13 |  |  | 2020-10-25 |  |  |  | 2020-10-28 |  |  | 2020-11-04 |  |  |  | 2020-11-07 |  |  | 2020-11-22 |  |  |  | 2020-12-04 |  | 2020-12-07
PH0900104 | 123.3386 | 8.5684 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Norte | Dipolog City | Santa Filomena | MIN | PH097202017 | 8762 | 40 | Monopole Tower | CO68 | 180.1445 | MIN-0900032 | Level 6 | phase3 | phase3 |  | Philcom_196 | Cluster M18 | TBD | [7 empty] | 2020-07-02 |  | 2020-07-04 | [13 empty] | 2020-07-09 | [11 empty] | 2020-08-08 | [27 empty] | 2020-08-15 |  |  | 2020-09-14 |  | 2020-08-22 | [16 empty] | 2020-09-12 |  |  | 2020-09-21 | [6 empty] | 2020-10-05 |  |  |  | 2020-10-05 |  |  |  |  | 2020-08-29 |  | 2020-09-08 |  |  | 2020-09-12 |  | 2020-09-15 |  |  | 2020-09-29 |  |  |  | 2020-10-06 |  | JGT-36-280C-2NPT |  |  | 2020-10-18 |  | 2020-09-26 | [6 empty] | 2020-10-26 | 2020-11-02 | [20 empty] | 2020-12-02 |  |  |  | 2020-12-05 | [8 empty] | 2020-10-11 |  | 2020-10-14 |  |  | 2020-10-26 |  |  |  | 2020-10-29 |  |  | 2020-11-05 |  |  |  | 2020-11-08 |  |  | 2020-11-23 |  |  |  | 2020-12-05 |  | 2020-12-08
PH0900107 | 123.3484 | 8.5964 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Norte | Dipolog City | Dicayas | MIN | PH097202007 | 7904 | 40 | Three Legged Tubular Tower | CO68 | 182.151 | MIN-0900033 | Level 6 | phase3 | phase3 |  | DepEd_2964 | Cluster M18 | TBD | [7 empty] | 2020-07-03 |  | 2020-07-05 | [13 empty] | 2020-07-10 | [11 empty] | 2020-08-09 | [27 empty] | 2020-08-16 |  |  | 2020-09-15 |  | 2020-08-23 | [16 empty] | 2020-09-13 |  |  | 2020-09-22 | [6 empty] | 2020-10-06 |  |  |  | 2020-10-06 |  |  |  |  | 2020-08-30 |  | 2020-09-09 |  |  | 2020-09-13 |  | 2020-09-16 |  |  | 2020-09-30 |  |  |  | 2020-10-07 |  | JGT-36-280C-2NPT |  |  | 2020-10-19 |  | 2020-09-27 | [6 empty] | 2020-10-27 | 2020-11-03 | [20 empty] | 2020-12-03 |  |  |  | 2020-12-06 | [8 empty] | 2020-10-12 |  | 2020-10-15 |  |  | 2020-10-27 |  |  |  | 2020-10-30 |  |  | 2020-11-06 |  |  |  | 2020-11-09 |  |  | 2020-11-24 |  |  |  | 2020-12-06 |  | 2020-12-09
PH0900108 | 123.3484 | 8.5852 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Norte | Dipolog City | Central | MIN | PH097202009 | 7590 | 40 | Monopole Tower | CO68 | 181.1077 | MIN-0900034 | Level 6 | phase3 | phase3 |  | DepEd_4961 | Cluster M18 | TBD | [7 empty] | 2020-07-04 |  | 2020-07-06 | [13 empty] | 2020-07-11 | [11 empty] | 2020-08-10 | [27 empty] | 2020-08-17 |  |  | 2020-09-16 |  | 2020-08-24 | [16 empty] | 2020-09-14 |  |  | 2020-09-23 | [6 empty] | 2020-10-07 |  |  |  | 2020-10-07 |  |  |  |  | 2020-08-31 |  | 2020-09-10 |  |  | 2020-09-14 |  | 2020-09-17 |  |  | 2020-10-01 |  |  |  | 2020-10-08 |  | JGT-36-280C-2NPT |  |  | 2020-10-20 |  | 2020-09-28 | [6 empty] | 2020-10-28 | 2020-11-04 | [20 empty] | 2020-12-04 |  |  |  | 2020-12-07 | [8 empty] | 2020-10-13 |  | 2020-10-16 |  |  | 2020-10-28 |  |  |  | 2020-10-31 |  |  | 2020-11-07 |  |  |  | 2020-11-10 |  |  | 2020-11-25 |  |  |  | 2020-12-07 |  | 2020-12-10
PH0900114 | 123.3679 | 8.574 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Norte | Dipolog City | Turno | MIN | PH097202020 | 10307 | 40 | Three Legged Tubular Tower | CO68 | 178.8898 | MIN-0900035 | Level 6 | phase3 | phase3 |  |  | Cluster M18 | TBD | [7 empty] | 2020-07-05 |  | 2020-07-07 | [13 empty] | 2020-07-12 | [11 empty] | 2020-08-11 | [27 empty] | 2020-08-18 |  |  | 2020-09-17 |  | 2020-08-25 | [16 empty] | 2020-09-15 |  |  | 2020-09-24 | [6 empty] | 2020-10-08 |  |  |  | 2020-10-08 |  |  |  |  | 2020-09-01 |  | 2020-09-11 |  |  | 2020-09-15 |  | 2020-09-18 |  |  | 2020-10-02 |  |  |  | 2020-10-09 |  | JGT-36-280C-2NPT |  |  | 2020-10-21 |  | 2020-09-29 | [6 empty] | 2020-10-29 | 2020-11-05 | [20 empty] | 2020-12-05 |  |  |  | 2020-12-08 | [8 empty] | 2020-10-14 |  | 2020-10-17 |  |  | 2020-10-29 |  |  |  | 2020-11-01 |  |  | 2020-11-08 |  |  |  | 2020-11-11 |  |  | 2020-11-26 |  |  |  | 2020-12-08 |  | 2020-12-11
PH0900118 | 123.407 | 8.63 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Norte | Dapitan City | Polo | MIN | PH097201031 | 3226 | 40 | Three Legged Tubular Tower | CO68 | 181.9194 | MIN-0900036 | Level 6 | phase3 | phase3 |  | DepEd_2983 | Cluster M18 | TBD | [7 empty] | 2020-07-06 |  | 2020-07-08 | [13 empty] | 2020-07-13 | [11 empty] | 2020-08-12 | [27 empty] | 2020-08-19 |  |  | 2020-09-18 |  | 2020-08-26 | [16 empty] | 2020-09-16 |  |  | 2020-09-25 | [6 empty] | 2020-10-09 |  |  |  | 2020-10-09 |  |  |  |  | 2020-09-02 |  | 2020-09-12 |  |  | 2020-09-16 |  | 2020-09-19 |  |  | 2020-10-03 |  |  |  | 2020-10-10 |  | JGT-36-280C-2NPT |  |  | 2020-10-22 |  | 2020-09-30 | [6 empty] | 2020-10-30 | 2020-11-06 | [20 empty] | 2020-12-06 |  |  |  | 2020-12-09 | [8 empty] | 2020-10-15 |  | 2020-10-18 |  |  | 2020-10-30 |  |  |  | 2020-11-02 |  |  | 2020-11-09 |  |  |  | 2020-11-12 |  |  | 2020-11-27 |  |  |  | 2020-12-09 |  | 2020-12-12
PH0900119 | 123.4201 | 8.6522 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Norte | Dapitan City | Dawo | MIN | PH097201051 | 2655 | 40 | Three Legged Tubular Tower | CO68 | 183.3259 | MIN-0900037 | Level 6 | phase3 | phase3 |  |  | Cluster M18 | TBD | [7 empty] | 2020-07-07 |  | 2020-07-09 | [13 empty] | 2020-07-14 | [11 empty] | 2020-08-13 | [27 empty] | 2020-08-20 |  |  | 2020-09-19 |  | 2020-08-27 | [16 empty] | 2020-09-17 |  |  | 2020-09-26 | [6 empty] | 2020-10-10 |  |  |  | 2020-10-10 |  |  |  |  | 2020-09-03 |  | 2020-09-13 |  |  | 2020-09-17 |  | 2020-09-20 |  |  | 2020-10-04 |  |  |  | 2020-10-11 |  | JGT-36-280C-2NPT |  |  | 2020-10-23 |  | 2020-10-01 | [6 empty] | 2020-10-31 | 2020-11-07 | [20 empty] | 2020-12-07 |  |  |  | 2020-12-10 | [8 empty] | 2020-10-16 |  | 2020-10-19 |  |  | 2020-10-31 |  |  |  | 2020-11-03 |  |  | 2020-11-10 |  |  |  | 2020-11-13 |  |  | 2020-11-28 |  |  |  | 2020-12-10 |  | 2020-12-13
PH0900123 | 123.4257 | 7.8449 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Sur | Pagadian City | Dao | MIN | PH097322014 | 5818 | 40 | Three Legged Tubular Tower | CO68 | 114.1435 | MIN-0900038 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-04 |  | 2020-07-06 | [13 empty] | 2020-07-11 | [11 empty] | 2020-08-10 | [27 empty] | 2020-08-17 |  |  | 2020-09-16 |  | 2020-08-24 | [16 empty] | 2020-09-14 |  |  | 2020-09-23 | [6 empty] | 2020-10-07 |  |  |  | 2020-10-07 |  |  |  |  | 2020-08-31 |  | 2020-09-10 |  |  | 2020-09-14 |  | 2020-09-17 |  |  | 2020-10-01 |  |  |  | 2020-10-08 |  | JGT-36-280C-2NPT |  |  | 2020-10-20 |  | 2020-09-28 | [6 empty] | 2020-10-28 | 2020-11-04 | [20 empty] | 2020-12-04 |  |  |  | 2020-12-07 | [8 empty] | 2020-10-13 |  | 2020-10-16 |  |  | 2020-10-28 |  |  |  | 2020-10-31 |  |  | 2020-11-07 |  |  |  | 2020-11-10 |  |  | 2020-11-25 |  |  |  | 2020-12-07 |  | 2020-12-10
PH0900125 | 123.4212 | 7.8221 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Sur | Pagadian City | Balangasan | MIN | PH097322002 | 14384 | 40 | Three Legged Tubular Tower | CO68 | 113.0235 | MIN-0900039 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-05 |  | 2020-07-07 | [13 empty] | 2020-07-12 | [11 empty] | 2020-08-11 | [27 empty] | 2020-08-18 |  |  | 2020-09-17 |  | 2020-08-25 | [16 empty] | 2020-09-15 |  |  | 2020-09-24 | [6 empty] | 2020-10-08 |  |  |  | 2020-10-08 |  |  |  |  | 2020-09-01 |  | 2020-09-11 |  |  | 2020-09-15 |  | 2020-09-18 |  |  | 2020-10-02 |  |  |  | 2020-10-09 |  | JGT-36-280C-2NPT |  |  | 2020-10-21 |  | 2020-09-29 | [6 empty] | 2020-10-29 | 2020-11-05 | [20 empty] | 2020-12-05 |  |  |  | 2020-12-08 | [8 empty] | 2020-10-14 |  | 2020-10-17 |  |  | 2020-10-29 |  |  |  | 2020-11-01 |  |  | 2020-11-08 |  |  |  | 2020-11-11 |  |  | 2020-11-26 |  |  |  | 2020-12-08 |  | 2020-12-11
PH0900129 | 123.4549 | 7.8392 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Zamboanga Peninsula (Region IX) | Zamboanga Del Sur | Pagadian City | Tiguma | MIN | PH097322045 | 12401 | 40 | Three Legged Tubular Tower | CO68 | 111.2121 | MIN-0900040 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-06 |  | 2020-07-08 | [13 empty] | 2020-07-13 | [11 empty] | 2020-08-12 | [27 empty] | 2020-08-19 |  |  | 2020-09-18 |  | 2020-08-26 | [16 empty] | 2020-09-16 |  |  | 2020-09-25 | [6 empty] | 2020-10-09 |  |  |  | 2020-10-09 |  |  |  |  | 2020-09-02 |  | 2020-09-12 |  |  | 2020-09-16 |  | 2020-09-19 |  |  | 2020-10-03 |  |  |  | 2020-10-10 |  | JGT-36-280C-2NPT |  |  | 2020-10-22 |  | 2020-09-30 | [6 empty] | 2020-10-30 | 2020-11-06 | [20 empty] | 2020-12-06 |  |  |  | 2020-12-09 | [8 empty] | 2020-10-15 |  | 2020-10-18 |  |  | 2020-10-30 |  |  |  | 2020-11-02 |  |  | 2020-11-09 |  |  |  | 2020-11-12 |  |  | 2020-11-27 |  |  |  | 2020-12-09 |  | 2020-12-12
PH0900133 | 121.9415 | 6.9843 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Talisayan | MIN | PH097332084 | 8220 | 40 | Three Legged Tubular Tower | CO69 | 16.7705 | MIN-0900041 | Level 6 | phase2_add | phase3 |  |  | Cluster M27 | JXD |  | Proposed PO 1 |  |  |  |  | 2020-02-05 | 2020-04-07 | 2020-02-03 | 2020-04-09 | 2020-02-04 |  |  |  | 2020-02-04 | [8 empty] | 2020-04-14 | [5 empty] | 2020-02-05 |  |  |  | 2020-02-05 |  | 2020-05-14 | [27 empty] | 2020-05-21 |  |  | 2020-06-20 |  | 2020-05-28 | [16 empty] | 2020-06-18 |  |  | 2020-06-27 | [6 empty] | 2020-07-11 |  |  |  | 2020-07-11 |  |  |  |  | 2020-06-04 |  | 2020-06-14 |  |  | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-05 |  |  |  | 2020-07-12 |  | JGT-42-280C-2NPT |  |  | 2020-07-24 |  | 2020-07-02 | [6 empty] | 2020-08-01 | 2020-08-08 | [20 empty] | 2020-09-07 |  |  |  | 2020-09-10 | [8 empty] | 2020-07-17 |  | 2020-07-20 |  |  | 2020-08-01 |  |  |  | 2020-08-04 |  |  | 2020-08-11 |  |  |  | 2020-08-14 |  |  | 2020-08-29 |  |  |  | 2020-09-10 |  | 2020-09-13
PH0900136 | 122.0388 | 6.9396 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | San Roque | MIN | PH097332072 | 27889 | 40 | Three Legged Tubular Tower | CO69 | 4.9418 | MIN-0900042 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | JXD |  | Proposed PO 1 |  |  |  |  | 2020-02-05 | 2020-04-10 | 2020-02-04 | 2020-04-12 | 2020-02-05 |  |  |  | 2020-02-05 | [8 empty] | 2020-04-17 | [11 empty] | 2020-05-17 | [27 empty] | 2020-05-24 |  |  | 2020-06-23 |  | 2020-05-31 | [16 empty] | 2020-06-21 |  |  | 2020-06-30 | [6 empty] | 2020-07-14 |  |  |  | 2020-07-14 |  |  |  |  | 2020-06-07 |  | 2020-06-17 |  |  | 2020-06-21 |  | 2020-06-24 |  |  | 2020-07-08 |  |  |  | 2020-07-15 |  | JGT-42-280C-2NPT |  |  | 2020-07-27 |  | 2020-07-05 | [6 empty] | 2020-08-04 | 2020-08-11 | [20 empty] | 2020-09-10 |  |  |  | 2020-09-13 | [8 empty] | 2020-07-20 |  | 2020-07-23 |  |  | 2020-08-04 |  |  |  | 2020-08-07 |  |  | 2020-08-14 |  |  |  | 2020-08-17 |  |  | 2020-09-01 |  |  |  | 2020-09-13 |  | 2020-09-16
PH0900141 | 122.093 | 6.9637 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Lumbangan | MIN | PH097332045 | 9931 | 40 | Three Legged Tubular Tower | CO69 | 4.7783 | MIN-0900043 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | JXD |  | Proposed PO 1 |  |  |  |  | 2020-02-05 | 2020-02-01 | 2020-02-11 | 2020-02-03 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-14 |  |  |  | 2020-02-14 |  |  |  | 2020-02-08 | 2020-02-14 |  |  |  | 2020-02-14 | 2020-03-02 |  |  |  | 2020-03-02 |  | 2020-03-09 | [5 empty] | A |  |  |  | 122.0942 | 6.9609 | [16 empty] | 2020-03-16 |  |  | 2020-04-15 |  | 2020-03-23 | [16 empty] | 2020-04-13 |  |  | 2020-04-22 | [6 empty] | 2020-05-06 |  |  |  | 2020-05-06 |  |  |  |  | 2020-03-30 |  | 2020-04-09 |  |  | 2020-04-13 |  | 2020-04-16 |  |  | 2020-04-30 |  |  |  | 2020-05-07 |  | JGT-42-280C-2NPT |  |  | 2020-05-19 |  | 2020-04-27 | [6 empty] | 2020-05-27 | 2020-06-03 | [20 empty] | 2020-07-03 |  |  |  | 2020-07-06 | [8 empty] | 2020-05-12 |  | 2020-05-15 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-06 |  |  |  | 2020-06-09 |  |  | 2020-06-24 |  |  |  | 2020-07-06 |  | 2020-07-09
PH0900144 | 122.1125 | 6.9189 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Tugbungan | MIN | PH097332092 | 23837 | 40 | Three Legged Tubular Tower | CO69 | 3.5917 | MIN-0900044 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | JXD |  | Proposed PO 1 |  |  |  |  | 2020-02-05 | 2020-02-04 | 2020-02-04 | 2020-02-06 | 2020-02-05 |  |  |  | 2020-02-05 | 2020-02-09 |  |  |  | 2020-02-09 |  |  |  | 2020-02-11 | 2020-02-09 |  |  |  | 2020-02-09 | 2020-03-02 |  |  |  | 2020-03-02 | 2020-03-02 | 2020-03-12 | 2020-03-12 |  |  | 2020-03-12 |  | A | ABDUL GAJIL BAMANG | MORNING BREEZE PUROK 7, TUGBUNGAN, ZAMBOANGA | Zamboanga Sibugay | 122.1099 | 6.9176 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-19 |  |  | 2020-04-18 |  | 2020-03-26 | [16 empty] | 2020-04-16 |  |  | 2020-04-25 | [6 empty] | 2020-05-09 |  |  |  | 2020-05-09 |  |  |  |  | 2020-04-02 |  | 2020-04-12 |  |  | 2020-04-16 |  | 2020-04-19 |  |  | 2020-05-03 |  |  |  | 2020-05-10 |  | 3GT-36-280C-2NPT |  |  | 2020-05-22 |  | 2020-04-30 | [6 empty] | 2020-05-30 | 2020-06-06 | [20 empty] | 2020-07-06 |  |  |  | 2020-07-09 | [8 empty] | 2020-05-15 |  | 2020-05-18 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-09 |  |  |  | 2020-06-12 |  |  | 2020-06-27 |  |  |  | 2020-07-09 |  | 2020-07-12
PH0900148 | 122.1416 | 6.9357 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Mercedes | MIN | PH097332053 | 14721 | 40 | Three Legged Tubular Tower | CO69 | 6.9372 | MIN-0900045 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M27 | JXD |  | Proposed PO 1 |  |  |  |  | 2020-02-05 | 2020-02-07 | 2020-02-07 | 2020-02-09 | 2020-02-08 |  |  |  | 2020-02-08 | [8 empty] | 2020-02-14 | [11 empty] | 2020-03-15 | [27 empty] | 2020-03-22 |  |  | 2020-04-21 |  | 2020-03-29 | [16 empty] | 2020-04-19 |  |  | 2020-04-28 | [6 empty] | 2020-05-12 |  |  |  | 2020-05-12 |  |  |  |  | 2020-04-05 |  | 2020-04-15 |  |  | 2020-04-19 |  | 2020-04-22 |  |  | 2020-05-06 |  |  |  | 2020-05-13 |  | 3GT-36-280C-2NPT |  |  | 2020-05-25 |  | 2020-05-03 | [6 empty] | 2020-06-02 | 2020-06-09 | [20 empty] | 2020-07-09 |  |  |  | 2020-07-12 | [8 empty] | 2020-05-18 |  | 2020-05-21 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-12 |  |  |  | 2020-06-15 |  |  | 2020-06-30 |  |  |  | 2020-07-12 |  | 2020-07-15
PH0900164 | 123.3288 | 8.5291 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Del Norte | Dipolog City | Olingan | MIN | PH097202008 | 13250 | 40 | Three Legged Tubular Tower | CO68 | 177.1537 | MIN-0900046 | Level 6 | phase3 | phase3 |  |  | Cluster M18 | TBD | [7 empty] | 2020-07-08 |  | 2020-07-10 | [13 empty] | 2020-07-15 | [11 empty] | 2020-08-14 | [27 empty] | 2020-08-21 |  |  | 2020-09-20 |  | 2020-08-28 | [16 empty] | 2020-09-18 |  |  | 2020-09-27 | [6 empty] | 2020-10-11 |  |  |  | 2020-10-11 |  |  |  |  | 2020-09-04 |  | 2020-09-14 |  |  | 2020-09-18 |  | 2020-09-21 |  |  | 2020-10-05 |  |  |  | 2020-10-12 |  | 3GT-36-280C-2NPT |  |  | 2020-10-24 |  | 2020-10-02 | [6 empty] | 2020-11-01 | 2020-11-08 | [20 empty] | 2020-12-08 |  |  |  | 2020-12-11 | [8 empty] | 2020-10-17 |  | 2020-10-20 |  |  | 2020-11-01 |  |  |  | 2020-11-04 |  |  | 2020-11-11 |  |  |  | 2020-11-14 |  |  | 2020-11-29 |  |  |  | 2020-12-11 |  | 2020-12-14
PH0900169 | 123.3581 | 8.5684 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Del Norte | Dipolog City | Santa Isabel | MIN | PH097202005 | 7359 | 40 | Three Legged Tubular Tower | CO68 | 178.9552 | MIN-0900047 | Level 6 | phase3 | phase3 |  |  | Cluster M18 | TBD | [7 empty] | 2020-07-09 |  | 2020-07-11 | [13 empty] | 2020-07-16 | [11 empty] | 2020-08-15 | [27 empty] | 2020-08-22 |  |  | 2020-09-21 |  | 2020-08-29 | [16 empty] | 2020-09-19 |  |  | 2020-09-28 | [6 empty] | 2020-10-12 |  |  |  | 2020-10-12 |  |  |  |  | 2020-09-05 |  | 2020-09-15 |  |  | 2020-09-19 |  | 2020-09-22 |  |  | 2020-10-06 |  |  |  | 2020-10-13 |  | JGT-42-280C-2NPT |  |  | 2020-10-25 |  | 2020-10-03 | [6 empty] | 2020-11-02 | 2020-11-09 | [20 empty] | 2020-12-09 |  |  |  | 2020-12-12 | [8 empty] | 2020-10-18 |  | 2020-10-21 |  |  | 2020-11-02 |  |  |  | 2020-11-05 |  |  | 2020-11-12 |  |  |  | 2020-11-15 |  |  | 2020-11-30 |  |  |  | 2020-12-12 |  | 2020-12-15
PH0900175 | 123.4125 | 7.8337 | Rural | Rooftop | Rooftop | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Del Sur | Pagadian City | Balintawak | MIN | PH097322003 | 2617 | 6 | Wall Mounted Pole | CO68 | 114.5658 | MIN-0900048 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-07 |  | 2020-07-09 | [13 empty] | 2020-07-14 | [11 empty] | 2020-08-13 | [27 empty] | 2020-08-20 |  |  | 2020-09-19 |  | 2020-08-27 | [16 empty] | 2020-09-17 |  |  | 2020-09-26 | [6 empty] | 2020-10-10 |  |  |  | 2020-10-10 |  |  |  |  | 2020-09-03 |  | 2020-09-13 |  |  | 2020-09-17 |  | 2020-09-20 |  |  | 2020-10-04 |  |  |  | 2020-10-11 |  | ZCG-9-340D-1NPT |  |  | 2020-10-23 |  | 2020-10-01 | [6 empty] | 2020-10-31 | 2020-11-07 | [20 empty] | 2020-12-07 |  |  |  | 2020-12-10 | [8 empty] | 2020-10-16 |  | 2020-10-19 |  |  | 2020-10-31 |  |  |  | 2020-11-03 |  |  | 2020-11-10 |  |  |  | 2020-11-13 |  |  | 2020-11-28 |  |  |  | 2020-12-10 |  | 2020-12-13
PH0900184 | 123.4637 | 7.8302 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Del Sur | Pagadian City | White Beach | MIN | PH097322034 | 3172 | 40 | Three Legged Tubular Tower | CO68 | 109.8292 | MIN-0900049 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-08 |  | 2020-07-10 | [13 empty] | 2020-07-15 | [11 empty] | 2020-08-14 | [27 empty] | 2020-08-21 |  |  | 2020-09-20 |  | 2020-08-28 | [16 empty] | 2020-09-18 |  |  | 2020-09-27 | [6 empty] | 2020-10-11 |  |  |  | 2020-10-11 |  |  |  |  | 2020-09-04 |  | 2020-09-14 |  |  | 2020-09-18 |  | 2020-09-21 |  |  | 2020-10-05 |  |  |  | 2020-10-12 |  | JGT-42-280C-2NPT |  |  | 2020-10-24 |  | 2020-10-02 | [6 empty] | 2020-11-01 | 2020-11-08 | [20 empty] | 2020-12-08 |  |  |  | 2020-12-11 | [8 empty] | 2020-10-17 |  | 2020-10-20 |  |  | 2020-11-01 |  |  |  | 2020-11-04 |  |  | 2020-11-11 |  |  |  | 2020-11-14 |  |  | 2020-11-29 |  |  |  | 2020-12-11 |  | 2020-12-14
PH0900189 | 122.2381 | 7.0995 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Bolong | MIN | PH097332011 | 6460 | 40 | Three Legged Tubular Tower | CO69 | 26.2785 | MIN-0900050 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_2890 | Cluster M27 | Richworld | PO2019122101PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-22 | 2020-01-30 | 2020-01-24 | 2020-01-31 |  |  |  | 2020-01-31 | 2020-02-02 |  |  |  | 2020-02-02 |  |  |  | 2020-01-29 | 2020-02-02 |  |  |  | 2020-02-02 | 2020-02-27 |  |  |  | 2020-02-27 |  | 2020-02-28 | [5 empty] | A |  |  |  | 122.237750° | 7.099200° | [16 empty] | 2020-03-06 | 2020-03-02 |  | 2020-04-05 |  | 2020-03-13 | [16 empty] | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 |  | 2020-03-30 |  |  | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-20 |  |  |  | 2020-04-27 |  | JGT-42-280C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH0900191 | 122.2292 | 7.2079 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Curuan | MIN | PH097332024 | 8796 | 40 | Three Legged Tubular Tower | CO69 | 35.7281 | MIN-0900051 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M27 | Richworld | PO2019122101PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-02-10 | 2020-02-03 | 2020-02-12 | 2020-02-04 | 2020-02-05 |  |  | 2020-02-04 |  | 2020-02-07 |  |  | 2020-02-07 |  |  |  | 2020-02-17 |  | 2020-02-07 |  |  | 2020-02-07 | 2020-02-04 | 2020-02-05 |  |  | 2020-02-04 |  | 2020-03-18 | [5 empty] | A |  |  |  | 122.2282 | 7.2072 | [16 empty] | 2020-03-25 |  |  | 2020-04-24 |  | 2020-04-01 | [16 empty] | 2020-04-22 |  |  | 2020-05-01 | [6 empty] | 2020-05-15 |  |  |  | 2020-05-15 |  |  |  |  | 2020-04-08 |  | 2020-04-18 |  |  | 2020-04-22 |  | 2020-04-25 |  |  | 2020-05-09 |  |  |  | 2020-05-16 |  | JGT-42-280C-2NPT |  |  | 2020-05-28 |  | 2020-05-06 | [6 empty] | 2020-06-05 | 2020-06-12 | [20 empty] | 2020-07-12 |  |  |  | 2020-07-15 | [8 empty] | 2020-05-21 |  | 2020-05-24 |  |  | 2020-06-05 |  |  |  | 2020-06-08 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-07-03 |  |  |  | 2020-07-15 |  | 2020-07-18
PH0900198 | 121.9114 | 7.0458 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Patalon | MIN | PH097332060 | 8128 | 40 | Three Legged Tubular Tower | CO69 | 23.1173 | MIN-0900052 | Level 6 | phase2_add | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-02-13 |  | 2020-02-15 | [13 empty] | 2020-02-20 | [11 empty] | 2020-03-21 | [27 empty] | 2020-03-28 |  |  | 2020-04-27 |  | 2020-04-04 | [16 empty] | 2020-04-25 |  |  | 2020-05-04 | [6 empty] | 2020-05-18 |  |  |  | 2020-05-18 |  |  |  |  | 2020-04-11 |  | 2020-04-21 |  |  | 2020-04-25 |  | 2020-04-28 |  |  | 2020-05-12 |  |  |  | 2020-05-19 |  | JGT-42-280C-2NPT |  |  | 2020-05-31 |  | 2020-05-09 | [6 empty] | 2020-06-08 | 2020-06-15 | [20 empty] | 2020-07-15 |  |  |  | 2020-07-18 | [8 empty] | 2020-05-24 |  | 2020-05-27 |  |  | 2020-06-08 |  |  |  | 2020-06-11 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-07-06 |  |  |  | 2020-07-18 |  | 2020-07-21
PH0900199 | 121.9148 | 7.0724 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Patalon | MIN | PH097332060 | 8128 | 45 | Three Legged Tubular Tower | CO69 | 24.7025 | MIN-0900053 | Level 6 | phase2_add | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-02-16 |  | 2020-02-18 | [13 empty] | 2020-02-23 | [11 empty] | 2020-03-24 | [27 empty] | 2020-03-31 |  |  | 2020-04-30 |  | 2020-04-07 | [16 empty] | 2020-04-28 |  |  | 2020-05-07 | [6 empty] | 2020-05-21 |  |  |  | 2020-05-21 |  |  |  |  | 2020-04-14 |  | 2020-04-24 |  |  | 2020-04-28 |  | 2020-05-01 |  |  | 2020-05-15 |  |  |  | 2020-05-22 |  | JGT-42-280C-2NPT |  |  | 2020-06-03 |  | 2020-05-12 | [6 empty] | 2020-06-11 | 2020-06-18 | [20 empty] | 2020-07-18 |  |  |  | 2020-07-21 | [8 empty] | 2020-05-27 |  | 2020-05-30 |  |  | 2020-06-11 |  |  |  | 2020-06-14 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-09 |  |  |  | 2020-07-21 |  | 2020-07-24
PH0900200 | 122.1991 | 7.0643 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Sangali | MIN | PH097332073 | 20766 | 40 | Monopole Tower | CO69 | 20.505 | MIN-0900054 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M27 | Richworld | PO2019122101PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-24 | 2020-01-30 | 2020-01-26 | 2020-01-31 | 2020-01-31 |  |  | 2020-01-31 | 2020-02-02 |  |  |  | 2020-02-02 |  |  |  | 2020-01-31 | 2020-02-02 |  |  |  | 2020-02-02 | 2020-02-28 | 2020-01-31 |  |  | 2020-01-31 |  | 2020-03-01 | [5 empty] | A |  |  |  | 122.199080° | 7.064240° | [16 empty] | 2020-03-08 |  |  | 2020-04-07 |  | 2020-03-15 | [16 empty] | 2020-04-05 |  |  | 2020-04-14 | [6 empty] | 2020-04-28 |  |  |  | 2020-04-28 |  |  |  |  | 2020-03-22 |  | 2020-04-01 |  |  | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-22 |  |  |  | 2020-04-29 |  | JGT-42-280C-2NPT |  |  | 2020-05-11 |  | 2020-04-19 | [6 empty] | 2020-05-19 | 2020-05-26 | [20 empty] | 2020-06-25 |  |  |  | 2020-06-28 | [8 empty] | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-05-29 |  |  |  | 2020-06-01 |  |  | 2020-06-16 |  |  |  | 2020-06-28 |  | 2020-07-01
PH0900203 | 122.3305 | 7.4545 | [20 empty] | OA_1231_no BTS | [102 empty] | 1900-01-11
PH0900223 | 122.9836 | 7.6899 | [20 empty] | OA_1231_no BTS | [102 empty] | 1900-01-11
PH0900262 | 123.3137 | 7.8312 | [20 empty] | OA_1231_no BTS | [102 empty] | 1900-01-11
PH0900295 | 123.5793 | 7.8561 | [20 empty] | OA_1231_no BTS | [102 empty] | 1900-01-11
PH0900326 | 123.6396 | 7.9348 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Del Sur | Aurora | Anonang | MIN | PH103505046 | 4446 | 40 | Three Legged Tubular Tower | CO68 | 103.8581 | MIN-0900055 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-09 |  | 2020-07-11 | [13 empty] | 2020-07-16 | [11 empty] | 2020-08-15 | [27 empty] | 2020-08-22 |  |  | 2020-09-21 |  | 2020-08-29 | [16 empty] | 2020-09-19 |  |  | 2020-09-28 | [6 empty] | 2020-10-12 |  |  |  | 2020-10-12 |  |  |  |  | 2020-09-05 |  | 2020-09-15 |  |  | 2020-09-19 |  | 2020-09-22 |  |  | 2020-10-06 |  |  |  | 2020-10-13 |  | JGT-42-280C-2NPT |  |  | 2020-10-25 |  | 2020-10-03 | [6 empty] | 2020-11-02 | 2020-11-09 | [20 empty] | 2020-12-09 |  |  |  | 2020-12-12 | [8 empty] | 2020-10-18 |  | 2020-10-21 |  |  | 2020-11-02 |  |  |  | 2020-11-05 |  |  | 2020-11-12 |  |  |  | 2020-11-15 |  |  | 2020-11-30 |  |  |  | 2020-12-12 |  | 2020-12-15
PH0900349 | 122.0178 | 7.1039 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Labuan | MIN | PH097332032 | 7557 | 45 | Three Legged Tubular Tower | CO69 | 21.3059 | MIN-0900056 | Level 6 | phase2_add | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-02-19 |  | 2020-02-21 | [13 empty] | 2020-02-26 | [11 empty] | 2020-03-27 | [27 empty] | 2020-04-03 |  |  | 2020-05-03 |  | 2020-04-10 | [16 empty] | 2020-05-01 |  |  | 2020-05-10 | [6 empty] | 2020-05-24 |  |  |  | 2020-05-24 |  |  |  |  | 2020-04-17 |  | 2020-04-27 |  |  | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-18 |  |  |  | 2020-05-25 |  | JGT-42-280C-2NPT |  |  | 2020-06-06 |  | 2020-05-15 | [6 empty] | 2020-06-14 | 2020-06-21 | [20 empty] | 2020-07-21 |  |  |  | 2020-07-24 | [8 empty] | 2020-05-30 |  | 2020-06-02 |  |  | 2020-06-14 |  |  |  | 2020-06-17 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-12 |  |  |  | 2020-07-24 |  | 2020-07-27
PH0900351 | 122.1111 | 7.1659 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Quiniput | MIN | PH097332013 | 7287 | 45 | Three Legged Tubular Tower | CO69 | 27.2603 | MIN-0900057 | Level 6 | phase2_add | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-02-22 |  | 2020-02-24 | [13 empty] | 2020-02-29 | [11 empty] | 2020-03-30 | [27 empty] | 2020-04-06 |  |  | 2020-05-06 |  | 2020-04-13 | [16 empty] | 2020-05-04 |  |  | 2020-05-13 | [6 empty] | 2020-05-27 |  |  |  | 2020-05-27 |  |  |  |  | 2020-04-20 |  | 2020-04-30 |  |  | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-21 |  |  |  | 2020-05-28 |  | JGT-42-280C-2NPT |  |  | 2020-06-09 |  | 2020-05-18 | [6 empty] | 2020-06-17 | 2020-06-24 | [20 empty] | 2020-07-24 |  |  |  | 2020-07-27 | [8 empty] | 2020-06-02 |  | 2020-06-05 |  |  | 2020-06-17 |  |  |  | 2020-06-20 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-15 |  |  |  | 2020-07-27 |  | 2020-07-30
PH0900352 | 122.1565 | 7.2177 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Curuan | MIN | PH097332024 | 8796 | 45 | Three Legged Tubular Tower | CO69 | 33.8744 | MIN-0900058 | Level 6 | phase2_add | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-02-25 |  | 2020-02-27 | [13 empty] | 2020-03-03 | [11 empty] | 2020-04-02 | [27 empty] | 2020-04-09 |  |  | 2020-05-09 |  | 2020-04-16 | [16 empty] | 2020-05-07 |  |  | 2020-05-16 | [6 empty] | 2020-05-30 |  |  |  | 2020-05-30 |  |  |  |  | 2020-04-23 |  | 2020-05-03 |  |  | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-24 |  |  |  | 2020-05-31 |  | JGT-42-280C-2NPT |  |  | 2020-06-12 |  | 2020-05-21 | [6 empty] | 2020-06-20 | 2020-06-27 | [20 empty] | 2020-07-27 |  |  |  | 2020-07-30 | [8 empty] | 2020-06-05 |  | 2020-06-08 |  |  | 2020-06-20 |  |  |  | 2020-06-23 |  |  | 2020-06-30 |  |  |  | 2020-07-03 |  |  | 2020-07-18 |  |  |  | 2020-07-30 |  | 2020-08-02
PH0900360 | 121.981 | 7.014 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Pamucutan | MIN | PH097332032 | 7557 | 45 | Three Legged Tubular Tower | CO69 | 14.9376 | MIN-0900059 | Level 6 | phase2_add | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-02-28 |  | 2020-03-01 | [13 empty] | 2020-03-06 | [11 empty] | 2020-04-05 | [27 empty] | 2020-04-12 |  |  | 2020-05-12 |  | 2020-04-19 | [16 empty] | 2020-05-10 |  |  | 2020-05-19 | [6 empty] | 2020-06-02 |  |  |  | 2020-06-02 |  |  |  |  | 2020-04-26 |  | 2020-05-06 |  |  | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-27 |  |  |  | 2020-06-03 |  | JGT-42-280C-2NPT |  |  | 2020-06-15 |  | 2020-05-24 | [6 empty] | 2020-06-23 | 2020-06-30 | [20 empty] | 2020-07-30 |  |  |  | 2020-08-02 | [8 empty] | 2020-06-08 |  | 2020-06-11 |  |  | 2020-06-23 |  |  |  | 2020-06-26 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-21 |  |  |  | 2020-08-02 |  | 2020-08-05
PH0900427 | 122.2638 | 7.246 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Muti | MIN | PH097332012 | 6485 | 45 | Three Legged Tubular Tower | CO69 | 41.2703 | MIN-0900060 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M27 | Richworld | PO2019122101PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-03-02 | 2020-01-28 | 2020-03-04 | 2020-01-31 |  |  |  | 2020-01-31 | [8 empty] | 2020-03-09 | [5 empty] | 2020-01-29 |  |  |  | 2020-01-29 |  | 2020-04-08 | [27 empty] | 2020-04-15 |  |  | 2020-05-15 |  | 2020-04-22 | [16 empty] | 2020-05-13 |  |  | 2020-05-22 | [6 empty] | 2020-06-05 |  |  |  | 2020-06-05 |  |  |  |  | 2020-04-29 |  | 2020-05-09 |  |  | 2020-05-13 |  | 2020-05-16 |  |  | 2020-05-30 |  |  |  | 2020-06-06 |  | JGT-42-280C-2NPT |  |  | 2020-06-18 |  | 2020-05-27 | [6 empty] | 2020-06-26 | 2020-07-03 | [20 empty] | 2020-08-02 |  |  |  | 2020-08-05 | [8 empty] | 2020-06-11 |  | 2020-06-14 |  |  | 2020-06-26 |  |  |  | 2020-06-29 |  |  | 2020-07-06 |  |  |  | 2020-07-09 |  |  | 2020-07-24 |  |  |  | 2020-08-05 |  | 2020-08-08
PH0900435 | 122.1696 | 6.9903 | Rural | Greenfield | Greenfield | Y1 | L7 | Zamboanga Peninsula (Region IX) | Zamboanga Sibugay | Zamboanga City | Culianan | MIN | PH097332015 | 6350 | 45 | Three Legged Tubular Tower | CO69 | 12.4051 | MIN-0900061 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M27 | Richworld | PO2019122101PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-26 | 2020-01-28 | 2020-01-28 | 2020-01-31 |  |  |  | 2020-01-31 | 2020-02-02 |  |  |  | 2020-02-02 |  |  |  | 2020-02-02 | 2020-02-02 |  |  |  | 2020-02-02 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-02-25 | 2020-03-03 | [5 empty] | A | Brima Alvarez | KM 17 MCLL Hiway, Cabaluay, Zamboanga City | Zamboanga Sibugay | 122.1709 | 6.9906 | Greenfield |  |  | 10 years | P16,000 exclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-10 | 2020-03-02 |  | 2020-04-09 |  | 2020-03-17 | [16 empty] | 2020-04-07 |  |  | 2020-04-16 | [6 empty] | 2020-04-30 |  |  |  | 2020-04-30 |  |  |  |  | 2020-03-24 |  | 2020-04-03 |  |  | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-24 |  |  |  | 2020-05-01 |  | 4GT-42-340C-2NPT |  |  | 2020-05-13 |  | 2020-04-21 | [6 empty] | 2020-05-21 | 2020-05-28 | [20 empty] | 2020-06-27 |  |  |  | 2020-06-30 | [8 empty] | 2020-05-06 |  | 2020-05-09 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-18 |  |  |  | 2020-06-30 |  | 2020-07-03
PH1000001 | 123.8027 | 8.4879 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Occidental | Oroquieta City | Lamac Lower | MIN | PH104209030 | 2640 | 30 | Monopole Tower | CO68 | 149.0505 | MIN-1000001 | Level 6 | phase3 | phase3 |  | DepEd_3175 | Cluster M18 | TBD | [7 empty] | 2020-07-11 |  | 2020-07-13 | [13 empty] | 2020-07-18 | [11 empty] | 2020-08-17 | [27 empty] | 2020-08-24 |  |  | 2020-09-23 |  | 2020-08-31 | [16 empty] | 2020-09-21 |  |  | 2020-09-30 | [6 empty] | 2020-10-14 |  |  |  | 2020-10-14 |  |  |  |  | 2020-09-07 |  | 2020-09-17 |  |  | 2020-09-21 |  | 2020-09-24 |  |  | 2020-10-08 |  |  |  | 2020-10-15 |  | ZCG-12-280C-1NPT |  |  | 2020-10-27 |  | 2020-10-05 | [6 empty] | 2020-11-04 | 2020-11-11 | [20 empty] | 2020-12-11 |  |  |  | 2020-12-14 | [8 empty] | 2020-10-20 |  | 2020-10-23 |  |  | 2020-11-04 |  |  |  | 2020-11-07 |  |  | 2020-11-14 |  |  |  | 2020-11-17 |  |  | 2020-12-02 |  |  |  | 2020-12-14 |  | 2020-12-17
PH1000003 | 123.846 | 8.1441 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Occidental | Ozamis City | Baybay Triunfo | MIN | PH104210037 | 6135 | 30 | Monopole Tower | CO68 | 111.6925 | MIN-1000002 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-20 |  | 2020-07-22 | [13 empty] | 2020-07-27 | [11 empty] | 2020-08-26 | [27 empty] | 2020-09-02 |  |  | 2020-10-02 |  | 2020-09-09 | [16 empty] | 2020-09-30 |  |  | 2020-10-09 | [6 empty] | 2020-10-23 |  |  |  | 2020-10-23 |  |  |  |  | 2020-09-16 |  | 2020-09-26 |  |  | 2020-09-30 |  | 2020-10-03 |  |  | 2020-10-17 |  |  |  | 2020-10-24 |  | ZCG-12-280C-1NPT |  |  | 2020-11-05 |  | 2020-10-14 | [6 empty] | 2020-11-13 | 2020-11-20 | [20 empty] | 2020-12-20 |  |  |  | 2020-12-23 | [8 empty] | 2020-10-29 |  | 2020-11-01 |  |  | 2020-11-13 |  |  |  | 2020-11-16 |  |  | 2020-11-23 |  |  |  | 2020-11-26 |  |  | 2020-12-11 |  |  |  | 2020-12-23 |  | 2020-12-26
PH1000004 | 124.2298 | 8.2119 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Tominobo Proper | MIN | PH103504028 | 8780 | 30 | Monopole Tower | CO70 | 109.0921 | MIN-1000003 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-21 | 2020-01-11 | 2020-01-23 | 2020-01-12 | 2020-02-20 |  |  | 2020-01-12 | 2020-01-17 |  |  |  | 2020-01-17 |  |  |  | 2020-01-28 | 2020-02-22 |  |  |  | 2020-02-22 | 2020-01-12 | 2020-02-20 |  |  | 2020-01-12 |  | 2020-02-27 | [5 empty] | B |  |  |  | 124.2294 | 8.2127 | [16 empty] | 2020-03-05 | 2020-01-27 |  | 2020-04-04 |  | 2020-03-12 | [11 empty] | 0917-7134253 |  |  |  |  | 2020-04-02 |  |  | 2020-04-11 | [6 empty] | 2020-04-25 |  |  |  | 2020-04-25 |  |  |  |  | 2020-03-19 |  | 2020-03-29 |  |  | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-19 |  |  |  | 2020-04-26 |  | DGT-30-280C-2NPT |  |  | 2020-05-08 |  | 2020-04-16 | [6 empty] | 2020-05-16 | 2020-05-23 | [20 empty] | 2020-06-22 |  |  |  | 2020-06-25 | [8 empty] | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-16 |  |  |  | 2020-05-19 |  |  | 2020-05-26 |  |  |  | 2020-05-29 |  |  | 2020-06-13 |  |  |  | 2020-06-25 |  | 2020-06-28
PH1000006 | 124.2361 | 8.2227 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Tambacan | MIN | PH103504025 | 17616 | 30 | Monopole Tower | CO70 | 109.0757 | MIN-1000004 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | Robinsons_18 | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-12 | 2020-01-11 | 2020-01-14 | 2020-01-12 | 2020-02-07 |  |  | 2020-01-12 | 2020-01-13 |  |  |  | 2020-01-13 |  |  |  | 2020-01-19 | 2020-01-13 |  |  |  | 2020-01-13 |  | 2020-02-07 |  |  | 2020-02-07 |  | 2020-02-18 | [5 empty] | A |  |  |  | 124.2365 | 8.223 | Greenfield | 5m | [14 empty] | 2020-02-25 |  |  | 2020-03-26 |  | 2020-03-03 | [16 empty] | 2020-03-24 |  |  | 2020-04-02 | [6 empty] | 2020-04-16 |  |  |  | 2020-04-16 |  |  |  |  | 2020-03-10 |  | 2020-03-20 |  |  | 2020-03-24 |  | 2020-03-27 |  |  | 2020-04-10 |  |  |  | 2020-04-17 |  | DGT-30-280C-2NPT |  |  | 2020-04-29 |  | 2020-04-07 | [6 empty] | 2020-05-07 | 2020-05-14 | [20 empty] | 2020-06-13 |  |  |  | 2020-06-16 | [8 empty] | 2020-04-22 |  | 2020-04-25 |  |  | 2020-05-07 |  |  |  | 2020-05-10 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-06-04 |  |  |  | 2020-06-16 |  | 2020-06-19
PH1000008 | 124.2424 | 8.2335 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | San Miguel | MIN | PH103504026 | 10171 | 30 | Three Legged Tubular Tower | CO70 | 109.0769 | MIN-1000005 | Level 6 | phase3 | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2020011302PH_WLS | PO Batch 3 | Enovell |  |  |  |  | 2020-01-09 | 2020-01-18 | 2020-01-11 | 2020-02-04 |  |  |  | 2020-02-04 | 2020-02-07 |  |  |  | 2020-02-07 |  |  |  | 2020-01-16 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-02-04 |  |  |  | 2020-02-04 |  | 2020-02-15 | [5 empty] | A |  |  |  | 124.2439 | 8.2337 | [16 empty] | 2020-02-22 |  |  | 2020-03-23 |  | 2020-02-29 | [16 empty] | 2020-03-21 |  |  | 2020-03-30 | [6 empty] | 2020-04-13 |  |  |  | 2020-04-13 |  |  |  |  | 2020-03-07 |  | 2020-03-17 |  |  | 2020-03-21 | 2020-03-12 | 2020-03-24 |  |  | 2020-04-07 |  |  |  | 2020-04-14 |  | DGT-30-280C-2NPT |  |  | 2020-04-26 |  | 2020-04-04 | [6 empty] | 2020-05-04 | 2020-05-11 | [20 empty] | 2020-06-10 |  |  |  | 2020-06-13 | [8 empty] | 2020-04-19 |  | 2020-04-22 |  |  | 2020-05-04 |  |  |  | 2020-05-07 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-06-01 |  |  |  | 2020-06-13 |  | 2020-06-16
PH1000009 | 124.2424 | 8.2263 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Villa Verde | MIN | PH103504012 | 9179 | 30 | Three Legged Tubular Tower | CO70 | 108.6739 | MIN-1000006 | Level 6 | phase3 | phase1_630 | P1_630 | DepEd_3102 | Cluster M26 | Enovell | PO2020011302PH_WLS | PO Batch 3 | Enovell |  |  |  |  | 2020-01-23 | 2020-01-18 | 2020-01-25 | 2020-02-01 | 2020-02-19 |  |  | 2020-02-01 | 2020-02-05 |  |  |  | 2020-02-05 |  |  |  | 2020-01-30 | 2020-02-05 |  |  |  | 2020-02-05 |  | 2020-02-19 |  |  | 2020-02-19 |  | 2020-02-29 | [5 empty] | A |  |  |  | 124.243 | 8.2244 | [16 empty] | 2020-03-07 |  |  | 2020-04-06 |  | 2020-03-14 | [16 empty] | 2020-04-04 |  |  | 2020-04-13 | [6 empty] | 2020-04-27 |  |  |  | 2020-04-27 |  |  |  |  | 2020-03-21 |  | 2020-03-31 |  |  | 2020-04-04 |  | 2020-04-07 |  |  | 2020-04-21 |  |  |  | 2020-04-28 |  | DGT-30-280C-2NPT |  |  | 2020-05-10 |  | 2020-04-18 | [6 empty] | 2020-05-18 | 2020-05-25 | [20 empty] | 2020-06-24 |  |  |  | 2020-06-27 | [8 empty] | 2020-05-03 |  | 2020-05-06 |  |  | 2020-05-18 |  |  |  | 2020-05-21 |  |  | 2020-05-28 |  |  |  | 2020-05-31 |  |  | 2020-06-15 |  |  |  | 2020-06-27 |  | 2020-06-30
PH1000011 | 124.2423 | 8.2118 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Tubod | MIN | PH103504030 | 31913 | 30 | Three Legged Tubular Tower | CO70 | 107.8811 | MIN-1000007 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-25 | 2020-01-16 | 2020-01-27 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-01-31 |  |  |  | 2020-01-31 |  |  |  | 2020-02-01 | 2020-01-31 |  |  |  | 2020-01-31 | [6 empty] | 2020-03-02 | [5 empty] | A |  |  |  | 124.2436 | 8.2126 | [16 empty] | 2020-03-09 |  |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 |  | 2020-04-02 |  |  | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-23 |  |  |  | 2020-04-30 |  | 3GT-30-280C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1000013 | 124.2487 | 8.2371 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | San Miguel | MIN | PH103504034 | 4955 | 30 | Three Legged Tubular Tower | CO70 | 108.684 | MIN-1000008 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-21 | 2020-01-20 | 2020-01-23 |  | 2020-02-09 |  |  | 2020-02-09 | [8 empty] | 2020-01-28 | [6 empty] | 2020-02-09 |  |  | 2020-02-09 |  | 2020-02-27 | [27 empty] | 2020-03-05 |  |  | 2020-04-04 |  | 2020-03-12 | [16 empty] | 2020-04-02 |  |  | 2020-04-11 | [6 empty] | 2020-04-25 |  |  |  | 2020-04-25 |  |  |  |  | 2020-03-19 |  | 2020-03-29 |  |  | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-19 |  |  |  | 2020-04-26 |  | DGT-30-280C-2NPT |  |  | 2020-05-08 |  | 2020-04-16 | [6 empty] | 2020-05-16 | 2020-05-23 | [20 empty] | 2020-06-22 |  |  |  | 2020-06-25 | [8 empty] | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-16 |  |  |  | 2020-05-19 |  |  | 2020-05-26 |  |  |  | 2020-05-29 |  |  | 2020-06-13 |  |  |  | 2020-06-25 |  | 2020-06-28
PH1000019 | 124.255 | 8.2263 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Del Carmen | MIN | PH103504016 | 9600 | 30 | Monopole Tower | CO70 | 107.4759 | MIN-1000009 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DICT_57 | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-23 | 2020-01-11 | 2020-01-25 | 2020-01-13 | 2020-02-19 |  |  | 2020-01-13 |  | 2020-02-22 |  |  | 2020-02-22 |  |  |  | 2020-01-30 |  | 2020-02-22 |  |  | 2020-02-22 |  | 2020-02-19 |  |  | 2020-02-19 |  | 2020-02-29 | [5 empty] | B |  |  |  | 124.2572 | 8.2331 | [16 empty] | 2020-03-07 |  |  | 2020-04-06 |  | 2020-03-14 | [16 empty] | 2020-04-04 |  |  | 2020-04-13 | [6 empty] | 2020-04-27 |  |  |  | 2020-04-27 |  |  |  |  | 2020-03-21 |  | 2020-03-31 |  |  | 2020-04-04 | 2020-03-12 | 2020-04-07 |  |  | 2020-04-21 |  |  |  | 2020-04-28 |  | DGT-30-280C-2NPT |  |  | 2020-05-10 |  | 2020-04-18 | [6 empty] | 2020-05-18 | 2020-05-25 | [20 empty] | 2020-06-24 |  |  |  | 2020-06-27 | [8 empty] | 2020-05-03 |  | 2020-05-06 |  |  | 2020-05-18 |  |  |  | 2020-05-21 |  |  | 2020-05-28 |  |  |  | 2020-05-31 |  |  | 2020-06-15 |  |  |  | 2020-06-27 |  | 2020-06-30
PH1000020 | 124.2613 | 8.2443 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Hinaplanon | MIN | PH103504008 | 12346 | 30 | Monopole Tower | CO70 | 107.9116 | MIN-1000010 | Level 6 | phase3 | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2020011302PH_WLS | PO Batch 3 | Enovell |  |  |  |  | 2020-01-27 | 2020-01-18 | 2020-01-29 | 2020-01-22 | 2020-02-01 |  |  | 2020-01-22 |  | 2020-02-03 |  |  | 2020-02-03 |  |  |  | 2020-02-03 |  | 2020-02-03 |  |  | 2020-02-03 | 2020-01-22 | 2020-02-01 |  |  | 2020-01-22 |  | 2020-03-04 | [5 empty] | B |  |  |  | 124.2617 | 8.2494 | [16 empty] | 2020-03-11 | 2020-02-28 |  | 2020-04-10 | 2020-03-11 | 2020-03-18 | [16 empty] | 2020-04-08 |  |  | 2020-04-17 | [6 empty] | 2020-05-01 |  |  |  | 2020-05-01 |  |  |  | Awaiting MOC approval | 2020-03-25 |  | 2020-04-04 |  |  | 2020-04-08 | 2020-03-12 | 2020-04-11 |  |  | 2020-04-25 |  |  |  | 2020-05-02 |  | DGT-30-280C-2NPT |  |  | 2020-05-14 |  | 2020-04-22 | [6 empty] | 2020-05-22 | 2020-05-29 | [20 empty] | 2020-06-28 |  |  |  | 2020-07-01 | [8 empty] | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-22 |  |  |  | 2020-05-25 |  |  | 2020-06-01 |  |  |  | 2020-06-04 |  |  | 2020-06-19 |  |  |  | 2020-07-01 |  | 2020-07-04
PH1000023 | 124.6459 | 8.4851 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Barangay 19 | MIN | PH104305015 | 352 | 15 | Pole | CO70 | 96.934 | MIN-1000011 | Level 6 | phase3 | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020011304PH_WLS | PO Batch 3 | JXD-2 |  |  |  |  | 2020-01-16 | 2020-01-16 | 2020-01-18 | 2020-02-27 |  |  |  | 2020-02-27 | [8 empty] | 2020-01-23 | [11 empty] | 2020-02-22 | [27 empty] | 2020-02-29 |  |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 |  | 2020-03-24 |  |  | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-14 |  |  |  | 2020-04-21 |  | ZCG-12-280C-1NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1000024 | 124.6459 | 8.478 | Urban | Rooftop | Rooftop | Y1 | L7+L21+L26 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Barangay 40 | MIN | PH104305035 | 315 | 15 | Pole | CO70 | 96.2622 | MIN-1000012 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-19 | 2020-01-16 | 2020-01-21 | 2020-01-30 |  |  |  | 2020-01-30 | 2020-01-31 |  |  |  | 2020-01-31 |  |  |  | 2020-01-26 | 2020-01-31 |  |  |  | 2020-01-31 | 2020-01-30 |  |  |  | 2020-01-30 | 2020-02-19 | 2020-02-25 | [5 empty] | A | Gloria Tan | 120 Brgy. 8, Cagayan de Oro City | Misamis Oriental | 124.6442 | 8.479 | Rooftop |  |  | 10 years | P25,000 exclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-03 | 2020-02-13 |  | 2020-04-02 |  | 2020-03-10 | [16 empty] | 2020-03-31 |  |  | 2020-04-09 | [6 empty] | 2020-04-23 |  |  |  | 2020-04-23 |  |  |  |  | 2020-03-17 |  | 2020-03-27 |  |  | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-17 |  |  |  | 2020-04-24 |  | ZCG-12-280C-1NPT |  |  | 2020-05-06 |  | 2020-04-14 | [6 empty] | 2020-05-14 | 2020-05-21 | [20 empty] | 2020-06-20 |  |  |  | 2020-06-23 | [8 empty] | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-11 |  |  |  | 2020-06-23 |  | 2020-06-26
PH1000026 | 124.6522 | 8.4816 | Urban | Rooftop | Rooftop | Y1 | L7+L21+L26 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Barangay 28 | MIN | PH104305023 | 536 | 2 | Wall Mounted Pole | CO70 | 96.2503 | MIN-1000013 | Level 6 | phase3 | phase1_630 | P1_630 | Philcom_100 | Cluster M19 | Marrox | PO2020011304PH_WLS | PO Batch 3 | JXD-2 |  |  |  |  | 2020-01-22 | 2020-01-16 | 2020-01-24 | 2020-01-31 | 2020-01-31 | 2020-01-31 |  | 2020-01-31 | 2020-02-02 |  |  |  | 2020-02-02 |  |  |  | 2020-01-29 | 2020-02-02 |  |  |  | 2020-02-02 | [6 empty] | 2020-02-28 | [5 empty] | B |  |  |  | 124.65 | 8.4826 | [16 empty] | 2020-03-06 | 2020-02-13 |  | 2020-04-05 |  | 2020-03-13 | [16 empty] | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 |  | 2020-03-30 |  |  | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-20 |  |  |  | 2020-04-27 |  | ZCG-9-340D-1NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1000027 | 124.6522 | 8.4744 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Nazareth | MIN | PH104305042 | 30927 | 30 | Three Legged Tubular Tower | CO70 | 95.5602 | MIN-1000014 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-25 | 2020-01-30 | 2020-01-27 | 2020-01-31 |  |  |  | 2020-01-31 | 2020-02-02 |  |  |  | 2020-02-02 |  |  |  | 2020-02-01 | 2020-02-02 |  |  |  | 2020-02-02 | 2020-01-31 |  |  |  | 2020-01-31 | 2020-02-10 | 2020-03-02 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Peter Lui | Dols Commercial, JR Borja Ext., Brgy. 37, Cagayan de Oro City | Misamis Oriental | 124.6525 | 8.4768 | Rooftop |  | 16m | 10 years | P30,000 exclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-09 | 2020-02-13 |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 |  | 2020-04-02 |  |  | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-23 |  |  |  | 2020-04-30 |  | ZCG-9-340D-1NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1000028 | 124.6586 | 8.4924 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Puntod | MIN | PH104305064 | 18796 | 30 | Three Legged Tubular Tower | CO70 | 96.9405 | MIN-1000015 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-27 | 2020-01-20 | 2020-01-29 | 2020-02-03 |  |  |  | 2020-02-03 | 2020-02-07 |  |  |  | 2020-02-07 |  |  |  | 2020-02-03 | 2020-02-07 |  |  |  | 2020-02-07 | [6 empty] | 2020-03-04 | [5 empty] | A |  |  |  | 124.6604 | 8.4916 | [16 empty] | 2020-03-11 | 2020-02-13 |  | 2020-04-10 |  | 2020-03-18 | [16 empty] | 2020-04-08 |  |  | 2020-04-17 | [6 empty] | 2020-05-01 |  |  |  | 2020-05-01 |  |  |  |  | 2020-03-25 |  | 2020-04-04 |  |  | 2020-04-08 | 2020-03-07 | 2020-04-11 | 2020-03-09 | 2020-03-09 | 2020-04-25 |  |  |  | 2020-05-02 |  | DGT-30-280C-2NPT |  |  | 2020-05-14 |  | 2020-04-22 | [6 empty] | 2020-05-22 | 2020-05-29 | [20 empty] | 2020-06-28 |  |  |  | 2020-07-01 | [8 empty] | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-22 |  |  |  | 2020-05-25 |  |  | 2020-06-01 |  |  |  | 2020-06-04 |  |  | 2020-06-19 |  |  |  | 2020-07-01 |  | 2020-07-04
PH1000052 | 123.7466 | 8.0646 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Occidental | Tangub City | Barangay IV - St. Michael | MIN | PH104215014 | 892 | 40 | Three Legged Tubular Tower | CO68 | 108.7836 | MIN-1000016 | Level 6 | phase2_add | phase2_1231 |  | DICT_61 | Cluster M25 | TBD | [7 empty] | 2020-07-10 |  | 2020-07-12 | [13 empty] | 2020-07-17 | [11 empty] | 2020-08-16 | [27 empty] | 2020-08-23 |  |  | 2020-09-22 |  | 2020-08-30 | [16 empty] | 2020-09-20 |  |  | 2020-09-29 | [6 empty] | 2020-10-13 |  |  |  | 2020-10-13 |  |  |  |  | 2020-09-06 |  | 2020-09-16 |  |  | 2020-09-20 |  | 2020-09-23 |  |  | 2020-10-07 |  |  |  | 2020-10-14 |  | JGT-36-280C-2NPT |  |  | 2020-10-26 |  | 2020-10-04 | [6 empty] | 2020-11-03 | 2020-11-10 | [20 empty] | 2020-12-10 |  |  |  | 2020-12-13 | [8 empty] | 2020-10-19 |  | 2020-10-22 |  |  | 2020-11-03 |  |  |  | 2020-11-06 |  |  | 2020-11-13 |  |  |  | 2020-11-16 |  |  | 2020-12-01 |  |  |  | 2020-12-13 |  | 2020-12-16
PH1000055 | 123.7929 | 8.0549 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Tubod | Poblacion | MIN | PH103522019 | 10260 | 40 | Three Legged Tubular Tower | CO68 | 105.3289 | MIN-1000017 | Level 6 | phase2_add | phase2_1231 | OA_1231 | DICT_15 | Cluster M25 | TBD | [6 empty] | 2020-02-12 | 2020-07-11 |  | 2020-07-13 | [13 empty] | 2020-07-18 | [11 empty] | 2020-08-17 | [27 empty] | 2020-08-24 |  |  | 2020-09-23 |  | 2020-08-31 | [16 empty] | 2020-09-21 |  |  | 2020-09-30 | [6 empty] | 2020-10-14 |  |  |  | 2020-10-14 |  |  |  |  | 2020-09-07 |  | 2020-09-17 |  |  | 2020-09-21 |  | 2020-09-24 |  |  | 2020-10-08 |  |  |  | 2020-10-15 |  | JGT-36-280C-2NPT |  |  | 2020-10-27 |  | 2020-10-05 | [6 empty] | 2020-11-04 | 2020-11-11 | [20 empty] | 2020-12-11 |  |  |  | 2020-12-14 | [8 empty] | 2020-10-20 |  | 2020-10-23 |  |  | 2020-11-04 |  |  |  | 2020-11-07 |  |  | 2020-11-14 |  |  |  | 2020-11-17 |  |  | 2020-12-02 |  |  |  | 2020-12-14 |  | 2020-12-17
PH1000059 | 123.8263 | 8.1498 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Occidental | Ozamis City | Banadero | MIN | PH104210002 | 8000 | 40 | Three Legged Tubular Tower | CO68 | 113.1486 | MIN-1000018 | Level 6 | phase2_add | phase3 |  | DepEd_3097 | Cluster M25 | TBD | [7 empty] | 2020-07-21 |  | 2020-07-23 | [13 empty] | 2020-07-28 | [11 empty] | 2020-08-27 | [27 empty] | 2020-09-03 |  |  | 2020-10-03 |  | 2020-09-10 | [16 empty] | 2020-10-01 |  |  | 2020-10-10 | [6 empty] | 2020-10-24 |  |  |  | 2020-10-24 |  |  |  |  | 2020-09-17 |  | 2020-09-27 |  |  | 2020-10-01 |  | 2020-10-04 |  |  | 2020-10-18 |  |  |  | 2020-10-25 |  | JGT-36-280C-2NPT |  |  | 2020-11-06 |  | 2020-10-15 | [6 empty] | 2020-11-14 | 2020-11-21 | [20 empty] | 2020-12-21 |  |  |  | 2020-12-24 | [8 empty] | 2020-10-30 |  | 2020-11-02 |  |  | 2020-11-14 |  |  |  | 2020-11-17 |  |  | 2020-11-24 |  |  |  | 2020-11-27 |  |  | 2020-12-12 |  |  |  | 2020-12-24 |  | 2020-12-27
PH1000060 | 123.8376 | 8.1554 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Occidental | Ozamis City | Bacolod | MIN | PH104210012 | 5223 | 40 | Three Legged Tubular Tower | CO68 | 113.2046 | MIN-1000019 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-22 |  | 2020-07-24 | [13 empty] | 2020-07-29 | [11 empty] | 2020-08-28 | [27 empty] | 2020-09-04 |  |  | 2020-10-04 |  | 2020-09-11 | [16 empty] | 2020-10-02 |  |  | 2020-10-11 | [6 empty] | 2020-10-25 |  |  |  | 2020-10-25 |  |  |  |  | 2020-09-18 |  | 2020-09-28 |  |  | 2020-10-02 |  | 2020-10-05 |  |  | 2020-10-19 |  |  |  | 2020-10-26 |  | JGT-36-280C-2NPT |  |  | 2020-11-07 |  | 2020-10-16 | [6 empty] | 2020-11-15 | 2020-11-22 | [20 empty] | 2020-12-22 |  |  |  | 2020-12-25 | [8 empty] | 2020-10-31 |  | 2020-11-03 |  |  | 2020-11-15 |  |  |  | 2020-11-18 |  |  | 2020-11-25 |  |  |  | 2020-11-28 |  |  | 2020-12-13 |  |  |  | 2020-12-25 |  | 2020-12-28
PH1000063 | 123.8521 | 8.1817 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Occidental | Ozamis City | Labo | MIN | PH104210021 | 5686 | 40 | Three Legged Tubular Tower | CO68 | 115.2773 | MIN-1000020 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-23 |  | 2020-07-25 | [13 empty] | 2020-07-30 | [11 empty] | 2020-08-29 | [27 empty] | 2020-09-05 |  |  | 2020-10-05 |  | 2020-09-12 | [16 empty] | 2020-10-03 |  |  | 2020-10-12 | [6 empty] | 2020-10-26 |  |  |  | 2020-10-26 |  |  |  |  | 2020-09-19 |  | 2020-09-29 |  |  | 2020-10-03 |  | 2020-10-06 |  |  | 2020-10-20 |  |  |  | 2020-10-27 |  | JGT-36-280C-2NPT |  |  | 2020-11-08 |  | 2020-10-17 | [6 empty] | 2020-11-16 | 2020-11-23 | [20 empty] | 2020-12-23 |  |  |  | 2020-12-26 | [8 empty] | 2020-11-01 |  | 2020-11-04 |  |  | 2020-11-16 |  |  |  | 2020-11-19 |  |  | 2020-11-26 |  |  |  | 2020-11-29 |  |  | 2020-12-14 |  |  |  | 2020-12-26 |  | 2020-12-29
PH1000066 | 123.8603 | 8.1877 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Occidental | Clarin | Lapasan | MIN | PH104205016 | 4428 | 40 | Three Legged Tubular Tower | CO68 | 115.5625 | MIN-1000021 | Level 6 | phase2_add | phase3 |  | DepEd_3124 | Cluster M25 | TBD | [7 empty] | 2020-07-13 |  | 2020-07-15 | [13 empty] | 2020-07-20 | [11 empty] | 2020-08-19 | [27 empty] | 2020-08-26 | 2020-01-22 |  | 2020-09-25 |  | 2020-09-02 | [16 empty] | 2020-09-23 |  |  | 2020-10-02 | [6 empty] | 2020-10-16 |  |  |  | 2020-10-16 |  |  |  |  | 2020-09-09 |  | 2020-09-19 |  |  | 2020-09-23 |  | 2020-09-26 |  |  | 2020-10-10 |  |  |  | 2020-10-17 |  | JGT-36-280C-2NPT |  |  | 2020-10-29 |  | 2020-10-07 | [6 empty] | 2020-11-06 | 2020-11-13 | [20 empty] | 2020-12-13 |  |  |  | 2020-12-16 | [8 empty] | 2020-10-22 |  | 2020-10-25 |  |  | 2020-11-06 |  |  |  | 2020-11-09 |  |  | 2020-11-16 |  |  |  | 2020-11-19 |  |  | 2020-12-04 |  |  |  | 2020-12-16 |  | 2020-12-19
PH1000067 | 123.8618 | 8.1764 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Occidental | Ozamis City | Gango | MIN | PH104210021 | 5686 | 40 | Three Legged Tubular Tower | CO68 | 114.3276 | MIN-1000022 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-24 |  | 2020-07-26 | [13 empty] | 2020-07-31 | [11 empty] | 2020-08-30 | [27 empty] | 2020-09-06 |  |  | 2020-10-06 |  | 2020-09-13 | [16 empty] | 2020-10-04 |  |  | 2020-10-13 | [6 empty] | 2020-10-27 |  |  |  | 2020-10-27 |  |  |  |  | 2020-09-20 |  | 2020-09-30 |  |  | 2020-10-04 |  | 2020-10-07 |  |  | 2020-10-21 |  |  |  | 2020-10-28 |  | JGT-36-280C-2NPT |  |  | 2020-11-09 |  | 2020-10-18 | [6 empty] | 2020-11-17 | 2020-11-24 | [20 empty] | 2020-12-24 |  |  |  | 2020-12-27 | [8 empty] | 2020-11-02 |  | 2020-11-05 |  |  | 2020-11-17 |  |  |  | 2020-11-20 |  |  | 2020-11-27 |  |  |  | 2020-11-30 |  |  | 2020-12-15 |  |  |  | 2020-12-27 |  | 2020-12-30
PH1000068 | 124.1377 | 8.1856 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Linamon | Larapan | MIN | PH103510008 | 3536 | 40 | Three Legged Tubular Tower | CO68 | 107.7848 | MIN-1000023 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-23 | 2020-01-11 | 2020-01-25 | 2020-01-13 |  |  |  | 2020-01-13 | 2020-01-23 |  |  |  | 2020-01-23 |  |  |  | 2020-01-30 | 2020-01-23 |  |  |  | 2020-01-23 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-02-25 | 2020-02-29 | [5 empty] | A | Saripada Hadjiyusoph | Brgy. Samburon, Linamon | Lanao del Norte | 124.1385 | 8.1853 | Greenfield | 24m |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-07 |  |  | 2020-04-06 |  | 2020-03-14 | [16 empty] | 2020-04-04 |  |  | 2020-04-13 | [6 empty] | 2020-04-27 |  |  |  | 2020-04-27 |  |  |  |  | 2020-03-21 |  | 2020-03-31 |  |  | 2020-04-04 |  | 2020-04-07 |  |  | 2020-04-21 |  |  |  | 2020-04-28 |  | JGT-36-280C-2NPT |  |  | 2020-05-10 |  | 2020-04-18 | [6 empty] | 2020-05-18 | 2020-05-25 | [20 empty] | 2020-06-24 |  |  |  | 2020-06-27 | [8 empty] | 2020-05-03 |  | 2020-05-06 |  |  | 2020-05-18 |  |  |  | 2020-05-21 |  |  | 2020-05-28 |  |  |  | 2020-05-31 |  |  | 2020-06-15 |  |  |  | 2020-06-27 |  | 2020-06-30
PH1000070 | 124.1747 | 8.1867 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Buru-Un | MIN | PH103504005 | 15164 | 40 | Three Legged Tubular Tower | CO68 | 107.5202 | MIN-1000024 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DICT_14 | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-25 | 2020-01-11 | 2020-01-27 | 2020-01-13 |  |  |  | 2020-01-13 | 2020-02-02 |  |  |  | 2020-02-02 |  |  |  | 2020-02-01 | 2020-02-02 |  |  |  | 2020-02-02 | [6 empty] | 2020-03-02 | [5 empty] | A |  |  |  | 124.1747 | 8.1827 | [16 empty] | 2020-03-09 |  |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 |  | 2020-04-02 |  |  | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-23 |  |  |  | 2020-04-30 |  | JGT-36-280C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1000076 | 124.2254 | 8.1909 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Santa Elena | MIN | PH103504021 | 9735 | 40 | Three Legged Tubular Tower | CO68 | 107.7089 | MIN-1000025 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-12 | 2020-01-11 | 2020-01-14 |  | 2020-02-03 |  |  | 2020-02-03 | 2020-01-13 |  |  |  | 2020-01-13 |  |  |  | 2020-01-19 | 2020-01-13 |  |  |  | 2020-01-13 |  | 2020-02-03 |  |  | 2020-02-03 |  | 2020-02-18 | [5 empty] | A |  |  |  | 124.2257 | 8.1912 | Greenfield | 57m | [14 empty] | 2020-02-25 |  |  | 2020-03-26 |  | 2020-03-03 | [16 empty] | 2020-03-24 |  |  | 2020-04-02 | [6 empty] | 2020-04-16 |  |  |  | 2020-04-16 |  |  |  |  | 2020-03-10 |  | 2020-03-20 |  |  | 2020-03-24 |  | 2020-03-27 |  |  | 2020-04-10 |  |  |  | 2020-04-17 |  | JGT-36-280C-2NPT |  |  | 2020-04-29 |  | 2020-04-07 | [6 empty] | 2020-05-07 | 2020-05-14 | [20 empty] | 2020-06-13 |  |  |  | 2020-06-16 | [8 empty] | 2020-04-22 |  | 2020-04-25 |  |  | 2020-05-07 |  |  |  | 2020-05-10 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-06-04 |  |  |  | 2020-06-16 |  | 2020-06-19
PH1000080 | 124.2557 | 8.2656 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Santa Filomena | MIN | PH103504022 | 6615 | 40 | Three Legged Tubular Tower | CO70 | 109.6826 | MIN-1000026 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-29 | 2020-01-20 | 2020-01-31 | 2020-01-22 | 2020-02-19 |  |  | 2020-01-22 |  | 2020-02-22 |  |  | 2020-02-22 |  |  |  | 2020-02-05 |  | 2020-02-22 |  |  | 2020-02-22 | 2020-01-22 | 2020-02-19 |  |  | 2020-01-22 |  | 2020-03-06 | [5 empty] | B |  |  |  | 124.2588 | 8.263 | [16 empty] | 2020-03-13 |  |  | 2020-04-12 |  | 2020-03-20 | [16 empty] | 2020-04-10 |  |  | 2020-04-19 | [6 empty] | 2020-05-03 |  |  |  | 2020-05-03 |  |  |  |  | 2020-03-27 |  | 2020-04-06 |  |  | 2020-04-10 |  | 2020-04-13 |  |  | 2020-04-27 |  |  |  | 2020-05-04 |  | JGT-36-280C-2NPT |  |  | 2020-05-16 |  | 2020-04-24 | [6 empty] | 2020-05-24 | 2020-05-31 | [20 empty] | 2020-06-30 |  |  |  | 2020-07-03 | [8 empty] | 2020-05-09 |  | 2020-05-12 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-03 |  |  |  | 2020-06-06 |  |  | 2020-06-21 |  |  |  | 2020-07-03 |  | 2020-07-06
PH1000082 | 124.2547 | 8.1964 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Tipanoy | MIN | PH103504027 | 14730 | 40 | Monopole Tower | CO70 | 105.8629 | MIN-1000027 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M26 | Enovell | [7 empty] | 2020-02-17 |  | 2020-02-19 | [13 empty] | 2020-02-24 | [11 empty] | 2020-03-25 | [27 empty] | 2020-04-01 |  |  | 2020-05-01 |  | 2020-04-08 | [16 empty] | 2020-04-29 |  |  | 2020-05-08 | [6 empty] | 2020-05-22 |  |  |  | 2020-05-22 |  |  |  |  | 2020-04-15 |  | 2020-04-25 |  |  | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-16 |  |  |  | 2020-05-23 |  | JGT-36-280C-2NPT |  |  | 2020-06-04 |  | 2020-05-13 | [6 empty] | 2020-06-12 | 2020-06-19 | [20 empty] | 2020-07-19 |  |  |  | 2020-07-22 | [8 empty] | 2020-05-28 |  | 2020-05-31 |  |  | 2020-06-12 |  |  |  | 2020-06-15 |  |  | 2020-06-22 |  |  |  | 2020-06-25 |  |  | 2020-07-10 |  |  |  | 2020-07-22 |  | 2020-07-25
PH1000083 | 124.2655 | 8.2824 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Kiwalan | MIN | PH103504011 | 7464 | 40 | Monopole Tower | CO70 | 109.7944 | MIN-1000028 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-31 | 2020-01-20 | 2020-02-02 | 2020-02-01 | 2020-02-19 |  |  | 2020-02-01 |  | 2020-02-22 |  |  | 2020-02-22 |  |  |  | 2020-02-07 |  | 2020-02-22 |  |  | 2020-02-22 | 2020-02-01 | 2020-02-19 |  |  | 2020-02-01 |  | 2020-03-08 | [5 empty] | B |  |  |  | 124.2712 | 8.2782 | [16 empty] | 2020-03-15 |  |  | 2020-04-14 |  | 2020-03-22 | [16 empty] | 2020-04-12 |  |  | 2020-04-21 | [6 empty] | 2020-05-05 |  |  |  | 2020-05-05 |  |  |  |  | 2020-03-29 |  | 2020-04-08 |  |  | 2020-04-12 |  | 2020-04-15 |  |  | 2020-04-29 |  |  |  | 2020-05-06 |  | JGT-36-280C-2NPT |  |  | 2020-05-18 |  | 2020-04-26 | [6 empty] | 2020-05-26 | 2020-06-02 | [20 empty] | 2020-07-02 |  |  |  | 2020-07-05 | [8 empty] | 2020-05-11 |  | 2020-05-14 |  |  | 2020-05-26 |  |  |  | 2020-05-29 |  |  | 2020-06-05 |  |  |  | 2020-06-08 |  |  | 2020-06-23 |  |  |  | 2020-07-05 |  | 2020-07-08
PH1000084 | 124.5192 | 8.5599 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | El Salvador City | Poblacion | MIN | PH104307012 | 8372 | 40 | Three Legged Tubular Tower | CO70 | 111.4802 | MIN-1000029 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-16 | 2020-02-25 | 2020-01-18 | 2020-02-25 |  |  |  | 2020-02-25 | 2020-02-25 |  |  |  | 2020-02-25 |  |  |  | 2020-01-23 | 2020-02-25 |  |  |  | 2020-02-25 | 2020-02-26 |  |  |  | 2020-02-26 | 2020-03-04 | 2020-02-22 | 2020-03-04 |  |  | 2020-03-05 | 2020-03-05 |  | JESUS NERI/ GENARA NERI | ZONE 3, POBLACION, EL SALVADOR CITY | Misamis Oriental | 124.5221 | 8.5597 | Greenfield |  |  | 10 years | P15,000 Exclusive of VAT and withholding tax | quarterly | 150sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-29 |  |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 | 2020-03-02 | 2020-03-24 | 2020-03-12 | 2020-03-12 | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-14 |  |  |  | 2020-04-21 |  | JGT-36-280C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1000085 | 124.5679 | 8.5317 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | El Salvador City | Molugan | MIN | PH104307011 | 10547 | 40 | Three Legged Tubular Tower | CO70 | 105.8838 | MIN-1000030 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-19 | 2020-01-21 | 2020-01-21 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-23 |  |  |  | 2020-01-23 |  |  |  | 2020-01-26 | 2020-01-23 |  |  |  | 2020-01-23 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-02-26 | 2020-02-25 | [5 empty] | A | Rodjer Belida | Zone 1, Molugan, El Salvador City | Misamis Oriental | 124.5675 | 8.5318 | Greenfield | 20m |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 150sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-03 | 2020-02-13 |  | 2020-04-02 |  | 2020-03-10 | [11 empty] | 0995-2612262 |  |  |  |  | 2020-03-31 |  |  | 2020-04-09 | [6 empty] | 2020-04-23 |  |  |  | 2020-04-23 |  |  |  |  | 2020-03-17 | 2020-02-26 | 2020-03-27 | 2020-02-28 | 2020-02-29 | 2020-03-31 | 2020-03-06 | 2020-04-03 | 2020-03-07 | 2020-03-07 | 2020-04-17 | 2020-03-07 | 2020-03-07 | 2020-03-07 | 2020-04-24 | 2020-03-07 | JGT-36-280C-2NPT |  |  | 2020-05-06 |  | 2020-04-14 | [6 empty] | 2020-05-14 | 2020-05-21 | [20 empty] | 2020-06-20 |  |  |  | 2020-06-23 | [8 empty] | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-11 |  |  |  | 2020-06-23 |  | 2020-06-26
PH1000086 | 124.5776 | 8.5148 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Opol | Taboc | MIN | PH104321015 | 3400 | 40 | Monopole Tower | CO70 | 103.7325 | MIN-1000031 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-22 | 2020-02-03 | 2020-01-24 | 2020-02-04 | 2020-02-05 |  |  | 2020-02-04 |  | 2020-02-07 |  |  | 2020-02-07 |  |  |  | 2020-01-29 |  | 2020-02-07 |  |  | 2020-02-07 | 2020-02-04 |  |  |  | 2020-02-04 | 2020-02-24 | 2020-02-28 | 2020-02-26 |  |  | 2020-02-26 | 2020-03-02 | A | Gil Ajoc | Zone 4, Bonbon, Opol | Misamis Oriental | 124.5699 | 8.5198 | Greenfield |  |  | 10 years | P18,000 exclusive of VAT and withholding tax | quarterly | 200sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-06 | 2020-02-13 |  | 2020-04-05 |  | 2020-03-13 | [16 empty] | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 | 2020-03-02 | 2020-03-30 | 2020-03-12 | 2020-03-12 | 2020-04-03 | 2020-03-06 | 2020-04-06 | 2020-03-09 | 2020-03-09 | 2020-04-20 |  |  |  | 2020-04-27 |  | JGT-36-280C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1000087 | 124.5873 | 8.5092 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Opol | Igpit | MIN | PH104321006 | 11800 | 40 | Monopole Tower | CO70 | 102.6208 | MIN-1000032 | Level 6 | phase3 | phase3 |  | DepEd_3101 | Cluster M19 | Marrox | [7 empty] | 2020-02-02 |  | 2020-02-04 | [13 empty] | 2020-02-09 | [11 empty] | 2020-03-10 | [27 empty] | 2020-03-17 |  |  | 2020-04-16 |  | 2020-03-24 | [16 empty] | 2020-04-14 |  |  | 2020-04-23 | [6 empty] | 2020-05-07 |  |  |  | 2020-05-07 |  |  |  |  | 2020-03-31 |  | 2020-04-10 |  |  | 2020-04-14 |  | 2020-04-17 |  |  | 2020-05-01 |  |  |  | 2020-05-08 |  | JGT-36-280C-2NPT |  |  | 2020-05-20 |  | 2020-04-28 | [6 empty] | 2020-05-28 | 2020-06-04 | [20 empty] | 2020-07-04 |  |  |  | 2020-07-07 | [8 empty] | 2020-05-13 |  | 2020-05-16 |  |  | 2020-05-28 |  |  |  | 2020-05-31 |  |  | 2020-06-07 |  |  |  | 2020-06-10 |  |  | 2020-06-25 |  |  |  | 2020-07-07 |  | 2020-07-10
PH1000091 | 124.597 | 8.5036 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Iponan | MIN | PH104321003 | 14665 | 40 | Three Legged Tubular Tower | CO70 | 101.512 | MIN-1000033 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-17 | 2020-02-06 | 2020-01-19 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-02-09 |  |  |  | 2020-02-09 |  |  |  | 2020-01-24 | 2020-02-09 |  |  |  | 2020-02-09 | 2020-03-03 |  |  |  | 2020-03-03 | 2020-03-04 | 2020-02-23 | 2020-03-04 |  |  | 2020-03-05 | 2020-03-05 | A | Romulo Silvestre | Iponan, Cagayan de Oro City | Misamis Oriental | 124.5967 | 8.5024 | Greenfield |  |  | 10 years | P21,000 Exclusive of VAT and withholding tax | quarterly | 150sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-01 | 2020-02-13 |  | 2020-03-31 |  | 2020-03-08 | [16 empty] | 2020-03-29 |  |  | 2020-04-07 | [6 empty] | 2020-04-21 |  |  |  | 2020-04-21 |  |  |  |  | 2020-03-15 | 2020-03-02 | 2020-03-25 | 2020-03-12 | 2020-03-12 | 2020-03-29 | 2020-03-07 | 2020-04-01 | 2020-03-09 | 2020-03-09 | 2020-04-15 |  |  |  | 2020-04-22 |  | JGT-36-280C-2NPT |  |  | 2020-05-04 |  | 2020-04-12 | [6 empty] | 2020-05-12 | 2020-05-19 | [20 empty] | 2020-06-18 |  |  |  | 2020-06-21 | [8 empty] | 2020-04-27 |  | 2020-04-30 |  |  | 2020-05-12 |  |  |  | 2020-05-15 |  |  | 2020-05-22 |  |  |  | 2020-05-25 |  |  | 2020-06-09 |  |  |  | 2020-06-21 |  | 2020-06-24
PH1000092 | 124.597 | 8.4923 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Iponan | MIN | PH104305051 | 26340 | 40 | Three Legged Tubular Tower | CO70 | 100.469 | MIN-1000034 | Level 6 | phase3 | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020011304PH_WLS | PO Batch 3 | JXD-2 |  |  |  |  | 2020-01-20 | 2020-01-27 | 2020-01-22 | 2020-01-28 |  |  |  | 2020-01-28 | 2020-02-08 |  |  |  | 2020-02-08 |  |  |  | 2020-01-27 | 2020-02-08 |  |  |  | 2020-02-08 | 2020-01-28 |  |  |  | 2020-01-28 | 2020-03-02 | 2020-02-26 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 | A | EDGAR DEGRACIA | FICCOVILLE IPONAN, CAGAYAN DE ORO CITY | Misamis Oriental | 124.5962 | 8.4917 | Greenfield |  |  | 10 years | P22,000 exclusive of VAT and withholding tax | quarterly | 150sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-04 | 2020-02-13 |  | 2020-04-03 |  | 2020-03-11 | [16 empty] | 2020-04-01 |  |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  |  | 2020-03-18 |  | 2020-03-28 |  |  | 2020-04-01 | 2020-03-07 | 2020-04-04 | 2020-03-09 | 2020-03-09 | 2020-04-18 |  |  |  | 2020-04-25 |  | JGT-36-280C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1000099 | 124.6066 | 8.4643 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Pagatpat | MIN | PH104305043 | 27815 | 40 | Three Legged Tubular Tower | CO70 | 97.2802 | MIN-1000035 | Level 6 | phase3 | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-02-05 |  | 2020-02-07 | [13 empty] | 2020-02-12 | [11 empty] | 2020-03-13 | [27 empty] | 2020-03-20 |  |  | 2020-04-19 |  | 2020-03-27 | [16 empty] | 2020-04-17 |  |  | 2020-04-26 | [6 empty] | 2020-05-10 |  |  |  | 2020-05-10 |  |  |  |  | 2020-04-03 |  | 2020-04-13 |  |  | 2020-04-17 |  | 2020-04-20 |  |  | 2020-05-04 |  |  |  | 2020-05-11 |  | JGT-36-280C-2NPT |  |  | 2020-05-23 |  | 2020-05-01 | [6 empty] | 2020-05-31 | 2020-06-07 | [20 empty] | 2020-07-07 |  |  |  | 2020-07-10 | [8 empty] | 2020-05-16 |  | 2020-05-19 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-10 |  |  |  | 2020-06-13 |  |  | 2020-06-28 |  |  |  | 2020-07-10 |  | 2020-07-13
PH1000101 | 124.6065 | 8.4306 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Lumbia | MIN | PH104305054 | 22429 | 40 | Three Legged Tubular Tower | CO70 | 94.1986 | MIN-1000036 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-17 | 2020-01-23 | 2020-01-19 | 2020-01-24 | 2020-01-30 |  |  | 2020-01-24 | 2020-01-31 |  |  |  | 2020-01-31 |  |  |  | 2020-01-24 | 2020-01-31 |  |  |  | 2020-01-31 | [6 empty] | 2020-02-23 | [5 empty] | B |  |  |  | 124.6082 | 8.4283 | [16 empty] | 2020-03-01 | 2020-02-13 |  | 2020-03-31 |  | 2020-03-08 | [16 empty] | 2020-03-29 |  |  | 2020-04-07 | [6 empty] | 2020-04-21 |  |  |  | 2020-04-21 |  |  |  |  | 2020-03-15 | 2020-02-26 | 2020-03-25 | 2020-02-28 | 2020-02-29 | 2020-03-29 | 2020-03-06 | 2020-04-01 | 2020-03-07 | 2020-03-07 | 2020-04-15 |  |  |  | 2020-04-22 |  | JGT-36-280C-2NPT |  |  | 2020-05-04 |  | 2020-04-12 | [6 empty] | 2020-05-12 | 2020-05-19 | [20 empty] | 2020-06-18 |  |  |  | 2020-06-21 | [8 empty] | 2020-04-27 |  | 2020-04-30 |  |  | 2020-05-12 |  |  |  | 2020-05-15 |  |  | 2020-05-22 |  |  |  | 2020-05-25 |  |  | 2020-06-09 |  |  |  | 2020-06-21 |  | 2020-06-24
PH1000103 | 124.6165 | 8.5035 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Bulua | MIN | PH104305003 | 32348 | 40 | Monopole Tower | CO70 | 100.3589 | MIN-1000037 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_3064 | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-25 | 2020-01-18 | 2020-01-27 | 2020-02-05 |  |  |  | 2020-02-05 | 2020-02-08 |  |  |  | 2020-02-08 |  |  |  | 2020-02-01 | 2020-02-08 |  |  |  | 2020-02-08 | [6 empty] | 2020-03-02 | [5 empty] | A |  |  |  | 124.6155 | 8.505 | [16 empty] | 2020-03-09 | 2020-02-13 |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 |  | 2020-04-02 |  |  | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-23 |  |  |  | 2020-04-30 |  | JGT-36-280C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1000104 | 124.6165 | 8.4923 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Patag | MIN | PH104305061 | 17742 | 40 | Three Legged Tubular Tower | CO70 | 99.3038 | MIN-1000038 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-28 | 2020-01-16 | 2020-01-30 | 2020-02-27 |  |  |  | 2020-02-27 | [8 empty] | 2020-02-04 | [5 empty] | 2020-02-28 |  |  |  | 2020-02-28 |  | 2020-03-05 | [27 empty] | 2020-03-12 |  |  | 2020-04-11 |  | 2020-03-19 | [16 empty] | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 |  | 2020-04-05 |  |  | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-26 |  |  |  | 2020-05-03 |  | JGT-36-280C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1000107 | 124.6164 | 8.4586 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Pagatpat | MIN | PH104305044 | 70492 | 40 | Three Legged Tubular Tower | CO70 | 96.166 | MIN-1000039 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-20 | 2020-02-12 | 2020-01-22 | 2020-02-13 |  |  |  | 2020-02-13 | [8 empty] | 2020-01-27 | [11 empty] | 2020-02-26 | [27 empty] | 2020-03-04 |  |  | 2020-04-03 |  | 2020-03-11 | [16 empty] | 2020-04-01 |  |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  |  | 2020-03-18 |  | 2020-03-28 |  |  | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-18 |  |  |  | 2020-04-25 |  | JGT-36-280C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1000111 | 124.6262 | 8.4866 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Patag | MIN | PH104305061 | 17742 | 40 | Three Legged Tubular Tower | CO70 | 98.2045 | MIN-1000040 | Level 6 | phase3 | phase3 |  | DICT_54 | Cluster M19 | Marrox | [7 empty] | 2020-02-08 | 2020-01-21 | 2020-02-10 | [13 empty] | 2020-02-15 | [11 empty] | 2020-03-16 | [27 empty] | 2020-03-23 |  |  | 2020-04-22 |  | 2020-03-30 | [16 empty] | 2020-04-20 |  |  | 2020-04-29 | [6 empty] | 2020-05-13 |  |  |  | 2020-05-13 |  |  |  |  | 2020-04-06 |  | 2020-04-16 |  |  | 2020-04-20 |  | 2020-04-23 |  |  | 2020-05-07 |  |  |  | 2020-05-14 |  | JGT-36-280C-2NPT |  |  | 2020-05-26 |  | 2020-05-04 | [6 empty] | 2020-06-03 | 2020-06-10 | [20 empty] | 2020-07-10 |  |  |  | 2020-07-13 | [8 empty] | 2020-05-19 |  | 2020-05-22 |  |  | 2020-06-03 |  |  |  | 2020-06-06 |  |  | 2020-06-13 |  |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  |  | 2020-07-13 |  | 2020-07-16
PH1000112 | 124.6262 | 8.4754 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Carmen | MIN | PH104305044 | 70492 | 40 | Three Legged Tubular Tower | CO70 | 97.1501 | MIN-1000041 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-23 | 2020-01-21 | 2020-01-25 | 2020-01-30 | 2020-02-08 |  |  | 2020-01-30 |  | 2020-02-10 |  |  | 2020-02-10 |  |  |  | 2020-01-30 |  | 2020-02-10 |  |  | 2020-02-10 | 2020-01-30 | 2020-02-08 |  |  | 2020-01-30 | 2020-03-02 | 2020-02-29 | 2020-03-04 |  |  | 2020-03-02 | 2020-03-04 | B | Patricio Ras | C.M. Recto Avenue, Lapasan, Cagayan de Oro City | Misamis Oriental | 124.6256 | 8.4709 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-07 | 2020-02-12 |  | 2020-04-06 |  | 2020-03-14 | [16 empty] | 2020-04-04 |  |  | 2020-04-13 | [6 empty] | 2020-04-27 |  |  |  | 2020-04-27 |  |  |  |  | 2020-03-21 |  | 2020-03-31 |  |  | 2020-04-04 | 2020-03-09 | 2020-04-07 |  |  | 2020-04-21 |  |  |  | 2020-04-28 |  | JGT-36-280C-2NPT |  |  | 2020-05-10 |  | 2020-04-18 | [6 empty] | 2020-05-18 | 2020-05-25 | [20 empty] | 2020-06-24 |  |  |  | 2020-06-27 | [8 empty] | 2020-05-03 |  | 2020-05-06 |  |  | 2020-05-18 |  |  |  | 2020-05-21 |  |  | 2020-05-28 |  |  |  | 2020-05-31 |  |  | 2020-06-15 |  |  |  | 2020-06-27 |  | 2020-06-30
PH1000114 | 124.6261 | 8.453 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Balulang | MIN | PH104305005 | 34793 | 15 | Pole | CO70 | 95.0551 | MIN-1000042 | Level 6 | phase3 | phase3 |  | Philcom_205 | Cluster M19 | Marrox | [7 empty] | 2020-02-11 | 2020-01-16 | 2020-02-13 | [13 empty] | 2020-02-18 | [11 empty] | 2020-03-19 | [27 empty] | 2020-03-26 |  |  | 2020-04-25 |  | 2020-04-02 | [16 empty] | 2020-04-23 |  |  | 2020-05-02 | [6 empty] | 2020-05-16 |  |  |  | 2020-05-16 |  |  |  |  | 2020-04-09 |  | 2020-04-19 |  |  | 2020-04-23 |  | 2020-04-26 |  |  | 2020-05-10 |  |  |  | 2020-05-17 |  | JGT-36-280C-2NPT |  |  | 2020-05-29 |  | 2020-05-07 | [6 empty] | 2020-06-06 | 2020-06-13 | [20 empty] | 2020-07-13 |  |  |  | 2020-07-16 | [8 empty] | 2020-05-22 |  | 2020-05-25 |  |  | 2020-06-06 |  |  |  | 2020-06-09 |  |  | 2020-06-16 |  |  |  | 2020-06-19 |  |  | 2020-07-04 |  |  |  | 2020-07-16 |  | 2020-07-19
PH1000115 | 124.626 | 8.4418 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Balulang | MIN | PH104305005 | 34793 | 40 | Three Legged Tubular Tower | CO70 | 94.0149 | MIN-1000043 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-28 |  | 2020-01-30 | [13 empty] | 2020-02-04 | [11 empty] | 2020-03-05 | [27 empty] | 2020-03-12 |  |  | 2020-04-11 |  | 2020-03-19 | [16 empty] | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 |  | 2020-04-05 |  |  | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-26 |  |  |  | 2020-05-03 |  | JGT-36-280C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1000118 | 124.6361 | 8.5034 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Bayabas | MIN | PH104305052 | 35069 | 40 | Three Legged Tubular Tower | CO70 | 99.2387 | MIN-1000044 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-30 | 2020-01-20 | 2020-02-01 | 2020-01-30 |  |  |  | 2020-01-30 | 2020-01-31 |  |  |  | 2020-01-31 |  |  |  | 2020-02-06 | 2020-01-31 |  |  |  | 2020-01-31 | 2020-01-30 |  |  |  | 2020-01-30 | 2020-02-19 | 2020-03-07 | [5 empty] | A | Mary Rose Shivanii Beja | San Marcos St., Kauswagan, Cagayan de Oro City | Misamis Oriental | 124.6353 | 8.5037 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-14 | 2020-02-13 |  | 2020-04-13 |  | 2020-03-21 | [16 empty] | 2020-04-11 |  |  | 2020-04-20 | [6 empty] | 2020-05-04 |  |  |  | 2020-05-04 |  |  |  |  | 2020-03-28 | 2020-02-26 | 2020-04-07 | 2020-02-28 | 2020-02-29 | 2020-04-11 | 2020-03-05 | 2020-04-14 | 2020-03-06 | 2020-03-06 | 2020-04-28 | 2020-03-07 | 2020-03-07 | 2020-03-07 | 2020-05-05 | 2020-03-07 | JGT-36-280C-2NPT |  |  | 2020-05-17 |  | 2020-04-25 | [6 empty] | 2020-05-25 | 2020-06-01 | [20 empty] | 2020-07-01 |  |  |  | 2020-07-04 | [8 empty] | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-04 |  |  |  | 2020-06-07 |  |  | 2020-06-22 |  |  |  | 2020-07-04 |  | 2020-07-07
PH1000119 | 124.636 | 8.4922 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Kauswagan | MIN | PH104305052 | 35069 | 40 | Three Legged Tubular Tower | CO70 | 98.1716 | MIN-1000045 | Level 6 | phase3 | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-02-14 |  | 2020-02-16 | [13 empty] | 2020-02-21 | [11 empty] | 2020-03-22 | [27 empty] | 2020-03-29 |  |  | 2020-04-28 |  | 2020-04-05 | [16 empty] | 2020-04-26 |  |  | 2020-05-05 | [6 empty] | 2020-05-19 |  |  |  | 2020-05-19 |  |  |  |  | 2020-04-12 |  | 2020-04-22 |  |  | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-13 |  |  |  | 2020-05-20 |  | JGT-36-280C-2NPT |  |  | 2020-06-01 |  | 2020-05-10 | [6 empty] | 2020-06-09 | 2020-06-16 | [20 empty] | 2020-07-16 |  |  |  | 2020-07-19 | [8 empty] | 2020-05-25 |  | 2020-05-28 |  |  | 2020-06-09 |  |  |  | 2020-06-12 |  |  | 2020-06-19 |  |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  |  | 2020-07-19 |  | 2020-07-22
PH1000120 | 124.6359 | 8.4698 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Carmen | MIN | PH104305044 | 70492 | 40 | Three Legged Tubular Tower | CO70 | 96.0504 | MIN-1000046 | Level 6 | phase3 | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-02-17 |  | 2020-02-19 | [13 empty] | 2020-02-24 | [11 empty] | 2020-03-25 | [27 empty] | 2020-04-01 |  |  | 2020-05-01 |  | 2020-04-08 | [16 empty] | 2020-04-29 |  |  | 2020-05-08 | [6 empty] | 2020-05-22 |  |  |  | 2020-05-22 |  |  |  |  | 2020-04-15 |  | 2020-04-25 |  |  | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-16 |  |  |  | 2020-05-23 |  | JGT-36-280C-2NPT |  |  | 2020-06-04 |  | 2020-05-13 | [6 empty] | 2020-06-12 | 2020-06-19 | [20 empty] | 2020-07-19 |  |  |  | 2020-07-22 | [8 empty] | 2020-05-28 |  | 2020-05-31 |  |  | 2020-06-12 |  |  |  | 2020-06-15 |  |  | 2020-06-22 |  |  |  | 2020-06-25 |  |  | 2020-07-10 |  |  |  | 2020-07-22 |  | 2020-07-25
PH1000121 | 124.6359 | 8.4585 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Macasandig | MIN | PH104305056 | 20738 | 40 | Three Legged Tubular Tower | CO70 | 94.9965 | MIN-1000047 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-30 | 2020-01-18 | 2020-02-01 | 2020-01-20 | 2020-02-01 | 2020-02-05 |  | 2020-01-20 | 2020-01-20 |  | 2020-02-07 |  | 2020-01-20 |  |  |  | 2020-02-06 |  | 2020-02-07 | 2020-02-11 |  | 2020-02-07 | 2020-01-20 | 2020-02-01 |  |  | 2020-01-20 | 2020-03-04 | 2020-03-07 | 2020-03-04 |  |  | 2020-03-05 | 2020-03-05 | A | Rey Yap | Lower Tambo, Macasandig, Cagayan de Oro City | Misamis Oriental | 124.6385 | 8.464 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-14 | 2020-02-12 |  | 2020-04-13 |  | 2020-03-21 | [11 empty] | 0935-4722049 |  |  |  |  | 2020-04-11 |  |  | 2020-04-20 | [6 empty] | 2020-05-04 |  |  |  | 2020-05-04 |  |  |  |  | 2020-03-28 | 2020-03-12 | 2020-04-07 | 2020-03-12 | 2020-03-12 | 2020-04-11 | 2020-03-07 | 2020-04-14 | 2020-03-10 | 2020-03-10 | 2020-04-28 |  |  |  | 2020-05-05 |  | JGT-36-280C-2NPT |  |  | 2020-05-17 |  | 2020-04-25 | [6 empty] | 2020-05-25 | 2020-06-01 | [20 empty] | 2020-07-01 |  |  |  | 2020-07-04 | [8 empty] | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-04 |  |  |  | 2020-06-07 |  |  | 2020-06-22 |  |  |  | 2020-07-04 |  | 2020-07-07
PH1000125 | 124.6458 | 8.4977 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Kauswagan | MIN | PH104305052 | 35069 | 40 | Three Legged Tubular Tower | CO70 | 98.1543 | MIN-1000048 | Level 6 | phase3 | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-02-20 |  | 2020-02-22 | [13 empty] | 2020-02-27 | [11 empty] | 2020-03-28 | [27 empty] | 2020-04-04 |  |  | 2020-05-04 |  | 2020-04-11 | [16 empty] | 2020-05-02 |  |  | 2020-05-11 | [6 empty] | 2020-05-25 |  |  |  | 2020-05-25 |  |  |  |  | 2020-04-18 |  | 2020-04-28 |  |  | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-19 |  |  |  | 2020-05-26 |  | JGT-36-280C-2NPT |  |  | 2020-06-07 |  | 2020-05-16 | [6 empty] | 2020-06-15 | 2020-06-22 | [20 empty] | 2020-07-22 |  |  |  | 2020-07-25 | [8 empty] | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-06-25 |  |  |  | 2020-06-28 |  |  | 2020-07-13 |  |  |  | 2020-07-25 |  | 2020-07-28
PH1000126 | 124.6456 | 8.4641 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Macasandig | MIN | PH104305056 | 20738 | 40 | Three Legged Tubular Tower | CO70 | 94.9541 | MIN-1000049 | Level 6 | phase3 | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-02-23 |  | 2020-02-25 | [13 empty] | 2020-03-01 | [11 empty] | 2020-03-31 | [27 empty] | 2020-04-07 |  |  | 2020-05-07 |  | 2020-04-14 | [16 empty] | 2020-05-05 |  |  | 2020-05-14 | [6 empty] | 2020-05-28 |  |  |  | 2020-05-28 |  |  |  |  | 2020-04-21 |  | 2020-05-01 |  |  | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-22 |  |  |  | 2020-05-29 |  | JGT-36-280C-2NPT |  |  | 2020-06-10 |  | 2020-05-19 | [6 empty] | 2020-06-18 | 2020-06-25 | [20 empty] | 2020-07-25 |  |  |  | 2020-07-28 | [8 empty] | 2020-06-03 |  | 2020-06-06 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-06-28 |  |  |  | 2020-07-01 |  |  | 2020-07-16 |  |  |  | 2020-07-28 |  | 2020-07-31
PH1000133 | 124.6635 | 8.4822 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Lapasan | MIN | PH104305053 | 43611 | 30 | Three Legged Tubular Tower | CO70 | 95.6825 | MIN-1000050 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_3093 | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-30 | 2020-02-05 | 2020-02-01 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-02-08 |  |  |  | 2020-02-08 |  |  |  | 2020-02-06 | 2020-02-08 |  |  |  | 2020-02-08 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-02-28 | 2020-03-07 | [5 empty] | A | Cresencio M. Tanucan/Metro Cebu Tourist Development, Inc. | C.M. Recto Ave., Lapasan, Cagayan de Oro City | Misamis Oriental | 124.663 | 8.4834 | Rooftop |  |  | 10 years | P30,000 Exclusive of VAT and withholding tax | quarterly | 17.76sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-14 | 2020-02-13 |  | 2020-04-13 |  | 2020-03-21 | [16 empty] | 2020-04-11 |  |  | 2020-04-20 | [6 empty] | 2020-05-04 |  |  |  | 2020-05-04 |  |  |  |  | 2020-03-28 |  | 2020-04-07 |  |  | 2020-04-11 | 2020-03-07 | 2020-04-14 |  |  | 2020-04-28 |  |  |  | 2020-05-05 |  | JGT-30-280C-2NPT（290KPH/D） |  |  | 2020-05-17 |  | 2020-04-25 | [6 empty] | 2020-05-25 | 2020-06-01 | [20 empty] | 2020-07-01 |  |  |  | 2020-07-04 | [8 empty] | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-04 |  |  |  | 2020-06-07 |  |  | 2020-06-22 |  |  |  | 2020-07-04 |  | 2020-07-07
PH1000135 | 124.6791 | 8.4775 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Gusa | MIN | PH104305049 | 26815 | 40 | Monopole Tower | CO70 | 94.3845 | MIN-1000051 | Level 6 | phase3 | phase2_1231 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-02-26 |  | 2020-02-28 | [13 empty] | 2020-03-04 | [11 empty] | 2020-04-03 | [27 empty] | 2020-04-10 |  |  | 2020-05-10 |  | 2020-04-17 | [16 empty] | 2020-05-08 |  |  | 2020-05-17 | [6 empty] | 2020-05-31 |  |  |  | 2020-05-31 |  |  |  |  | 2020-04-24 |  | 2020-05-04 |  |  | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-25 |  |  |  | 2020-06-01 |  | JGT-36-280C-2NPT |  |  | 2020-06-13 |  | 2020-05-22 | [6 empty] | 2020-06-21 | 2020-06-28 | [20 empty] | 2020-07-28 |  |  |  | 2020-07-31 | [8 empty] | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-01 |  |  |  | 2020-07-04 |  |  | 2020-07-19 |  |  |  | 2020-07-31 |  | 2020-08-03
PH1000137 | 124.6986 | 8.4663 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Cugman | MIN | PH104305046 | 22383 | 40 | Three Legged Tubular Tower | CO70 | 92.2545 | MIN-1000052 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-16 | 2020-01-20 | 2020-01-18 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-02 |  |  |  | 2020-02-02 |  |  |  | 2020-01-23 | 2020-02-02 |  |  |  | 2020-02-02 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-19 | 2020-02-22 | [5 empty] | A | Maricel D. Naguio | Zone 9, Cugman, Cagayan de Oro City | Misamis Oriental | 124.6961 | 8.4702 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-29 | 2020-02-12 |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 | 2020-02-26 | 2020-03-24 | 2020-02-28 | 2020-02-29 | 2020-03-28 | 2020-03-05 | 2020-03-31 | 2020-03-06 | 2020-03-08 | 2020-04-14 | 2020-03-09 |  |  | 2020-04-21 |  | JGT-36-280C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1000144 | 124.7377 | 8.4885 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Agusan | MIN | PH104305001 | 16261 | 40 | Monopole Tower | CO70 | 92.5242 | MIN-1000053 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_4963 | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-18 | 2020-02-02 | 2020-01-20 | 2020-02-03 |  |  |  | 2020-02-03 | 2020-02-06 |  |  |  | 2020-02-06 |  |  |  | 2020-01-25 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-02-03 |  |  |  | 2020-02-03 | 2020-02-24 | 2020-02-24 | 2020-02-26 |  |  | 2020-02-26 | 2020-03-02 | A | Frederick Oracion | Zone 4, Agusan, Cagayan de Oro City | Misamis Oriental | 124.7431 | 8.4905 | Greenfield |  |  | 10 years | P16,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-02 | 2020-02-13 |  | 2020-04-01 |  | 2020-03-09 | [16 empty] | 2020-03-30 |  |  | 2020-04-08 | [6 empty] | 2020-04-22 |  |  |  | 2020-04-22 |  |  |  |  | 2020-03-16 |  | 2020-03-26 |  |  | 2020-03-30 | 2020-03-06 | 2020-04-02 | 2020-03-11 | 2020-03-11 | 2020-04-16 |  |  |  | 2020-04-23 |  | JGT-36-280C-2NPT |  |  | 2020-05-05 |  | 2020-04-13 | [6 empty] | 2020-05-13 | 2020-05-20 | [20 empty] | 2020-06-19 |  |  |  | 2020-06-22 | [8 empty] | 2020-04-28 |  | 2020-05-01 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-10 |  |  |  | 2020-06-22 |  | 2020-06-25
PH1000149 | 124.7574 | 8.522 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Tagoloan | Casinglot | MIN | PH104324002 | 9711 | 40 | Angular Steel Tower | CO70 | 95.0417 | MIN-1000054 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-16 | 2020-02-25 | 2020-01-18 | 2020-02-23 |  |  |  | 2020-02-23 | 2020-02-23 |  |  |  | 2020-02-23 |  |  |  | 2020-01-23 | 2020-02-23 |  |  |  | 2020-02-23 | [6 empty] | 2020-02-22 | [9 empty] | 124.7565 | 8.5214 | [16 empty] | 2020-02-29 | 2020-02-12 |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 |  | 2020-03-24 |  |  | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-14 |  |  |  | 2020-04-21 |  | JGT-36-280C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1000151 | 124.7573 | 8.4996 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Puerto | MIN | PH104305063 | 14318 | 40 | Angular Steel Tower | CO70 | 92.7583 | MIN-1000055 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-19 | 2020-01-23 | 2020-01-21 | [13 empty] | 2020-01-26 | [5 empty] | 2020-03-02 |  |  |  | 2020-03-02 |  | 2020-02-25 | [27 empty] | 2020-03-03 |  |  | 2020-04-02 |  | 2020-03-10 | [16 empty] | 2020-03-31 |  |  | 2020-04-09 | [6 empty] | 2020-04-23 |  |  |  | 2020-04-23 |  |  |  |  | 2020-03-17 |  | 2020-03-27 |  |  | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-17 |  |  |  | 2020-04-24 |  | JGT-36-280C-2NPT |  |  | 2020-05-06 |  | 2020-04-14 | [6 empty] | 2020-05-14 | 2020-05-21 | [20 empty] | 2020-06-20 |  |  |  | 2020-06-23 | [8 empty] | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-11 |  |  |  | 2020-06-23 |  | 2020-06-26
PH1000153 | 124.7768 | 8.5107 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Bugo | MIN | PH104305041 | 30893 | 40 | Angular Steel Tower | CO70 | 93.0579 | MIN-1000056 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-22 | 2020-02-07 | 2020-01-24 | 2020-02-08 |  |  |  | 2020-02-08 | [8 empty] | 2020-01-29 | [5 empty] | 2020-02-08 |  |  |  | 2020-02-08 |  | 2020-02-28 | [27 empty] | 2020-03-06 |  |  | 2020-04-05 |  | 2020-03-13 | [16 empty] | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 |  | 2020-03-30 |  |  | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-20 |  |  |  | 2020-04-27 |  | JGT-36-280C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1000157 | 125.0814 | 7.8848 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Lumbo | MIN | PH101321016 | 16082 | 40 | Angular Steel Tower | CO70 | 16.6415 | MIN-1000057 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-04 | 2020-02-11 | 2020-02-06 | 2020-02-12 |  |  |  | 2020-02-12 | [8 empty] | 2020-02-11 | [5 empty] | 2020-02-12 |  |  |  | 2020-02-12 |  | 2020-03-12 | [27 empty] | 2020-03-19 |  |  | 2020-04-18 |  | 2020-03-26 | [16 empty] | 2020-04-16 |  |  | 2020-04-25 | [6 empty] | 2020-05-09 |  |  |  | 2020-05-09 |  |  |  |  | 2020-04-02 |  | 2020-04-12 |  |  | 2020-04-16 |  | 2020-04-19 |  |  | 2020-05-03 |  |  |  | 2020-05-10 |  | JGT-36-340C-2NPT |  |  | 2020-05-22 |  | 2020-04-30 | [6 empty] | 2020-05-30 | 2020-06-06 | [20 empty] | 2020-07-06 |  |  |  | 2020-07-09 | [8 empty] | 2020-05-15 |  | 2020-05-18 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-09 |  |  |  | 2020-06-12 |  |  | 2020-06-27 |  |  |  | 2020-07-09 |  | 2020-07-12
PH1000160 | 125.0913 | 7.9127 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Poblacion | MIN | PH101321024 | 35793 | 40 | Angular Steel Tower | CO70 | 19.6815 | MIN-1000058 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-07 | 2020-02-16 | 2020-02-09 | 2020-02-17 |  |  |  | 2020-02-17 | 2020-02-21 |  |  |  | 2020-02-21 |  |  |  | 2020-02-14 | 2020-02-21 |  |  |  | 2020-02-21 | 2020-02-17 |  |  |  | 2020-02-17 | 2020-02-26 | 2020-03-15 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 | A | Romulo V. Garcia | Purok 16, Brgy. Poblacion, Valencia City | Bukidnon | 125.0902 | 7.9125 | Greenfield |  |  | 10 years | P16,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-22 | 2020-03-02 |  | 2020-04-21 |  | 2020-03-29 | [16 empty] | 2020-04-19 |  |  | 2020-04-28 | [6 empty] | 2020-05-12 |  |  |  | 2020-05-12 |  |  |  |  | 2020-04-05 |  | 2020-04-15 |  |  | 2020-04-19 |  | 2020-04-22 |  |  | 2020-05-06 |  |  |  | 2020-05-13 |  | JGT-36-340C-2NPT |  |  | 2020-05-25 |  | 2020-05-03 | [6 empty] | 2020-06-02 | 2020-06-09 | [20 empty] | 2020-07-09 |  |  |  | 2020-07-12 | [8 empty] | 2020-05-18 |  | 2020-05-21 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-12 |  |  |  | 2020-06-15 |  |  | 2020-06-30 |  |  |  | 2020-07-12 |  | 2020-07-15
PH1000162 | 125.106 | 8.8262 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Gingoog City | Barangay 17 | MIN | PH104308041 | 2270 | 35 | Monopole Tower | CO64 | 49.8177 | MIN-1000059 | Level 6 | phase2_add | phase3 |  |  | Cluster M20 | Marrox | [7 empty] | 2020-02-01 |  | 2020-02-03 | [13 empty] | 2020-02-08 | [11 empty] | 2020-03-09 | [27 empty] | 2020-03-16 |  |  | 2020-04-15 |  | 2020-03-23 | [16 empty] | 2020-04-13 |  |  | 2020-04-22 | [6 empty] | 2020-05-06 |  |  |  | 2020-05-06 |  |  |  |  | 2020-03-30 |  | 2020-04-09 |  |  | 2020-04-13 |  | 2020-04-16 |  |  | 2020-04-30 |  |  |  | 2020-05-07 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-05-19 |  | 2020-04-27 | [6 empty] | 2020-05-27 | 2020-06-03 | [20 empty] | 2020-07-03 |  |  |  | 2020-07-06 | [8 empty] | 2020-05-12 |  | 2020-05-15 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-06 |  |  |  | 2020-06-09 |  |  | 2020-06-24 |  |  |  | 2020-07-06 |  | 2020-07-09
PH1000163 | 125.1059 | 8.815 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Misamis Oriental | Gingoog City | Barangay 22-A | MIN | PH104308051 | 4874 | 40 | Angular Steel Tower | CO64 | 50.1979 | MIN-1000060 | Level 6 | phase2_add | phase3 |  | DICT_50 | Cluster M20 | Marrox | [7 empty] | 2020-02-03 | 2020-01-17 | 2020-02-05 | 2020-01-28 |  |  |  | 2020-01-28 | [8 empty] | 2020-02-10 | [5 empty] | 2020-01-28 |  |  |  | 2020-01-28 |  | 2020-03-11 | [27 empty] | 2020-03-18 |  |  | 2020-04-17 |  | 2020-03-25 | [16 empty] | 2020-04-15 |  |  | 2020-04-24 | [6 empty] | 2020-05-08 |  |  |  | 2020-05-08 |  |  |  |  | 2020-04-01 |  | 2020-04-11 |  |  | 2020-04-15 |  | 2020-04-18 |  |  | 2020-05-02 |  |  |  | 2020-05-09 |  | JGT-36-340C-2NPT |  |  | 2020-05-21 |  | 2020-04-29 | [6 empty] | 2020-05-29 | 2020-06-05 | [20 empty] | 2020-07-05 |  |  |  | 2020-07-08 | [8 empty] | 2020-05-14 |  | 2020-05-17 |  |  | 2020-05-29 |  |  |  | 2020-06-01 |  |  | 2020-06-08 |  |  |  | 2020-06-11 |  |  | 2020-06-26 |  |  |  | 2020-07-08 |  | 2020-07-11
PH1000164 | 125.1001 | 7.7277 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Bukidnon | Quezon | Poblacion (Kiokong) | MIN | PH101317028 | 15247 | 40 | Angular Steel Tower | CO70 | 1.006 | MIN-1000061 | Level 6 | phase2_add | phase1_630 | P1_630 | DICT_13 | Cluster M06 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  |  |  |  | 2020-01-26 | 2020-01-15 | 2020-01-28 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2020-02-02 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-02-24 | 2020-03-03 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | A | Saturnino Espiritu | Purok 5, Poblacion, Quezon | Bukidnon | 125.0993 | 7.7261 | Greenfield | 274m |  | 15 years | P16,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-03-10 | 2020-01-27 |  | 2020-04-09 |  | 2020-03-17 | [11 empty] | 0917-7196255 |  |  |  |  | 2020-04-07 | ok |  | 2020-04-16 | [6 empty] | 2020-04-30 |  |  |  | 2020-04-30 |  |  |  |  | 2020-03-24 | 2020-02-26 | 2020-04-03 |  |  | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-24 |  |  |  | 2020-05-01 |  | JGT-36-340C-2NPT |  |  | 2020-05-13 |  | 2020-04-21 | [6 empty] | 2020-05-21 | 2020-05-28 |  |  |  | 2020-03-09 | [16 empty] | 2020-06-27 |  |  |  | 2020-06-30 | [8 empty] | 2020-05-06 |  | 2020-05-09 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-18 |  |  |  | 2020-06-30 |  | 2020-07-03
PH1000166 | 125.1121 | 8.1704 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Kalasungay | MIN | PH101312019 | 8272 | 40 | Angular Steel Tower | CO70 | 48.3629 | MIN-1000062 | Level 6 | phase2_add | phase1_630 | P1_630 |  | Cluster M10 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  |  |  |  | 2020-01-20 | 2020-01-15 | 2020-01-22 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2020-01-27 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-03-05 | 2020-02-26 | 2020-03-05 |  |  | 2020-03-05 | 2020-03-06 | A | Rodrigo Niere | Purok 2, Kalasungay, Malaybalay City | Bukidnon | 125.1058 | 8.1731 | Greenfield | 274m |  | 15 years | P16,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-03-04 | 2020-01-29 |  | 2020-04-03 | 2020-02-19 | 2020-03-11 |  |  | 2020-02-27 |  |  | 2020-03-05 | [10 empty] | 2020-04-01 | ok | 2020-03-05 | 2020-04-10 | 2020-03-11 | [5 empty] | 2020-04-24 |  | 2020-03-09 | 2020-03-11 | 2020-04-24 |  |  |  | RFP approved, follow up cheque release | 2020-03-18 | 2020-02-27 | 2020-03-28 | 2020-03-11 | 2020-03-11 | 2020-04-01 | 2020-02-15 | 2020-04-04 | 2020-02-27 | 2020-02-28 | 2020-04-18 |  |  |  | 2020-04-25 |  | JGT-36-340C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 |  |  |  | 2020-03-09 | [16 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1000172 | 125.1218 | 8.1536 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Barangay 2 | MIN | PH101312053 | 2942 | 40 | Three Legged Tubular Tower | CO70 | 46.5418 | MIN-1000063 | Level 1 (OA) | phase2_add | phase1_630 | OA_630 |  | Cluster M10 | EPC | PO2019122103PH_WLS | Batch 2 | EPC |  | EPC |  | 2020-01-20 | 2020-01-22 | 2020-01-10 | 2020-01-24 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-01-23 |  |  |  | 2020-01-23 |  |  |  | 2020-01-29 | 2020-01-23 |  |  |  | 2020-01-23 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-02-21 | 2020-02-28 | 2020-03-13 |  |  | 2020-03-13 |  | A | Christine Lim Salazar | Zone 1, Brgy. 11, Malaybalay City | Bukidnon | 125.1213 | 8.1491 | Greenfield | 501m |  | 15 years | P21,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-03-06 | 2020-01-30 |  | 2020-04-05 |  | 2020-03-13 | 2020-03-02 | 2020-03-02 | 2020-03-02 | [13 empty] | 2020-04-03 | ok |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 | 2020-03-02 | 2020-03-30 |  |  | 2020-04-03 | 2020-02-02 | 2020-04-06 | 2020-02-04 | 2020-02-04 | 2020-04-20 | 2020-02-04 |  |  | 2020-04-27 |  | JGT-36-340C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1000173 | 125.1217 | 8.1424 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Barangay 10 | MIN | PH101312012 | 25696 | 40 | Angular Steel Tower | CO70 | 45.2974 | MIN-1000064 | Level 6 | phase2_add | phase1_630 | P1_630 |  | Cluster M10 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  |  |  |  | 2020-01-28 | 2020-01-15 | 2020-01-30 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-02-06 |  |  |  | 2020-02-06 |  |  |  | 2020-02-04 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-01-29 |  |  |  | 2020-01-29 |  | 2020-03-05 | [5 empty] | A |  |  |  | 125.1245 | 8.1405 | [16 empty] | 2020-03-12 | 2020-02-10 |  | 2020-04-11 | 2020-03-09 | 2020-03-19 |  |  | 2020-03-02 | [13 empty] | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  | Awaiting MOC approval | 2020-03-26 | 2020-02-28 | 2020-04-05 |  |  | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-26 |  |  |  | 2020-05-03 |  | JGT-36-340C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1000175 | 125.1195 | 7.7052 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Bukidnon | Quezon | Salawagan | MIN | PH101317030 | 7945 | 40 | Angular Steel Tower | CO70 | 4.2735 | MIN-1000065 | Level 6 | phase2_add | phase1_630 | P1_630 |  | Cluster M06 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  | EPC |  |  | 2020-01-28 | 2020-01-15 | 2020-01-30 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2020-02-04 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-02-24 | 2020-03-05 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | A | Marilou Diaz | Purok Tala sa Umaga, Salawagan, Quezon | Bukidnon | 125.1167 | 7.7056 | Greenfield | 294m |  | 15 years | P16,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-03-12 | 2020-01-27 |  | 2020-04-11 |  | 2020-03-19 |  |  | 2020-02-27 | [13 empty] | 2020-04-09 | ok |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 | 2020-02-25 | 2020-04-05 | 2020-03-11 | 2020-03-11 | 2020-04-09 | 2020-02-04 | 2020-04-12 | 2020-02-04 | 2020-02-05 | 2020-04-26 | 2020-02-06 |  |  | 2020-05-03 |  | JGT-36-340C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1000176 | 125.1315 | 8.1591 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Sumpong | MIN | PH101312038 | 5293 | 40 | Angular Steel Tower | CO70 | 47.2352 | MIN-1000066 | Level 6 | phase2_add | phase1_630 | P1_630 |  | Cluster M10 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  | EPC |  |  | 2020-01-24 | 2020-01-15 | 2020-01-26 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-01-22 |  |  |  | 2020-01-22 |  |  |  | 2020-01-31 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-02-24 | 2020-03-01 | [5 empty] | A | Marilyn Mendoza | Pimentel St., Heights, Brgy. 1, Malaybalay City | Bukidnon | 125.1282 | 8.162 | Rooftop | 661m | 10m | 15 years | P16,000 inclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-03-08 | 2020-01-29 |  | 2020-04-07 |  | 2020-03-15 | [16 empty] | 2020-04-05 | ok |  | 2020-04-14 | [6 empty] | 2020-04-28 |  |  |  | 2020-04-28 |  |  |  |  | 2020-03-22 |  | 2020-04-01 |  |  | 2020-04-05 | 2020-02-06 | 2020-04-08 | 2020-02-15 | 2020-02-16 | 2020-04-22 | 2020-02-06 |  |  | 2020-04-29 |  | ZCG-9-340D-1NPT |  |  | 2020-05-11 |  | 2020-04-19 | [6 empty] | 2020-05-19 | 2020-05-26 | [20 empty] | 2020-06-25 |  |  |  | 2020-06-28 | [8 empty] | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-05-29 |  |  |  | 2020-06-01 |  |  | 2020-06-16 |  |  |  | 2020-06-28 |  | 2020-07-01
PH1000178 | 125.1314 | 8.1367 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Barangay 8 | MIN | PH101312012 | 25696 | 40 | Angular Steel Tower | CO70 | 44.7505 | MIN-1000067 | Level 6 | phase2_add | phase1_630 | P1_630 |  | Cluster M10 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  |  |  |  | 2020-01-30 | 2020-01-20 | 2020-02-01 | 2020-01-25 |  |  |  | 2020-01-25 | [8 empty] | 2020-02-06 | [5 empty] | 2020-01-25 |  |  |  | 2020-01-25 |  | 2020-03-07 | [27 empty] | 2020-03-14 |  |  | 2020-04-13 |  | 2020-03-21 | [16 empty] | 2020-04-11 |  |  | 2020-04-20 | [6 empty] | 2020-05-04 |  |  |  | 2020-05-04 |  |  |  |  | 2020-03-28 |  | 2020-04-07 |  |  | 2020-04-11 |  | 2020-04-14 |  |  | 2020-04-28 |  |  |  | 2020-05-05 |  | JGT-36-340C-2NPT |  |  | 2020-05-17 |  | 2020-04-25 | [6 empty] | 2020-05-25 | 2020-06-01 | [20 empty] | 2020-07-01 |  |  |  | 2020-07-04 | [8 empty] | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-04 |  |  |  | 2020-06-07 |  |  | 2020-06-22 |  |  |  | 2020-07-04 |  | 2020-07-07
PH1000180 | 123.7401 | 8.077 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Occidental | Tangub City | Manga | MIN | PH104215015 | 2127 | 40 | Three Legged Tubular Tower | CO68 | 110.3336 | MIN-1000068 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-14 |  | 2020-07-16 | [13 empty] | 2020-07-21 | [11 empty] | 2020-08-20 | [27 empty] | 2020-08-27 |  |  | 2020-09-26 |  | 2020-09-03 | [16 empty] | 2020-09-24 |  |  | 2020-10-03 | [6 empty] | 2020-10-17 |  |  |  | 2020-10-17 |  |  |  |  | 2020-09-10 |  | 2020-09-20 |  |  | 2020-09-24 |  | 2020-09-27 |  |  | 2020-10-11 |  |  |  | 2020-10-18 |  | 3GT-36-280C-2NPT |  |  | 2020-10-30 |  | 2020-10-08 | [6 empty] | 2020-11-07 | 2020-11-14 | [20 empty] | 2020-12-14 |  |  |  | 2020-12-17 | [8 empty] | 2020-10-23 |  | 2020-10-26 |  |  | 2020-11-07 |  |  |  | 2020-11-10 |  |  | 2020-11-17 |  |  |  | 2020-11-20 |  |  | 2020-12-05 |  |  |  | 2020-12-17 |  | 2020-12-20
PH1000182 | 123.7855 | 8.4948 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Occidental | Oroquieta City | Mobod | MIN | PH104209026 | 6108 | 40 | Three Legged Tubular Tower | CO68 | 150.401 | MIN-1000069 | Level 6 | phase3 | phase3 |  |  | Cluster M18 | TBD | [7 empty] | 2020-07-12 |  | 2020-07-14 | [13 empty] | 2020-07-19 | [11 empty] | 2020-08-18 | [27 empty] | 2020-08-25 |  |  | 2020-09-24 |  | 2020-09-01 | [16 empty] | 2020-09-22 |  |  | 2020-10-01 | [6 empty] | 2020-10-15 |  |  |  | 2020-10-15 |  |  |  |  | 2020-09-08 |  | 2020-09-18 |  |  | 2020-09-22 |  | 2020-09-25 |  |  | 2020-10-09 |  |  |  | 2020-10-16 |  | 3GT-36-280C-2NPT |  |  | 2020-10-28 |  | 2020-10-06 | [6 empty] | 2020-11-05 | 2020-11-12 | [20 empty] | 2020-12-12 |  |  |  | 2020-12-15 | [8 empty] | 2020-10-21 |  | 2020-10-24 |  |  | 2020-11-05 |  |  |  | 2020-11-08 |  |  | 2020-11-15 |  |  |  | 2020-11-18 |  |  | 2020-12-03 |  |  |  | 2020-12-15 |  | 2020-12-18
PH1000185 | 123.8068 | 8.4667 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Occidental | Oroquieta City | San Vicente Bajo | MIN | PH104209039 | 4147 | 40 | Three Legged Tubular Tower | CO68 | 146.678 | MIN-1000070 | Level 6 | phase3 | phase3 |  |  | Cluster M18 | TBD | [7 empty] | 2020-07-13 |  | 2020-07-15 | [13 empty] | 2020-07-20 | [11 empty] | 2020-08-19 | [27 empty] | 2020-08-26 |  |  | 2020-09-25 |  | 2020-09-02 | [16 empty] | 2020-09-23 |  |  | 2020-10-02 | [6 empty] | 2020-10-16 |  |  |  | 2020-10-16 |  |  |  |  | 2020-09-09 |  | 2020-09-19 |  |  | 2020-09-23 |  | 2020-09-26 |  |  | 2020-10-10 |  |  |  | 2020-10-17 |  | 3GT-36-280C-2NPT |  |  | 2020-10-29 |  | 2020-10-07 | [6 empty] | 2020-11-06 | 2020-11-13 | [20 empty] | 2020-12-13 |  |  |  | 2020-12-16 | [8 empty] | 2020-10-22 |  | 2020-10-25 |  |  | 2020-11-06 |  |  |  | 2020-11-09 |  |  | 2020-11-16 |  |  |  | 2020-11-19 |  |  | 2020-12-04 |  |  |  | 2020-12-16 |  | 2020-12-19
PH1000186 | 123.8026 | 8.0605 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Tubod | Pigcarangan | MIN | PH103522017 | 3166 | 40 | Three Legged Tubular Tower | CO68 | 105.3688 | MIN-1000071 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-15 |  | 2020-07-17 | [13 empty] | 2020-07-22 | [11 empty] | 2020-08-21 | [27 empty] | 2020-08-28 |  |  | 2020-09-27 |  | 2020-09-04 | [16 empty] | 2020-09-25 |  |  | 2020-10-04 | [6 empty] | 2020-10-18 |  |  |  | 2020-10-18 |  |  |  |  | 2020-09-11 |  | 2020-09-21 |  |  | 2020-09-25 |  | 2020-09-28 |  |  | 2020-10-12 |  |  |  | 2020-10-19 |  | JGT-42-280C-2NPT |  |  | 2020-10-31 |  | 2020-10-09 | [6 empty] | 2020-11-08 | 2020-11-15 | [20 empty] | 2020-12-15 |  |  |  | 2020-12-18 | [8 empty] | 2020-10-24 |  | 2020-10-27 |  |  | 2020-11-08 |  |  |  | 2020-11-11 |  |  | 2020-11-18 |  |  |  | 2020-11-21 |  |  | 2020-12-06 |  |  |  | 2020-12-18 |  | 2020-12-21
PH1000192 | 123.8256 | 8.1302 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Occidental | Ozamis City | Malaubang | MIN | PH104210033 | 7867 | 40 | Three Legged Tubular Tower | CO68 | 111.2009 | MIN-1000072 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-25 |  | 2020-07-27 | [13 empty] | 2020-08-01 | [11 empty] | 2020-08-31 | [27 empty] | 2020-09-07 |  |  | 2020-10-07 |  | 2020-09-14 | [16 empty] | 2020-10-05 |  |  | 2020-10-14 | [6 empty] | 2020-10-28 |  |  |  | 2020-10-28 |  |  |  |  | 2020-09-21 |  | 2020-10-01 |  |  | 2020-10-05 |  | 2020-10-08 |  |  | 2020-10-22 |  |  |  | 2020-10-29 |  | 3GT-36-280C-2NPT |  |  | 2020-11-10 |  | 2020-10-19 | [6 empty] | 2020-11-18 | 2020-11-25 | [20 empty] | 2020-12-25 |  |  |  | 2020-12-28 | [8 empty] | 2020-11-03 |  | 2020-11-06 |  |  | 2020-11-18 |  |  |  | 2020-11-21 |  |  | 2020-11-28 |  |  |  | 2020-12-01 |  |  | 2020-12-16 |  |  |  | 2020-12-28 |  | 2020-12-31
PH1000196 | 123.8549 | 8.1694 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Occidental | Ozamis City | Maningcol | MIN | PH104210021 | 5686 | 40 | Three Legged Tubular Tower | CO68 | 113.8989 | MIN-1000073 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-16 |  | 2020-07-18 | [13 empty] | 2020-07-23 | [11 empty] | 2020-08-22 | [27 empty] | 2020-08-29 |  |  | 2020-09-28 |  | 2020-09-05 | [16 empty] | 2020-09-26 |  |  | 2020-10-05 | [6 empty] | 2020-10-19 |  |  |  | 2020-10-19 |  |  |  |  | 2020-09-12 |  | 2020-09-22 |  |  | 2020-09-26 |  | 2020-09-29 |  |  | 2020-10-13 |  |  |  | 2020-10-20 |  | 3GT-36-280C-2NPT |  |  | 2020-11-01 |  | 2020-10-10 | [6 empty] | 2020-11-09 | 2020-11-16 | [20 empty] | 2020-12-16 |  |  |  | 2020-12-19 | [8 empty] | 2020-10-25 |  | 2020-10-28 |  |  | 2020-11-09 |  |  |  | 2020-11-12 |  |  | 2020-11-19 |  |  |  | 2020-11-22 |  |  | 2020-12-07 |  |  |  | 2020-12-19 |  | 2020-12-22
PH1000198 | 124.2017 | 8.2016 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Maria Cristina | MIN | PH103504015 | 11383 | 40 | Three Legged Tubular Tower | CO68 | 108.9928 | MIN-1000074 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-27 | 2020-01-16 | 2020-01-29 | 2020-01-16 | 2020-02-09 |  |  | 2020-01-16 | 2020-01-17 |  |  |  | 2020-01-17 |  |  |  | 2020-02-03 | [5 empty] | 2020-01-16 | 2020-02-09 |  |  | 2020-01-16 |  | 2020-03-04 | [27 empty] | 2020-03-11 |  |  | 2020-04-10 |  | 2020-03-18 | [16 empty] | 2020-04-08 |  |  | 2020-04-17 | [6 empty] | 2020-05-01 |  |  |  | 2020-05-01 |  |  |  |  | 2020-03-25 |  | 2020-04-04 |  |  | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-25 |  |  |  | 2020-05-02 |  | JGT-42-280C-2NPT |  |  | 2020-05-14 |  | 2020-04-22 | [6 empty] | 2020-05-22 | 2020-05-29 | [20 empty] | 2020-06-28 |  |  |  | 2020-07-01 | [8 empty] | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-22 |  |  |  | 2020-05-25 |  |  | 2020-06-01 |  |  |  | 2020-06-04 |  |  | 2020-06-19 |  |  |  | 2020-07-01 |  | 2020-07-04
PH1000200 | 124.2034 | 8.1731 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Maria Cristina | MIN | PH103502015 | 6485 | 40 | Three Legged Tubular Tower | CO68 | 105.8172 | MIN-1000075 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_3157 | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-29 | 2020-01-11 | 2020-01-31 |  | 2020-01-13 |  |  | 2020-01-13 |  | 2020-02-13 |  |  | 2020-02-13 |  |  |  | 2020-02-05 |  | 2020-02-13 |  |  | 2020-02-13 |  | 2020-02-10 |  |  | 2020-02-10 | 2020-02-25 | 2020-03-06 | [5 empty] | B | Alawi M. Natangcop | Purok 6, Maria Cristina | Lanao del Norte | 124.2058 | 8.1723 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-13 | 2020-02-28 |  | 2020-04-12 | 2020-03-11 | 2020-03-20 | [16 empty] | 2020-04-10 |  |  | 2020-04-19 | [6 empty] | 2020-05-03 |  |  |  | 2020-05-03 |  |  |  | Awaiting MOC approval | 2020-03-27 |  | 2020-04-06 |  |  | 2020-04-10 |  | 2020-04-13 |  |  | 2020-04-27 |  |  |  | 2020-05-04 |  | JGT-42-280C-2NPT |  |  | 2020-05-16 |  | 2020-04-24 | [6 empty] | 2020-05-24 | 2020-05-31 | [20 empty] | 2020-06-30 |  |  |  | 2020-07-03 | [8 empty] | 2020-05-09 |  | 2020-05-12 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-03 |  |  |  | 2020-06-06 |  |  | 2020-06-21 |  |  |  | 2020-07-03 |  | 2020-07-06
PH1000204 | 124.2449 | 8.2021 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Tubod | MIN | PH103504027 | 14730 | 40 | Three Legged Tubular Tower | CO70 | 107.1033 | MIN-1000076 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-27 | 2020-01-20 | 2020-01-29 | 2020-02-01 |  | 2020-02-19 |  | 2020-02-01 | 2020-02-05 |  |  |  | 2020-02-05 |  |  |  | 2020-02-03 | 2020-02-05 |  |  |  | 2020-02-05 | 2020-02-01 |  | 2020-02-19 |  | 2020-02-01 |  | 2020-03-04 | [5 empty] | A |  |  |  | 124.2513 | 8.1962 | [16 empty] | 2020-03-11 |  |  | 2020-04-10 |  | 2020-03-18 | [16 empty] | 2020-04-08 |  |  | 2020-04-17 | [6 empty] | 2020-05-01 |  |  |  | 2020-05-01 |  |  |  |  | 2020-03-25 |  | 2020-04-04 |  |  | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-25 |  |  |  | 2020-05-02 |  | JGT-42-280C-2NPT |  |  | 2020-05-14 |  | 2020-04-22 | [6 empty] | 2020-05-22 | 2020-05-29 | [20 empty] | 2020-06-28 |  |  |  | 2020-07-01 | [8 empty] | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-22 |  |  |  | 2020-05-25 |  |  | 2020-06-01 |  |  |  | 2020-06-04 |  |  | 2020-06-19 |  |  |  | 2020-07-01 |  | 2020-07-04
PH1000206 | 124.2559 | 8.3216 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Dalipuga | MIN | PH103504006 | 19721 | 40 | Three Legged Tubular Tower | CO70 | 113.1321 | MIN-1000077 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-24 | 2020-01-11 | 2020-01-26 | 2020-01-12 | 2020-02-20 |  |  | 2020-01-12 | [8 empty] | 2020-01-31 | [6 empty] | 2020-02-20 |  |  | 2020-02-20 |  | 2020-03-01 | [27 empty] | 2020-03-08 |  |  | 2020-04-07 |  | 2020-03-15 | [16 empty] | 2020-04-05 |  |  | 2020-04-14 | [6 empty] | 2020-04-28 |  |  |  | 2020-04-28 |  |  |  |  | 2020-03-22 |  | 2020-04-01 |  |  | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-22 |  |  |  | 2020-04-29 |  | JGT-42-280C-2NPT |  |  | 2020-05-11 |  | 2020-04-19 | [6 empty] | 2020-05-19 | 2020-05-26 | [20 empty] | 2020-06-25 |  |  |  | 2020-06-28 | [8 empty] | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-05-29 |  |  |  | 2020-06-01 |  |  | 2020-06-16 |  |  |  | 2020-06-28 |  | 2020-07-01
PH1000207 | 124.2546 | 8.1852 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Tipanoy | MIN | PH103504001 | 5423 | 40 | Three Legged Tubular Tower | CO70 | 105.2697 | MIN-1000078 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_3027 | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  |  |  | 2020-01-20 | 2020-01-29 | 2020-01-16 | 2020-01-31 | 2020-01-22 | 2020-01-16 |  |  | 2020-01-16 | 2020-01-22 | 2020-01-17 |  |  | 2020-01-17 |  |  |  | 2020-02-05 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-22 | 2020-01-16 |  |  | 2020-01-16 |  | 2020-03-06 | [5 empty] | A |  |  |  | 124.2569 | 8.1839 | Greenfield | 43m | [14 empty] | 2020-03-13 | 2020-02-12 |  | 2020-04-12 |  | 2020-03-20 | [16 empty] | 2020-04-10 |  |  | 2020-04-19 | [6 empty] | 2020-05-03 |  |  |  | 2020-05-03 |  |  |  |  | 2020-03-27 |  | 2020-04-06 |  |  | 2020-04-10 |  | 2020-04-13 |  |  | 2020-04-27 |  |  |  | 2020-05-04 |  | JGT-42-280C-2NPT |  |  | 2020-05-16 |  | 2020-04-24 | [6 empty] | 2020-05-24 | 2020-05-31 | [20 empty] | 2020-06-30 |  |  |  | 2020-07-03 | [8 empty] | 2020-05-09 |  | 2020-05-12 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-03 |  |  |  | 2020-06-06 |  |  | 2020-06-21 |  |  |  | 2020-07-03 |  | 2020-07-06
PH1000209 | 124.2657 | 8.3384 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Lugait | Lower Talacogon | MIN | PH104316007 | 8435 | 40 | Three Legged Tubular Tower | CO70 | 113.3433 | MIN-1000079 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) |  |  |  |  | 2020-01-20 | 2020-02-20 | 2020-01-11 | 2020-02-22 | 2020-01-13 |  |  |  | 2020-01-13 | [8 empty] | 2020-02-27 | [5 empty] | 2020-01-13 |  |  |  | 2020-01-13 |  | 2020-03-28 | [27 empty] | 2020-04-04 |  |  | 2020-05-04 |  | 2020-04-11 | [16 empty] | 2020-05-02 |  |  | 2020-05-11 | [6 empty] | 2020-05-25 |  |  |  | 2020-05-25 |  |  |  |  | 2020-04-18 |  | 2020-04-28 |  |  | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-19 |  |  |  | 2020-05-26 |  | JGT-42-280C-2NPT |  |  | 2020-06-07 |  | 2020-05-16 | [6 empty] | 2020-06-15 | 2020-06-22 | [20 empty] | 2020-07-22 |  |  |  | 2020-07-25 | [8 empty] | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-06-25 |  |  |  | 2020-06-28 |  |  | 2020-07-13 |  |  |  | 2020-07-25 |  | 2020-07-28
PH1000212 | 124.2655 | 8.2711 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Santa Filomena | MIN | PH103504038 | 6471 | 40 | Three Legged Tubular Tower | CO70 | 109.1135 | MIN-1000080 | Level 6 | phase2_add | phase2_1231 |  | DepEd_3029 | Cluster M26 | Enovell | [7 empty] | 2020-01-08 |  | 2020-01-10 | [13 empty] | 2020-01-15 | [11 empty] | 2020-02-14 | [5 empty] | A |  |  |  | 125.6097 | 7.0946 | [16 empty] | 2020-02-21 |  |  | 2020-03-22 |  | 2020-02-28 | [16 empty] | 2020-03-20 |  |  | 2020-03-29 | [6 empty] | 2020-04-12 |  |  |  | 2020-04-12 |  |  |  |  | 2020-03-06 |  | 2020-03-16 |  |  | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-06 |  |  |  | 2020-04-13 |  | JGT-42-280C-2NPT |  |  | 2020-04-25 |  | 2020-04-03 | [6 empty] | 2020-05-03 | 2020-05-10 | [20 empty] | 2020-06-09 |  |  |  | 2020-06-12 | [8 empty] | 2020-04-18 |  | 2020-04-21 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-31 |  |  |  | 2020-06-12 |  | 2020-06-15
PH1000214 | 124.2753 | 8.2767 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Acmac | MIN | PH103504010 | 2123 | 40 | Three Legged Tubular Tower | CO70 | 108.5556 | MIN-1000081 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M26 | Enovell | [7 empty] | 2020-02-23 |  | 2020-02-25 | [13 empty] | 2020-03-01 | [11 empty] | 2020-03-31 | [27 empty] | 2020-04-07 |  |  | 2020-05-07 |  | 2020-04-14 | [16 empty] | 2020-05-05 |  |  | 2020-05-14 | [6 empty] | 2020-05-28 |  |  |  | 2020-05-28 |  |  |  |  | 2020-04-21 |  | 2020-05-01 |  |  | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-22 |  |  |  | 2020-05-29 |  | JGT-42-280C-2NPT |  |  | 2020-06-10 |  | 2020-05-19 | [6 empty] | 2020-06-18 | 2020-06-25 | [20 empty] | 2020-07-25 |  |  |  | 2020-07-28 | [8 empty] | 2020-06-03 |  | 2020-06-06 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-06-28 |  |  |  | 2020-07-01 |  |  | 2020-07-16 |  |  |  | 2020-07-28 |  | 2020-07-31
PH1000216 | 124.3055 | 8.2442 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Mandulog | MIN | PH103504014 | 3867 | 40 | Three Legged Tubular Tower | CO70 | 103.7859 | MIN-1000082 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) |  |  |  |  | 2020-01-20 | 2020-02-26 | 2020-02-18 | 2020-02-28 | 2020-02-19 |  |  |  | 2020-02-19 | [8 empty] | 2020-03-04 | [5 empty] | 2020-02-19 |  |  |  | 2020-02-19 |  | 2020-04-03 | [27 empty] | 2020-04-10 |  |  | 2020-05-10 |  | 2020-04-17 | [16 empty] | 2020-05-08 |  |  | 2020-05-17 | [6 empty] | 2020-05-31 |  |  |  | 2020-05-31 |  |  |  |  | 2020-04-24 |  | 2020-05-04 |  |  | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-25 |  |  |  | 2020-06-01 |  | JGT-42-280C-2NPT |  |  | 2020-06-13 |  | 2020-05-22 | [6 empty] | 2020-06-21 | 2020-06-28 | [20 empty] | 2020-07-28 |  |  |  | 2020-07-31 | [8 empty] | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-01 |  |  |  | 2020-07-04 |  |  | 2020-07-19 |  |  |  | 2020-07-31 |  | 2020-08-03
PH1000218 | 124.5095 | 8.5544 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | El Salvador City | Poblacion | MIN | PH104307006 | 2705 | 40 | Three Legged Tubular Tower | CO70 | 111.5913 | MIN-1000083 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-25 | 2020-01-21 | 2020-01-27 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-02-25 |  |  |  | 2020-02-25 |  |  |  | 2020-02-01 | 2020-02-25 |  |  |  | 2020-02-25 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-03-04 | 2020-03-02 | 2020-03-04 |  |  | 2020-03-05 | 2020-03-05 |  | Florencio Seno | Brgy. Bulo-Bulo, El Salvador City | Misamis Oriental | 124.5296 | 8.5507 | Greenfield |  |  | 10 years | P15,000 Exclusive of VAT and withholding tax | quarterly | 150sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-09 |  |  | 2020-04-08 |  | 2020-03-16 | [11 empty] | 0936-7704592 |  |  |  |  | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 | 2020-02-29 | 2020-04-02 | 2020-03-06 | 2020-03-06 | 2020-04-06 | 2020-03-08 | 2020-04-09 | 2020-03-10 | 2020-03-10 | 2020-04-23 |  |  |  | 2020-04-30 |  | 3GT-36-280C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1000228 | 124.5838 | 8.4499 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Pagatpat | MIN | PH104305060 | 8456 | 40 | Three Legged Tubular Tower | CO70 | 97.3836 | MIN-1000084 | Level 6 | phase2_add | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-02-29 |  | 2020-03-02 | [13 empty] | 2020-03-07 | [11 empty] | 2020-04-06 | [27 empty] | 2020-04-13 |  |  | 2020-05-13 |  | 2020-04-20 | [16 empty] | 2020-05-11 |  |  | 2020-05-20 | [6 empty] | 2020-06-03 |  |  |  | 2020-06-03 |  |  |  |  | 2020-04-27 |  | 2020-05-07 |  |  | 2020-05-11 |  | 2020-05-14 |  |  | 2020-05-28 |  |  |  | 2020-06-04 |  | JGT-42-280C-2NPT |  |  | 2020-06-16 |  | 2020-05-25 | [6 empty] | 2020-06-24 | 2020-07-01 | [20 empty] | 2020-07-31 |  |  |  | 2020-08-03 | [8 empty] | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-04 |  |  |  | 2020-07-07 |  |  | 2020-07-22 |  |  |  | 2020-08-03 |  | 2020-08-06
PH1000233 | 124.6455 | 8.4417 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Macasandig | MIN | PH104305050 | 16179 | 40 | Three Legged Tubular Tower | CO70 | 92.843 | MIN-1000085 | Level 6 | phase3 | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-03-03 |  | 2020-03-05 | [13 empty] | 2020-03-10 | [11 empty] | 2020-04-09 | [27 empty] | 2020-04-16 |  |  | 2020-05-16 |  | 2020-04-23 | [16 empty] | 2020-05-14 |  |  | 2020-05-23 | [6 empty] | 2020-06-06 |  |  |  | 2020-06-06 |  |  |  |  | 2020-04-30 |  | 2020-05-10 |  |  | 2020-05-14 |  | 2020-05-17 |  |  | 2020-05-31 |  |  |  | 2020-06-07 |  | JGT-42-280C-2NPT |  |  | 2020-06-19 |  | 2020-05-28 | [6 empty] | 2020-06-27 | 2020-07-04 | [20 empty] | 2020-08-03 |  |  |  | 2020-08-06 | [8 empty] | 2020-06-12 |  | 2020-06-15 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-07 |  |  |  | 2020-07-10 |  |  | 2020-07-25 |  |  |  | 2020-08-06 |  | 2020-08-09
PH1000236 | 124.695 | 8.4579 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Cugman | MIN | PH104305046 | 22383 | 40 | Three Legged Tubular Tower | CO70 | 91.6232 | MIN-1000086 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-20 | 2020-01-20 | 2020-01-22 | 2020-02-03 |  |  |  | 2020-02-03 | 2020-02-06 |  |  |  | 2020-02-06 |  |  |  | 2020-01-27 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-03-02 |  |  |  | 2020-03-02 | 2020-03-05 | 2020-02-26 | 2020-03-06 |  |  | 2020-03-05 | 2020-03-06 | A | Susan Lugtu | 312 Bolonsiri, Brgy. Camaman-an, Cagayan de Oro City | Misamis Oriental | 124.6576 | 8.4668 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-04 | 2020-02-12 |  | 2020-04-03 |  | 2020-03-11 | [16 empty] | 2020-04-01 |  |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  |  | 2020-03-18 | 2020-03-12 | 2020-03-28 | 2020-03-12 | 2020-03-12 | 2020-04-01 | 2020-03-06 | 2020-04-04 | 2020-03-09 | 2020-03-09 | 2020-04-18 | 2020-03-09 |  |  | 2020-04-25 |  | JGT-42-280C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1000240 | 124.7442 | 8.4756 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Tablon | MIN | PH104305067 | 23004 | 40 | Three Legged Tubular Tower | CO70 | 90.9264 | MIN-1000087 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-03-06 |  | 2020-03-08 | [13 empty] | 2020-03-13 | [11 empty] | 2020-04-12 | [27 empty] | 2020-04-19 |  |  | 2020-05-19 |  | 2020-04-26 | [16 empty] | 2020-05-17 |  |  | 2020-05-26 | [6 empty] | 2020-06-09 |  |  |  | 2020-06-09 |  |  |  |  | 2020-05-03 |  | 2020-05-13 |  |  | 2020-05-17 |  | 2020-05-20 |  |  | 2020-06-03 |  |  |  | 2020-06-10 |  | JGT-42-280C-2NPT |  |  | 2020-06-22 |  | 2020-05-31 | [6 empty] | 2020-06-30 | 2020-07-07 | [20 empty] | 2020-08-06 |  |  |  | 2020-08-09 | [8 empty] | 2020-06-15 |  | 2020-06-18 |  |  | 2020-06-30 |  |  |  | 2020-07-03 |  |  | 2020-07-10 |  |  |  | 2020-07-13 |  |  | 2020-07-28 |  |  |  | 2020-08-09 |  | 2020-08-12
PH1000241 | 124.7652 | 8.5537 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Tagoloan | Santa Cruz | MIN | PH104324009 | 14758 | 40 | Three Legged Tubular Tower | CO64 | 96.1627 | MIN-1000088 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-25 | 2020-02-25 | 2020-01-27 | 2020-02-26 |  |  |  | 2020-02-26 | 2020-03-06 |  |  |  | 2020-03-06 |  |  |  | 2020-02-01 | 2020-03-06 |  |  |  | 2020-03-06 | 2020-02-21 |  |  |  | 2020-02-21 |  | 2020-03-02 | [5 empty] | A |  |  |  | 124.769 | 8.5457 | [16 empty] | 2020-03-09 |  |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 |  | 2020-04-02 |  |  | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-23 |  |  |  | 2020-04-30 |  | 3GT-36-280C-2NPT（290KPH/C） |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1000253 | 125.0912 | 7.8903 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Lumbo | MIN | PH101321016 | 16082 | 40 | Three Legged Tubular Tower | CO70 | 17.1901 | MIN-1000089 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-10 | 2020-02-09 | 2020-02-12 | 2020-02-10 |  |  |  | 2020-02-10 | [8 empty] | 2020-02-17 | [5 empty] | 2020-02-10 |  |  |  | 2020-02-10 |  | 2020-03-18 | [27 empty] | 2020-03-25 |  |  | 2020-04-24 |  | 2020-04-01 | [16 empty] | 2020-04-22 |  |  | 2020-05-01 | [6 empty] | 2020-05-15 |  |  |  | 2020-05-15 |  |  |  |  | 2020-04-08 |  | 2020-04-18 |  |  | 2020-04-22 |  | 2020-04-25 |  |  | 2020-05-09 |  |  |  | 2020-05-16 |  | 4GT-42-340C-2NPT |  |  | 2020-05-28 |  | 2020-05-06 | [6 empty] | 2020-06-05 | 2020-06-12 | [20 empty] | 2020-07-12 |  |  |  | 2020-07-15 | [8 empty] | 2020-05-21 |  | 2020-05-24 |  |  | 2020-06-05 |  |  |  | 2020-06-08 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-07-03 |  |  |  | 2020-07-15 |  | 2020-07-18
PH1000254 | 125.1058 | 8.8038 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Gingoog City | Murallon | MIN | PH104308051 | 4874 | 40 | Three Legged Tubular Tower | CO64 | 50.6059 | MIN-1000090 | Level 6 | phase2_add | phase3 |  |  | Cluster M20 | Marrox | [7 empty] | 2020-02-06 |  | 2020-02-08 | [13 empty] | 2020-02-13 | [11 empty] | 2020-03-14 | [27 empty] | 2020-03-21 |  |  | 2020-04-20 |  | 2020-03-28 | [16 empty] | 2020-04-18 |  |  | 2020-04-27 | [6 empty] | 2020-05-11 |  |  |  | 2020-05-11 |  |  |  |  | 2020-04-04 |  | 2020-04-14 |  |  | 2020-04-18 |  | 2020-04-21 |  |  | 2020-05-05 |  |  |  | 2020-05-12 |  | 4GT-42-340C-2NPT |  |  | 2020-05-24 |  | 2020-05-02 | [6 empty] | 2020-06-01 | 2020-06-08 | [20 empty] | 2020-07-08 |  |  |  | 2020-07-11 | [8 empty] | 2020-05-17 |  | 2020-05-20 |  |  | 2020-06-01 |  |  |  | 2020-06-04 |  |  | 2020-06-11 |  |  |  | 2020-06-14 |  |  | 2020-06-29 |  |  |  | 2020-07-11 |  | 2020-07-14
PH1000257 | 125.1005 | 7.9451 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Bagontaas | MIN | PH101321001 | 10619 | 40 | Three Legged Tubular Tower | CO70 | 23.2769 | MIN-1000091 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-13 |  | 2020-02-15 | [13 empty] | 2020-02-20 | [11 empty] | 2020-03-21 | [27 empty] | 2020-03-28 |  |  | 2020-04-27 |  | 2020-04-04 | [16 empty] | 2020-04-25 |  |  | 2020-05-04 | [6 empty] | 2020-05-18 |  |  |  | 2020-05-18 |  |  |  |  | 2020-04-11 |  | 2020-04-21 |  |  | 2020-04-25 |  | 2020-04-28 |  |  | 2020-05-12 |  |  |  | 2020-05-19 |  | 4GT-42-340C-2NPT |  |  | 2020-05-31 |  | 2020-05-09 | [6 empty] | 2020-06-08 | 2020-06-15 | [20 empty] | 2020-07-15 |  |  |  | 2020-07-18 | [8 empty] | 2020-05-24 |  | 2020-05-27 |  |  | 2020-06-08 |  |  |  | 2020-06-11 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-07-06 |  |  |  | 2020-07-18 |  | 2020-07-21
PH1000263 | 125.1121 | 8.1592 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Sumpong | MIN | PH101312053 | 2942 | 40 | Three Legged Tubular Tower | CO70 | 47.1171 | MIN-1000092 | Level 6 | phase2_add | phase1_630 | P1_630 |  | Cluster M10 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  |  |  |  | 2020-01-26 | 2020-01-23 | 2020-01-28 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-01-27 |  |  |  | 2020-01-27 |  |  |  | 2020-02-02 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-02-24 | 2020-03-03 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | A | Celso Barberan | Zone 5, Brgy. 11, Impalambong, Malaybalay City | Bukidnon | 125.1165 | 8.1444 | Greenfield | 610m |  | 10 years | P17,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-10 | 2020-02-27 |  | 2020-04-09 |  | 2020-03-17 | 2020-02-27 |  | 2020-02-27 | [13 empty] | 2020-04-07 | ok |  | 2020-04-16 | [6 empty] | 2020-04-30 |  |  |  | 2020-04-30 |  |  |  |  | 2020-03-24 | 2020-03-03 | 2020-04-03 |  |  | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-24 |  |  |  | 2020-05-01 |  | 4GT-42-340C-2NPT |  |  | 2020-05-13 |  | 2020-04-21 | [6 empty] | 2020-05-21 | 2020-05-28 | [20 empty] | 2020-06-27 |  |  |  | 2020-06-30 | [8 empty] | 2020-05-06 |  | 2020-05-09 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-18 |  |  |  | 2020-06-30 |  | 2020-07-03
PH1000264 | 125.1119 | 8.1256 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Casisang | MIN | PH101312012 | 25696 | 40 | Three Legged Tubular Tower | CO70 | 43.3802 | MIN-1000093 | Level 6 | phase2_add | phase1_630 | P1_630 |  | Cluster M10 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  |  |  |  | 2020-01-20 | 2020-01-18 | 2020-01-22 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-02-06 |  |  |  | 2020-02-06 |  |  |  | 2020-01-27 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-02-25 | 2020-02-26 | [5 empty] | A | Hector T. Balba | KM 4, Casisang, Malaybalay City | Bukidnon | 125.1251 | 8.1224 | Greenfield |  |  | 15 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-04 | 2020-02-10 |  | 2020-04-03 | 2020-03-09 | 2020-03-11 | 2020-02-27 | 2020-03-02 | 2020-03-02 | [13 empty] | 2020-04-01 | ok |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  | Awaiting MOC approval | 2020-03-18 | 2020-03-04 | 2020-03-28 |  |  | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-18 |  |  |  | 2020-04-25 |  | 4GT-42-340C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 |  |  |  | 2020-03-09 | [16 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1000266 | 125.1155 | 7.7375 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Quezon | Poblacion (Kiokong) | MIN | PH101317019 | 4102 | 40 | Three Legged Tubular Tower | CO70 | 2.1605 | MIN-1000094 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-01 | 2020-02-28 | 2020-02-03 | [13 empty] | 2020-02-08 | [5 empty] | 2020-03-02 |  |  |  | 2020-03-02 |  | 2020-03-09 | [27 empty] | 2020-03-16 |  |  | 2020-04-15 |  | 2020-03-23 | [16 empty] | 2020-04-13 |  |  | 2020-04-22 | [6 empty] | 2020-05-06 |  |  |  | 2020-05-06 |  |  |  |  | 2020-03-30 |  | 2020-04-09 |  |  | 2020-04-13 |  | 2020-04-16 |  |  | 2020-04-30 |  |  |  | 2020-05-07 |  | JGT-36-340C-2NPT |  |  | 2020-05-19 |  | 2020-04-27 | [6 empty] | 2020-05-27 | 2020-06-03 | [20 empty] | 2020-07-03 |  |  |  | 2020-07-06 | [8 empty] | 2020-05-12 |  | 2020-05-15 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-06 |  |  |  | 2020-06-09 |  |  | 2020-06-24 |  |  |  | 2020-07-06 |  | 2020-07-09
PH1000273 | 125.1412 | 8.1423 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Barangay 6 | MIN | PH101312052 | 9022 | 40 | Three Legged Tubular Tower | CO70 | 45.4709 | MIN-1000095 | Level 6 | phase2_add | phase1_630 | P1_630 |  | Cluster M10 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  |  |  |  | 2020-01-26 | 2020-01-20 | 2020-01-28 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-01-30 |  |  |  | 2020-01-30 |  |  |  | 2020-02-02 | 2020-01-30 |  |  |  | 2020-01-30 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-02-24 | 2020-03-03 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | A | Michael Randy M. Alvarez | Brgy. 7, Malaybalay City | Bukidnon | 125.1309 | 8.1496 | Rooftop |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 49sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-10 | 2020-02-10 |  | 2020-04-09 |  | 2020-03-17 | [16 empty] | 2020-04-07 |  |  | 2020-04-16 | [6 empty] | 2020-04-30 |  |  |  | 2020-04-30 |  |  |  |  | 2020-03-24 |  | 2020-04-03 |  |  | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-24 |  |  |  | 2020-05-01 |  | 4GT-42-340C-2NPT |  |  | 2020-05-13 |  | 2020-04-21 | [6 empty] | 2020-05-21 | 2020-05-28 | [20 empty] | 2020-06-27 |  |  |  | 2020-06-30 | [8 empty] | 2020-05-06 |  | 2020-05-09 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-18 |  |  |  | 2020-06-30 |  | 2020-07-03
PH1000274 | 124.7858 | 8.4751 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Puerto | MIN | PH104305063 | 14318 | 40 | Three Legged Tubular Tower | CO70 | 89.0114 | MIN-1000096 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-22 | 2020-01-21 | 2020-01-24 | 2020-02-11 |  |  |  | 2020-02-11 | 2020-02-21 |  |  |  | 2020-02-21 |  |  |  | 2020-01-29 | 2020-02-21 |  |  |  | 2020-02-21 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-26 | 2020-02-28 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 | B | Serapion Tiongson/Jonah Leonar | Purok 7, Mambatangan Upper Puerto, Cagayan de Oro City | Misamis Oriental | 124.7916 | 8.4633 | Greenfield |  |  | 10 years | P15,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-06 | 2020-02-28 |  | 2020-04-05 |  | 2020-03-13 | [16 empty] | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 |  | 2020-03-30 |  |  | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-20 |  |  |  | 2020-04-27 |  | JGT-42-280C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1000275 | 124.904 | 8.3753 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Manolo Fortich | Dalirig | MIN | PH101314004 | 4844 | 15 | Pole | CO70 | 74.1819 | MIN-1000097 | Level 6 | phase2_add | phase3 |  | DepEd_3081 | Cluster M19 | Marrox | [7 empty] | 2020-03-09 |  | 2020-03-11 | [13 empty] | 2020-03-16 | [11 empty] | 2020-04-15 | [27 empty] | 2020-04-22 |  |  | 2020-05-22 |  | 2020-04-29 | [16 empty] | 2020-05-20 |  |  | 2020-05-29 | [6 empty] | 2020-06-12 |  |  |  | 2020-06-12 |  |  |  |  | 2020-05-06 |  | 2020-05-16 |  |  | 2020-05-20 |  | 2020-05-23 |  |  | 2020-06-06 |  |  |  | 2020-06-13 |  | 4GT-42-340C-2NPT |  |  | 2020-06-25 |  | 2020-06-03 | [6 empty] | 2020-07-03 | 2020-07-10 | [20 empty] | 2020-08-09 |  |  |  | 2020-08-12 | [8 empty] | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-13 |  |  |  | 2020-07-16 |  |  | 2020-07-31 |  |  |  | 2020-08-12 |  | 2020-08-15
PH1000278 | 125.0032 | 7.898 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Tugaya | MIN | PH101321010 | 6347 | 15 | Pole | CO70 | 20.7282 | MIN-1000098 | Level 6 | phase2_add | phase3 |  |  | Cluster M10 | EPC | [7 empty] | 2020-02-16 |  | 2020-02-18 | [13 empty] | 2020-02-23 | [11 empty] | 2020-03-24 | [27 empty] | 2020-03-31 |  |  | 2020-04-30 |  | 2020-04-07 | [16 empty] | 2020-04-28 |  |  | 2020-05-07 | [6 empty] | 2020-05-21 |  |  |  | 2020-05-21 |  |  |  |  | 2020-04-14 |  | 2020-04-24 |  |  | 2020-04-28 |  | 2020-05-01 |  |  | 2020-05-15 |  |  |  | 2020-05-22 |  | JGT-36-340C-2NPT |  |  | 2020-06-03 |  | 2020-05-12 | [6 empty] | 2020-06-11 | 2020-06-18 | [20 empty] | 2020-07-18 |  |  |  | 2020-07-21 | [8 empty] | 2020-05-27 |  | 2020-05-30 |  |  | 2020-06-11 |  |  |  | 2020-06-14 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-09 |  |  |  | 2020-07-21 |  | 2020-07-24
PH1000279 | 125.1809 | 7.8859 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Laligan | MIN | PH101321012 | 7003 | 30 | Three Legged Tubular Tower | CO70 | 19.1412 | MIN-1000099 | Level 6 | phase2_add | phase2_1231 |  | DepEd_3121 | Cluster M06 | EPC | [7 empty] | 2020-02-19 | 2020-03-04 | 2020-02-21 | 2020-03-06 |  |  |  | 2020-03-06 | [8 empty] | 2020-02-26 | [5 empty] | 2020-03-06 |  |  |  | 2020-03-06 |  | 2020-03-27 | [27 empty] | 2020-04-03 |  |  | 2020-05-03 |  | 2020-04-10 | [16 empty] | 2020-05-01 |  |  | 2020-05-10 | [6 empty] | 2020-05-24 |  |  |  | 2020-05-24 |  |  |  |  | 2020-04-17 |  | 2020-04-27 |  |  | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-18 |  |  |  | 2020-05-25 |  | JGT-36-340C-2NPT |  |  | 2020-06-06 |  | 2020-05-15 | [6 empty] | 2020-06-14 | 2020-06-21 | [20 empty] | 2020-07-21 |  |  |  | 2020-07-24 | [8 empty] | 2020-05-30 |  | 2020-06-02 |  |  | 2020-06-14 |  |  |  | 2020-06-17 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-12 |  |  |  | 2020-07-24 |  | 2020-07-27
PH1000280 | 125.0488 | 7.9665 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | San Carlos | MIN | PH101321017 | 8078 | 30 | Three Legged Tubular Tower | CO70 | 26.177 | MIN-1000100 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-02-22 |  | 2020-02-24 | [13 empty] | 2020-02-29 | [11 empty] | 2020-03-30 | [27 empty] | 2020-04-06 |  |  | 2020-05-06 |  | 2020-04-13 | [16 empty] | 2020-05-04 |  |  | 2020-05-13 | [6 empty] | 2020-05-27 |  |  |  | 2020-05-27 |  |  |  |  | 2020-04-20 |  | 2020-04-30 |  |  | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-21 |  |  |  | 2020-05-28 |  | 4GT-42-340C-2NPT |  |  | 2020-06-09 |  | 2020-05-18 | [6 empty] | 2020-06-17 | 2020-06-24 | [20 empty] | 2020-07-24 |  |  |  | 2020-07-27 | [8 empty] | 2020-06-02 |  | 2020-06-05 |  |  | 2020-06-17 |  |  |  | 2020-06-20 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-15 |  |  |  | 2020-07-27 |  | 2020-07-30
PH1000281 | 125.1346 | 7.9731 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Mailag | MIN | PH101321020 | 6805 | 30 | Three Legged Tubular Tower | CO70 | 26.7318 | MIN-1000101 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-25 | 2020-03-04 | 2020-02-27 | 2020-03-06 |  |  |  | 2020-03-06 | [8 empty] | 2020-03-03 | [5 empty] | 2020-03-06 |  |  |  | 2020-03-06 |  | 2020-04-02 | [27 empty] | 2020-04-09 |  |  | 2020-05-09 |  | 2020-04-16 | [16 empty] | 2020-05-07 |  |  | 2020-05-16 | [6 empty] | 2020-05-30 |  |  |  | 2020-05-30 |  |  |  |  | 2020-04-23 |  | 2020-05-03 |  |  | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-24 |  |  |  | 2020-05-31 |  | JGT-36-340C-2NPT |  |  | 2020-06-12 |  | 2020-05-21 | [6 empty] | 2020-06-20 | 2020-06-27 | [20 empty] | 2020-07-27 |  |  |  | 2020-07-30 | [8 empty] | 2020-06-05 |  | 2020-06-08 |  |  | 2020-06-20 |  |  |  | 2020-06-23 |  |  | 2020-06-30 |  |  |  | 2020-07-03 |  |  | 2020-07-18 |  |  |  | 2020-07-30 |  | 2020-08-02
PH1000284 | 125.1418 | 7.8774 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Sinayawan | MIN | PH101321029 | 7006 | 45 | Three Legged Tubular Tower | CO70 | 16.5315 | MIN-1000102 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-28 | 2020-03-04 | 2020-03-01 | 2020-03-06 |  |  |  | 2020-03-06 | [8 empty] | 2020-03-06 | [5 empty] | 2020-03-06 |  |  |  | 2020-03-06 |  | 2020-04-05 | [27 empty] | 2020-04-12 |  |  | 2020-05-12 |  | 2020-04-19 | [16 empty] | 2020-05-10 |  |  | 2020-05-19 | [6 empty] | 2020-06-02 |  |  |  | 2020-06-02 |  |  |  |  | 2020-04-26 |  | 2020-05-06 |  |  | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-27 |  |  |  | 2020-06-03 |  | JGT-36-340C-2NPT |  |  | 2020-06-15 |  | 2020-05-24 | [6 empty] | 2020-06-23 | 2020-06-30 | [20 empty] | 2020-07-30 |  |  |  | 2020-08-02 | [8 empty] | 2020-06-08 |  | 2020-06-11 |  |  | 2020-06-23 |  |  |  | 2020-06-26 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-21 |  |  |  | 2020-08-02 |  | 2020-08-05
PH1000286 | 125.1594 | 8.8451 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Gingoog City | Anakan | MIN | PH104308003 | 3683 | 40 | Monopole Tower | CO64 | 43.5933 | MIN-1000103 | Level 6 | phase2_add | phase3 |  |  | Cluster M20 | Marrox | [7 empty] | 2020-02-09 |  | 2020-02-11 | [13 empty] | 2020-02-16 | [11 empty] | 2020-03-17 | [27 empty] | 2020-03-24 |  |  | 2020-04-23 |  | 2020-03-31 | [16 empty] | 2020-04-21 |  |  | 2020-04-30 | [6 empty] | 2020-05-14 |  |  |  | 2020-05-14 |  |  |  |  | 2020-04-07 |  | 2020-04-17 |  |  | 2020-04-21 |  | 2020-04-24 |  |  | 2020-05-08 |  |  |  | 2020-05-15 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-05-27 |  | 2020-05-05 | [6 empty] | 2020-06-04 | 2020-06-11 | [20 empty] | 2020-07-11 |  |  |  | 2020-07-14 | [8 empty] | 2020-05-20 |  | 2020-05-23 |  |  | 2020-06-04 |  |  |  | 2020-06-07 |  |  | 2020-06-14 |  |  |  | 2020-06-17 |  |  | 2020-07-02 |  |  |  | 2020-07-14 |  | 2020-07-17
PH1000289 | 125.0734 | 7.8112 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Quezon | Butong | MIN | PH101317001 | 13258 | 40 | Three Legged Tubular Tower | CO70 | 8.745 | MIN-1000104 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-04 | 2020-02-12 | 2020-02-06 | 2020-02-17 |  |  |  | 2020-02-17 | [8 empty] | 2020-02-11 | [5 empty] | 2020-02-17 |  |  |  | 2020-02-17 |  | 2020-03-12 | [27 empty] | 2020-03-19 |  |  | 2020-04-18 |  | 2020-03-26 | [16 empty] | 2020-04-16 |  |  | 2020-04-25 | [6 empty] | 2020-05-09 |  |  |  | 2020-05-09 |  |  |  |  | 2020-04-02 |  | 2020-04-12 |  |  | 2020-04-16 |  | 2020-04-19 |  |  | 2020-05-03 |  |  |  | 2020-05-10 |  | JGT-36-340C-2NPT |  |  | 2020-05-22 |  | 2020-04-30 | [6 empty] | 2020-05-30 | 2020-06-06 | [20 empty] | 2020-07-06 |  |  |  | 2020-07-09 | [8 empty] | 2020-05-15 |  | 2020-05-18 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-09 |  |  |  | 2020-06-12 |  |  | 2020-06-27 |  |  |  | 2020-07-09 |  | 2020-07-12
PH1000290 | 125.0645 | 8.0261 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Lantapan | Bantuanon | MIN | PH101310004 | 6130 | 40 | Three Legged Tubular Tower | CO70 | 32.4652 | MIN-1000105 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-03-02 | 2020-02-10 | 2020-03-04 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-15 |  |  |  | 2020-02-15 |  |  |  | 2020-03-09 | 2020-02-15 |  |  |  | 2020-02-15 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-24 | 2020-04-08 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | A | Wilmer M. Miasco | Open Space of Brgy. Bantuanon, Lantapan | Bukidnon | 125.0736 | 8.0133 | Greenfield |  |  | 10 years | P17,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-15 | 2020-02-11 |  | 2020-05-15 |  | 2020-04-22 | 2020-03-02 | [15 empty] | 2020-05-13 |  |  | 2020-05-22 | [6 empty] | 2020-06-05 |  |  |  | 2020-06-05 |  |  |  |  | 2020-04-29 |  | 2020-05-09 |  |  | 2020-05-13 |  | 2020-05-16 |  |  | 2020-05-30 |  |  |  | 2020-06-06 |  | 4GT-42-340C-2NPT |  |  | 2020-06-18 |  | 2020-05-27 | [6 empty] | 2020-06-26 | 2020-07-03 | [20 empty] | 2020-08-02 |  |  |  | 2020-08-05 | [8 empty] | 2020-06-11 |  | 2020-06-14 |  |  | 2020-06-26 |  |  |  | 2020-06-29 |  |  | 2020-07-06 |  |  |  | 2020-07-09 |  |  | 2020-07-24 |  |  |  | 2020-08-05 |  | 2020-08-08
PH1000293 | 125.0516 | 7.8597 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Maramag | Dologon | MIN | PH101315008 | 14093 | 40 | Three Legged Tubular Tower | CO70 | 14.6229 | MIN-1000106 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-03-05 |  | 2020-03-07 | [13 empty] | 2020-03-12 | [11 empty] | 2020-04-11 | [27 empty] | 2020-04-18 |  |  | 2020-05-18 |  | 2020-04-25 | [16 empty] | 2020-05-16 |  |  | 2020-05-25 | [6 empty] | 2020-06-08 |  |  |  | 2020-06-08 |  |  |  |  | 2020-05-02 |  | 2020-05-12 |  |  | 2020-05-16 |  | 2020-05-19 |  |  | 2020-06-02 |  |  |  | 2020-06-09 |  | JGT-36-340C-2NPT |  |  | 2020-06-21 |  | 2020-05-30 | [6 empty] | 2020-06-29 | 2020-07-06 | [20 empty] | 2020-08-05 |  |  |  | 2020-08-08 | [8 empty] | 2020-06-14 |  | 2020-06-17 |  |  | 2020-06-29 |  |  |  | 2020-07-02 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-27 |  |  |  | 2020-08-08 |  | 2020-08-11
PH1000296 | 125.0309 | 7.8391 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Maramag | Tubigon | MIN | PH101315008 | 14093 | 40 | Three Legged Tubular Tower | CO70 | 13.5401 | MIN-1000107 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-07 |  | 2020-02-09 | [13 empty] | 2020-02-14 | [11 empty] | 2020-03-15 | [27 empty] | 2020-03-22 |  |  | 2020-04-21 |  | 2020-03-29 | [16 empty] | 2020-04-19 |  |  | 2020-04-28 | [6 empty] | 2020-05-12 |  |  |  | 2020-05-12 |  |  |  |  | 2020-04-05 |  | 2020-04-15 |  |  | 2020-04-19 |  | 2020-04-22 |  |  | 2020-05-06 |  |  |  | 2020-05-13 |  | JGT-36-340C-2NPT |  |  | 2020-05-25 |  | 2020-05-03 | [6 empty] | 2020-06-02 | 2020-06-09 | [20 empty] | 2020-07-09 |  |  |  | 2020-07-12 | [8 empty] | 2020-05-18 |  | 2020-05-21 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-12 |  |  |  | 2020-06-15 |  |  | 2020-06-30 |  |  |  | 2020-07-12 |  | 2020-07-15
PH1000297 | 125.0424 | 8.8748 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Gingoog City | San Luis | MIN | PH104308066 | 5286 | 40 | Three Legged Tubular Tower | CO64 | 55.4095 | MIN-1000108 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M20 | Marrox | [7 empty] | 2020-02-12 |  | 2020-02-14 | [13 empty] | 2020-02-19 | [11 empty] | 2020-03-20 | [27 empty] | 2020-03-27 |  |  | 2020-04-26 |  | 2020-04-03 | [16 empty] | 2020-04-24 |  |  | 2020-05-03 | [6 empty] | 2020-05-17 |  |  |  | 2020-05-17 |  |  |  |  | 2020-04-10 |  | 2020-04-20 |  |  | 2020-04-24 |  | 2020-04-27 |  |  | 2020-05-11 |  |  |  | 2020-05-18 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-05-30 |  | 2020-05-08 | [6 empty] | 2020-06-07 | 2020-06-14 | [20 empty] | 2020-07-14 |  |  |  | 2020-07-17 | [8 empty] | 2020-05-23 |  | 2020-05-26 |  |  | 2020-06-07 |  |  |  | 2020-06-10 |  |  | 2020-06-17 |  |  |  | 2020-06-20 |  |  | 2020-07-05 |  |  |  | 2020-07-17 |  | 2020-07-20
PH1000298 | 125.0341 | 8.2228 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Dalwangan | MIN | PH101312014 | 7004 | 40 | Three Legged Tubular Tower | CO70 | 54.584 | MIN-1000109 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-03-08 | 2020-02-21 | 2020-03-10 | [13 empty] | 2020-03-15 | [5 empty] | 2020-02-22 |  |  |  | 2020-02-22 |  | 2020-04-14 | [27 empty] | 2020-04-21 |  |  | 2020-05-21 |  | 2020-04-28 | [16 empty] | 2020-05-19 |  |  | 2020-05-28 | [6 empty] | 2020-06-11 |  |  |  | 2020-06-11 |  |  |  |  | 2020-05-05 |  | 2020-05-15 |  |  | 2020-05-19 |  | 2020-05-22 |  |  | 2020-06-05 |  |  |  | 2020-06-12 |  | 4GT-42-340C-2NPT |  |  | 2020-06-24 |  | 2020-06-02 | [6 empty] | 2020-07-02 | 2020-07-09 | [20 empty] | 2020-08-08 |  |  |  | 2020-08-11 | [8 empty] | 2020-06-17 |  | 2020-06-20 |  |  | 2020-07-02 |  |  |  | 2020-07-05 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-30 |  |  |  | 2020-08-11 |  | 2020-08-14
PH1000299 | 125.0935 | 7.6433 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Quezon | Kiburiao | MIN | PH101317008 | 4531 | 40 | Three Legged Tubular Tower | CO70 | 10.2848 | MIN-1000110 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-10 | 2020-03-04 | 2020-02-12 | 2020-03-06 |  |  |  | 2020-03-06 | [8 empty] | 2020-02-17 | [5 empty] | 2020-03-06 |  |  |  | 2020-03-06 |  | 2020-03-18 | [27 empty] | 2020-03-25 |  |  | 2020-04-24 |  | 2020-04-01 | [16 empty] | 2020-04-22 |  |  | 2020-05-01 | [6 empty] | 2020-05-15 |  |  |  | 2020-05-15 |  |  |  |  | 2020-04-08 |  | 2020-04-18 |  |  | 2020-04-22 |  | 2020-04-25 |  |  | 2020-05-09 |  |  |  | 2020-05-16 |  | 4GT-42-340C-2NPT |  |  | 2020-05-28 |  | 2020-05-06 | [6 empty] | 2020-06-05 | 2020-06-12 | [20 empty] | 2020-07-12 |  |  |  | 2020-07-15 | [8 empty] | 2020-05-21 |  | 2020-05-24 |  |  | 2020-06-05 |  |  |  | 2020-06-08 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-07-03 |  |  |  | 2020-07-15 |  | 2020-07-18
PH1000302 | 125.0566 | 8.8467 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Gingoog City | Lunao | MIN | PH104308020 | 7496 | 40 | Three Legged Tubular Tower | CO64 | 54.4841 | MIN-1000111 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M20 | Marrox | [7 empty] | 2020-02-15 |  | 2020-02-17 | [13 empty] | 2020-02-22 | [11 empty] | 2020-03-23 | [27 empty] | 2020-03-30 |  |  | 2020-04-29 |  | 2020-04-06 | [16 empty] | 2020-04-27 |  |  | 2020-05-06 | [6 empty] | 2020-05-20 |  |  |  | 2020-05-20 |  |  |  |  | 2020-04-13 |  | 2020-04-23 |  |  | 2020-04-27 |  | 2020-04-30 |  |  | 2020-05-14 |  |  |  | 2020-05-21 |  | JGT-36-340C-2NPT |  |  | 2020-06-02 |  | 2020-05-11 | [6 empty] | 2020-06-10 | 2020-06-17 | [20 empty] | 2020-07-17 |  |  |  | 2020-07-20 | [8 empty] | 2020-05-26 |  | 2020-05-29 |  |  | 2020-06-10 |  |  |  | 2020-06-13 |  |  | 2020-06-20 |  |  |  | 2020-06-23 |  |  | 2020-07-08 |  |  |  | 2020-07-20 |  | 2020-07-23
PH1000303 | 124.8119 | 8.4181 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Manolo Fortich | Alae | MIN | PH101314002 | 9135 | 40 | Three Legged Tubular Tower | CO70 | 82.0584 | MIN-1000112 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-24 | 2020-01-31 | 2020-01-26 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-13 |  |  |  | 2020-02-13 |  |  |  | 2020-01-31 | 2020-02-13 |  |  |  | 2020-02-13 | 2020-02-26 | 2020-02-12 | 2020-02-12 |  | 2020-02-12 | 2020-02-24 | 2020-03-01 | 2020-02-26 |  |  | 2020-02-26 | 2020-03-02 | B | Gerardo Puga | Purok 1, Alae, Manolo Fortich | Bukidnon | 124.812 | 8.4266 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 150sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-08 | 2020-02-26 |  | 2020-04-07 |  | 2020-03-15 | [16 empty] | 2020-04-05 |  |  | 2020-04-14 | [6 empty] | 2020-04-28 |  |  |  | 2020-04-28 |  |  |  |  | 2020-03-22 | 2020-03-02 | 2020-04-01 | 2020-03-12 | 2020-03-12 | 2020-04-05 | 2020-03-08 | 2020-04-08 | 2020-03-13 |  | 2020-04-22 |  |  |  | 2020-04-29 |  | JGT-42-280C-2NPT（290KPH/D） |  |  | 2020-05-11 |  | 2020-04-19 | [6 empty] | 2020-05-19 | 2020-05-26 | [20 empty] | 2020-06-25 |  |  |  | 2020-06-28 | [8 empty] | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-05-29 |  |  |  | 2020-06-01 |  |  | 2020-06-16 |  |  |  | 2020-06-28 |  | 2020-07-01
PH1000304 | 124.866 | 8.3673 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Manolo Fortich | Tankulan | MIN | PH101314017 | 8711 | 40 | Three Legged Tubular Tower | CO70 | 74.6517 | MIN-1000113 | Level 6 | phase2_add | phase3 |  | AFP_22 | Cluster M19 | Marrox | [7 empty] | 2020-03-12 | 2020-01-23 | 2020-03-14 | [13 empty] | 2020-03-19 | [11 empty] | 2020-04-18 | [27 empty] | 2020-04-25 |  |  | 2020-05-25 |  | 2020-05-02 | [16 empty] | 2020-05-23 |  |  | 2020-06-01 | [6 empty] | 2020-06-15 |  |  |  | 2020-06-15 |  |  |  |  | 2020-05-09 |  | 2020-05-19 |  |  | 2020-05-23 |  | 2020-05-26 |  |  | 2020-06-09 |  |  |  | 2020-06-16 |  | 4GT-42-340C-2NPT |  |  | 2020-06-28 |  | 2020-06-06 | [6 empty] | 2020-07-06 | 2020-07-13 | [20 empty] | 2020-08-12 |  |  |  | 2020-08-15 | [8 empty] | 2020-06-21 |  | 2020-06-24 |  |  | 2020-07-06 |  |  |  | 2020-07-09 |  |  | 2020-07-16 |  |  |  | 2020-07-19 |  |  | 2020-08-03 |  |  |  | 2020-08-15 |  | 2020-08-18
PH1000305 | 125.0202 | 7.7078 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Maramag | Camp I | MIN | PH101315004 | 4852 | 40 | Three Legged Tubular Tower | CO70 | 8.9121 | MIN-1000114 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-13 | 2020-02-04 | 2020-02-15 | 2020-02-05 |  |  |  | 2020-02-05 | 2020-02-08 |  |  |  | 2020-02-08 |  |  |  | 2020-02-20 | 2020-02-08 |  |  |  | 2020-02-08 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-03-05 | 2020-03-21 | 2020-03-05 |  |  | 2020-03-05 | 2020-03-05 | A | LEONITA D. CHAVEZ | PUROK 1, CAMP ONE, MARAMAG | Bukidnon | 125.0108 | 7.7169 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-28 | 2020-03-02 |  | 2020-04-27 |  | 2020-04-04 | [16 empty] | 2020-04-25 | ok |  | 2020-05-04 | [6 empty] | 2020-05-18 |  |  |  | 2020-05-18 |  |  |  |  | 2020-04-11 |  | 2020-04-21 |  |  | 2020-04-25 |  | 2020-04-28 |  |  | 2020-05-12 |  |  |  | 2020-05-19 |  | JGT-36-340C-2NPT |  |  | 2020-05-31 |  | 2020-05-09 | [6 empty] | 2020-06-08 | 2020-06-15 | [20 empty] | 2020-07-15 |  |  |  | 2020-07-18 | [8 empty] | 2020-05-24 |  | 2020-05-27 |  |  | 2020-06-08 |  |  |  | 2020-06-11 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-07-06 |  |  |  | 2020-07-18 |  | 2020-07-21
PH1000306 | 125.0087 | 7.7391 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Maramag | South Poblacion | MIN | PH101315015 | 12165 | 40 | Three Legged Tubular Tower | CO70 | 9.6233 | MIN-1000115 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-16 | 2020-02-04 | 2020-02-18 | 2020-02-05 |  |  |  | 2020-02-05 | 2020-02-08 |  |  |  | 2020-02-08 |  |  |  | 2020-02-23 | 2020-02-08 |  |  |  | 2020-02-08 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-03-05 | 2020-03-24 | 2020-03-06 |  |  | 2020-03-05 | 2020-03-06 | A | JOY CRIS V YROY | PUROK 6, BRGY SOUTH, MARAMAG | Bukidnon | 125.0052 | 7.7547 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 180sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-31 | 2020-03-02 |  | 2020-04-30 |  | 2020-04-07 | [16 empty] | 2020-04-28 | ok |  | 2020-05-07 | [6 empty] | 2020-05-21 |  |  |  | 2020-05-21 |  |  |  |  | 2020-04-14 |  | 2020-04-24 |  |  | 2020-04-28 |  | 2020-05-01 |  |  | 2020-05-15 |  |  |  | 2020-05-22 |  | 4GT-42-340C-2NPT |  |  | 2020-06-03 |  | 2020-05-12 | [6 empty] | 2020-06-11 | 2020-06-18 | [20 empty] | 2020-07-18 |  |  |  | 2020-07-21 | [8 empty] | 2020-05-27 |  | 2020-05-30 |  |  | 2020-06-11 |  |  |  | 2020-06-14 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-09 |  |  |  | 2020-07-21 |  | 2020-07-24
PH1000308 | 125.0101 | 7.7708 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Maramag | North Poblacion | MIN | PH101315014 | 14799 | 40 | Three Legged Tubular Tower | CO70 | 10.2294 | MIN-1000116 | Level 6 | phase2_add | phase2_1231 |  | DICT_11 | Cluster M06 | EPC | [7 empty] | 2020-02-19 |  | 2020-02-21 | [13 empty] | 2020-02-26 | [11 empty] | 2020-03-27 | [27 empty] | 2020-04-03 |  |  | 2020-05-03 |  | 2020-04-10 | [16 empty] | 2020-05-01 |  |  | 2020-05-10 | [6 empty] | 2020-05-24 |  |  |  | 2020-05-24 |  |  |  |  | 2020-04-17 |  | 2020-04-27 |  |  | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-18 |  |  |  | 2020-05-25 |  | JGT-36-340C-2NPT |  |  | 2020-06-06 |  | 2020-05-15 | [6 empty] | 2020-06-14 | 2020-06-21 | [20 empty] | 2020-07-21 |  |  |  | 2020-07-24 | [8 empty] | 2020-05-30 |  | 2020-06-02 |  |  | 2020-06-14 |  |  |  | 2020-06-17 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-12 |  |  |  | 2020-07-24 |  | 2020-07-27
PH1000310 | 125.0644 | 8.1962 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Patpat (Lapu-Lapu) | MIN | PH101312025 | 3833 | 40 | Three Legged Tubular Tower | CO70 | 51.3091 | MIN-1000117 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-03-11 | 2020-02-23 | 2020-03-13 | 2020-02-25 |  |  |  | 2020-02-25 | 2020-02-26 |  |  |  | 2020-02-26 |  |  |  | 2020-03-18 | 2020-02-26 |  |  |  | 2020-02-26 | 2020-02-25 |  |  |  | 2020-02-25 | 2020-03-05 | 2020-04-17 | 2020-03-05 |  |  | 2020-03-05 | 2020-03-05 |  | FREDDIE OKIT | PUROK 3, BRGY PATPAT, MALAYBALAY | Bukidnon | 125.0653 | 8.1975 | Greenfield |  |  | 10 years | P15,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-24 | 2020-03-03 |  | 2020-05-24 |  | 2020-05-01 | [16 empty] | 2020-05-22 |  |  | 2020-05-31 | [6 empty] | 2020-06-14 |  |  |  | 2020-06-14 |  |  |  |  | 2020-05-08 |  | 2020-05-18 |  |  | 2020-05-22 |  | 2020-05-25 |  |  | 2020-06-08 |  |  |  | 2020-06-15 |  | 4GT-42-340C-2NPT |  |  | 2020-06-27 |  | 2020-06-05 | [6 empty] | 2020-07-05 | 2020-07-12 | [20 empty] | 2020-08-11 |  |  |  | 2020-08-14 | [8 empty] | 2020-06-20 |  | 2020-06-23 |  |  | 2020-07-05 |  |  |  | 2020-07-08 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-08-02 |  |  |  | 2020-08-14 |  | 2020-08-17
PH1000312 | 125.1769 | 8.8794 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Gingoog City | Talisay | MIN | PH104308069 | 2132 | 40 | Three Legged Tubular Tower | CO64 | 40.796 | MIN-1000118 | Level 6 | phase2_add | phase3 |  |  | Cluster M20 | Marrox | [7 empty] | 2020-02-18 |  | 2020-02-20 | [13 empty] | 2020-02-25 | [11 empty] | 2020-03-26 | [27 empty] | 2020-04-02 |  |  | 2020-05-02 |  | 2020-04-09 | [16 empty] | 2020-04-30 |  |  | 2020-05-09 | [6 empty] | 2020-05-23 |  |  |  | 2020-05-23 |  |  |  |  | 2020-04-16 |  | 2020-04-26 |  |  | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-17 |  |  |  | 2020-05-24 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-06-05 |  | 2020-05-14 | [6 empty] | 2020-06-13 | 2020-06-20 | [20 empty] | 2020-07-20 |  |  |  | 2020-07-23 | [8 empty] | 2020-05-29 |  | 2020-06-01 |  |  | 2020-06-13 |  |  |  | 2020-06-16 |  |  | 2020-06-23 |  |  |  | 2020-06-26 |  |  | 2020-07-11 |  |  |  | 2020-07-23 |  | 2020-07-26
PH1000315 | 124.5966 | 8.2344 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Talakag | Barangay 4 | MIN | PH101320021 | 1703 | 40 | Three Legged Tubular Tower | CO70 | 78.0903 | MIN-1000119 | Level 6 | phase3 | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-03-15 |  | 2020-03-17 | [13 empty] | 2020-03-22 | [11 empty] | 2020-04-21 | [27 empty] | 2020-04-28 |  |  | 2020-05-28 |  | 2020-05-05 | [16 empty] | 2020-05-26 |  |  | 2020-06-04 | [6 empty] | 2020-06-18 |  |  |  | 2020-06-18 |  |  |  |  | 2020-05-12 |  | 2020-05-22 |  |  | 2020-05-26 |  | 2020-05-29 |  |  | 2020-06-12 |  |  |  | 2020-06-19 |  | JGT-42-280C-2NPT |  |  | 2020-07-01 |  | 2020-06-09 | [6 empty] | 2020-07-09 | 2020-07-16 | [20 empty] | 2020-08-15 |  |  |  | 2020-08-18 | [8 empty] | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-19 |  |  |  | 2020-07-22 |  |  | 2020-08-06 |  |  |  | 2020-08-18 |  | 2020-08-21
PH1000316 | 124.9954 | 7.6697 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Don Carlos | Don Carlos Sur | MIN | PH101304022 | 11385 | 40 | Three Legged Tubular Tower | CO70 | 13.2952 | MIN-1000120 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-22 | 2020-02-26 | 2020-02-24 | [13 empty] | 2020-02-29 | [5 empty] | 2020-02-27 |  |  |  | 2020-02-27 |  | 2020-03-30 | [27 empty] | 2020-04-06 | 2020-03-03 |  | 2020-05-06 |  | 2020-04-13 | [16 empty] | 2020-05-04 |  |  | 2020-05-13 | [6 empty] | 2020-05-27 |  |  |  | 2020-05-27 |  |  |  |  | 2020-04-20 |  | 2020-04-30 |  |  | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-21 |  |  |  | 2020-05-28 |  | 4GT-42-340C-2NPT |  |  | 2020-06-09 |  | 2020-05-18 | [6 empty] | 2020-06-17 | 2020-06-24 | [20 empty] | 2020-07-24 |  |  |  | 2020-07-27 | [8 empty] | 2020-06-02 |  | 2020-06-05 |  |  | 2020-06-17 |  |  |  | 2020-06-20 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-15 |  |  |  | 2020-07-27 |  | 2020-07-30
PH1000317 | 125.0278 | 8.0828 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Lantapan | Capitan Juan | MIN | PH101312034 | 979 | 40 | Three Legged Tubular Tower | CO70 | 39.3073 | MIN-1000121 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-03-14 | 2020-03-04 | 2020-03-16 | 2020-03-06 |  |  |  | 2020-03-06 | [8 empty] | 2020-03-21 | [5 empty] | 2020-03-06 |  |  |  | 2020-03-06 |  | 2020-04-20 | [27 empty] | 2020-04-27 | 2020-03-03 |  | 2020-05-27 |  | 2020-05-04 | [16 empty] | 2020-05-25 |  |  | 2020-06-03 | [6 empty] | 2020-06-17 |  |  |  | 2020-06-17 |  |  |  |  | 2020-05-11 |  | 2020-05-21 |  |  | 2020-05-25 |  | 2020-05-28 |  |  | 2020-06-11 |  |  |  | 2020-06-18 |  | 4GT-42-340C-2NPT |  |  | 2020-06-30 |  | 2020-06-08 | [6 empty] | 2020-07-08 | 2020-07-15 | [20 empty] | 2020-08-14 |  |  |  | 2020-08-17 | [8 empty] | 2020-06-23 |  | 2020-06-26 |  |  | 2020-07-08 |  |  |  | 2020-07-11 |  |  | 2020-07-18 |  |  |  | 2020-07-21 |  |  | 2020-08-05 |  |  |  | 2020-08-17 |  | 2020-08-20
PH1000320 | 125.0217 | 7.999 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Lantapan | Balila | MIN | PH101310012 | 8025 | 40 | Three Legged Tubular Tower | CO70 | 30.3913 | MIN-1000122 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-03-17 | 2020-02-24 | 2020-03-19 | 2020-02-25 |  |  |  | 2020-02-25 | [8 empty] | 2020-03-24 | [5 empty] | 2020-02-25 |  |  |  | 2020-02-25 |  | 2020-04-23 | [27 empty] | 2020-04-30 | 2020-03-03 |  | 2020-05-30 |  | 2020-05-07 | [16 empty] | 2020-05-28 |  |  | 2020-06-06 | [6 empty] | 2020-06-20 |  |  |  | 2020-06-20 |  |  |  |  | 2020-05-14 |  | 2020-05-24 |  |  | 2020-05-28 |  | 2020-05-31 |  |  | 2020-06-14 |  |  |  | 2020-06-21 |  | 4GT-42-340C-2NPT |  |  | 2020-07-03 |  | 2020-06-11 | [6 empty] | 2020-07-11 | 2020-07-18 | [20 empty] | 2020-08-17 |  |  |  | 2020-08-20 | [8 empty] | 2020-06-26 |  | 2020-06-29 |  |  | 2020-07-11 |  |  |  | 2020-07-14 |  |  | 2020-07-21 |  |  |  | 2020-07-24 |  |  | 2020-08-08 |  |  |  | 2020-08-20 |  | 2020-08-23
PH1000327 | 123.7047 | 8.0583 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Occidental | Tangub City | Pangabuan | MIN | PH104215022 | 2718 | 40 | Three Legged Tubular Tower | CO68 | 110.6221 | MIN-1000123 | Level 6 | phase2_add | phase3 |  | DepEd_3134 | Cluster M25 | TBD | [7 empty] | 2020-07-17 |  | 2020-07-19 | [13 empty] | 2020-07-24 | [11 empty] | 2020-08-23 | [27 empty] | 2020-08-30 |  |  | 2020-09-29 |  | 2020-09-06 | [16 empty] | 2020-09-27 |  |  | 2020-10-06 | [6 empty] | 2020-10-20 |  |  |  | 2020-10-20 |  |  |  |  | 2020-09-13 |  | 2020-09-23 |  |  | 2020-09-27 |  | 2020-09-30 |  |  | 2020-10-14 |  |  |  | 2020-10-21 |  | 3GT-36-280C-2NPT |  |  | 2020-11-02 |  | 2020-10-11 | [6 empty] | 2020-11-10 | 2020-11-17 | [20 empty] | 2020-12-17 |  |  |  | 2020-12-20 | [8 empty] | 2020-10-26 |  | 2020-10-29 |  |  | 2020-11-10 |  |  |  | 2020-11-13 |  |  | 2020-11-20 |  |  |  | 2020-11-23 |  |  | 2020-12-08 |  |  |  | 2020-12-20 |  | 2020-12-23
PH1000341 | 124.7488 | 8.6606 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Jasaan | Bobontugan | MIN | PH104311002 | 6055 | 40 | Three Legged Tubular Tower | CO64 | 92.927 | MIN-1000124 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-28 | 2020-01-20 | 2020-01-30 | 2020-01-22 | 2020-02-06 |  |  | 2020-01-22 |  | 2020-02-09 |  |  | 2020-02-09 |  |  |  | 2020-02-04 |  | 2020-02-09 |  |  | 2020-02-09 | 2020-01-22 | 2020-02-06 |  |  | 2020-01-22 | 2020-02-24 | 2020-03-05 | 2020-02-26 |  |  | 2020-02-26 | 2020-03-02 | A | Juan A. Po | Poblacion, Jasaan | Misamis Oriental | 124.7507 | 8.6554 | Greenfield |  |  | 10 years | P18,000 exclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-12 | 2020-02-13 |  | 2020-04-11 |  | 2020-03-19 | [16 empty] | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 |  | 2020-04-05 |  |  | 2020-04-09 | 2020-03-08 | 2020-04-12 | 2020-03-13 |  | 2020-04-26 |  |  |  | 2020-05-03 |  | JGT-42-280C-2NPT（290KPH/D） |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1000342 | 124.7808 | 8.5867 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Villanueva | Poblacion | MIN | PH104326007 | 2539 | 40 | Three Legged Tubular Tower | CO64 | 92.9672 | MIN-1000125 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-30 | 2020-01-17 | 2020-02-01 | 2020-02-04 |  |  |  | 2020-02-04 | 2020-02-07 |  |  |  | 2020-02-07 |  |  |  | 2020-02-06 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-02-04 |  |  |  | 2020-02-04 | 2020-03-06 | 2020-03-07 | 2020-03-09 |  |  | 2020-03-09 |  | A | Elena T. Abrea | Zone 1, Brgy. Katipunan, Villanueva | Misamis Oriental | 124.7741 | 8.5807 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-14 | 2020-02-12 |  | 2020-04-13 | 2020-02-27 | 2020-03-21 | [16 empty] | 2020-04-11 | ok |  | 2020-04-20 | [6 empty] | 2020-05-04 |  |  |  | 2020-05-04 |  |  |  | Awaiting NRAF approval | 2020-03-28 | 2020-02-26 | 2020-04-07 | 2020-02-28 | 2020-02-29 | 2020-04-11 | 2020-03-05 | 2020-04-14 | 2020-03-06 | 2020-03-06 | 2020-04-28 | 2020-03-07 | 2020-03-07 | 2020-03-07 | 2020-05-05 | 2020-03-07 | 3GT-36-280C-2NPT（290KPH/C） |  |  | 2020-05-17 |  | 2020-04-25 | [6 empty] | 2020-05-25 | 2020-06-01 | [20 empty] | 2020-07-01 |  |  |  | 2020-07-04 | [8 empty] | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-04 |  |  |  | 2020-06-07 |  |  | 2020-06-22 |  |  |  | 2020-07-04 |  | 2020-07-07
PH1000343 | 124.7779 | 8.7436 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Balingasag | Barangay 5 | MIN | PH104302024 | 916 | 40 | Three Legged Tubular Tower | CO64 | 86.9976 | MIN-1000126 | Level 1 (OA) | phase3 | phase3 | OA_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-19 | 2020-01-17 | 2020-01-21 | 2020-02-08 | 2020-02-08 | 2020-02-10 |  | 2020-02-08 | 2020-02-23 |  |  |  | 2020-02-23 |  |  |  | 2020-01-26 | 2020-02-23 |  |  |  | 2020-02-23 | 2020-02-08 | 2020-02-08 | 2020-02-10 |  | 2020-02-08 | 2020-02-21 | 2020-02-25 | [6 empty] | Ricky Bernales | Brgy. Cogon, Palingasag | Misamis Oriental | 124.7807 | 8.7559 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 150sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-03 | 2020-02-24 |  | 2020-04-02 | 2020-03-13 | 2020-03-10 | [16 empty] | 2020-03-31 |  |  | 2020-04-09 | [6 empty] | 2020-04-23 |  |  |  | 2020-04-23 |  |  |  | Awaiting MOC approval | 2020-03-17 | 2020-02-29 | 2020-03-27 | 2020-03-06 | 2020-03-06 | 2020-03-31 | 2020-03-06 | 2020-04-03 | 2020-03-07 | 2020-03-08 | 2020-04-17 |  |  |  | 2020-04-24 |  | 3GT-36-280C-2NPT（290KPH/D） |  |  | 2020-05-06 |  | 2020-04-14 | [6 empty] | 2020-05-14 | 2020-05-21 | [20 empty] | 2020-06-20 |  |  |  | 2020-06-23 | [8 empty] | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-11 |  |  |  | 2020-06-23 |  | 2020-06-26
PH1000346 | 125.1569 | 8.052 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Linabo | MIN | PH101312026 | 6933 | 40 | Three Legged Tubular Tower | CO70 | 35.7923 | MIN-1000127 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-01-12 | 2020-02-22 | 2020-01-14 | 2020-02-23 |  |  |  | 2020-02-23 | 2020-02-24 |  |  |  | 2020-02-24 |  |  |  | 2020-01-19 | 2020-02-24 |  |  |  | 2020-02-24 | 2020-02-23 |  |  |  | 2020-02-23 | 2020-03-05 | 2020-02-18 | 2020-03-06 |  |  | 2020-03-05 | 2020-03-06 | A | Cecilia Llamoso | Purok 2, Brgy. Linabo, Malaybalay City | Bukidnon | 125.1561 | 8.0526 | Greenfield |  |  | 10 years | P15,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-25 | 2020-03-03 |  | 2020-03-26 |  | 2020-03-03 | [16 empty] | 2020-03-24 |  |  | 2020-04-02 | [6 empty] | 2020-04-16 |  |  |  | 2020-04-16 |  |  |  |  | 2020-03-10 |  | 2020-03-20 |  |  | 2020-03-24 |  | 2020-03-27 |  |  | 2020-04-10 |  |  |  | 2020-04-17 |  | JGT-36-340C-2NPT |  |  | 2020-04-29 |  | 2020-04-07 | [6 empty] | 2020-05-07 | 2020-05-14 | [20 empty] | 2020-06-13 |  |  |  | 2020-06-16 | [8 empty] | 2020-04-22 |  | 2020-04-25 |  |  | 2020-05-07 |  |  |  | 2020-05-10 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-06-04 |  |  |  | 2020-06-16 |  | 2020-06-19
PH1000357 | 124.9844 | 7.7749 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Maramag | Base Camp | MIN | PH101315002 | 7569 | 40 | Three Legged Tubular Tower | CO70 | 13.0404 | MIN-1000128 | Level 6 | phase2_add | phase2_1231 |  | DepEd_3050 | Cluster M06 | EPC | [7 empty] | 2020-02-25 |  | 2020-02-27 | [13 empty] | 2020-03-03 | [11 empty] | 2020-04-02 | [27 empty] | 2020-04-09 | 2020-03-03 |  | 2020-05-09 |  | 2020-04-16 | [16 empty] | 2020-05-07 |  |  | 2020-05-16 | [6 empty] | 2020-05-30 |  |  |  | 2020-05-30 |  |  |  |  | 2020-04-23 |  | 2020-05-03 |  |  | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-24 |  |  |  | 2020-05-31 |  | JGT-36-340C-2NPT |  |  | 2020-06-12 |  | 2020-05-21 | [6 empty] | 2020-06-20 | 2020-06-27 | [20 empty] | 2020-07-27 |  |  |  | 2020-07-30 | [8 empty] | 2020-06-05 |  | 2020-06-08 |  |  | 2020-06-20 |  |  |  | 2020-06-23 |  |  | 2020-06-30 |  |  |  | 2020-07-03 |  |  | 2020-07-18 |  |  |  | 2020-07-30 |  | 2020-08-02
PH1000368 | 125.1178 | 8.0323 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Lantapan | Bugcaon | MIN | PH101310006 | 5412 | 40 | Three Legged Tubular Tower | CO70 | 33.0571 | MIN-1000129 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-03-20 | 2020-02-10 | 2020-03-22 | 2020-02-11 |  |  |  | 2020-02-11 | 2020-02-12 |  |  |  | 2020-02-12 |  |  |  | 2020-03-27 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-11 |  |  |  | 2020-02-11 | 2020-02-25 | 2020-04-26 | [5 empty] | A | Jerry Fabiana | Zone 1, Bugcaon, Lantapan | Bukidnon | 125.1161 | 8.0438 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-03 | 2020-03-03 |  | 2020-06-02 |  | 2020-05-10 | [16 empty] | 2020-05-31 |  |  | 2020-06-09 | [6 empty] | 2020-06-23 |  |  |  | 2020-06-23 |  |  |  |  | 2020-05-17 |  | 2020-05-27 |  |  | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-17 |  |  |  | 2020-06-24 |  | 4GT-42-340C-2NPT |  |  | 2020-07-06 |  | 2020-06-14 | [6 empty] | 2020-07-14 | 2020-07-21 | [20 empty] | 2020-08-20 |  |  |  | 2020-08-23 | [8 empty] | 2020-06-29 |  | 2020-07-02 |  |  | 2020-07-14 |  |  |  | 2020-07-17 |  |  | 2020-07-24 |  |  |  | 2020-07-27 |  |  | 2020-08-11 |  |  |  | 2020-08-23 |  | 2020-08-26
PH1000376 | 125.1021 | 7.991 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Bagontaas | MIN | PH101321006 | 3065 | 40 | Three Legged Tubular Tower | CO70 | 28.3829 | MIN-1000130 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-03-20 | 2020-02-10 | 2020-03-22 | 2020-02-17 |  |  |  | 2020-02-17 | 2020-02-19 |  |  |  | 2020-02-19 |  |  |  | 2020-03-27 | 2020-02-19 |  |  |  | 2020-02-19 | 2020-02-17 |  |  |  | 2020-02-17 | 2020-03-13 | 2020-04-26 | 2020-03-13 |  |  | 2020-03-12 | 2020-03-13 |  | Dennis Ferrera | Purok 2, Patag, Valencia City | Bukidnon | 125.11 | 7.96 | Greenfield |  |  | 10 years | P15,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-03 | 2020-03-03 |  | 2020-06-02 |  | 2020-05-10 | [16 empty] | 2020-05-31 |  |  | 2020-06-09 | [6 empty] | 2020-06-23 |  |  |  | 2020-06-23 |  |  |  |  | 2020-05-17 |  | 2020-05-27 |  |  | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-17 |  |  |  | 2020-06-24 |  | JGT-36-340C-2NPT |  |  | 2020-07-06 |  | 2020-06-14 | [6 empty] | 2020-07-14 | 2020-07-21 | [20 empty] | 2020-08-20 |  |  |  | 2020-08-23 | [8 empty] | 2020-06-29 |  | 2020-07-02 |  |  | 2020-07-14 |  |  |  | 2020-07-17 |  |  | 2020-07-24 |  |  |  | 2020-07-27 |  |  | 2020-08-11 |  |  |  | 2020-08-23 |  | 2020-08-26
PH1000377 | 125.1322 | 7.916 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Batangan | MIN | PH101321004 | 11550 | 40 | Three Legged Tubular Tower | CO70 | 20.4271 | MIN-1000131 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-03-23 | 2020-02-10 | 2020-03-25 | 2020-02-11 |  |  |  | 2020-02-11 | 2020-02-12 |  |  |  | 2020-02-12 |  |  |  | 2020-03-30 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-11 |  |  |  | 2020-02-11 | 2020-02-25 | 2020-04-29 | [5 empty] | A | Michille Paran Sayson | Purok 10, Batangan, Valencia City | Bukidnon | 125.1208 | 7.9047 | Greenfield |  |  | 10 years | P18,000 exclusive of VAT and withholding tax | quarterly | 180sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-06 | 2020-03-04 |  | 2020-06-05 |  | 2020-05-13 | [16 empty] | 2020-06-03 |  |  | 2020-06-12 | [6 empty] | 2020-06-26 |  |  |  | 2020-06-26 |  |  |  |  | 2020-05-20 |  | 2020-05-30 |  |  | 2020-06-03 |  | 2020-06-06 |  |  | 2020-06-20 |  |  |  | 2020-06-27 |  | JGT-36-340C-2NPT |  |  | 2020-07-09 |  | 2020-06-17 | [6 empty] | 2020-07-17 | 2020-07-24 | [20 empty] | 2020-08-23 |  |  |  | 2020-08-26 | [8 empty] | 2020-07-02 |  | 2020-07-05 |  |  | 2020-07-17 |  |  |  | 2020-07-20 |  |  | 2020-07-27 |  |  |  | 2020-07-30 |  |  | 2020-08-14 |  |  |  | 2020-08-26 |  | 2020-08-29
PH1000387 | 125.0394 | 7.8994 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Lumbo | MIN | PH101321003 | 4123 | 40 | Three Legged Tubular Tower | CO70 | 19.2295 | MIN-1000132 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-03-26 | 2020-02-10 | 2020-03-28 | 2020-02-11 |  |  |  | 2020-02-11 | 2020-02-12 |  |  |  | 2020-02-12 |  |  |  | 2020-04-02 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-11 |  |  |  | 2020-02-11 | 2020-02-25 | 2020-05-02 | [5 empty] | A | David Hermos | Purok 4, Tagostos, Valencia City | Bukidnon | 125.0795 | 7.9046 | Greenfield |  |  | 10 years | P18,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-09 | 2020-03-04 |  | 2020-06-08 |  | 2020-05-16 | [16 empty] | 2020-06-06 |  |  | 2020-06-15 | [6 empty] | 2020-06-29 |  |  |  | 2020-06-29 |  |  |  |  | 2020-05-23 |  | 2020-06-02 |  |  | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-23 |  |  |  | 2020-06-30 |  | JGT-36-340C-2NPT |  |  | 2020-07-12 |  | 2020-06-20 | [6 empty] | 2020-07-20 | 2020-07-27 | [20 empty] | 2020-08-26 |  |  |  | 2020-08-29 | [8 empty] | 2020-07-05 |  | 2020-07-08 |  |  | 2020-07-20 |  |  |  | 2020-07-23 |  |  | 2020-07-30 |  |  |  | 2020-08-02 |  |  | 2020-08-17 |  |  |  | 2020-08-29 |  | 2020-09-01
PH1000390 | 124.4708 | 8.5693 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Alubijid | Benigwayan | MIN | PH104301010 | 2986 | 40 | Three Legged Tubular Tower | CO70 | 115.4313 | MIN-1000133 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-28 | 2020-02-16 | 2020-01-30 | 2020-02-17 |  |  |  | 2020-02-17 | 2020-02-21 |  |  |  | 2020-02-21 |  |  |  | 2020-02-04 | 2020-02-21 |  |  |  | 2020-02-21 | 2020-02-17 |  |  |  | 2020-02-17 | 2020-03-02 | 2020-03-05 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 | A | Wenceslao Magdale | Purok 3, Lanao, Alubijid | Misamis Oriental | 124.469 | 8.5735 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-12 | 2020-03-05 |  | 2020-04-11 |  | 2020-03-19 | [16 empty] | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 | 2020-03-02 | 2020-04-05 | 2020-03-12 | 2020-03-12 | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-26 |  |  |  | 2020-05-03 |  | 3GT-36-280C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1000400 | 123.7862 | 8.0222 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Baroy | Poblacion | MIN | PH103503015 | 3019 | 40 | Three Legged Tubular Tower | CO68 | 102.5166 | MIN-1000134 | Level 6 | phase2_add | phase3 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-18 |  | 2020-07-20 | [13 empty] | 2020-07-25 | [11 empty] | 2020-08-24 | [27 empty] | 2020-08-31 |  |  | 2020-09-30 |  | 2020-09-07 | [16 empty] | 2020-09-28 |  |  | 2020-10-07 | [6 empty] | 2020-10-21 |  |  |  | 2020-10-21 |  |  |  |  | 2020-09-14 |  | 2020-09-24 |  |  | 2020-09-28 |  | 2020-10-01 |  |  | 2020-10-15 |  |  |  | 2020-10-22 |  | JGT-42-280C-2NPT |  |  | 2020-11-03 |  | 2020-10-12 | [6 empty] | 2020-11-11 | 2020-11-18 | [20 empty] | 2020-12-18 |  |  |  | 2020-12-21 | [8 empty] | 2020-10-27 |  | 2020-10-30 |  |  | 2020-11-11 |  |  |  | 2020-11-14 |  |  | 2020-11-21 |  |  |  | 2020-11-24 |  |  | 2020-12-09 |  |  |  | 2020-12-21 |  | 2020-12-24
PH1000417 | 124.7888 | 8.8074 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Lagonglong | Poblacion | MIN | PH104313008 | 3862 | 40 | Monopole Tower | CO64 | 84.1747 | MIN-1000135 | Level 6 | phase3 | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-02-21 |  | 2020-02-23 | [13 empty] | 2020-02-28 | [11 empty] | 2020-03-29 | [27 empty] | 2020-04-05 |  |  | 2020-05-05 |  | 2020-04-12 | [16 empty] | 2020-05-03 |  |  | 2020-05-12 | [6 empty] | 2020-05-26 |  |  |  | 2020-05-26 |  |  |  |  | 2020-04-19 |  | 2020-04-29 |  |  | 2020-05-03 |  | 2020-05-06 |  |  | 2020-05-20 |  |  |  | 2020-05-27 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-06-08 |  | 2020-05-17 | [6 empty] | 2020-06-16 | 2020-06-23 | [20 empty] | 2020-07-23 |  |  |  | 2020-07-26 | [8 empty] | 2020-06-01 |  | 2020-06-04 |  |  | 2020-06-16 |  |  |  | 2020-06-19 |  |  | 2020-06-26 |  |  |  | 2020-06-29 |  |  | 2020-07-14 |  |  |  | 2020-07-26 |  | 2020-07-29
PH1000428 | 125.022 | 8.9065 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Medina | Cabug | MIN | PH104319018 | 3471 | 40 | Three Legged Tubular Tower | CO64 | 57.1807 | MIN-1000136 | Level 1 (OA) | phase2_add | phase2_1231 | OA_630 |  | Cluster M20 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  | Enovell |  | 2020-01-20 | 2020-01-26 | 2020-01-17 | 2020-01-28 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-02 |  |  |  | 2020-02-02 |  |  |  | 2020-02-02 | 2020-02-02 |  |  |  | 2020-02-02 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-19 | 2020-03-03 | [5 empty] | A | Virgilio E. Alaba | South Poblacion, Medina | Misamis Oriental | 125.0236 | 8.906 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 150sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-10 | 2020-02-13 |  | 2020-04-09 |  | 2020-03-17 | [16 empty] | 2020-04-07 |  |  | 2020-04-16 | [6 empty] | 2020-04-30 |  |  |  | 2020-04-30 |  |  |  |  | 2020-03-24 |  | 2020-04-03 |  |  | 2020-04-07 | 2020-02-26 | 2020-04-10 | 2020-02-27 | 2020-02-29 | 2020-04-24 |  |  |  | 2020-05-01 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-05-13 |  | 2020-04-21 | [6 empty] | 2020-05-21 | 2020-05-28 | [20 empty] | 2020-06-27 |  |  |  | 2020-06-30 | [8 empty] | 2020-05-06 |  | 2020-05-09 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-18 |  |  |  | 2020-06-30 |  | 2020-07-03
PH1000436 | 124.2904 | 8.3991 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Manticao | Poblacion | MIN | PH104318010 | 8367 | 40 | Three Legged Tubular Tower | CO70 | 115.3467 | MIN-1000137 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) |  |  |  |  | 2020-01-20 | 2020-02-29 | 2020-01-11 | 2020-03-02 |  | 2020-01-12 |  |  | 2020-01-12 | 2020-01-18 |  |  |  | 2020-01-18 |  |  |  | 2020-03-07 | 2020-01-18 |  |  |  | 2020-01-18 |  | 2020-01-12 |  |  | 2020-01-12 | 2020-02-25 | 2020-04-06 | [5 empty] | A | Nelson Dy Jr. | Purok 82, Brgy Poblacion, Manticao | Misamis Oriental | 124.291 | 8.3984 | Greenfield | 13m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-13 | 2020-02-01 |  | 2020-05-13 | 2020-03-11 | 2020-04-20 | [16 empty] | 2020-05-11 |  |  | 2020-05-20 | [6 empty] | 2020-06-03 |  |  |  | 2020-06-03 |  |  |  | Awaiting MOC approval | 2020-04-27 | 2020-03-04 | 2020-05-07 |  |  | 2020-05-11 | 2020-02-14 | 2020-05-14 | 2020-02-28 |  | 2020-05-28 |  |  |  | 2020-06-04 |  | JGT-42-280C-2NPT |  |  | 2020-06-16 |  | 2020-05-25 | [6 empty] | 2020-06-24 | 2020-07-01 | [20 empty] | 2020-07-31 |  |  |  | 2020-08-03 | [8 empty] | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-04 |  |  |  | 2020-07-07 |  |  | 2020-07-22 |  |  |  | 2020-08-03 |  | 2020-08-06
PH1000438 | 124.7853 | 8.8553 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Salay | Casulog | MIN | PH104322019 | 3168 | 40 | Three Legged Tubular Tower | CO64 | 83.6731 | MIN-1000138 | Level 6 | phase3 | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-02-24 |  | 2020-02-26 | [13 empty] | 2020-03-02 | [11 empty] | 2020-04-01 | [27 empty] | 2020-04-08 |  |  | 2020-05-08 |  | 2020-04-15 | [16 empty] | 2020-05-06 |  |  | 2020-05-15 | [6 empty] | 2020-05-29 |  |  |  | 2020-05-29 |  |  |  |  | 2020-04-22 |  | 2020-05-02 |  |  | 2020-05-06 |  | 2020-05-09 |  |  | 2020-05-23 |  |  |  | 2020-05-30 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-06-11 |  | 2020-05-20 | [6 empty] | 2020-06-19 | 2020-06-26 | [20 empty] | 2020-07-26 |  |  |  | 2020-07-29 | [8 empty] | 2020-06-04 |  | 2020-06-07 |  |  | 2020-06-19 |  |  |  | 2020-06-22 |  |  | 2020-06-29 |  |  |  | 2020-07-02 |  |  | 2020-07-17 |  |  |  | 2020-07-29 |  | 2020-08-01
PH1000454 | 124.9776 | 8.3399 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Sumilao | Kisolon | MIN | PH101319001 | 11532 | 40 | Three Legged Tubular Tower | CO70 | 68.4254 | MIN-1000139 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-03-29 | 2020-01-16 | 2020-03-31 | 2020-02-17 |  |  |  | 2020-02-17 | 2020-02-19 |  |  |  | 2020-02-19 |  |  |  | 2020-04-05 | 2020-02-19 |  |  |  | 2020-02-19 | 2020-02-14 |  |  |  | 2020-02-14 | 2020-02-25 | 2020-05-05 | [6 empty] | Estrella Baula | Purok 1, Brgy Kisolon, Sumilao | Bukidnon | 124.9773 | 8.3312 | Greenfield |  |  | 15 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-12 | 2020-03-04 |  | 2020-06-11 |  | 2020-05-19 | [16 empty] | 2020-06-09 |  |  | 2020-06-18 | [6 empty] | 2020-07-02 |  |  |  | 2020-07-02 |  |  |  |  | 2020-05-26 |  | 2020-06-05 |  |  | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-26 |  |  |  | 2020-07-03 |  | 4GT-42-340C-2NPT |  |  | 2020-07-15 |  | 2020-06-23 | [6 empty] | 2020-07-23 | 2020-07-30 | [20 empty] | 2020-08-29 |  |  |  | 2020-09-01 | [8 empty] | 2020-07-08 |  | 2020-07-11 |  |  | 2020-07-23 |  |  |  | 2020-07-26 |  |  | 2020-08-02 |  |  |  | 2020-08-05 |  |  | 2020-08-20 |  |  |  | 2020-09-01 |  | 2020-09-04
PH1000464 | 123.6701 | 7.9276 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Kapatagan | Taguitic | MIN | PH103505034 | 2991 | 40 | Three Legged Tubular Tower | CO68 | 101.0938 | MIN-1000140 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M25 | TBD | [7 empty] | 2020-07-19 |  | 2020-07-21 | [13 empty] | 2020-07-26 | [11 empty] | 2020-08-25 | [27 empty] | 2020-09-01 |  |  | 2020-10-01 |  | 2020-09-08 | [16 empty] | 2020-09-29 |  |  | 2020-10-08 | [6 empty] | 2020-10-22 |  |  |  | 2020-10-22 |  |  |  |  | 2020-09-15 |  | 2020-09-25 |  |  | 2020-09-29 |  | 2020-10-02 |  |  | 2020-10-16 |  |  |  | 2020-10-23 |  | JGT-42-280C-2NPT |  |  | 2020-11-04 |  | 2020-10-13 | [6 empty] | 2020-11-12 | 2020-11-19 | [20 empty] | 2020-12-19 |  |  |  | 2020-12-22 | [8 empty] | 2020-10-28 |  | 2020-10-31 |  |  | 2020-11-12 |  |  |  | 2020-11-15 |  |  | 2020-11-22 |  |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  |  | 2020-12-22 |  | 2020-12-25
PH1000468 | 125.0261 | 8.2683 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Impasug-Ong | Cawayan | MIN | PH101305008 | 6183 | 40 | Three Legged Tubular Tower | CO70 | 59.7103 | MIN-1000141 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-04-01 | 2020-03-04 | 2020-04-03 | 2020-03-06 |  |  |  | 2020-03-06 | [8 empty] | 2020-04-08 | [5 empty] | 2020-03-06 |  |  |  | 2020-03-06 |  | 2020-05-08 | [27 empty] | 2020-05-15 |  |  | 2020-06-14 |  | 2020-05-22 | [11 empty] | 09354453709/09655416841 |  |  |  |  | 2020-06-12 |  |  | 2020-06-21 | [6 empty] | 2020-07-05 |  |  |  | 2020-07-05 |  |  |  |  | 2020-05-29 |  | 2020-06-08 |  |  | 2020-06-12 |  | 2020-06-15 |  |  | 2020-06-29 |  |  |  | 2020-07-06 |  | 4GT-42-340C-2NPT |  |  | 2020-07-18 |  | 2020-06-26 | [6 empty] | 2020-07-26 | 2020-08-02 | [20 empty] | 2020-09-01 |  |  |  | 2020-09-04 | [8 empty] | 2020-07-11 |  | 2020-07-14 |  |  | 2020-07-26 |  |  |  | 2020-07-29 |  |  | 2020-08-05 |  |  |  | 2020-08-08 |  |  | 2020-08-23 |  |  |  | 2020-09-04 |  | 2020-09-07
PH1000476 | 124.2106 | 8.1265 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Baloi | Maria-Cristina | MIN | PH103502017 | 3420 | 40 | Three Legged Tubular Tower | CO68 | 100.6043 | MIN-1000142 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 | DICT_59 | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) |  |  |  |  | 2020-01-20 | 2020-03-03 | 2020-01-14 | 2020-03-05 | 2020-01-15 |  | 2020-01-19 |  | 2020-01-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-03-10 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-15 |  | 2020-01-19 |  | 2020-01-15 | 2020-02-24 | 2020-04-09 | [5 empty] | C | Elias Ali | PUROK 1, BRGY NANGKA, BALAO-I | Lanao del Norte | 124.2215 | 8.1153 | Greenfield | 386m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-16 |  |  | 2020-05-16 |  | 2020-04-23 | [16 empty] | 2020-05-14 |  |  | 2020-05-23 | [6 empty] | 2020-06-06 |  |  |  | 2020-06-06 |  |  |  |  | 2020-04-30 |  | 2020-05-10 |  |  | 2020-05-14 |  | 2020-05-17 |  |  | 2020-05-31 |  |  |  | 2020-06-07 |  | JGT-42-280C-2NPT |  |  | 2020-06-19 |  | 2020-05-28 | [6 empty] | 2020-06-27 | 2020-07-04 | [20 empty] | 2020-08-03 |  |  |  | 2020-08-06 | [8 empty] | 2020-06-12 |  | 2020-06-15 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-07 |  |  |  | 2020-07-10 |  |  | 2020-07-25 |  |  |  | 2020-08-06 |  | 2020-08-09
PH1000482 | 124.3037 | 8.4972 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Initao | Poblacion | MIN | PH104310011 | 7817 | 40 | Monopole Tower | CO70 | 121.5495 | MIN-1000143 | Level 1 (OA) | phase3 | phase3 | OA_630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) | Enovell |  | Enovell |  | 2020-01-20 | 2020-01-16 | 2020-01-11 | 2020-01-18 |  | 2020-01-15 |  |  | 2020-01-15 |  | 2020-01-16 |  |  | 2020-01-16 |  |  |  | 2020-01-23 |  | 2020-01-16 |  |  | 2020-01-16 |  | 2020-01-15 |  |  | 2020-01-15 | 2020-02-21 | 2020-02-22 | [5 empty] | B | Nelsie Ebesa | ZONE 12, POBLACION INITAO | Misamis Oriental | 124.3055 | 8.4968 | Greenfield | 15m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-29 | 2020-02-01 |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 | 2020-03-05 | 2020-03-24 |  |  | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-14 |  |  |  | 2020-04-21 |  | JGT-42-280C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1000491 | 125.1702 | 8.0231 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Managok | MIN | PH101312031 | 7200 | 40 | Three Legged Tubular Tower | CO70 | 32.9808 | MIN-1000144 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-04-04 | 2020-02-20 | 2020-04-06 | [13 empty] | 2020-04-11 | [5 empty] | 2020-02-21 |  |  |  | 2020-02-21 |  | 2020-05-11 | [27 empty] | 2020-05-18 |  |  | 2020-06-17 |  | 2020-05-25 | [16 empty] | 2020-06-15 |  |  | 2020-06-24 | [6 empty] | 2020-07-08 |  |  |  | 2020-07-08 |  |  |  |  | 2020-06-01 |  | 2020-06-11 |  |  | 2020-06-15 |  | 2020-06-18 |  |  | 2020-07-02 |  |  |  | 2020-07-09 |  | 4GT-42-340C-2NPT |  |  | 2020-07-21 |  | 2020-06-29 | [6 empty] | 2020-07-29 | 2020-08-05 | [20 empty] | 2020-09-04 |  |  |  | 2020-09-07 | [8 empty] | 2020-07-14 |  | 2020-07-17 |  |  | 2020-07-29 |  |  |  | 2020-08-01 |  |  | 2020-08-08 |  |  |  | 2020-08-11 |  |  | 2020-08-26 |  |  |  | 2020-09-07 |  | 2020-09-10
PH1000493 | 125.0238 | 8.1489 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Imbayao | MIN | PH101312010 | 1160 | 40 | Three Legged Tubular Tower | CO70 | 46.6199 | MIN-1000145 | Level 6 | phase2_add | phase2_1231 |  | DepEd_3109 | Cluster M10 | EPC | [7 empty] | 2020-04-07 | 2020-03-04 | 2020-04-09 | 2020-03-06 |  |  |  | 2020-03-06 | [8 empty] | 2020-04-14 | [5 empty] | 2020-03-06 |  |  |  | 2020-03-06 |  | 2020-05-14 | [27 empty] | 2020-05-21 |  |  | 2020-06-20 |  | 2020-05-28 | [16 empty] | 2020-06-18 |  |  | 2020-06-27 | [6 empty] | 2020-07-11 |  |  |  | 2020-07-11 |  |  |  |  | 2020-06-04 |  | 2020-06-14 |  |  | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-05 |  |  |  | 2020-07-12 |  | 4GT-42-340C-2NPT |  |  | 2020-07-24 |  | 2020-07-02 | [6 empty] | 2020-08-01 | 2020-08-08 | [20 empty] | 2020-09-07 |  |  |  | 2020-09-10 | [8 empty] | 2020-07-17 |  | 2020-07-20 |  |  | 2020-08-01 |  |  |  | 2020-08-04 |  |  | 2020-08-11 |  |  |  | 2020-08-14 |  |  | 2020-08-29 |  |  |  | 2020-09-10 |  | 2020-09-13
PH1000494 | 123.8083 | 8.4449 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Occidental | Aloran | Pelong | MIN | PH104201036 | 741 | 40 | Three Legged Tubular Tower | CO68 | 144.3366 | MIN-1000146 | Level 6 | phase3 | phase3 |  |  | Cluster M18 | TBD | [7 empty] | 2020-07-14 |  | 2020-07-16 | [13 empty] | 2020-07-21 | [11 empty] | 2020-08-20 | [27 empty] | 2020-08-27 |  |  | 2020-09-26 |  | 2020-09-03 | [16 empty] | 2020-09-24 |  |  | 2020-10-03 | [6 empty] | 2020-10-17 |  |  |  | 2020-10-17 |  |  |  |  | 2020-09-10 |  | 2020-09-20 |  |  | 2020-09-24 |  | 2020-09-27 |  |  | 2020-10-11 |  |  |  | 2020-10-18 |  | 3GT-36-280C-2NPT |  |  | 2020-10-30 |  | 2020-10-08 | [6 empty] | 2020-11-07 | 2020-11-14 | [20 empty] | 2020-12-14 |  |  |  | 2020-12-17 | [8 empty] | 2020-10-23 |  | 2020-10-26 |  |  | 2020-11-07 |  |  |  | 2020-11-10 |  |  | 2020-11-17 |  |  |  | 2020-11-20 |  |  | 2020-12-05 |  |  |  | 2020-12-17 |  | 2020-12-20
PH1000498 | 125.0848 | 8.7934 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Gingoog City | Murallon | MIN | PH104308029 | 1140 | 45 | Three Legged Tubular Tower | CO64 | 53.1758 | MIN-1000147 | Level 6 | phase2_add | phase3 |  |  | Cluster M20 | Marrox | [7 empty] | 2020-02-27 |  | 2020-02-29 | [13 empty] | 2020-03-05 | [11 empty] | 2020-04-04 | [27 empty] | 2020-04-11 |  |  | 2020-05-11 |  | 2020-04-18 | [16 empty] | 2020-05-09 |  |  | 2020-05-18 | [6 empty] | 2020-06-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-04-25 |  | 2020-05-05 |  |  | 2020-05-09 |  | 2020-05-12 |  |  | 2020-05-26 |  |  |  | 2020-06-02 |  | 4GT-42-340C-2NPT |  |  | 2020-06-14 |  | 2020-05-23 | [6 empty] | 2020-06-22 | 2020-06-29 | [20 empty] | 2020-07-29 |  |  |  | 2020-08-01 | [8 empty] | 2020-06-07 |  | 2020-06-10 |  |  | 2020-06-22 |  |  |  | 2020-06-25 |  |  | 2020-07-02 |  |  |  | 2020-07-05 |  |  | 2020-07-20 |  |  |  | 2020-08-01 |  | 2020-08-04
PH1000499 | 125.1132 | 8.7765 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Gingoog City | Lawit | MIN | PH104308019 | 623 | 45 | Three Legged Tubular Tower | CO64 | 50.9469 | MIN-1000148 | Level 6 | phase2_add | phase3 |  |  | Cluster M20 | Marrox | [7 empty] | 2020-03-01 |  | 2020-03-03 | [13 empty] | 2020-03-08 | [11 empty] | 2020-04-07 | [27 empty] | 2020-04-14 |  |  | 2020-05-14 |  | 2020-04-21 | [16 empty] | 2020-05-12 |  |  | 2020-05-21 | [6 empty] | 2020-06-04 |  |  |  | 2020-06-04 |  |  |  |  | 2020-04-28 |  | 2020-05-08 |  |  | 2020-05-12 |  | 2020-05-15 |  |  | 2020-05-29 |  |  |  | 2020-06-05 |  | 4GT-42-340C-2NPT |  |  | 2020-06-17 |  | 2020-05-26 | [6 empty] | 2020-06-25 | 2020-07-02 | [20 empty] | 2020-08-01 |  |  |  | 2020-08-04 | [8 empty] | 2020-06-10 |  | 2020-06-13 |  |  | 2020-06-25 |  |  |  | 2020-06-28 |  |  | 2020-07-05 |  |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  |  | 2020-08-04 |  | 2020-08-07
PH1000502 | 125.1359 | 8.789 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Gingoog City | Mimbalagon | MIN | PH104308071 | 521 | 45 | Three Legged Tubular Tower | CO64 | 48.11 | MIN-1000149 | Level 6 | phase2_add | phase3 |  |  | Cluster M20 | Marrox | [7 empty] | 2020-03-04 |  | 2020-03-06 | [13 empty] | 2020-03-11 | [11 empty] | 2020-04-10 | [27 empty] | 2020-04-17 |  |  | 2020-05-17 |  | 2020-04-24 | [16 empty] | 2020-05-15 |  |  | 2020-05-24 | [6 empty] | 2020-06-07 |  |  |  | 2020-06-07 |  |  |  |  | 2020-05-01 |  | 2020-05-11 |  |  | 2020-05-15 |  | 2020-05-18 |  |  | 2020-06-01 |  |  |  | 2020-06-08 |  | 4GT-42-340C-2NPT |  |  | 2020-06-20 |  | 2020-05-29 | [6 empty] | 2020-06-28 | 2020-07-05 | [20 empty] | 2020-08-04 |  |  |  | 2020-08-07 | [8 empty] | 2020-06-13 |  | 2020-06-16 |  |  | 2020-06-28 |  |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  |  | 2020-07-11 |  |  | 2020-07-26 |  |  |  | 2020-08-07 |  | 2020-08-10
PH1000507 | 125.0712 | 7.7127 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Quezon | San Isidro | MIN | PH101317032 | 7691 | 45 | Three Legged Tubular Tower | CO70 | 3.7447 | MIN-1000150 | Level 6 | phase2_add | phase1_630 | P1_630 |  | Cluster M06 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  |  |  |  | 2020-01-30 | 2020-01-15 | 2020-02-01 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2020-02-06 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-02-25 | 2020-03-07 | [5 empty] | A | Mila Teresa Cariaga | Purok 2, Kitao Kitao | Bukidnon | 125.0056 | 7.6387 | Greenfield | 342m |  | 15 years | P16,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-03-14 | 2020-01-27 |  | 2020-04-13 | 2020-03-13 | 2020-03-21 | 2020-02-27 |  | 2020-02-27 | [13 empty] | 2020-04-11 | ok |  | 2020-04-20 | [6 empty] | 2020-05-04 |  |  |  | 2020-05-04 |  |  |  | Awaiting MOC approval | 2020-03-28 | 2020-02-24 | 2020-04-07 |  |  | 2020-04-11 |  | 2020-04-14 |  |  | 2020-04-28 |  |  |  | 2020-05-05 |  | 4GT-42-340C-2NPT |  |  | 2020-05-17 |  | 2020-04-25 | [6 empty] | 2020-05-25 | 2020-06-01 | [20 empty] | 2020-07-01 |  |  |  | 2020-07-04 | [8 empty] | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-04 |  |  |  | 2020-06-07 |  |  | 2020-06-22 |  |  |  | 2020-07-04 |  | 2020-07-07
PH1000508 | 125.0794 | 7.7652 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Quezon | Butong | MIN | PH101317001 | 13258 | 45 | Three Legged Tubular Tower | CO70 | 3.7485 | MIN-1000151 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M06 | EPC | [7 empty] | 2020-02-28 |  | 2020-03-01 | [13 empty] | 2020-03-06 | [11 empty] | 2020-04-05 | [27 empty] | 2020-04-12 |  |  | 2020-05-12 |  | 2020-04-19 | [16 empty] | 2020-05-10 |  |  | 2020-05-19 | [6 empty] | 2020-06-02 |  |  |  | 2020-06-02 |  |  |  |  | 2020-04-26 |  | 2020-05-06 |  |  | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-27 |  |  |  | 2020-06-03 |  | 4GT-42-340C-2NPT |  |  | 2020-06-15 |  | 2020-05-24 | [6 empty] | 2020-06-23 | 2020-06-30 | [20 empty] | 2020-07-30 |  |  |  | 2020-08-02 | [8 empty] | 2020-06-08 |  | 2020-06-11 |  |  | 2020-06-23 |  |  |  | 2020-06-26 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-21 |  |  |  | 2020-08-02 |  | 2020-08-05
PH1000513 | 124.5893 | 8.3963 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | Lumbia | MIN | PH104305054 | 22429 | 45 | Three Legged Tubular Tower | CO70 | 92.2262 | MIN-1000152 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-03-18 | 2020-01-18 | 2020-03-20 | 2020-01-28 | 2020-02-01 | 2020-02-17 |  | 2020-01-28 |  |  | 2020-02-21 |  | 2020-02-21 |  |  |  | 2020-03-25 |  |  | 2020-02-21 |  | 2020-02-21 | 2020-01-28 |  | 2020-02-17 |  | 2020-01-28 | 2020-03-02 | 2020-04-24 | 2020-03-12 |  |  | 2020-03-12 |  | C | GERONIMO GARCIA | ZONE 2, LUMBIA, CAGAYAN DE ORO | Misamis Oriental | 124.5958 | 8.3985 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-01 | 2020-02-21 |  | 2020-05-31 |  | 2020-05-08 | [16 empty] | 2020-05-29 |  |  | 2020-06-07 | [6 empty] | 2020-06-21 |  |  |  | 2020-06-21 |  |  |  |  | 2020-05-15 | 2020-02-29 | 2020-05-25 | 2020-03-06 | 2020-03-06 | 2020-05-29 |  | 2020-06-01 |  |  | 2020-06-15 |  |  |  | 2020-06-22 |  | JGT-42-280C-2NPT |  |  | 2020-07-04 |  | 2020-06-12 | [6 empty] | 2020-07-12 | 2020-07-19 | [20 empty] | 2020-08-18 |  |  |  | 2020-08-21 | [8 empty] | 2020-06-27 |  | 2020-06-30 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-22 |  |  |  | 2020-07-25 |  |  | 2020-08-09 |  |  |  | 2020-08-21 |  | 2020-08-24
PH1000514 | 124.5587 | 8.4361 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | San Simon | MIN | PH104305065 | 1391 | 45 | Three Legged Tubular Tower | CO70 | 97.7851 | MIN-1000153 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-03-21 | 2020-01-27 | 2020-03-23 | 2020-01-28 | 2020-02-28 |  |  | 2020-01-28 | [8 empty] | 2020-03-28 | [5 empty] | 2020-01-28 |  |  |  | 2020-01-28 |  | 2020-04-27 | [27 empty] | 2020-05-04 |  |  | 2020-06-03 |  | 2020-05-11 | [16 empty] | 2020-06-01 |  |  | 2020-06-10 | [6 empty] | 2020-06-24 |  |  |  | 2020-06-24 |  |  |  |  | 2020-05-18 |  | 2020-05-28 |  |  | 2020-06-01 |  | 2020-06-04 |  |  | 2020-06-18 |  |  |  | 2020-06-25 |  | JGT-42-280C-2NPT |  |  | 2020-07-07 |  | 2020-06-15 | [6 empty] | 2020-07-15 | 2020-07-22 | [20 empty] | 2020-08-21 |  |  |  | 2020-08-24 | [8 empty] | 2020-06-30 |  | 2020-07-03 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-07-25 |  |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  |  | 2020-08-24 |  | 2020-08-27
PH1000516 | 124.7333 | 8.4333 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | Cagayan de Oro City | F. S. Catanico | MIN | PH104305048 | 2502 | 45 | Three Legged Tubular Tower | CO70 | 87.2356 | MIN-1000154 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-28 | 2020-02-25 | 2020-01-30 | 2020-02-26 |  |  |  | 2020-02-26 | 2020-02-27 |  |  |  | 2020-02-27 |  |  |  | 2020-02-04 | 2020-02-27 |  |  |  | 2020-02-27 | 2020-02-26 |  |  |  | 2020-02-26 | 2020-03-10 | 2020-03-05 | 2020-03-11 |  |  | 2020-03-10 | 2020-03-11 | A | TOP STONE CORPORATION/MARTHEL ESTROSAS | PUROK -9, LINANGOHAN, BALOY, TABLON, CAGAYAN DE ORO CITY | Misamis Oriental | 124.7157 | 8.4696 | Greenfield |  |  | 10 years | P22,500 inclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-12 | 2020-03-03 |  | 2020-04-11 |  | 2020-03-19 | [16 empty] | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 | 2020-03-12 | 2020-04-05 | 2020-03-12 | 2020-03-12 | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-26 | 2020-02-19 |  |  | 2020-05-03 |  | JGT-42-280C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1000524 | 124.3191 | 8.3126 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Bunawan | MIN | PH103504003 | 2218 | 45 | Three Legged Tubular Tower | CO70 | 106.9116 | MIN-1000155 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) |  |  |  |  | 2020-01-20 | 2020-03-06 | 2020-02-18 | 2020-03-08 | 2020-02-19 |  |  |  | 2020-02-19 | [8 empty] | 2020-03-13 | [5 empty] | 2020-02-19 |  |  |  | 2020-02-19 |  | 2020-04-12 | [27 empty] | 2020-04-19 |  |  | 2020-05-19 |  | 2020-04-26 | [16 empty] | 2020-05-17 |  |  | 2020-05-26 | [6 empty] | 2020-06-09 |  |  |  | 2020-06-09 |  |  |  |  | 2020-05-03 |  | 2020-05-13 |  |  | 2020-05-17 |  | 2020-05-20 |  |  | 2020-06-03 |  |  |  | 2020-06-10 |  | JGT-42-280C-2NPT |  |  | 2020-06-22 |  | 2020-05-31 | [6 empty] | 2020-06-30 | 2020-07-07 | [20 empty] | 2020-08-06 |  |  |  | 2020-08-09 | [8 empty] | 2020-06-15 |  | 2020-06-18 |  |  | 2020-06-30 |  |  |  | 2020-07-03 |  |  | 2020-07-10 |  |  |  | 2020-07-13 |  |  | 2020-07-28 |  |  |  | 2020-08-09 |  | 2020-08-12
PH1000527 | 124.2885 | 8.1924 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Lanao Del Norte | Iligan City | Tipanoy | MIN | PH103504018 | 7460 | 45 | Three Legged Tubular Tower | CO70 | 102.3922 | MIN-1000156 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M26 | Enovell | PO2019122502PH_WLS | Batch 2 (additional) |  |  |  |  | 2020-01-20 | 2020-03-09 | 2020-02-18 | 2020-03-11 | 2020-02-19 |  |  |  | 2020-02-19 | [8 empty] | 2020-03-16 | [5 empty] | 2020-02-19 |  |  |  | 2020-02-19 |  | 2020-04-15 | [27 empty] | 2020-04-22 |  |  | 2020-05-22 |  | 2020-04-29 | [16 empty] | 2020-05-20 |  |  | 2020-05-29 | [6 empty] | 2020-06-12 |  |  |  | 2020-06-12 |  |  |  |  | 2020-05-06 |  | 2020-05-16 |  |  | 2020-05-20 |  | 2020-05-23 |  |  | 2020-06-06 |  |  |  | 2020-06-13 |  | JGT-42-280C-2NPT |  |  | 2020-06-25 |  | 2020-06-03 | [6 empty] | 2020-07-03 | 2020-07-10 | [20 empty] | 2020-08-09 |  |  |  | 2020-08-12 | [8 empty] | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-13 |  |  |  | 2020-07-16 |  |  | 2020-07-31 |  |  |  | 2020-08-12 |  | 2020-08-15
PH1000533 | 125.0827 | 8.1293 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Malaybalay City | Barangay 11 | MIN | PH101312012 | 25696 | 45 | Three Legged Tubular Tower | CO70 | 43.7849 | MIN-1000157 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-04-10 | 2020-02-12 | 2020-04-12 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-15 |  |  |  | 2020-02-15 |  |  |  | 2020-04-17 | 2020-02-15 |  |  |  | 2020-02-15 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-25 | 2020-05-17 | [5 empty] | A | Oscar Lozarito | Purok 6, Casisang, Malaybalay City | Bukidnon | 125.1198 | 8.1353 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-24 | 2020-03-04 |  | 2020-06-23 |  | 2020-05-31 | [16 empty] | 2020-06-21 |  |  | 2020-06-30 | [6 empty] | 2020-07-14 |  |  |  | 2020-07-14 |  |  |  |  | 2020-06-07 |  | 2020-06-17 |  |  | 2020-06-21 |  | 2020-06-24 |  |  | 2020-07-08 |  |  |  | 2020-07-15 |  | 4GT-42-340C-2NPT |  |  | 2020-07-27 |  | 2020-07-05 | [6 empty] | 2020-08-04 | 2020-08-11 | [20 empty] | 2020-09-10 |  |  |  | 2020-09-13 | [8 empty] | 2020-07-20 |  | 2020-07-23 |  |  | 2020-08-04 |  |  |  | 2020-08-07 |  |  | 2020-08-14 |  |  |  | 2020-08-17 |  |  | 2020-09-01 |  |  |  | 2020-09-13 |  | 2020-09-16
PH1000545 | 124.9438 | 7.9709 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Valencia City | Lilingayon | MIN | PH101321021 | 3069 | 45 | Three Legged Tubular Tower | CO70 | 31.05 | MIN-1000158 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M10 | EPC | [7 empty] | 2020-04-13 |  | 2020-04-15 | [13 empty] | 2020-04-20 | [11 empty] | 2020-05-20 | [27 empty] | 2020-05-27 |  |  | 2020-06-26 |  | 2020-06-03 | [16 empty] | 2020-06-24 |  |  | 2020-07-03 | [6 empty] | 2020-07-17 |  |  |  | 2020-07-17 |  |  |  |  | 2020-06-10 |  | 2020-06-20 |  |  | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-11 |  |  |  | 2020-07-18 |  | 4GT-42-340C-2NPT |  |  | 2020-07-30 |  | 2020-07-08 | [6 empty] | 2020-08-07 | 2020-08-14 | [20 empty] | 2020-09-13 |  |  |  | 2020-09-16 | [8 empty] | 2020-07-23 |  | 2020-07-26 |  |  | 2020-08-07 |  |  |  | 2020-08-10 |  |  | 2020-08-17 |  |  |  | 2020-08-20 |  |  | 2020-09-04 |  |  |  | 2020-09-16 |  | 2020-09-19
PH1000565 | 124.5035 | 8.5167 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Misamis Oriental | El Salvador City | Bolisong | MIN | PH104307014 | 1763 | 45 | Three Legged Tubular Tower | CO70 | 108.599 | MIN-1000159 | Level 4 (220) | phase1_220_20% | phase2_1231 | PO Issued not 630 |  | Cluster M19 | Marrox | PO2020010202PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-03-24 | 2020-01-27 | 2020-03-26 | 2020-01-28 | 2020-02-28 |  |  | 2020-01-28 | [8 empty] | 2020-03-31 | [5 empty] | 2020-01-28 |  |  |  | 2020-01-28 |  | 2020-04-30 | [27 empty] | 2020-05-07 |  |  | 2020-06-06 |  | 2020-05-14 | [16 empty] | 2020-06-04 |  |  | 2020-06-13 | [6 empty] | 2020-06-27 |  |  |  | 2020-06-27 |  |  |  |  | 2020-05-21 |  | 2020-05-31 |  |  | 2020-06-04 |  | 2020-06-07 |  |  | 2020-06-21 |  |  |  | 2020-06-28 |  | JGT-42-280C-2NPT |  |  | 2020-07-10 |  | 2020-06-18 | [6 empty] | 2020-07-18 | 2020-07-25 | [20 empty] | 2020-08-24 |  |  |  | 2020-08-27 | [8 empty] | 2020-07-03 |  | 2020-07-06 |  |  | 2020-07-18 |  |  |  | 2020-07-21 |  |  | 2020-07-28 |  |  |  | 2020-07-31 |  |  | 2020-08-15 |  |  |  | 2020-08-27 |  | 2020-08-30
PH1000580 | 124.6108 | 8.3733 | Rural | Greenfield | Greenfield | Y1 | L7 | Northern Mindanao (Region X) | Bukidnon | Baungon | Nicdao | MIN | PH104305038 | 3289 | 45 | Three Legged Tubular Tower | CO70 | 88.7578 | MIN-1000160 | Level 6 | phase3 | phase3 |  |  | Cluster M19 | Marrox | [7 empty] | 2020-03-27 |  | 2020-03-29 | [13 empty] | 2020-04-03 | [11 empty] | 2020-05-03 | [27 empty] | 2020-05-10 |  |  | 2020-06-09 |  | 2020-05-17 | [16 empty] | 2020-06-07 |  |  | 2020-06-16 | [6 empty] | 2020-06-30 |  |  |  | 2020-06-30 |  |  |  |  | 2020-05-24 |  | 2020-06-03 |  |  | 2020-06-07 |  | 2020-06-10 |  |  | 2020-06-24 |  |  |  | 2020-07-01 |  | JGT-42-280C-2NPT |  |  | 2020-07-13 |  | 2020-06-21 | [6 empty] | 2020-07-21 | 2020-07-28 | [20 empty] | 2020-08-27 |  |  |  | 2020-08-30 | [8 empty] | 2020-07-06 |  | 2020-07-09 |  |  | 2020-07-21 |  |  |  | 2020-07-24 |  |  | 2020-07-31 |  |  |  | 2020-08-03 |  |  | 2020-08-18 |  |  |  | 2020-08-30 |  | 2020-09-02
PH1100001 | 125.5432 | 7.0634 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bago Gallera | MIN | PH112402116 | 59678 | 30 | Monopole Tower | CO66 | 9.5962 | MIN-1100001 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M12 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  | JXD |  | 2019-11-27 | 2019-12-17 | 2019-12-17 | 2019-12-19 | 2019-12-18 | 2020-01-22 |  |  | 2019-12-18 | 2019-12-19 |  |  |  | 2019-12-19 |  |  |  | 2019-12-24 | [5 empty] | 2019-12-18 | 2020-01-22 |  |  | 2019-12-18 |  | 2020-01-23 | [27 empty] | 2020-01-30 |  |  | 2020-02-29 |  | 2020-02-06 | [11 empty] | 0997-3480311 |  |  |  |  | 2020-02-27 |  |  | 2020-03-07 | [6 empty] | 2020-03-21 |  |  |  | 2020-03-21 |  |  |  |  | 2020-02-13 |  | 2020-02-23 |  |  | 2020-02-27 |  | 2020-03-01 |  |  | 2020-03-15 |  |  |  | 2020-03-22 |  | JGT-30-340C-2NPT |  |  | 2020-04-03 |  | 2020-03-12 | [6 empty] | 2020-04-11 | 2020-04-18 | [20 empty] | 2020-05-18 |  |  |  | 2020-05-21 | [8 empty] | 2020-03-27 |  | 2020-03-30 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-09 |  |  |  | 2020-05-21 |  | 2020-05-24
PH1100002 | 125.5432 | 7.0562 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402116 | 59678 | 15 | Pole | CO66 | 9.9542 | MIN-1100002 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | MJV |  | 2019-12-13 | 2019-12-19 | 2019-12-19 | 2019-12-21 | 2020-02-05 | 2019-12-21 |  |  | 2019-12-21 |  | 2019-12-21 |  |  | 2019-12-21 |  |  |  | 2019-12-26 |  | 2019-12-22 |  |  | 2019-12-22 | 2019-12-23 | 2020-02-05 |  |  | 2019-12-23 | 2020-03-05 | 2020-01-25 | 2020-03-06 |  |  | 2020-03-05 | 2020-03-06 | B | Tito C. Lucero | KM8, Upper Ulas, Talomo, Davao City | Davao del Sur | 125.5438 | 7.0553 | Rooftop | 2m | 8m | 10 years | P35,000 inclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-01 | 2020-01-19 |  | 2020-03-02 | 2020-01-29 | 2020-02-08 | [16 empty] | 2020-02-29 | ok |  | 2020-03-09 | [6 empty] | 2020-03-23 |  | 2020-03-10 |  | 2020-03-23 |  |  |  | RFP rejected, incorrect DITO information on BR | 2020-02-15 |  | 2020-02-25 |  |  | 2020-02-29 | 2020-02-21 | 2020-03-03 | 2020-02-21 |  | 2020-03-17 | 2020-02-22 |  |  | 2020-03-24 |  | ZCG-9-340D-1NPT |  |  | 2020-04-05 |  | 2020-03-14 | 2020-01-29 | [5 empty] | 2020-04-13 | 2020-04-20 | [20 empty] | 2020-05-20 |  |  |  | 2020-05-23 | [7 empty] | 2020-02-19 | 2020-03-29 |  | 2020-04-01 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-11 |  |  |  | 2020-05-23 |  | 2020-05-26
PH1100003 | 125.5495 | 7.067 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402030 | 32461 | 30 | Monopole Tower | CO66 | 8.8008 | MIN-1100003 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M12 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2019-12-12 | 2019-12-12 | 2019-12-14 | [13 empty] | 2019-12-19 | [11 empty] | 2020-01-18 | [27 empty] | 2020-01-25 |  |  | 2020-02-24 |  | 2020-02-01 | [16 empty] | 2020-02-22 |  |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  |  | 2020-02-08 |  | 2020-02-18 |  |  | 2020-02-22 |  | 2020-02-25 |  |  | 2020-03-10 |  |  |  | 2020-03-17 |  | ZCG-12-340D-1NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100004 | 125.5494 | 7.0598 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402116 | 59678 | 30 | Monopole Tower | CO66 | 9.1547 | MIN-1100004 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | MJV |  | 2019-12-13 | 2019-12-17 | 2019-12-17 | 2019-12-19 | 2019-12-27 |  |  |  | 2019-12-27 | 2019-12-27 |  |  |  | 2019-12-27 |  |  |  | 2019-12-24 | 2019-12-28 |  |  |  | 2019-12-28 | 2019-12-27 |  |  |  | 2019-12-27 | 2020-03-04 | 2020-01-23 | 2020-03-04 |  |  | 2020-03-05 | 2020-03-05 | A | Flavia Annic A. Ambrocio | Ortiga Village, Talomo Davao City | Davao del Sur | 125.5493 | 7.0613 | Greenfield |  |  | 15 years | P25,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-14 | n/a |  |  |  | n/a | 2020-01-30 | 2020-01-08 |  | 2020-02-29 | 2020-01-29 | 2020-02-06 |  |  | 2020-01-22 | [13 empty] | 2020-02-27 | ok |  | 2020-03-07 | [6 empty] | 2020-03-21 |  | 2020-03-08 | 2020-03-11 | 2020-03-21 | 2020-03-13 |  |  | Cheque released | 2020-02-13 | 2020-01-15 | 2020-02-23 | 2020-01-21 | 2020-01-21 | 2020-02-27 | 2020-02-20 | 2020-03-01 | 2020-02-20 | 2020-02-21 | 2020-03-15 | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-03-22 | 2020-02-20 | DGT-30-340C-2NPT |  |  | 2020-04-03 |  | 2020-03-12 | 2020-01-29 | [5 empty] | 2020-04-11 | 2020-04-18 | [20 empty] | 2020-05-18 |  |  |  | 2020-05-21 | [7 empty] | 2020-02-19 | 2020-03-27 |  | 2020-03-30 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-09 |  |  |  | 2020-05-21 |  | 2020-05-24
PH1100005 | 125.5488 | 7.0519 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402116 | 59678 | 30 | Monopole Tower | CO66 | 9.6623 | MIN-1100005 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | RW |  | JXD |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-10 |  |  |  | 2019-12-10 |  |  |  | 2019-12-13 | 2019-12-10 |  |  |  | 2019-12-10 | 2019-12-06 |  |  |  | 2019-12-06 | 2020-02-19 | 2020-01-12 | 2019-12-27 |  |  | 2020-01-24 | 2020-02-19 | A | Manuel Ang | Josephina Highway, Talomo, Davao City | Davao del Sur | 125.5487 | 7.052 | Greenfield | 9m |  | 15 years | P25,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-22 | n/a |  |  |  | n/a | 2020-01-19 | 2020-01-08 |  | 2020-02-18 | 2020-02-06 | 2020-01-26 | 2020-01-22 |  | 2020-01-22 | [8 empty] | 0915-5913067 | 81 Talomo Beach, Talomo Proper, Davao City |  |  |  | 2020-02-16 | ok |  | 2020-02-25 | [6 empty] | 2020-03-10 |  | 2020-02-21 | 2020-02-26 | 2020-03-10 | 2020-03-02 | 2020-03-04 | 2020-03-05 | Cheque released | 2020-02-02 | 2020-01-26 | 2020-02-12 | 2020-02-06 | 2020-02-06 | 2020-02-16 | 2020-01-31 | 2020-02-19 | 2020-02-01 | 2020-02-02 | 2020-03-04 | 2020-02-04 | 2020-02-04 | 2020-02-04 | 2020-03-11 | 2020-02-04 | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | 2020-01-29 | [5 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [7 empty] | 2020-02-21 | 2020-03-16 | 2020-03-05 | 2020-03-19 | 2020-03-06 |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100006 | 125.5558 | 7.0706 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Catalunan Grande | MIN | PH112402077 | 18081 | 30 | Monopole Tower | CO66 | 8.0063 | MIN-1100006 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-18 | 2019-12-18 | 2019-12-20 | [13 empty] | 2019-12-25 | [11 empty] | 2020-01-24 | [27 empty] | 2020-01-31 |  |  | 2020-03-01 |  | 2020-02-07 | [16 empty] | 2020-02-28 |  |  | 2020-03-08 | [6 empty] | 2020-03-22 |  |  |  | 2020-03-22 |  |  |  |  | 2020-02-14 |  | 2020-02-24 |  |  | 2020-02-28 |  | 2020-03-02 |  |  | 2020-03-16 |  |  |  | 2020-03-23 |  | JGT-30-340C-2NPT |  |  | 2020-04-04 |  | 2020-03-13 | [6 empty] | 2020-04-12 | 2020-04-19 | [20 empty] | 2020-05-19 |  |  |  | 2020-05-22 | [8 empty] | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-10 |  |  |  | 2020-05-22 |  | 2020-05-25
PH1100007 | 125.5557 | 7.0634 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402116 | 59678 | 30 | Three Legged Tubular Tower | CO66 | 8.3552 | MIN-1100007 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 | 2020-01-08 | 2020-01-20 |  | 2019-12-07 |  |  | 2020-01-20 |  | 2020-01-20 |  |  |  | 2019-12-13 |  |  | 2020-02-15 |  | 2020-02-15 | 2019-12-06 | 2020-01-24 | 2020-01-20 |  | 2019-12-06 |  | 2020-01-12 | [5 empty] | C |  |  |  | 125.5545 | 7.0637 | [16 empty] | 2020-01-19 | 2020-02-19 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 | ok |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 | 2020-03-11 | 2020-02-12 |  |  | 2020-02-16 | 2020-02-21 | 2020-02-19 | 2020-02-22 | 2020-02-24 | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100008 | 125.5557 | 7.0561 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402116 | 59678 | 30 | Three Legged Tubular Tower | CO66 | 8.7643 | MIN-1100008 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  | JXD |  | 2019-11-27 | 2019-12-09 | 2019-12-09 | 2019-12-11 | 2019-12-10 | 2019-12-11 | 2020-01-21 |  | 2019-12-10 | 2019-12-10 | 2019-12-11 |  |  | 2019-12-10 |  |  |  | 2019-12-16 | 2019-12-10 |  |  |  | 2019-12-10 | 2019-12-10 |  | 2020-01-21 |  | 2019-12-10 | 2020-02-19 | 2020-01-15 | [5 empty] | A | Susan Dimos | Purok 1, Santos Marketing, Bangkal, Davao City | Davao del Sur | 125.5556 | 7.0571 | Greenfield | 18m |  | 15 years | P30,000 exclusive of VAT and withholding tax | monthly | 360sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-22 |  |  | 2020-02-21 |  | 2020-01-29 | [16 empty] | 2020-02-19 |  |  | 2020-02-28 | [6 empty] | 2020-03-13 |  |  |  | 2020-03-13 |  |  |  |  | 2020-02-05 |  | 2020-02-15 |  |  | 2020-02-19 | 2020-02-25 | 2020-02-22 |  |  | 2020-03-07 |  |  |  | 2020-03-14 |  | DGT-30-340C-2NPT |  |  | 2020-03-26 |  | 2020-03-04 | [6 empty] | 2020-04-03 | 2020-04-10 | [20 empty] | 2020-05-10 |  |  |  | 2020-05-13 | [8 empty] | 2020-03-19 |  | 2020-03-22 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-05-01 |  |  |  | 2020-05-13 |  | 2020-05-16
PH1100010 | 125.562 | 7.067 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402077 | 18081 | 30 | Three Legged Tubular Tower | CO66 | 7.5558 | MIN-1100009 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M12 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2020-01-19 | 2020-01-15 | 2020-01-21 | 2020-03-03 |  |  |  | 2020-03-03 | [8 empty] | 2020-01-26 | 2020-03-04 |  |  |  | 2020-03-04 | 2020-01-30 |  |  |  | 2020-01-30 | 2020-03-10 | 2020-02-25 | 2020-03-11 |  |  | 2020-03-10 | 2020-03-11 | A | Hiram Enrico Magtoto | TALOMO, DAVAO CITY | Davao Del Sur | 125.5606 | 7.0686 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 200sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-03 |  |  | 2020-04-02 |  | 2020-03-10 | [16 empty] | 2020-03-31 |  |  | 2020-04-09 | [6 empty] | 2020-04-23 |  |  |  | 2020-04-23 |  |  |  |  | 2020-03-17 |  | 2020-03-27 |  |  | 2020-03-31 | 2020-03-10 | 2020-04-03 | 2020-03-12 | 2020-03-12 | 2020-04-17 |  |  |  | 2020-04-24 |  | JGT-30-340C-2NPT |  |  | 2020-05-06 |  | 2020-04-14 | [6 empty] | 2020-05-14 | 2020-05-21 | [20 empty] | 2020-06-20 |  |  |  | 2020-06-23 | [8 empty] | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-11 |  |  |  | 2020-06-23 |  | 2020-06-26
PH1100011 | 125.5619 | 7.0612 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402075 | 32436 | 30 | Monopole Tower | CO66 | 7.8842 | MIN-1100010 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 | DepEd_3298 | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-24 | 2019-12-24 | 2019-12-26 | 2019-12-25 |  |  |  | 2019-12-25 | 2020-01-17 |  |  |  | 2020-01-17 |  |  |  | 2019-12-31 | 2020-01-17 |  |  |  | 2020-01-17 | 2019-12-25 |  |  |  | 2019-12-25 | 2020-02-07 | 2020-01-30 | [6 empty] | Eric Armigos | 217 Springtime Ave., Bangkal, Davao City | Davao del Sur | 124.2436 | 8.2126 | Greenfield |  |  | 15 years | P30,000 inclusive of VAT and withholding tax | monthly | 100sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-06 |  |  | 2020-03-07 |  | 2020-02-13 | [16 empty] | 2020-03-05 |  |  | 2020-03-14 | [6 empty] | 2020-03-28 |  |  |  | 2020-03-28 |  |  |  |  | 2020-02-20 |  | 2020-03-01 |  |  | 2020-03-05 |  | 2020-03-08 |  |  | 2020-03-22 |  |  |  | 2020-03-29 |  | DGT-30-340C-2NPT |  |  | 2020-04-10 |  | 2020-03-19 | [6 empty] | 2020-04-18 | 2020-04-25 | [20 empty] | 2020-05-25 |  |  |  | 2020-05-28 | [8 empty] | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-18 |  |  |  | 2020-04-21 |  |  | 2020-04-28 |  |  |  | 2020-05-01 |  |  | 2020-05-16 |  |  |  | 2020-05-28 |  | 2020-05-31
PH1100012 | 125.5619 | 7.0525 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402116 | 59678 | 30 | Monopole Tower | CO66 | 8.4318 | MIN-1100011 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2020-01-28 | 2020-02-06 |  |  | 2020-01-28 | 2020-01-29 |  |  |  | 2020-01-29 |  |  |  | 2019-12-19 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-01-26 | 2020-02-06 |  |  | 2020-01-26 |  | 2020-01-18 | [5 empty] | A |  |  |  | 125.5608 | 7.0527 | [16 empty] | 2020-01-25 | 2020-02-28 |  | 2020-02-24 |  | 2020-02-01 | [11 empty] | 0917-8791114 |  |  |  |  | 2020-02-22 |  |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  |  | 2020-02-08 |  | 2020-02-18 |  |  | 2020-02-22 |  | 2020-02-25 |  |  | 2020-03-10 |  |  |  | 2020-03-17 |  | DGT-30-340C-2NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100013 | 125.5683 | 7.0705 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Pangi | MIN | PH112402077 | 18081 | 30 | Monopole Tower | CO66 | 6.7566 | MIN-1100012 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2020-02-07 | 2020-01-07 |  |  | 2020-01-07 | 2020-01-04 | 2020-02-08 |  |  | 2020-01-04 |  |  |  | 2019-12-13 | 2020-02-08 |  |  |  | 2020-02-08 | 2020-01-03 | 2020-01-07 | 2020-02-05 |  | 2020-01-03 |  | 2020-01-12 | [5 empty] | A |  |  |  | 125.567827° | 7.070824° | [16 empty] | 2020-01-19 | 2020-03-04 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100014 | 125.5683 | 7.0633 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402075 | 32436 | 30 | Monopole Tower | CO66 | 7.1666 | MIN-1100013 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-12 | 2020-04-10 | 2020-01-15 | 2020-04-12 | [13 empty] | 2020-04-17 | [5 empty] | 2020-01-28 |  |  |  | 2020-01-28 |  | 2020-05-17 | [27 empty] | 2020-05-24 |  |  | 2020-06-23 |  | 2020-05-31 | [16 empty] | 2020-06-21 |  |  | 2020-06-30 | [6 empty] | 2020-07-14 |  |  |  | 2020-07-14 |  |  |  |  | 2020-06-07 |  | 2020-06-17 |  |  | 2020-06-21 |  | 2020-06-24 |  |  | 2020-07-08 |  |  |  | 2020-07-15 |  | ZCG-12-340D-1NPT |  |  | 2020-07-27 |  | 2020-07-05 | [6 empty] | 2020-08-04 | 2020-08-11 | [20 empty] | 2020-09-10 |  |  |  | 2020-09-13 | [8 empty] | 2020-07-20 |  | 2020-07-23 |  |  | 2020-08-04 |  |  |  | 2020-08-07 |  |  | 2020-08-14 |  |  |  | 2020-08-17 |  |  | 2020-09-01 |  |  |  | 2020-09-13 |  | 2020-09-16
PH1100015 | 125.5682 | 7.0561 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402075 | 32436 | 30 | Monopole Tower | CO66 | 7.6395 | MIN-1100014 | Level 2 (Davao City) - U | phase3 | phase1_630 | P1_630 | DepEd_5011 | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2020-02-06 |  | 2020-01-28 |  | 2020-01-28 | 2020-01-29 |  |  |  | 2020-01-29 |  |  |  | 2019-12-19 | 2020-01-29 |  |  |  | 2020-01-29 |  |  | 2020-01-28 |  | 2020-01-28 | 2020-02-21 | 2020-01-18 | [5 empty] | A | Romeo Guerra | Matina, Aplaya, Davao City | Davao del Sur | 125.5671 | 7.0566 | Greenfield |  |  | 10 years | P25,000 exclusive of VAT and withholding tax | quarterly | 250sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-25 | 2020-02-28 |  | 2020-02-24 | 2020-03-06 | 2020-02-01 | [16 empty] | 2020-02-22 |  |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  | Awaiting MOC approval | 2020-02-08 | 2020-03-09 | 2020-02-18 | 2020-03-11 | 2020-03-11 | 2020-02-22 | 2020-02-28 | 2020-02-25 | 2020-02-29 | 2020-03-05 | 2020-03-10 |  |  |  | 2020-03-17 |  | DGT-30-340C-2NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100016 | 125.5682 | 7.0488 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Aplaya | MIN | PH112402074 | 33384 | 30 | Monopole Tower | CO66 | 8.1644 | MIN-1100015 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-06 | 2020-01-20 |  |  | 2019-12-06 |  | 2020-01-22 |  |  | 2020-01-22 |  |  |  | 2019-12-13 |  | 2020-01-22 |  |  | 2020-01-22 | 2019-12-06 | 2020-01-20 | 2020-12-19 |  | 2019-12-06 | 2020-02-19 | 2020-01-12 | 2020-03-13 |  |  | 2020-03-13 | 2020-03-13 | B | Cristina Babo Bustamante | Pagasa, Balete Drive, Matina Aplaya, Davao City | Davao del Sur | 125.5698 | 7.0514 | Greenfield | 17m |  | 15 years | P34,000 inclusive of VAT and withholding tax | monthly | 270sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-02-28 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 | 2020-03-11 | 2020-02-12 |  |  | 2020-02-16 | 2020-02-21 | 2020-02-19 | 2020-02-22 | 2020-03-08 | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100018 | 125.5746 | 7.0669 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Pangi | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 6.3683 | MIN-1100016 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | [8 empty] | 2019-12-13 | [11 empty] | 2020-01-12 | [27 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | ZCG-12-340D-1NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100019 | 125.5745 | 7.0597 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402075 | 32436 | 30 | Monopole Tower | CO66 | 6.8491 | MIN-1100017 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 | DepEd_3313 | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-12 | 2019-12-26 | 2019-12-26 | 2019-12-28 | 2019-12-27 |  |  |  | 2019-12-27 | 2019-12-28 |  |  |  | 2019-12-28 |  |  |  | 2020-01-02 | [5 empty] | 2019-12-27 |  |  |  | 2019-12-27 |  | 2020-02-01 | [27 empty] | 2020-02-08 |  |  | 2020-03-09 |  | 2020-02-15 | [16 empty] | 2020-03-07 |  |  | 2020-03-16 | [6 empty] | 2020-03-30 |  |  |  | 2020-03-30 |  |  |  |  | 2020-02-22 |  | 2020-03-03 |  |  | 2020-03-07 |  | 2020-03-10 |  |  | 2020-03-24 |  |  |  | 2020-03-31 |  | ZCG-12-340D-1NPT |  |  | 2020-04-12 |  | 2020-03-21 | [6 empty] | 2020-04-20 | 2020-04-27 | [20 empty] | 2020-05-27 |  |  |  | 2020-05-30 | [8 empty] | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-18 |  |  |  | 2020-05-30 |  | 2020-06-02
PH1100020 | 125.5745 | 7.0524 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 7.3864 | MIN-1100018 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 | DepEd_3258 | Cluster M12 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-12 | 2019-12-10 | 2019-12-10 | 2019-12-12 | 2019-12-11 | 2019-12-27 |  |  | 2019-12-11 | 2019-12-12 | 2019-12-28 |  |  | 2019-12-12 |  |  |  | 2019-12-17 | 2020-03-09 |  |  |  | 2020-03-09 | 2019-12-11 | 2019-12-27 |  |  | 2019-12-11 |  | 2020-01-16 | [5 empty] | A |  |  |  | 125.5744 | 7.0526 | [16 empty] | 2020-01-23 |  |  | 2020-02-22 |  | 2020-01-30 | [16 empty] | 2020-02-20 |  |  | 2020-02-29 | [6 empty] | 2020-03-14 |  |  |  | 2020-03-14 |  |  |  |  | 2020-02-06 |  | 2020-02-16 |  |  | 2020-02-20 | 2020-03-13 | 2020-02-23 |  |  | 2020-03-08 |  |  |  | 2020-03-15 |  | ZCG-12-340D-1NPT |  |  | 2020-03-27 |  | 2020-03-05 | [6 empty] | 2020-04-04 | 2020-04-11 | [20 empty] | 2020-05-11 |  |  |  | 2020-05-14 | [8 empty] | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-05-02 |  |  |  | 2020-05-14 |  | 2020-05-17
PH1100022 | 125.5748 | 7.0303 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Aplaya | MIN | PH112402074 | 33384 | 45 | Three Legged Tubular Tower | CO66 | 9.2446 | MIN-1100019 | Level 2 (Davao City) - U | phase3 | phase3 | P1_630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | MJV |  | 2019-12-13 | 2019-12-29 | 2019-12-29 | 2019-12-31 | 2019-12-30 |  |  |  | 2019-12-30 | 2020-01-03 |  |  |  | 2020-01-03 |  |  |  | 2020-01-05 | 2020-01-03 |  |  |  | 2020-01-03 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-02-19 | 2020-02-04 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Nida Lamoste | Matina Shanghai, Dumalag, Matina Aplaya, Davao City | Davao del Sur | 125.5746 | 7.0402 | Rooftop |  | 9m | 15 years | P35,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-11 | 2020-02-10 |  | 2020-03-12 | 2020-02-20 | 2020-02-18 | [11 empty] | 0906-6493988 |  |  |  |  | 2020-03-10 | ok |  | 2020-03-19 | [6 empty] | 2020-04-02 |  |  |  | 2020-04-02 |  |  |  | For RFP submission in DingTalk | 2020-02-25 |  | 2020-03-06 |  |  | 2020-03-10 | 2020-02-28 | 2020-03-13 | 2020-03-02 | 2020-03-06 | 2020-03-27 |  |  |  | 2020-04-03 |  | ZCG-12-280C-1NPT |  |  | 2020-04-15 |  | 2020-03-24 | 2020-01-29 | [5 empty] | 2020-04-23 | 2020-04-30 | [20 empty] | 2020-05-30 |  |  |  | 2020-06-02 | [7 empty] | 2020-02-22 | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-21 |  |  |  | 2020-06-02 |  | 2020-06-05
PH1100025 | 125.5808 | 7.056 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 6.6137 | MIN-1100020 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 | JXD |  | Enovell |  | 2019-12-13 | 2019-12-11 | 2019-12-11 | 2019-12-13 | [13 empty] | 2019-12-18 | [11 empty] | 2020-01-17 | [27 empty] | 2020-01-24 |  |  | 2020-02-23 |  | 2020-01-31 | [16 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  |  | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 |  | 2020-02-24 |  |  | 2020-03-09 |  |  |  | 2020-03-16 |  | ZCG-12-340D-1NPT |  |  | 2020-03-28 |  | 2020-03-06 | [6 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [8 empty] | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100028 | 125.5851 | 7.0752 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Ma-A | MIN | PH112402061 | 59803 | 30 | Monopole Tower | CO66 | 4.8931 | MIN-1100021 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope | DepEd_3288 | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  | Gaskie |  | 2019-11-27 | 2019-12-29 | 2020-01-02 | 2019-12-31 | 2020-01-03 |  |  |  | 2020-01-03 | 2020-01-04 |  |  |  | 2020-01-04 |  |  |  | 2020-01-05 | 2020-01-04 |  |  |  | 2020-01-04 | 2020-01-03 |  |  |  | 2020-01-03 | 2020-02-06 | 2020-02-04 | [5 empty] | A | Roy Tiongco Bahala | Purok 14, Ma-a, Davao City | Davao del Sur | 125.5866 | 7.0744 | Rooftop | 22m | 9m | 15 years | P57,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-11 | 2020-01-14 |  | 2020-03-12 |  | 2020-02-18 | 2020-01-22 |  | 2020-01-22 | [9 empty] | Purok 14, Bugac, Ma-a, Davao City |  |  |  | 2020-03-10 | ok |  | 2020-03-19 | [6 empty] | 2020-04-02 |  |  |  | 2020-04-02 |  |  |  |  | 2020-02-25 | 2020-03-09 | 2020-03-06 | 2020-03-12 | 2020-03-12 | 2020-03-10 | 2020-02-06 | 2020-03-13 | 2020-02-06 | 2020-02-07 | 2020-03-27 | 2020-02-10 |  |  | 2020-04-03 |  | ZCG-12-340D-1NPT |  |  | 2020-04-15 |  | 2020-03-24 | [6 empty] | 2020-04-23 | 2020-04-30 | [20 empty] | 2020-05-30 |  |  |  | 2020-06-02 | [8 empty] | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-21 |  |  |  | 2020-06-02 |  | 2020-06-05
PH1100029 | 125.5871 | 7.0668 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Ma-A | MIN | PH112402061 | 59803 | 30 | Monopole Tower | CO66 | 5.2769 | MIN-1100022 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2019-12-25 | 2019-12-25 | 2019-12-27 | 2019-12-26 |  |  |  | 2019-12-26 | 2019-12-27 |  |  |  | 2019-12-27 |  |  |  | 2020-01-01 | 2020-03-09 |  |  |  | 2020-03-09 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-03-13 | 2020-01-31 | 2020-03-13 |  |  | 2020-03-12 | 2020-03-13 | B | AIDA P. JANEA | NACILIA VILLAGE, MAA, DAVAO CITY | Davao Del Sur | 125.5838 | 7.0671 | Greenfield |  |  | 10 YEARS | P20,750 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-07 |  |  | 2020-03-08 |  | 2020-02-14 | [16 empty] | 2020-03-06 |  |  | 2020-03-15 | [6 empty] | 2020-03-29 |  |  |  | 2020-03-29 |  |  |  |  | 2020-02-21 |  | 2020-03-02 |  |  | 2020-03-06 |  | 2020-03-09 |  |  | 2020-03-23 |  |  |  | 2020-03-30 |  | ZCG-12-340D-1NPT |  |  | 2020-04-11 |  | 2020-03-20 | [6 empty] | 2020-04-19 | 2020-04-26 | [20 empty] | 2020-05-26 |  |  |  | 2020-05-29 | [8 empty] | 2020-04-04 |  | 2020-04-07 |  |  | 2020-04-19 |  |  |  | 2020-04-22 |  |  | 2020-04-29 |  |  |  | 2020-05-02 |  |  | 2020-05-17 |  |  |  | 2020-05-29 |  | 2020-06-01
PH1100031 | 125.587 | 7.0524 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Aplaya | MIN | PH112402020 | 83964 | 15 | Pole | CO66 | 6.4691 | MIN-1100023 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope | Philcom_281 | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-12-12 | 2019-12-13 | 2019-12-13 | 2019-12-15 | [13 empty] | 2019-12-20 | [5 empty] | 2020-01-24 |  |  |  | 2020-01-24 |  | 2020-01-19 | [27 empty] | 2020-01-26 |  |  | 2020-02-25 |  | 2020-02-02 | [16 empty] | 2020-02-23 |  |  | 2020-03-03 | [6 empty] | 2020-03-17 |  |  |  | 2020-03-17 |  |  |  |  | 2020-02-09 |  | 2020-02-19 |  |  | 2020-02-23 |  | 2020-02-26 |  |  | 2020-03-11 |  |  |  | 2020-03-18 |  | ZGJ(G)-12-340C-2NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [8 empty] | 2020-03-23 |  | 2020-03-26 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100033 | 125.5939 | 7.0772 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | n.a. ( 39395) | MIN | PH112402141 | 11075 | 30 | Monopole Tower | CO66 | 3.963 | MIN-1100024 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2019-12-11 | 2019-12-11 | 2019-12-13 | 2019-12-17 | 2019-12-26 |  |  | 2019-12-17 | 2019-12-19 | 2019-12-27 |  |  | 2019-12-19 |  |  |  | 2019-12-18 | [5 empty] | 2019-12-17 | 2020-01-23 | 2020-01-28 |  | 2019-12-17 |  | 2020-01-17 | [27 empty] | 2020-01-24 |  |  | 2020-02-23 |  | 2020-01-31 | [16 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  |  | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 |  | 2020-02-24 |  |  | 2020-03-09 |  |  |  | 2020-03-16 |  | JGT-30-340C-2NPT |  |  | 2020-03-28 |  | 2020-03-06 | [6 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [8 empty] | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100035 | 125.5933 | 7.0632 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402061 | 59803 | 30 | Monopole Tower | CO66 | 5.0933 | MIN-1100025 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2019-12-11 | 2019-12-11 | 2019-12-13 | 2020-01-17 | 2020-01-17 |  |  | 2020-01-17 | 2020-01-18 | 2020-01-18 |  |  | 2020-01-18 |  |  |  | 2019-12-18 | [5 empty] | 2020-01-17 | 2020-01-17 |  |  | 2020-01-17 |  | 2020-01-17 | [27 empty] | 2020-01-24 |  |  | 2020-02-23 |  | 2020-01-31 | [16 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  |  | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 |  | 2020-02-24 |  |  | 2020-03-09 |  |  |  | 2020-03-16 |  | JGT-30-340C-2NPT |  |  | 2020-03-28 |  | 2020-03-06 | [6 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [8 empty] | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100036 | 125.5933 | 7.0559 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 5.7397 | MIN-1100026 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | Gaskie |  | 2019-12-13 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-13 | 2019-12-12 |  |  |  | 2019-12-12 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-02-19 | 2020-01-12 | [5 empty] | A | Rodel Dela Cruz | Juana Subd., Ecoland Drive, Matina, Davao City | Davao del Sur | 125.5936 | 7.056 | Greenfield |  |  | 15 years | P20,000 exclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [11 empty] | 0905-5571316 |  |  |  |  | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100037 | 125.5933 | 7.0487 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bucana | MIN | PH112402020 | 83964 | 30 | Three Legged Tubular Tower | CO66 | 6.4217 | MIN-1100027 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2020-04-13 | 2020-03-09 | 2020-04-15 | 2020-03-11 |  |  |  | 2020-03-11 | [8 empty] | 2020-04-20 | [5 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  | 2020-05-20 | [27 empty] | 2020-05-27 |  |  | 2020-06-26 |  | 2020-06-03 | [16 empty] | 2020-06-24 |  |  | 2020-07-03 | [6 empty] | 2020-07-17 |  |  |  | 2020-07-17 |  |  |  |  | 2020-06-10 |  | 2020-06-20 |  |  | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-11 |  |  |  | 2020-07-18 |  | ZCG-12-340D-1NPT |  |  | 2020-07-30 |  | 2020-07-08 | [6 empty] | 2020-08-07 | 2020-08-14 | [20 empty] | 2020-09-13 |  |  |  | 2020-09-16 | [8 empty] | 2020-07-23 |  | 2020-07-26 |  |  | 2020-08-07 |  |  |  | 2020-08-10 |  |  | 2020-08-17 |  |  |  | 2020-08-20 |  |  | 2020-09-04 |  |  |  | 2020-09-16 |  | 2020-09-19
PH1100038 | 125.5999 | 7.1101 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Tigatto | MIN | PH112402125 | 36387 | 30 | Three Legged Tubular Tower | CO66 | 2.8224 | MIN-1100028 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-18 | 2019-12-18 | 2019-12-20 | [13 empty] | 2019-12-25 | [11 empty] | 2020-01-24 | [27 empty] | 2020-01-31 |  |  | 2020-03-01 |  | 2020-02-07 | [16 empty] | 2020-02-28 |  |  | 2020-03-08 | [6 empty] | 2020-03-22 |  |  |  | 2020-03-22 |  |  |  |  | 2020-02-14 |  | 2020-02-24 |  |  | 2020-02-28 |  | 2020-03-02 |  |  | 2020-03-16 |  |  |  | 2020-03-23 |  | ZCG-12-340D-1NPT |  |  | 2020-04-04 |  | 2020-03-13 | [6 empty] | 2020-04-12 | 2020-04-19 | [20 empty] | 2020-05-19 |  |  |  | 2020-05-22 | [8 empty] | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-10 |  |  |  | 2020-05-22 |  | 2020-05-25
PH1100039 | 125.5989 | 7.1036 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402152 | 31766 | 15 | Pole | CO66 | 2.6822 | MIN-1100029 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | MJV |  | 2019-12-12 | 2019-12-11 | 2019-12-11 | 2019-12-13 | 2019-12-16 | 2020-01-19 |  |  | 2019-12-16 | 2019-12-17 |  |  |  | 2019-12-17 |  |  |  | 2019-12-18 | 2020-01-20 |  |  |  | 2020-01-20 | 2019-12-16 | 2019-12-30 | 2020-01-19 |  | 2019-12-16 | 2020-02-25 | 2020-01-17 | [5 empty] | B | Anwar Mangacop | 1 Blueberry St., Alonzo Terrazas Subd., Buhangin, Davao City | Davao del Sur | 125.5983 | 7.1031 | Greenfield | 13m |  | 15 years | P25,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-24 | 2020-02-12 |  | 2020-02-23 |  | 2020-01-31 | [16 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  |  | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 | 2020-02-20 | 2020-02-24 | 2020-02-22 | 2020-02-25 | 2020-03-09 | 2020-02-22 |  |  | 2020-03-16 |  | DGT-30-340C-2NPT |  |  | 2020-03-28 |  | 2020-03-06 | [6 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [8 empty] | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100040 | 125.6 | 7.0954 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Magtuod | MIN | PH112402152 | 31766 | 30 | Three Legged Tubular Tower | CO66 | 2.5246 | MIN-1100030 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | Richworld |  | 2019-12-12 | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2019-12-23 |  | 2020-01-27 | 2020-02-13 | 2019-12-23 | 2019-12-23 | 2019-12-21 |  |  | 2019-12-21 |  |  |  | 2019-12-25 | 2019-12-23 | 2019-12-22 |  |  | 2019-12-22 | 2019-12-19 |  | 2020-01-27 | 2020-02-13 | 2019-12-19 |  | 2020-01-24 |  | y | Above Lease Cap, Need to Renego or Change candidates |  |  | B |  |  |  | 125.5994 | 7.0937 | Greenfield | 22m | [14 empty] | 2020-01-31 | 2020-02-12 |  | 2020-03-01 |  | 2020-02-07 | [11 empty] | 0917-5784562 |  |  |  |  | 2020-02-28 |  |  | 2020-03-08 | [6 empty] | 2020-03-22 |  |  |  | 2020-03-22 |  |  |  |  | 2020-02-14 |  | 2020-02-24 |  |  | 2020-02-28 |  | 2020-03-02 |  |  | 2020-03-16 |  |  |  | 2020-03-23 |  | DGT-30-340C-2NPT |  |  | 2020-04-04 |  | 2020-03-13 | [6 empty] | 2020-04-12 | 2020-04-19 | [20 empty] | 2020-05-19 |  |  |  | 2020-05-22 | [8 empty] | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-10 |  |  |  | 2020-05-22 |  | 2020-05-25
PH1100042 | 125.5997 | 7.0812 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | n.a. ( 39395) | MIN | PH112402142 | 5698 | 30 | Three Legged Tubular Tower | CO66 | 3.1823 | MIN-1100031 | Level 2 (Davao City) - U | phase3 | phase1_630 | P1_630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | Teltrends |  | 2019-12-12 | 2019-12-17 | 2019-12-17 | 2019-12-19 | 2020-01-13 | 2020-01-19 |  |  | 2020-01-13 | 2020-01-15 |  |  |  | 2020-01-15 |  |  |  | 2019-12-24 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-23 | 2020-01-13 |  |  | 2020-01-13 | 2020-02-06 | 2020-01-23 | [5 empty] | A | Pepito Veloso | Domsat Road, San Rafael Village, Brgy. 9-B, Davao City | Davao del Sur | 125.5978 | 7.0827 | Greenfield | 21m |  | 15 years | P40,000 inclusive of VAT and withholding tax | monthly | 200sqm | 3 months | 1 month | 4.5% increase on the 4th year | [6 empty] | 2020-01-30 |  |  | 2020-02-29 |  | 2020-02-06 | [16 empty] | 2020-02-27 |  |  | 2020-03-07 | [6 empty] | 2020-03-21 |  |  |  | 2020-03-21 |  |  |  |  | 2020-02-13 |  | 2020-02-23 |  |  | 2020-02-27 |  | 2020-03-01 |  |  | 2020-03-15 |  |  |  | 2020-03-22 |  | DGT-30-340C-2NPT |  |  | 2020-04-03 |  | 2020-03-12 | [6 empty] | 2020-04-11 | 2020-04-18 | [20 empty] | 2020-05-18 |  |  |  | 2020-05-21 | [8 empty] | 2020-03-27 |  | 2020-03-30 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-09 |  |  |  | 2020-05-21 |  | 2020-05-24
PH1100043 | 125.5997 | 7.074 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Gov. Paciano Bangoy | MIN | PH112402141 | 11075 | 30 | Monopole Tower | CO66 | 3.7281 | MIN-1100032 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 | DICT_22 | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-17 | 2019-12-17 | 2019-12-19 | 2019-12-18 |  |  |  | 2019-12-18 | [8 empty] | 2019-12-24 | [5 empty] | 2019-12-18 |  |  |  | 2019-12-18 |  | 2020-01-23 | [27 empty] | 2020-01-30 |  |  | 2020-02-29 |  | 2020-02-06 | [16 empty] | 2020-02-27 |  |  | 2020-03-07 | [6 empty] | 2020-03-21 |  |  |  | 2020-03-21 |  |  |  |  | 2020-02-13 |  | 2020-02-23 |  |  | 2020-02-27 |  | 2020-03-01 |  |  | 2020-03-15 |  |  |  | 2020-03-22 |  | ZCG-12-340D-1NPT |  |  | 2020-04-03 |  | 2020-03-12 | [6 empty] | 2020-04-11 | 2020-04-18 | [20 empty] | 2020-05-18 |  |  |  | 2020-05-21 | [8 empty] | 2020-03-27 |  | 2020-03-30 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-09 |  |  |  | 2020-05-21 |  | 2020-05-24
PH1100044 | 125.6015 | 7.066 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Barangay 5-A | MIN | PH112402138 | 11436 | 3 | Wall Mounted Pole | CO66 | 4.3045 | MIN-1100033 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-07 | 2020-02-28 |  |  | 2020-01-07 | 2020-01-07 |  |  |  | 2020-01-07 |  |  |  | 2020-01-12 | 2020-01-07 |  |  |  | 2020-01-07 | 2020-01-07 | 2020-02-28 |  |  | 2020-01-07 | 2020-02-06 | 2020-02-11 | [5 empty] | A | Oroderm Beauty Hotel | Oroderm Beauty Hotel A. Pichon St. Magallanes St. Davao City | Davao del Sur | 125.6033 | 7.0677 | Rooftop | 33m | 19m | 15 years | P39,772 inclusive of VAT and withholding tax | monthly | 25sqm | 1 month | 1 month | 4.5% increase on the 4th year | [6 empty] | 2020-02-18 |  |  | 2020-03-19 |  | 2020-02-25 | [16 empty] | 2020-03-17 |  |  | 2020-03-26 | [6 empty] | 2020-04-09 |  |  |  | 2020-04-09 |  |  |  |  | 2020-03-03 |  | 2020-03-13 |  |  | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-03 |  |  |  | 2020-04-10 |  | ZCG-9-340D-1NPT |  |  | 2020-04-22 |  | 2020-03-31 | [6 empty] | 2020-04-30 | 2020-05-07 | [20 empty] | 2020-06-06 |  |  |  | 2020-06-09 | [8 empty] | 2020-04-15 |  | 2020-04-18 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-10 |  |  |  | 2020-05-13 |  |  | 2020-05-28 |  |  |  | 2020-06-09 |  | 2020-06-12
PH1100045 | 125.5996 | 7.0595 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402020 | 83964 | 30 | Monopole Tower | CO66 | 5.0317 | MIN-1100034 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | [8 empty] | 2019-12-13 | [5 empty] | 2019-12-07 |  |  |  | 2019-12-07 |  | 2020-01-12 | [27 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100046 | 125.5995 | 7.0523 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bucana | MIN | PH112402020 | 83964 | 6 | Pole with counterweight | CO66 | 5.7417 | MIN-1100035 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-12 | 2019-12-12 | 2019-12-14 |  | 2020-01-09 | 2019-12-12 |  | 2019-12-12 |  | 2020-01-10 |  |  | 2020-01-10 |  |  |  | 2019-12-19 |  | 2020-01-10 |  |  | 2020-01-10 |  | 2020-01-09 | 2020-01-17 |  | 2020-01-09 | 2020-02-06 | 2020-01-18 | [5 empty] | B | Maria Esther Ecoland | 187 Sparrow St. Ecoland Phase 2, Davao City | Davao del Sur | 125.5997 | 7.0519 | Greenfield | 22m |  | 15 years | P46,000 inclusive of VAT and withholding tax | monthly | 100sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-25 |  |  | 2020-02-24 |  | 2020-02-01 | [16 empty] | 2020-02-22 |  |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  |  | 2020-02-08 |  | 2020-02-18 |  |  | 2020-02-22 |  | 2020-02-25 |  |  | 2020-03-10 |  |  |  | 2020-03-17 |  | DGT-30-340C-2NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100047 | 125.6061 | 7.1137 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Tigatto | MIN | PH112402021 | 65461 | 3 | Wall Mounted Pole | CO66 | 2.4785 | MIN-1100036 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope | DepEd_5005 | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-08 | 2019-12-12 |  |  | 2019-12-08 | 2019-12-09 | 2019-12-12 |  |  | 2019-12-09 |  |  |  | 2019-12-14 | 2019-12-09 |  |  |  | 2019-12-09 | 2020-01-27 | 2019-12-12 |  |  | 2019-12-12 |  | 2020-01-13 | [5 empty] | A |  |  |  | 125.6053 | 7.1146 | Greenfield | 50m | [14 empty] | 2020-01-20 | 2020-02-28 |  | 2020-02-19 |  | 2020-01-27 | [16 empty] | 2020-02-17 |  |  | 2020-02-26 | [6 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  |  | 2020-02-03 | 2020-01-15 | 2020-02-13 | 2020-01-21 | 2020-01-21 | 2020-02-17 | 2020-02-21 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-03-05 | 2020-02-21 | 2020-02-21 | 2020-02-21 | 2020-03-12 | 2020-02-22 | JGT-30-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 | [20 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [8 empty] | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1100048 | 125.6061 | 7.1065 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 2.0245 | MIN-1100037 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  |  |  | 2019-12-12 | 2020-01-20 | 2020-01-08 | 2020-01-22 | [13 empty] | 2020-01-27 | [11 empty] | 2020-02-26 | [27 empty] | 2020-03-04 |  |  | 2020-04-03 |  | 2020-03-11 | [16 empty] | 2020-04-01 |  |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  |  | 2020-03-18 |  | 2020-03-28 |  |  | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-18 |  |  |  | 2020-04-25 |  | JGT-30-340C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1100049 | 125.6061 | 7.0992 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 1.8294 | MIN-1100038 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-30 | 2019-12-30 | 2020-01-01 | 2019-12-31 | 2020-02-12 | 2020-02-07 |  | 2019-12-31 | 2020-01-01 | 2020-02-21 |  |  | 2020-01-01 |  |  |  | 2020-01-06 |  | 2020-02-21 |  |  | 2020-02-21 | 2019-12-31 | 2020-02-12 | 2020-02-07 |  | 2019-12-31 | 2020-02-26 | 2020-02-05 | 2020-03-13 |  |  | 2020-03-13 |  | C | Christie B. Alquiza | Zambales St., Rolling Hills Subd., Brgy. 19-B, Bacaca, Davao City | Davao del Sur | 125.6045 | 7.1 | Greenfield |  |  | 10 years | P22,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-12 | 2020-02-28 |  | 2020-03-13 |  | 2020-02-19 | [16 empty] | 2020-03-11 |  |  | 2020-03-20 | [6 empty] | 2020-04-03 |  |  |  | 2020-04-03 |  |  |  |  | 2020-02-26 |  | 2020-03-07 |  |  | 2020-03-11 | 2020-03-11 | 2020-03-14 |  |  | 2020-03-28 |  |  |  | 2020-04-04 |  | DGT-30-340C-2NPT |  |  | 2020-04-16 |  | 2020-03-25 | [6 empty] | 2020-04-24 | 2020-05-01 | [20 empty] | 2020-05-31 |  |  |  | 2020-06-03 | [8 empty] | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-04 |  |  |  | 2020-05-07 |  |  | 2020-05-22 |  |  |  | 2020-06-03 |  | 2020-06-06
PH1100050 | 125.606 | 7.092 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | n.a. ( 39395) | MIN | PH112402152 | 31766 | 30 | Monopole Tower | CO66 | 1.9715 | MIN-1100039 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-13 | 2019-12-13 | 2019-12-15 | 2019-12-13 |  |  |  | 2019-12-13 | 2019-12-18 |  |  |  | 2019-12-18 |  |  |  | 2019-12-20 | 2019-12-18 |  |  |  | 2019-12-18 | 2019-12-13 |  |  |  | 2019-12-13 | 2020-01-24 | 2020-01-19 | 2020-01-10 |  |  | 2020-01-10 | 2020-02-04 | A | Napoleon Castillo | Garoia Height, Gov. Caned Road, Brgy. 19-B, Davao City | Davao del Sur | 125.6066 | 7.0919 | Greenfield | 35m |  | 15 years | P25,000 exclusive of VAT and withholding tax | monthly | 100sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-26 | 2020-02-19 |  | 2020-02-25 |  | 2020-02-02 | [16 empty] | 2020-02-23 |  |  | 2020-03-03 | [6 empty] | 2020-03-17 |  |  |  | 2020-03-17 |  |  |  |  | 2020-02-09 | 2020-03-11 | 2020-02-19 |  |  | 2020-02-23 | 2020-02-28 | 2020-02-26 | 2020-02-29 | 2020-03-06 | 2020-03-11 |  |  |  | 2020-03-18 |  | DGT-30-340C-2NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [8 empty] | 2020-03-23 |  | 2020-03-26 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100052 | 125.6062 | 7.0776 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Gov. Paciano Bangoy | MIN | PH112402143 | 6764 | 30 | Monopole Tower | CO66 | 2.9575 | MIN-1100040 | Level 2 (Davao City) - U | phase3 | phase1_630 | old 630 Scope | DepEd_5012 | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  |  |  | 2019-12-12 | 2020-01-21 | 2020-01-09 | 2020-01-23 | 2020-01-03 | 2020-01-10 |  |  | 2020-01-03 | 2020-01-04 | 2020-01-25 |  |  | 2020-01-04 |  |  |  | 2020-01-28 |  | 2020-01-25 |  |  | 2020-01-25 | 2020-01-03 | 2020-01-22 |  |  | 2020-01-03 |  | 2020-02-27 | [5 empty] | B |  |  |  | 125.6049 | 7.0767 | Rooftop | 25m | 9m | [13 empty] | 2020-03-05 | 2020-03-04 |  | 2020-04-04 |  | 2020-03-12 | [16 empty] | 2020-04-02 |  |  | 2020-04-11 | [6 empty] | 2020-04-25 |  |  |  | 2020-04-25 |  |  |  |  | 2020-03-19 |  | 2020-03-29 |  |  | 2020-04-02 | 2020-03-02 | 2020-04-05 |  |  | 2020-04-19 |  |  |  | 2020-04-26 |  | ZGJ(G)-12-340C-2NPT |  |  | 2020-05-08 |  | 2020-04-16 | [6 empty] | 2020-05-16 | 2020-05-23 | [20 empty] | 2020-06-22 |  |  |  | 2020-06-25 | [8 empty] | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-16 |  |  |  | 2020-05-19 |  |  | 2020-05-26 |  |  |  | 2020-05-29 |  |  | 2020-06-13 |  |  |  | 2020-06-25 |  | 2020-06-28
PH1100053 | 125.6059 | 7.0703 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Barangay 11-B | MIN | PH112402136 | 370 | 3 | Wall Mounted Pole | CO66 | 3.6418 | MIN-1100041 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2020-01-23 | 2020-01-08 | 2020-01-25 | [13 empty] | 2020-01-30 | [11 empty] | 2020-02-29 | [27 empty] | 2020-03-07 |  |  | 2020-04-06 |  | 2020-03-14 | [16 empty] | 2020-04-04 |  |  | 2020-04-13 | [6 empty] | 2020-04-27 |  |  |  | 2020-04-27 |  |  |  |  | 2020-03-21 |  | 2020-03-31 |  |  | 2020-04-04 |  | 2020-04-07 |  |  | 2020-04-21 |  |  |  | 2020-04-28 |  | ZCG-9-340D-1NPT |  |  | 2020-05-10 |  | 2020-04-18 | [6 empty] | 2020-05-18 | 2020-05-25 | [20 empty] | 2020-06-24 |  |  |  | 2020-06-27 | [8 empty] | 2020-05-03 |  | 2020-05-06 |  |  | 2020-05-18 |  |  |  | 2020-05-21 |  |  | 2020-05-28 |  |  |  | 2020-05-31 |  |  | 2020-06-15 |  |  |  | 2020-06-27 |  | 2020-06-30
PH1100054 | 125.6049 | 7.0629 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402020 | 83964 | 30 | Monopole Tower | CO66 | 4.4269 | MIN-1100042 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD |  | Teltrends |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 | 2019-12-07 |  |  | 2019-12-07 | 2019-12-08 | 2019-12-08 |  |  | 2019-12-08 |  |  |  | 2019-12-13 | 2019-12-09 |  |  |  | 2019-12-09 | 2020-01-10 | 2019-12-07 |  |  | 2019-12-07 | 2020-01-24 | 2020-01-12 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Lou Sapak | Blk 4, Phase 1,76-A, Bucana Rivera, New Matina, Davao City | Davao del Sur | 125.6052 | 7.0622 | Rooftop |  |  | 15 years | P30,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-22 | n/a |  |  |  | n/a | 2020-01-19 | 2020-01-09 |  | 2020-02-18 | 2020-03-06 | 2020-01-26 | 2020-01-22 | [11 empty] | Blk 6 Lot 6, 87 Patnubay SIR, New Matina, Davao City |  |  |  | 2020-02-16 | ok |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  | For MOC/NRAF resubmission (different option approved) | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 | 2020-02-21 | 2020-02-19 | 2020-02-21 |  | 2020-03-04 |  |  |  | 2020-03-11 |  | ZGJ(G)-12-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100055 | 125.6058 | 7.0559 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bucana | MIN | PH112402020 | 83964 | 30 | Monopole Tower | CO66 | 5.0965 | MIN-1100043 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2020-01-26 | 2020-01-26 | 2020-01-28 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-01-28 |  |  |  | 2020-01-28 |  |  |  | 2020-02-02 | 2020-01-28 |  |  |  | 2020-01-28 | 2020-01-25 |  |  |  | 2020-01-25 |  | 2020-03-03 | [5 empty] | A |  |  |  | 125.6063 | 7.0574 | Greenfield | 20m | [14 empty] | 2020-03-10 | 2020-02-13 |  | 2020-04-09 |  | 2020-03-17 | [16 empty] | 2020-04-07 |  |  | 2020-04-16 | [6 empty] | 2020-04-30 |  |  |  | 2020-04-30 |  |  |  |  | 2020-03-24 |  | 2020-04-03 |  |  | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-24 |  |  |  | 2020-05-01 |  | DGT-30-340C-2NPT |  |  | 2020-05-13 |  | 2020-04-21 | [6 empty] | 2020-05-21 | 2020-05-28 | [20 empty] | 2020-06-27 |  |  |  | 2020-06-30 | [8 empty] | 2020-05-06 |  | 2020-05-09 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-18 |  |  |  | 2020-06-30 |  | 2020-07-03
PH1100058 | 125.6124 | 7.1028 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 1.2291 | MIN-1100044 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2020-01-20 | 2020-01-23 | 2020-01-22 | [13 empty] | 2020-01-27 | [5 empty] | 2020-01-24 |  |  |  | 2020-01-24 |  | 2020-02-26 | [27 empty] | 2020-03-04 |  |  | 2020-04-03 |  | 2020-03-11 | [16 empty] | 2020-04-01 |  |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  |  | 2020-03-18 |  | 2020-03-28 |  |  | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-18 |  |  |  | 2020-04-25 |  | JGT-30-340C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1100059 | 125.6123 | 7.0956 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402152 | 31766 | 3 | Wall Mounted Pole | CO66 | 1.1853 | MIN-1100045 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-08 | 2020-01-27 |  |  | 2019-12-08 | 2019-12-09 | 2020-01-28 |  |  | 2019-12-09 |  |  |  | 2019-12-14 |  | 2020-01-28 |  |  | 2020-01-28 | 2019-12-08 | 2020-01-22 |  |  | 2019-12-08 | 2020-03-05 | 2020-01-13 | 2020-03-06 |  |  | 2020-03-05 | 2020-03-06 | A | Ma. Cristina Fuentes | 1 Ilang-Ilang St., NCCC Village, Bajada, Davao City | Davao del Sur | 125.6129 | 7.0968 | Rooftop | 36m | 9m | 10 years | P25,000 exclusive of VAT and withholding tax | quarterly | 250sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-20 | 2020-02-10 |  | 2020-02-19 | 2020-02-21 | 2020-01-27 | [16 empty] | 2020-02-17 | ok |  | 2020-02-26 | [6 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  | For RFP submission in DingTalk | 2020-02-03 |  | 2020-02-13 |  |  | 2020-02-17 |  | 2020-02-20 |  |  | 2020-03-05 |  |  |  | 2020-03-12 |  | ZGJ(G)-12-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 | [20 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [8 empty] | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1100060 | 125.6123 | 7.0884 | Urban | Rooftop | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402153 | 4581 | 3 | Wall Mounted Pole | CO66 | 1.6098 | MIN-1100046 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 | DepEd_3306 | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-12 | 2020-03-29 | 2020-01-16 | 2020-03-31 | [13 empty] | 2020-04-05 | [11 empty] | 2020-05-05 | [27 empty] | 2020-05-12 |  |  | 2020-06-11 |  | 2020-05-19 | [16 empty] | 2020-06-09 |  |  | 2020-06-18 | [6 empty] | 2020-07-02 |  |  |  | 2020-07-02 |  |  |  |  | 2020-05-26 |  | 2020-06-05 |  |  | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-26 |  |  |  | 2020-07-03 |  | ZCG-12-340D-1NPT |  |  | 2020-07-15 |  | 2020-06-23 | [6 empty] | 2020-07-23 | 2020-07-30 | [20 empty] | 2020-08-29 |  |  |  | 2020-09-01 | [8 empty] | 2020-07-08 |  | 2020-07-11 |  |  | 2020-07-23 |  |  |  | 2020-07-26 |  |  | 2020-08-02 |  |  |  | 2020-08-05 |  |  | 2020-08-20 |  |  |  | 2020-09-01 |  | 2020-09-04
PH1100061 | 125.6122 | 7.0811 | Urban | Greenfield | Greenfield | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Wilfredo Aquino | MIN | PH112402145 | 840 | 30 | Three Legged Tubular Tower | CO66 | 2.2518 | MIN-1100047 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope | DepEd_3325 | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2020-01-25 | 2020-01-08 | 2020-01-27 | [13 empty] | 2020-02-01 | [11 empty] | 2020-03-02 | [27 empty] | 2020-03-09 | 2020-01-27 |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 |  | 2020-04-02 |  |  | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-23 |  |  |  | 2020-04-30 |  | JGT-30-340C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1100062 | 125.6122 | 7.0739 | Urban | Rooftop | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Barangay 20-B | MIN | PH112402165 | 1985 | 3 | Wall Mounted Pole | CO66 | 2.9735 | MIN-1100048 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD |  | Gaskie |  | 2019-11-27 | 2020-01-08 | 2020-01-07 | 2020-01-10 | 2020-01-08 | 2020-01-17 |  |  | 2020-01-08 | 2020-01-08 |  |  |  | 2020-01-08 |  |  |  | 2020-01-15 | 2020-01-08 |  |  |  | 2020-01-08 | 2020-01-08 | 2020-01-17 |  |  | 2020-01-08 | 2020-02-19 | 2020-02-14 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Jenny Gimenes | Ramon Magsaysay St., Brgy. 20-B, Davao City | Davao del Sur | 125.6134 | 7.0733 | Rooftop | 19m | 9m | 15 years | P35,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-21 | 2020-01-16 |  | 2020-03-22 | 2020-02-18 | 2020-02-28 | [16 empty] | 2020-03-20 | ok |  | 2020-03-29 | [6 empty] | 2020-04-12 |  | 2020-02-25 |  | 2020-04-12 |  |  |  | RFP rejected, incorrect DITO information on BR | 2020-03-06 |  | 2020-03-16 |  |  | 2020-03-20 | 2020-02-05 | 2020-03-23 | 2020-02-05 |  | 2020-04-06 |  |  |  | 2020-04-13 |  | ZCG-12-340D-1NPT |  |  | 2020-04-25 |  | 2020-04-03 | [6 empty] | 2020-05-03 | 2020-05-10 | [20 empty] | 2020-06-09 |  |  |  | 2020-06-12 | [8 empty] | 2020-04-18 |  | 2020-04-21 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-31 |  |  |  | 2020-06-12 |  | 2020-06-15
PH1100063 | 125.6122 | 7.0667 | Urban | Rooftop | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Barangay 15-B | MIN | PH112402168 | 578 | 12 | Pole | CO66 | 3.729 | MIN-1100049 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD |  | Enovell |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2020-01-08 | 2020-01-09 | 2019-12-07 |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-13 |  | 2020-01-10 | 2019-12-08 |  | 2019-12-08 | 2020-01-08 | 2020-01-09 |  |  | 2020-01-08 | 2020-02-07 | 2020-01-12 | [5 empty] | B | Jecelyn M. Rosit | Brgy. 15-B, ArciagaSt. Davao City | Davao del Sur | 125.6114 | 7.0668 | Rooftop | 13m | 9m | 15 years | P35,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-02-21 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 | 2020-02-07 | 2020-02-19 | 2020-02-07 |  | 2020-03-04 |  |  |  | 2020-03-11 |  | ZGJ(G)-12-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100064 | 125.61 | 7.0607 | Urban | Rooftop | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Barangay 2-A | MIN | PH112402173 | 2437 | 3 | Wall Mounted Pole | CO66 | 4.5409 | MIN-1100050 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-13 | [11 empty] | 2020-01-12 | [27 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | ZCG-12-340D-1NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100065 | 125.6187 | 7.1136 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Monopole Tower | CO66 | 1.7316 | MIN-1100051 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope | DepEd_3414 | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-26 | 2019-12-26 | 2019-12-28 | 2019-12-27 | 2020-01-10 | 2020-01-24 |  | 2019-12-27 | 2019-12-28 |  |  |  | 2019-12-28 |  |  |  | 2020-01-02 |  |  | 2020-01-24 |  | 2020-01-24 | 2019-12-27 | 2020-01-10 | 2020-01-24 |  | 2019-12-27 | 2020-02-07 | 2020-02-01 | [5 empty] | C | Mary S. Bagolor | Blk. 1 Old San Isidro Buhangin, Davao City | Davao del Sur | 125.615 | 7.1156 | Rooftop | 37m | 6m | 15 years | P35,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-08 | 2020-02-19 |  | 2020-03-09 |  | 2020-02-15 | [16 empty] | 2020-03-07 |  |  | 2020-03-16 | [6 empty] | 2020-03-30 |  |  |  | 2020-03-30 |  |  |  |  | 2020-02-22 |  | 2020-03-03 |  |  | 2020-03-07 | 2020-02-28 | 2020-03-10 | 2020-03-03 | 2020-03-06 | 2020-03-24 |  |  |  | 2020-03-31 |  | ZCG-12-340D-1NPT |  |  | 2020-04-12 |  | 2020-03-21 | [6 empty] | 2020-04-20 | 2020-04-27 | [20 empty] | 2020-05-27 |  |  |  | 2020-05-30 | [8 empty] | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-18 |  |  |  | 2020-05-30 |  | 2020-06-02
PH1100066 | 125.6186 | 7.1064 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 0.97688 | MIN-1100052 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | RW |  | MJV |  | 2019-11-27 | 2019-12-26 | 2019-12-26 | 2019-12-28 | 2019-12-27 |  |  |  | 2019-12-27 | 2019-12-27 |  |  |  | 2019-12-27 |  |  |  | 2020-01-02 | 2019-12-28 |  |  |  | 2019-12-28 | 2019-12-27 |  |  |  | 2019-12-27 | 2020-02-13 | 2020-02-01 | 2020-03-11 |  |  | 2020-03-09 | 2020-03-11 | A | Eric M. Prado | Blk. 25 Lot 12 Sto. Nino St. Dumanlas, Davao City | Davao del Sur | 125.6187 | 7.1057 | Rooftop | 25m | 9m | 15 years | P35,000 exclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-08 | 2020-01-25 |  | 2020-03-09 | 2020-02-03 | 2020-02-15 | 2020-01-22 | 2020-01-22 | 2020-01-22 |  |  | 2020-03-13 | [6 empty] | Blk 25 Lot 10, Sto. Nino St., Dumanlas, Buhangin, Davao City |  | Y |  | 2020-03-07 | ok | 2020-03-13 | 2020-03-16 | 2020-03-12 | [5 empty] | 2020-03-30 |  | 2020-03-13 |  | 2020-03-30 |  |  |  | RFP submitted, ongoing review | 2020-02-22 |  | 2020-03-03 |  |  | 2020-03-07 | 2020-01-13 | 2020-03-10 | 2020-02-07 | 2020-02-08 | 2020-03-24 | 2020-01-21 | 2020-01-27 |  | 2020-03-31 |  | ZCG-12-340D-1NPT |  |  | 2020-04-12 |  | 2020-03-21 | [6 empty] | 2020-04-20 | 2020-04-27 | [20 empty] | 2020-05-27 |  |  |  | 2020-05-30 | [7 empty] | 2020-02-26 | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-18 |  |  |  | 2020-05-30 |  | 2020-06-02
PH1100067 | 125.6186 | 7.0992 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 0.44989 | MIN-1100053 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-04-01 | 2020-01-07 | 2020-04-03 | 2020-01-08 | 2020-02-28 |  |  | 2020-01-08 | 2020-02-25 |  |  |  | 2020-02-25 |  |  |  | 2020-04-08 | 2020-02-25 |  |  |  | 2020-02-25 | 2020-01-08 | 2020-02-28 |  |  | 2020-01-08 |  | 2020-05-08 | [9 empty] | 125.62 | 7.0985 | [16 empty] | 2020-05-15 |  |  | 2020-06-14 |  | 2020-05-22 | [16 empty] | 2020-06-12 |  |  | 2020-06-21 | [6 empty] | 2020-07-05 |  |  |  | 2020-07-05 |  |  |  |  | 2020-05-29 |  | 2020-06-08 |  |  | 2020-06-12 |  | 2020-06-15 |  |  | 2020-06-29 |  |  |  | 2020-07-06 |  | ZCG-12-340D-1NPT |  |  | 2020-07-18 |  | 2020-06-26 | [6 empty] | 2020-07-26 | 2020-08-02 | [20 empty] | 2020-09-01 |  |  |  | 2020-09-04 | [8 empty] | 2020-07-11 |  | 2020-07-14 |  |  | 2020-07-26 |  |  |  | 2020-07-29 |  |  | 2020-08-05 |  |  |  | 2020-08-08 |  |  | 2020-08-23 |  |  |  | 2020-09-04 |  | 2020-09-07
PH1100068 | 125.6186 | 7.0919 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | San Antonio | MIN | PH112402181 | 8816 | 30 | Three Legged Tubular Tower | CO66 | 0.86187 | MIN-1100054 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-01-08 | 2020-01-07 | 2020-01-10 | 2020-01-08 |  |  |  | 2020-01-08 | 2020-01-08 |  |  |  | 2020-01-08 |  |  |  | 2020-01-15 | 2020-01-08 |  |  |  | 2020-01-08 | 2020-01-08 |  |  |  | 2020-01-08 |  | 2020-02-14 |  | y | Above Lease Cap, Need to Renego or Change candidates |  |  | A |  |  |  | 125.6185 | 7.0919 | Rooftop | 23m | 13m | [13 empty] | 2020-02-21 | 2020-03-04 |  | 2020-03-22 |  | 2020-02-28 | [16 empty] | 2020-03-20 |  |  | 2020-03-29 | [6 empty] | 2020-04-12 |  |  |  | 2020-04-12 |  |  |  |  | 2020-03-06 |  | 2020-03-16 |  |  | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-06 |  |  |  | 2020-04-13 |  | ZCG-12-340D-1NPT |  |  | 2020-04-25 |  | 2020-04-03 | [6 empty] | 2020-05-03 | 2020-05-10 | [20 empty] | 2020-06-09 |  |  |  | 2020-06-12 | [8 empty] | 2020-04-18 |  | 2020-04-21 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-31 |  |  |  | 2020-06-12 |  | 2020-06-15
PH1100069 | 125.6184 | 7.0848 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | San Antonio | MIN | PH112402149 | 840 | 30 | Monopole Tower | CO66 | 1.6028 | MIN-1100055 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-09 | 2019-12-09 | 2019-12-11 | 2019-12-09 |  | 2020-02-28 |  | 2019-12-09 | 2019-12-10 |  | 2020-03-03 |  | 2019-12-10 |  |  |  | 2019-12-16 |  |  | 2020-03-03 |  | 2020-03-03 | 2019-12-10 |  | 2020-02-28 |  | 2019-12-10 | 2020-03-12 | 2020-01-15 | 2020-03-12 |  |  | 2020-03-12 |  | C | REYNANTE PICARDO | 89-A VINZON ST., PONCIANO BANGOY, DAVAO CITY | Davao Del Sur | 125.6194 | 7.085 | Rooftop |  |  | 10 years | P30,000 Inclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-22 | 2020-02-28 |  | 2020-02-21 | 2020-03-11 | 2020-01-29 | [16 empty] | 2020-02-19 |  |  | 2020-02-28 | [6 empty] | 2020-03-13 |  |  |  | 2020-03-13 |  |  |  | Awaiting MOC approval | 2020-02-05 |  | 2020-02-15 |  |  | 2020-02-19 |  | 2020-02-22 |  |  | 2020-03-07 |  |  |  | 2020-03-14 |  | ZCG-12-340D-1NPT |  |  | 2020-03-26 |  | 2020-03-04 | [6 empty] | 2020-04-03 | 2020-04-10 | [20 empty] | 2020-05-10 |  |  |  | 2020-05-13 | [8 empty] | 2020-03-19 |  | 2020-03-22 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-05-01 |  |  |  | 2020-05-13 |  | 2020-05-16
PH1100070 | 125.6185 | 7.0775 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Gov. Vicente Duterte | MIN | PH112402147 | 1175 | 15 | Pole | CO66 | 2.3877 | MIN-1100056 | Level 2 (Davao City) - U | phase3 | phase1_630 | old 630 Scope |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  |  |  | 2019-12-12 | 2020-01-27 | 2020-01-02 | 2020-01-29 | 2020-01-03 | 2020-02-17 |  |  | 2020-01-03 |  | 2020-02-17 |  |  | 2020-02-17 |  |  |  | 2020-02-03 |  | 2020-02-17 |  |  | 2020-02-17 | 2020-01-03 | 2020-02-17 |  |  | 2020-01-03 | 2020-02-25 | 2020-03-04 | [6 empty] | Carl Olano | Sobrecarey, Sta. Ana Ave., Davao City | Davao del Sur | 125.6192 | 7.077 | Rooftop |  |  | 15 years | P34,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-11 | 2020-03-04 |  | 2020-04-10 |  | 2020-03-18 | [16 empty] | 2020-04-08 |  |  | 2020-04-17 | [6 empty] | 2020-05-01 |  |  |  | 2020-05-01 |  |  |  |  | 2020-03-25 |  | 2020-04-04 |  |  | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-25 |  |  |  | 2020-05-02 |  | ZCG-12-340D-1NPT |  |  | 2020-05-14 |  | 2020-04-22 | [6 empty] | 2020-05-22 | 2020-05-29 | [20 empty] | 2020-06-28 |  |  |  | 2020-07-01 | [8 empty] | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-22 |  |  |  | 2020-05-25 |  |  | 2020-06-01 |  |  |  | 2020-06-04 |  |  | 2020-06-19 |  |  |  | 2020-07-01 |  | 2020-07-04
PH1100071 | 125.6192 | 7.0691 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Kap. Tomas Monteverde, Sr. | MIN | PH112402158 | 1967 | 30 | Monopole Tower | CO66 | 3.3022 | MIN-1100057 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M05 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2020-01-29 | 2020-01-08 | 2020-01-31 | 2020-01-09 |  |  |  | 2020-01-09 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2020-02-05 | [5 empty] | 2020-01-09 |  |  |  | 2020-01-09 |  | 2020-03-06 | [27 empty] | 2020-03-13 |  |  | 2020-04-12 |  | 2020-03-20 | [16 empty] | 2020-04-10 |  |  | 2020-04-19 | [6 empty] | 2020-05-03 |  |  |  | 2020-05-03 |  |  |  |  | 2020-03-27 |  | 2020-04-06 |  |  | 2020-04-10 |  | 2020-04-13 |  |  | 2020-04-27 |  |  |  | 2020-05-04 |  | JGT-30-340C-2NPT |  |  | 2020-05-16 |  | 2020-04-24 | [6 empty] | 2020-05-24 | 2020-05-31 | [20 empty] | 2020-06-30 |  |  |  | 2020-07-03 | [8 empty] | 2020-05-09 |  | 2020-05-12 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-03 |  |  |  | 2020-06-06 |  |  | 2020-06-21 |  |  |  | 2020-07-03 |  | 2020-07-06
PH1100072 | 125.6215 | 7.1296 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Communal | MIN | PH112402023 | 43758 | 30 | Monopole Tower | CO66 | 3.4557 | MIN-1100058 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 | DepEd_5007 | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-27 | 2019-12-27 | 2019-12-29 | 2019-12-29 |  |  |  | 2019-12-29 | 2020-02-25 |  |  |  | 2020-02-25 |  |  |  | 2020-01-03 | 2020-02-25 |  |  |  | 2020-02-25 | 2019-12-29 |  |  |  | 2019-12-29 | 2020-03-13 | 2020-02-02 | 2020-03-13 |  |  | 2020-03-13 |  |  | ROY GARRIDO | BLK-6 LOT 11, COUNTRY HOMES, CABANTIAN, DAVAO CITY | Davao Del Sur | 125.62 | 7.1285 | Rooftop |  |  | 15 YEARS | P35,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-09 | 2020-02-28 |  | 2020-03-10 | 2020-03-05 | 2020-02-16 | [16 empty] | 2020-03-08 |  |  | 2020-03-17 | [6 empty] | 2020-03-31 |  |  |  | 2020-03-31 |  |  |  | Awaiting MOC approval | 2020-02-23 |  | 2020-03-04 |  |  | 2020-03-08 | 2020-03-11 | 2020-03-11 |  |  | 2020-03-25 |  |  |  | 2020-04-01 |  | ZCG-12-340D-1NPT |  |  | 2020-04-13 |  | 2020-03-22 | [6 empty] | 2020-04-21 | 2020-04-28 | [20 empty] | 2020-05-28 |  |  |  | 2020-05-31 | [8 empty] | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-01 |  |  |  | 2020-05-04 |  |  | 2020-05-19 |  |  |  | 2020-05-31 |  | 2020-06-03
PH1100074 | 125.6249 | 7.11 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 1.2952 | MIN-1100059 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | MJV |  | 2019-12-13 | 2019-12-11 | 2019-12-11 | 2019-12-13 | 2019-12-31 |  |  |  | 2019-12-31 | 2020-01-05 |  |  |  | 2020-01-05 |  |  |  | 2019-12-18 | 2020-01-03 |  |  |  | 2020-01-03 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-03-10 | 2020-01-17 | 2020-03-13 |  |  | 2020-03-10 | 2020-03-13 | A | Neil Jubelag | Talisay St., Hillside Subd., Brgy. Buhangin Proper, Davao City | Davao del Sur | 125.6249 | 7.1099 | Rooftop | 23m | 9m | 10 years | P35,000 inclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-24 | 2020-01-25 |  | 2020-02-23 | 2020-02-03 | 2020-01-31 | [16 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  | Awaiting Lessor ID | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 | 2020-02-10 | 2020-02-24 | 2020-02-10 | 2020-02-11 | 2020-03-09 |  |  |  | 2020-03-16 |  | ZCG-12-340D-1NPT |  |  | 2020-03-28 |  | 2020-03-06 | 2020-01-29 | [5 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [7 empty] | 2020-02-22 | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100076 | 125.6248 | 7.0955 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Rafael Castillo | MIN | PH112402196 | 9903 | 30 | Three Legged Tubular Tower | CO66 | 0.4169 | MIN-1100060 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-04-04 | 2020-01-08 | 2020-04-06 | [13 empty] | 2020-04-11 | [11 empty] | 2020-05-11 | [27 empty] | 2020-05-18 |  |  | 2020-06-17 |  | 2020-05-25 | [16 empty] | 2020-06-15 |  |  | 2020-06-24 | [6 empty] | 2020-07-08 |  |  |  | 2020-07-08 |  |  |  |  | 2020-06-01 |  | 2020-06-11 |  |  | 2020-06-15 |  | 2020-06-18 |  |  | 2020-07-02 |  |  |  | 2020-07-09 |  | ZCG-12-340D-1NPT |  |  | 2020-07-21 |  | 2020-06-29 | [6 empty] | 2020-07-29 | 2020-08-05 | [20 empty] | 2020-09-04 |  |  |  | 2020-09-07 | [8 empty] | 2020-07-14 |  | 2020-07-17 |  |  | 2020-07-29 |  |  |  | 2020-08-01 |  |  | 2020-08-08 |  |  |  | 2020-08-11 |  |  | 2020-08-26 |  |  |  | 2020-09-07 |  | 2020-09-10
PH1100077 | 125.6248 | 7.0883 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Centro (San Juan) | MIN | PH112402196 | 9903 | 30 | Monopole Tower | CO66 | 1.1664 | MIN-1100061 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-26 | 2019-12-26 | 2019-12-28 | 2019-12-27 |  |  |  | 2019-12-27 | 2019-12-27 |  |  |  | 2019-12-27 |  |  |  | 2020-01-02 | 2019-12-28 |  |  |  | 2019-12-28 | 2019-12-27 |  |  |  | 2019-12-27 |  | 2020-02-01 |  | y | Above Lease Cap, Need to Renego or Change candidates |  |  | A |  |  |  | 125.6257 | 7.0879 | Rooftop | 27m | 12m | [13 empty] | 2020-02-08 | 2020-01-07 |  | 2020-03-09 |  | 2020-02-15 | [16 empty] | 2020-03-07 |  |  | 2020-03-16 | [6 empty] | 2020-03-30 |  |  |  | 2020-03-30 |  |  |  |  | 2020-02-22 |  | 2020-03-03 |  |  | 2020-03-07 | 2020-02-19 | 2020-03-10 |  |  | 2020-03-24 | 2020-02-21 |  |  | 2020-03-31 |  | ZCG-12-340D-1NPT |  |  | 2020-04-12 |  | 2020-03-21 | [6 empty] | 2020-04-20 | 2020-04-27 | [20 empty] | 2020-05-27 |  |  |  | 2020-05-30 | [8 empty] | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-18 |  |  |  | 2020-05-30 |  | 2020-06-02
PH1100079 | 125.6251 | 7.074 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Leon Garcia, Sr. | MIN | PH112402160 | 2152 | 30 | Monopole Tower | CO66 | 2.7491 | MIN-1100062 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-01-16 | 2020-01-08 | 2020-01-18 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-23 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-02-26 | 2020-02-22 | [5 empty] | A | Romulo Busuego | Medical Mission Group Hospital, Brgy. 27-C, Davao City | Davao del Sur | 125.6252 | 7.0764 | Rooftop | 21m | 7m | 15 years | P35,000 inclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-29 |  |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 |  | 2020-03-24 |  |  | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-14 |  |  |  | 2020-04-21 |  | ZCG-12-340D-1NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1100080 | 125.6277 | 7.1332 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Communal | MIN | PH112402035 | 16740 | 30 | Three Legged Tubular Tower | CO66 | 3.8923 | MIN-1100063 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2019-12-18 |  |  |  | 2019-12-18 | 2019-12-19 |  |  |  | 2019-12-19 |  |  |  | 2019-12-25 | 2019-12-19 |  |  |  | 2019-12-19 | 2019-12-18 |  |  |  | 2019-12-18 |  | 2020-01-24 |  | y | Advance Rental not approved | [6 empty] | 125.6282 | 7.134 | [16 empty] | 2020-01-31 |  |  | 2020-03-01 |  | 2020-02-07 | [16 empty] | 2020-02-28 |  |  | 2020-03-08 | [6 empty] | 2020-03-22 |  |  |  | 2020-03-22 |  |  |  |  | 2020-02-14 |  | 2020-02-24 |  |  | 2020-02-28 |  | 2020-03-02 |  |  | 2020-03-16 |  |  |  | 2020-03-23 |  | DGT-30-340C-2NPT |  |  | 2020-04-04 |  | 2020-03-13 | [6 empty] | 2020-04-12 | 2020-04-19 | [20 empty] | 2020-05-19 |  |  |  | 2020-05-22 | [8 empty] | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-10 |  |  |  | 2020-05-22 |  | 2020-05-25
PH1100082 | 125.6277 | 7.1187 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Communal | MIN | PH112402023 | 43758 | 30 | Three Legged Tubular Tower | CO66 | 2.3112 | MIN-1100064 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD |  | MJV |  | 2019-11-27 | 2020-01-28 | 2020-01-19 | 2020-01-30 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-01-22 |  |  |  | 2020-01-22 |  |  |  | 2020-02-04 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-02-25 | 2020-03-05 | [5 empty] | A | Erlinda Dela Pena | 45 Block 21, Cabantian, Davao City | Davao del Sur | 125.6271 | 7.1167 | Rooftop | 53m | 9m | 10 years | P35,000 Exclusive of VAT and withholding tax | quarterly | 30sqm | n/a | 3 months | 4.5% increase on the 4th year | 2020-02-19 | n/a |  |  |  |  | 2020-03-12 | 2020-01-30 |  | 2020-04-11 | 2020-02-19 | 2020-03-19 | [16 empty] | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  | Awaiting MOC approval | 2020-03-26 |  | 2020-04-05 |  |  | 2020-04-09 | 2020-02-07 | 2020-04-12 | 2020-02-07 | 2020-02-08 | 2020-04-26 |  |  |  | 2020-05-03 |  | ZCG-12-340D-1NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [7 empty] | 2020-02-21 | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1100083 | 125.6312 | 7.1063 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Pampanga | MIN | PH112402197 | 13539 | 30 | Monopole Tower | CO66 | 1.2791 | MIN-1100065 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2020-03-26 | 2020-03-02 | 2020-03-28 | 2020-03-03 |  |  |  | 2020-03-03 | [8 empty] | 2020-04-02 | [5 empty] | 2020-03-03 |  |  |  | 2020-03-03 |  | 2020-05-02 | [27 empty] | 2020-05-09 |  |  | 2020-06-08 |  | 2020-05-16 | [16 empty] | 2020-06-06 |  |  | 2020-06-15 | [6 empty] | 2020-06-29 |  |  |  | 2020-06-29 |  |  |  |  | 2020-05-23 |  | 2020-06-02 |  |  | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-23 |  |  |  | 2020-06-30 |  | JGT-30-340C-2NPT |  |  | 2020-07-12 |  | 2020-06-20 | [6 empty] | 2020-07-20 | 2020-07-27 | [20 empty] | 2020-08-26 |  |  |  | 2020-08-29 | [8 empty] | 2020-07-05 |  | 2020-07-08 |  |  | 2020-07-20 |  |  |  | 2020-07-23 |  |  | 2020-07-30 |  |  |  | 2020-08-02 |  |  | 2020-08-17 |  |  |  | 2020-08-29 |  | 2020-09-01
PH1100084 | 125.6311 | 7.0991 | Urban | Rooftop | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Pampanga | MIN | PH112402192 | 10306 | 3 | Wall Mounted Pole | CO66 | 0.9404 | MIN-1100066 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 | Philcom_74 | Cluster M04 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2020-03-29 |  | 2020-03-31 | [13 empty] | 2020-04-05 | [11 empty] | 2020-05-05 | [27 empty] | 2020-05-12 |  |  | 2020-06-11 |  | 2020-05-19 | [16 empty] | 2020-06-09 |  |  | 2020-06-18 | [6 empty] | 2020-07-02 |  |  |  | 2020-07-02 |  |  |  |  | 2020-05-26 |  | 2020-06-05 |  |  | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-26 |  |  |  | 2020-07-03 |  | JGT-30-340C-2NPT |  |  | 2020-07-15 |  | 2020-06-23 | [6 empty] | 2020-07-23 | 2020-07-30 | [20 empty] | 2020-08-29 |  |  |  | 2020-09-01 | [8 empty] | 2020-07-08 |  | 2020-07-11 |  |  | 2020-07-23 |  |  |  | 2020-07-26 |  |  | 2020-08-02 |  |  |  | 2020-08-05 |  |  | 2020-08-20 |  |  |  | 2020-09-01 |  | 2020-09-04
PH1100085 | 125.6311 | 7.0919 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Lapu-Lapu | MIN | PH112402192 | 10306 | 30 | Monopole Tower | CO66 | 1.1937 | MIN-1100067 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-27 | 2019-12-27 | 2019-12-29 | 2019-12-29 |  |  |  | 2019-12-29 | 2019-12-30 |  |  |  | 2019-12-30 |  |  |  | 2020-01-03 | [5 empty] | 2019-12-29 |  |  |  | 2019-12-29 |  | 2020-02-02 | [27 empty] | 2020-02-09 |  |  | 2020-03-10 |  | 2020-02-16 | [16 empty] | 2020-03-08 |  |  | 2020-03-17 | [6 empty] | 2020-03-31 |  |  |  | 2020-03-31 |  |  |  |  | 2020-02-23 |  | 2020-03-04 |  |  | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-25 |  |  |  | 2020-04-01 |  | ZCG-12-340D-1NPT |  |  | 2020-04-13 |  | 2020-03-22 | [6 empty] | 2020-04-21 | 2020-04-28 | [20 empty] | 2020-05-28 |  |  |  | 2020-05-31 | [8 empty] | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-01 |  |  |  | 2020-05-04 |  |  | 2020-05-19 |  |  |  | 2020-05-31 |  | 2020-06-03
PH1100088 | 125.634 | 7.1295 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Communal | MIN | PH112402035 | 16740 | 30 | Three Legged Tubular Tower | CO66 | 3.6662 | MIN-1100068 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-23 | 2019-12-23 | 2019-12-25 | 2019-12-24 |  |  |  | 2019-12-24 | 2019-12-27 |  |  |  | 2019-12-27 |  |  |  | 2019-12-30 | 2019-12-28 |  |  |  | 2019-12-28 | 2019-12-24 | 2020-01-23 |  |  | 2019-12-24 | 2020-02-21 | 2020-01-29 | [5 empty] | A | Rebecca Rono | Block 10 Lot 3, Mutual Homes Subd., Catitipan, Davao City | Davao del Sur | 125.6339 | 7.1296 | Rooftop | 53m | 6m | 15 years | P25,000 exclusive of VAT and withholding tax | monthly | 150sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-05 | 2020-01-21 |  | 2020-03-06 |  | 2020-02-12 | 2020-01-22 |  | 2020-01-22 | [11 empty] | Y |  | 2020-03-04 |  |  | 2020-03-13 | [6 empty] | 2020-03-27 |  |  |  | 2020-03-27 |  |  |  |  | 2020-02-19 |  | 2020-02-29 |  |  | 2020-03-04 |  | 2020-03-07 |  |  | 2020-03-21 |  |  |  | 2020-03-28 |  | ZCG-12-340D-1NPT |  |  | 2020-04-09 |  | 2020-03-18 | [6 empty] | 2020-04-17 | 2020-04-24 | [20 empty] | 2020-05-24 |  |  |  | 2020-05-27 | [8 empty] | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-04-27 |  |  |  | 2020-04-30 |  |  | 2020-05-15 |  |  |  | 2020-05-27 |  | 2020-05-30
PH1100089 | 125.6339 | 7.1223 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402023 | 43758 | 30 | Three Legged Tubular Tower | CO66 | 2.9218 | MIN-1100069 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-04-02 | 2020-01-08 | 2020-04-04 | 2020-02-28 |  |  |  | 2020-02-28 | [8 empty] | 2020-04-09 | [5 empty] | 2020-02-28 |  |  |  | 2020-02-28 |  | 2020-05-09 | [27 empty] | 2020-05-16 | 2020-02-28 |  | 2020-06-15 |  | 2020-05-23 | [16 empty] | 2020-06-13 |  |  | 2020-06-22 | [6 empty] | 2020-07-06 |  |  |  | 2020-07-06 |  |  |  |  | 2020-05-30 |  | 2020-06-09 |  |  | 2020-06-13 |  | 2020-06-16 |  |  | 2020-06-30 |  |  |  | 2020-07-07 |  | JGT-30-340C-2NPT |  |  | 2020-07-19 |  | 2020-06-27 | [6 empty] | 2020-07-27 | 2020-08-03 | [20 empty] | 2020-09-02 |  |  |  | 2020-09-05 | [8 empty] | 2020-07-12 |  | 2020-07-15 |  |  | 2020-07-27 |  |  |  | 2020-07-30 |  |  | 2020-08-06 |  |  |  | 2020-08-09 |  |  | 2020-08-24 |  |  |  | 2020-09-05 |  | 2020-09-08
PH1100090 | 125.6375 | 7.1099 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402197 | 13539 | 30 | Three Legged Tubular Tower | CO66 | 2.0669 | MIN-1100070 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2020-04-05 | 2020-01-08 | 2020-04-07 | [13 empty] | 2020-04-12 | [11 empty] | 2020-05-12 | [27 empty] | 2020-05-19 |  |  | 2020-06-18 |  | 2020-05-26 | [16 empty] | 2020-06-16 |  |  | 2020-06-25 | [6 empty] | 2020-07-09 |  |  |  | 2020-07-09 |  |  |  |  | 2020-06-02 |  | 2020-06-12 |  |  | 2020-06-16 |  | 2020-06-19 |  |  | 2020-07-03 |  |  |  | 2020-07-10 |  | JGT-30-340C-2NPT |  |  | 2020-07-22 |  | 2020-06-30 | [6 empty] | 2020-07-30 | 2020-08-06 | [20 empty] | 2020-09-05 |  |  |  | 2020-09-08 | [8 empty] | 2020-07-15 |  | 2020-07-18 |  |  | 2020-07-30 |  |  |  | 2020-08-02 |  |  | 2020-08-09 |  |  |  | 2020-08-12 |  |  | 2020-08-27 |  |  |  | 2020-09-08 |  | 2020-09-11
PH1100091 | 125.6375 | 7.1028 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Pampanga | MIN | PH112402197 | 13539 | 30 | Monopole Tower | CO66 | 1.704 | MIN-1100071 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-24 | 2019-12-24 | 2019-12-26 | 2019-12-25 |  |  |  | 2019-12-25 | 2019-12-26 |  |  |  | 2019-12-26 |  |  |  | 2019-12-31 | 2019-12-27 |  |  |  | 2019-12-27 | 2019-12-25 | 2020-01-28 |  |  | 2019-12-25 |  | 2020-01-30 |  | y | Above Lease Cap, Need to Renego or Change candidates |  |  | A |  |  |  | 125.6375 | 7.1031 | Greenfield | 8m | [14 empty] | 2020-02-06 | 2020-01-14 |  | 2020-03-07 |  | 2020-02-13 | [16 empty] | 2020-03-05 |  |  | 2020-03-14 | [6 empty] | 2020-03-28 |  |  |  | 2020-03-28 |  |  |  |  | 2020-02-20 |  | 2020-03-01 |  |  | 2020-03-05 |  | 2020-03-08 |  |  | 2020-03-22 |  |  |  | 2020-03-29 |  | DGT-30-340C-2NPT |  |  | 2020-04-10 |  | 2020-03-19 | [6 empty] | 2020-04-18 | 2020-04-25 | [20 empty] | 2020-05-25 |  |  |  | 2020-05-28 | [8 empty] | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-18 |  |  |  | 2020-04-21 |  |  | 2020-04-28 |  |  |  | 2020-05-01 |  |  | 2020-05-16 |  |  |  | 2020-05-28 |  | 2020-05-31
PH1100092 | 125.6374 | 7.0955 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Lapu-Lapu | MIN | PH112402186 | 11738 | 30 | Monopole Tower | CO66 | 1.664 | MIN-1100072 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2019-12-15 | 2019-12-15 | 2019-12-17 | 2019-12-16 |  |  |  | 2019-12-16 | [8 empty] | 2019-12-22 | [5 empty] | 2019-12-16 |  |  |  | 2019-12-16 |  | 2020-01-21 | [27 empty] | 2020-01-28 |  |  | 2020-02-27 |  | 2020-02-04 | [16 empty] | 2020-02-25 |  |  | 2020-03-05 | [6 empty] | 2020-03-19 |  |  |  | 2020-03-19 |  |  |  |  | 2020-02-11 |  | 2020-02-21 |  |  | 2020-02-25 |  | 2020-02-28 |  |  | 2020-03-13 |  |  |  | 2020-03-20 |  | ZCG-12-340D-1NPT |  |  | 2020-04-01 |  | 2020-03-10 | [6 empty] | 2020-04-09 | 2020-04-16 | [20 empty] | 2020-05-16 |  |  |  | 2020-05-19 | [8 empty] | 2020-03-25 |  | 2020-03-28 |  |  | 2020-04-09 |  |  |  | 2020-04-12 |  |  | 2020-04-19 |  |  |  | 2020-04-22 |  |  | 2020-05-07 |  |  |  | 2020-05-19 |  | 2020-05-22
PH1100097 | 125.6403 | 7.1331 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402035 | 16740 | 30 | Monopole Tower | CO66 | 4.3083 | MIN-1100073 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2019-12-26 | 2019-12-26 | 2019-12-28 | 2019-12-27 |  |  |  | 2019-12-27 | 2019-12-28 |  |  |  | 2019-12-28 |  |  |  | 2020-01-02 | [5 empty] | 2019-12-27 |  |  |  | 2019-12-27 |  | 2020-02-01 | [27 empty] | 2020-02-08 |  |  | 2020-03-09 |  | 2020-02-15 | [16 empty] | 2020-03-07 |  |  | 2020-03-16 | [6 empty] | 2020-03-30 |  |  |  | 2020-03-30 |  |  |  |  | 2020-02-22 |  | 2020-03-03 |  |  | 2020-03-07 |  | 2020-03-10 |  |  | 2020-03-24 |  |  |  | 2020-03-31 |  | JGT-30-340C-2NPT |  |  | 2020-04-12 |  | 2020-03-21 | [6 empty] | 2020-04-20 | 2020-04-27 | [20 empty] | 2020-05-27 |  |  |  | 2020-05-30 | [8 empty] | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-18 |  |  |  | 2020-05-30 |  | 2020-06-02
PH1100099 | 125.6438 | 7.1135 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402198 | 11265 | 30 | Monopole Tower | CO66 | 2.8614 | MIN-1100074 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2019-12-26 | 2019-12-26 | 2019-12-28 | 2019-12-27 |  |  |  | 2019-12-27 | [8 empty] | 2020-01-02 | [5 empty] | 2019-12-27 |  |  |  | 2019-12-27 |  | 2020-02-01 | [27 empty] | 2020-02-08 |  |  | 2020-03-09 |  | 2020-02-15 | [16 empty] | 2020-03-07 |  |  | 2020-03-16 | [6 empty] | 2020-03-30 |  |  |  | 2020-03-30 |  |  |  |  | 2020-02-22 |  | 2020-03-03 |  |  | 2020-03-07 |  | 2020-03-10 |  |  | 2020-03-24 |  |  |  | 2020-03-31 |  | JGT-30-340C-2NPT |  |  | 2020-04-12 |  | 2020-03-21 | [6 empty] | 2020-04-20 | 2020-04-27 | [20 empty] | 2020-05-27 |  |  |  | 2020-05-30 | [8 empty] | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-18 |  |  |  | 2020-05-30 |  | 2020-06-02
PH1100100 | 125.6437 | 7.1063 | Urban | Greenfield | Greenfield | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Pampanga | MIN | PH112402198 | 11265 | 30 | Monopole Tower | CO66 | 2.4787 | MIN-1100075 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M04 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-08 | 2020-01-22 |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-13 | [5 empty] | 2019-12-06 | 2020-01-22 |  |  | 2019-12-06 |  | 2020-01-12 | [27 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-30-340C-2NPT（340KPH/D） |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100102 | 125.6467 | 7.1512 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Panacan | MIN | PH112402087 | 35806 | 30 | Three Legged Tubular Tower | CO66 | 6.4212 | MIN-1100076 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2019-12-11 | 2019-12-11 | 2019-12-13 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-13 |  |  |  | 2019-12-13 |  |  |  | 2019-12-18 | 2020-03-04 |  |  |  | 2020-03-04 | 2019-12-20 |  |  |  | 2019-12-20 | 2020-03-10 | 2020-01-17 | 2020-03-10 |  |  | 2020-03-10 |  | A | LORETA MAGPANTAY/EDITH JULIAN | PANACAN DAVAO CITY | Davao Del Sur | 125.6473 | 7.1512 | Greenfield |  |  | 10 years | P20,750 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-24 |  |  | 2020-02-23 |  | 2020-01-31 | [16 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  |  | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 |  | 2020-02-24 |  |  | 2020-03-09 |  |  |  | 2020-03-16 |  | JGT-30-340C-2NPT |  |  | 2020-03-28 |  | 2020-03-06 | [6 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [8 empty] | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100103 | 125.6466 | 7.1439 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Panacan | MIN | PH112402101 | 52386 | 30 | Three Legged Tubular Tower | CO66 | 5.6966 | MIN-1100077 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-04-08 | 2020-01-13 | 2020-04-10 | 2020-01-13 |  |  |  | 2020-01-13 | [8 empty] | 2020-04-15 | [5 empty] | 2020-01-13 |  |  |  | 2020-01-13 |  | 2020-05-15 | [27 empty] | 2020-05-22 |  |  | 2020-06-21 |  | 2020-05-29 | [16 empty] | 2020-06-19 |  |  | 2020-06-28 | [6 empty] | 2020-07-12 |  |  |  | 2020-07-12 |  |  |  |  | 2020-06-05 |  | 2020-06-15 |  |  | 2020-06-19 |  | 2020-06-22 |  |  | 2020-07-06 |  |  |  | 2020-07-13 |  | JGT-30-340C-2NPT |  |  | 2020-07-25 |  | 2020-07-03 | [6 empty] | 2020-08-02 | 2020-08-09 | [20 empty] | 2020-09-08 |  |  |  | 2020-09-11 | [8 empty] | 2020-07-18 |  | 2020-07-21 |  |  | 2020-08-02 |  |  |  | 2020-08-05 |  |  | 2020-08-12 |  |  |  | 2020-08-15 |  |  | 2020-08-30 |  |  |  | 2020-09-11 |  | 2020-09-14
PH1100104 | 125.6466 | 7.1367 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402101 | 52386 | 30 | Three Legged Tubular Tower | CO66 | 4.9962 | MIN-1100078 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-11 | 2019-12-11 | 2019-12-13 | [13 empty] | 2019-12-18 | [11 empty] | 2020-01-17 | [27 empty] | 2020-01-24 |  |  | 2020-02-23 |  | 2020-01-31 | [16 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  |  | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 |  | 2020-02-24 |  |  | 2020-03-09 |  |  |  | 2020-03-16 |  | JGT-30-340C-2NPT |  |  | 2020-03-28 |  | 2020-03-06 | [6 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [8 empty] | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100105 | 125.6503 | 7.1264 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402101 | 52386 | 30 | Three Legged Tubular Tower | CO66 | 4.3499 | MIN-1100079 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-13 | 2019-12-09 |  |  |  | 2019-12-09 | [6 empty] | 2020-01-12 | [5 empty] | A |  |  |  | 125.6499 | 7.1259 | Greenfield | [15 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100106 | 125.6498 | 7.1186 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402101 | 52386 | 30 | Three Legged Tubular Tower | CO66 | 3.7356 | MIN-1100080 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | [8 empty] | 2019-12-13 | [11 empty] | 2020-01-12 | [27 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100107 | 125.65 | 7.1098 | Urban | Greenfield | Greenfield | Y1 | L7+L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402086 | 14381 | 30 | Three Legged Tubular Tower | CO66 | 3.27 | MIN-1100081 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-03-03 |  |  |  | 2020-03-03 |  |  |  | 2019-12-25 | 2020-03-03 |  |  |  | 2020-03-03 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-03-12 | 2020-01-24 | 2020-03-12 |  |  | 2020-03-12 |  | A | VERANIO DIGAL PACATANG | PACATANG BLDG., BELEN ROAD, BRGY HIZON, LANANG, DAVAO CITY | Davao Del Sur | 125.6491 | 7.1111 | Rooftop |  |  | 10 years | P30,000 Inclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 2 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-31 |  |  | 2020-03-01 |  | 2020-02-07 | [16 empty] | 2020-02-28 |  |  | 2020-03-08 | [6 empty] | 2020-03-22 |  |  |  | 2020-03-22 |  |  |  |  | 2020-02-14 |  | 2020-02-24 |  |  | 2020-02-28 |  | 2020-03-02 |  |  | 2020-03-16 |  |  |  | 2020-03-23 |  | ZCG-12-340D-1NPT |  |  | 2020-04-04 |  | 2020-03-13 | [6 empty] | 2020-04-12 | 2020-04-19 | [20 empty] | 2020-05-19 |  |  |  | 2020-05-22 | [8 empty] | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-10 |  |  |  | 2020-05-22 |  | 2020-05-25
PH1100109 | 125.6529 | 7.1475 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Panacan | MIN | PH112402087 | 35806 | 30 | Three Legged Tubular Tower | CO66 | 6.3856 | MIN-1100082 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD |  | MJV |  | 2019-11-27 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2019-12-13 | 2020-02-03 |  |  | 2019-12-13 | 2020-01-23 |  |  |  | 2020-01-23 |  |  |  | 2019-12-19 | 2020-01-23 |  |  |  | 2020-01-23 | 2019-12-13 | 2020-02-03 |  |  | 2019-12-13 |  | 2020-01-18 | [5 empty] | A |  |  |  | 125.6525 | 7.1494 | Greenfield | 26m | [14 empty] | 2020-01-25 | 2020-02-28 |  | 2020-02-24 | 2020-03-04 | 2020-02-01 | [16 empty] | 2020-02-22 |  |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  | Awaiting MOC approval | 2020-02-08 | 2020-02-11 | 2020-02-18 | 2020-02-22 | 2020-02-22 | 2020-02-22 | 2020-02-04 | 2020-02-25 | 2020-02-04 | 2020-03-11 | 2020-03-10 | 2020-02-05 |  |  | 2020-03-17 |  | DGT-30-340C-2NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100110 | 125.6529 | 7.1403 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402101 | 52386 | 30 | Monopole Tower | CO66 | 5.7133 | MIN-1100083 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-11 | 2019-12-11 | 2019-12-13 |  | 2020-02-03 |  |  | 2020-02-03 |  | 2020-02-06 |  |  | 2020-02-06 |  |  |  | 2019-12-18 |  | 2020-02-06 |  |  | 2020-02-06 |  | 2020-02-03 |  |  | 2020-02-03 |  | 2020-01-17 | [5 empty] | A |  |  |  | 125.6525 | 7.1404 | [16 empty] | 2020-01-24 |  |  | 2020-02-23 |  | 2020-01-31 | [16 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  |  | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 |  | 2020-02-24 |  |  | 2020-03-09 |  |  |  | 2020-03-16 |  | DGT-30-340C-2NPT |  |  | 2020-03-28 |  | 2020-03-06 | [6 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [8 empty] | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100111 | 125.6566 | 7.13 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402101 | 52386 | 30 | Monopole Tower | CO66 | 5.1247 | MIN-1100084 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-15 | 2019-12-13 | 2020-02-28 |  |  | 2019-12-13 | 2020-02-25 |  |  |  | 2020-02-25 |  |  |  | 2019-12-20 | 2020-02-25 |  |  |  | 2020-02-25 | 2019-12-13 | 2020-01-22 |  |  | 2019-12-13 |  | 2020-01-19 | [9 empty] | 125.6572 | 7.1293 | [16 empty] | 2020-01-26 | 2020-02-28 |  | 2020-02-25 |  | 2020-02-02 | [16 empty] | 2020-02-23 |  |  | 2020-03-03 | [6 empty] | 2020-03-17 |  |  |  | 2020-03-17 |  |  |  |  | 2020-02-09 |  | 2020-02-19 |  |  | 2020-02-23 |  | 2020-02-26 |  |  | 2020-03-11 |  |  |  | 2020-03-18 |  | ZCG-12-340D-1NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [8 empty] | 2020-03-23 |  | 2020-03-26 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100112 | 125.6561 | 7.1222 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402101 | 52386 | 30 | Monopole Tower | CO66 | 4.5307 | MIN-1100085 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M04 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2019-12-25 | 2020-02-05 |  |  | 2019-12-25 | 2019-12-26 | 2020-02-15 |  |  | 2019-12-26 |  |  |  | 2019-12-19 |  | 2020-02-15 |  |  | 2020-02-15 | 2019-12-25 | 2020-01-29 |  |  | 2019-12-25 |  | 2020-01-18 | [5 empty] | A |  |  |  | 125.657 | 7.1234 | [16 empty] | 2020-01-25 | 2020-02-28 |  | 2020-02-24 |  | 2020-02-01 | [16 empty] | 2020-02-22 |  |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  |  | 2020-02-08 |  | 2020-02-18 |  |  | 2020-02-22 | 2020-03-09 | 2020-02-25 | 2020-03-12 |  | 2020-03-10 |  |  |  | 2020-03-17 |  | DGT-30-340C-2NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100113 | 125.6563 | 7.1134 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402086 | 14381 | 6 | Pole with counterweight | CO66 | 4.0647 | MIN-1100086 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2019-12-16 |  |  |  | 2019-12-16 | 2019-12-17 |  |  |  | 2019-12-17 |  |  |  | 2019-12-19 | [5 empty] | 2019-12-16 |  |  |  | 2019-12-16 |  | 2020-01-18 | [27 empty] | 2020-01-25 |  |  | 2020-02-24 |  | 2020-02-01 | [16 empty] | 2020-02-22 |  |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  |  | 2020-02-08 |  | 2020-02-18 |  |  | 2020-02-22 |  | 2020-02-25 |  |  | 2020-03-10 |  |  |  | 2020-03-17 |  | ZCG-12-340D-1NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100114 | 125.6591 | 7.1439 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402087 | 35806 | 30 | Three Legged Tubular Tower | CO66 | 6.4499 | MIN-1100087 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2019-12-19 |  |  |  | 2019-12-19 | [8 empty] | 2019-12-25 | [5 empty] | 2019-12-19 |  |  |  | 2019-12-19 |  | 2020-01-24 | [27 empty] | 2020-01-31 |  |  | 2020-03-01 |  | 2020-02-07 | [16 empty] | 2020-02-28 |  |  | 2020-03-08 | [6 empty] | 2020-03-22 |  |  |  | 2020-03-22 |  |  |  |  | 2020-02-14 |  | 2020-02-24 |  |  | 2020-02-28 |  | 2020-03-02 |  |  | 2020-03-16 |  |  |  | 2020-03-23 |  | ZCG-12-340D-1NPT |  |  | 2020-04-04 |  | 2020-03-13 | [6 empty] | 2020-04-12 | 2020-04-19 | [20 empty] | 2020-05-19 |  |  |  | 2020-05-22 | [8 empty] | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-10 |  |  |  | 2020-05-22 |  | 2020-05-25
PH1100115 | 125.6618 | 7.1344 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402101 | 52386 | 30 | Monopole Tower | CO66 | 5.8798 | MIN-1100088 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2019-12-19 | 2020-02-04 | 2020-02-05 |  | 2019-12-19 | 2020-01-24 |  |  |  | 2020-01-24 |  |  |  | 2019-12-25 | 2020-01-24 |  |  |  | 2020-01-24 | 2019-12-19 | 2020-02-04 | 2020-02-05 |  | 2019-12-19 |  | 2020-01-24 | [5 empty] | A |  |  |  | 125.6616 | 7.1372 | Rooftop | 67m | 9m | [13 empty] | 2020-01-31 |  |  | 2020-03-01 |  | 2020-02-07 | [16 empty] | 2020-02-28 |  |  | 2020-03-08 | [6 empty] | 2020-03-22 |  |  |  | 2020-03-22 |  |  |  |  | 2020-02-14 |  | 2020-02-24 |  |  | 2020-02-28 | 2020-03-03 | 2020-03-02 | 2020-03-05 | 2020-03-08 | 2020-03-16 |  |  |  | 2020-03-23 |  | ZCG-9-340D-1NPT |  |  | 2020-04-04 |  | 2020-03-13 | [6 empty] | 2020-04-12 | 2020-04-19 | [20 empty] | 2020-05-19 |  |  |  | 2020-05-22 | [8 empty] | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-10 |  |  |  | 2020-05-22 |  | 2020-05-25
PH1100117 | 125.3411 | 6.7536 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Digos City | Tiguman | MIN | PH112403027 | 16595 | 30 | Monopole Tower | CO66 | 49.3692 | MIN-1100089 | Level 5 | phase3 | phase3 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-11-30 | 2019-11-30 | 2019-12-02 | 2019-12-10 | 2020-01-22 |  |  | 2019-12-10 | 2019-12-10 |  |  |  | 2019-12-10 |  |  |  | 2019-12-07 | 2019-12-12 |  |  |  | 2019-12-12 |  | 2020-01-22 |  |  | 2020-01-22 | 2020-02-25 | 2020-01-06 | 2020-03-13 |  |  | 2020-03-12 | 2020-03-13 | A | Diofer Saldivar | Purok Santolan, Tres De Mayo, Digos City | Davao del Sur | 125.34 | 6.7537 | Greenfield | 28m |  | 10 years | P20,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-13 | 2020-02-24 |  | 2020-02-12 |  | 2020-01-20 | [16 empty] | 2020-02-10 |  |  | 2020-02-19 | [6 empty] | 2020-03-04 |  |  |  | 2020-03-04 |  |  |  |  | 2020-01-27 |  | 2020-02-06 |  |  | 2020-02-10 |  | 2020-02-13 |  |  | 2020-02-27 |  |  |  | 2020-03-05 |  | DGT-30-340C-2NPT |  |  | 2020-03-17 |  | 2020-02-24 | [6 empty] | 2020-03-25 | 2020-04-01 | [20 empty] | 2020-05-01 |  |  |  | 2020-05-04 | [8 empty] | 2020-03-10 |  | 2020-03-13 |  |  | 2020-03-25 |  |  |  | 2020-03-28 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-22 |  |  |  | 2020-05-04 |  | 2020-05-07
PH1100122 | 125.3473 | 6.7355 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Digos City | San Jose (Balutakay) | MIN | PH112403022 | 15422 | 30 | Monopole Tower | CO66 | 50.5368 | MIN-1100090 | Level 5 | phase3 | phase3 | P1_630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-13 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-13 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-07 |  |  |  | 2019-12-07 | 2020-01-24 | 2020-01-12 | 2020-01-10 |  |  | 2020-01-10 | 2020-02-04 | A | Wilma O. Hipolito | Purok Gemelina, Brgy. San Miguel, Digos City | Davao del Sur | 125.3451 | 6.7365 | Greenfield | 19m |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 225sqm | n/a | n/a | 4.5% increase on the 4th year | 2020-01-23 | n/a |  |  |  | n/a | 2020-01-19 | 2020-01-08 |  | 2020-02-18 | 2020-02-06 | 2020-01-26 | 2020-01-29 | 2020-01-29 | 2020-02-27 |  |  | 2020-02-28 |  |  | Wilma O. Hipolito | BDO/One Network Bank/Digos City | 040150032331 | 0915-5068917 |  |  |  |  | 2020-02-16 | ok | 2020-02-28 | 2020-02-25 | 2020-02-28 | [5 empty] | 2020-03-10 |  | 2020-02-06 | 2020-02-11 | 2020-03-10 | 2020-02-12 | 2020-02-17 | 2020-02-25 | Cheque released | 2020-02-02 | 2020-01-22 | 2020-02-12 | 2020-02-07 | 2020-02-07 | 2020-02-16 | 2020-01-23 | 2020-02-19 | 2020-01-23 | 2020-02-08 | 2020-03-04 | 2020-01-24 | 2020-01-25 | 2020-02-11 | 2020-03-11 | 2020-02-14 | JGT-30-340C-2NPT |  |  | 2020-03-23 | 2020-03-06 | 2020-03-01 | 2020-02-11 | [5 empty] | 2020-03-31 | 2020-04-07 |  |  |  | 2020-03-02 | [16 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [7 empty] | 2020-01-29 | 2020-03-16 | 2020-01-30 | 2020-03-19 | 2020-02-19 | 2020-02-24 | 2020-03-31 | 2020-03-02 |  | 2020-03-04 | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100123 | 125.3536 | 6.7535 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Digos City | Zone 3 | MIN | PH112403029 | 8402 | 30 | Monopole Tower | CO66 | 48.5159 | MIN-1100091 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-04-07 | 2020-01-22 | 2020-04-09 |  | 2020-02-06 |  |  | 2020-02-06 | [8 empty] | 2020-04-14 | [6 empty] | 2020-02-06 |  |  | 2020-02-06 |  | 2020-05-14 | [27 empty] | 2020-05-21 |  |  | 2020-06-20 |  | 2020-05-28 | [16 empty] | 2020-06-18 |  |  | 2020-06-27 | [6 empty] | 2020-07-11 |  |  |  | 2020-07-11 |  |  |  |  | 2020-06-04 |  | 2020-06-14 |  |  | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-05 |  |  |  | 2020-07-12 |  | DGT-30-340C-2NPT |  |  | 2020-07-24 |  | 2020-07-02 | [6 empty] | 2020-08-01 | 2020-08-08 | [20 empty] | 2020-09-07 |  |  |  | 2020-09-10 | [8 empty] | 2020-07-17 |  | 2020-07-20 |  |  | 2020-08-01 |  |  |  | 2020-08-04 |  |  | 2020-08-11 |  |  |  | 2020-08-14 |  |  | 2020-08-29 |  |  |  | 2020-09-10 |  | 2020-09-13
PH1100124 | 125.3536 | 6.7463 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Digos City | Zone 3 | MIN | PH112403030 | 17885 | 30 | Monopole Tower | CO66 | 49.1567 | MIN-1100092 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | JXD |  | 2019-12-12 | 2019-12-10 | 2019-12-10 | 2019-12-12 | 2019-12-11 | 2019-12-20 |  |  | 2019-12-11 | 2019-12-12 | 2019-12-21 |  |  | 2019-12-12 |  |  |  | 2019-12-17 |  | 2019-12-21 |  |  | 2019-12-21 | 2019-12-11 | 2019-12-21 |  |  | 2019-12-11 | 2020-01-24 | 2020-01-16 | 2020-01-09 |  |  | 2020-01-10 | 2020-02-04 | B | Kent Gamuyao | Lapu-Lapu Ext., Brgy. Zone 3, Digos City | Davao del Sur | 125.3534 | 6.7461 | Greenfield | 24m |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-23 | 2020-01-10 |  | 2020-02-22 | 2020-03-04 | 2020-01-30 | [16 empty] | 2020-02-20 |  |  | 2020-02-29 | [6 empty] | 2020-03-14 |  |  |  | 2020-03-14 |  |  |  | Awaiting Lessor ID | 2020-02-06 |  | 2020-02-16 |  |  | 2020-02-20 |  | 2020-02-23 |  |  | 2020-03-08 |  |  |  | 2020-03-15 |  | DGT-30-340C-2NPT |  |  | 2020-03-27 |  | 2020-03-05 | [6 empty] | 2020-04-04 | 2020-04-11 | [20 empty] | 2020-05-11 |  |  |  | 2020-05-14 | [8 empty] | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-05-02 |  |  |  | 2020-05-14 |  | 2020-05-17
PH1100127 | 125.3599 | 6.7499 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Digos City | Aplaya | MIN | PH112403029 | 8402 | 30 | Monopole Tower | CO66 | 48.421 | MIN-1100093 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-13 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-07 |  |  |  | 2019-12-07 |  | 2020-01-12 | [5 empty] | A |  |  |  | 125.3609 | 6.7499 | Greenfield | [15 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100128 | 125.3598 | 6.7426 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Digos City | Aplaya | MIN | PH112403030 | 17885 | 30 | Monopole Tower | CO66 | 49.0696 | MIN-1100094 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 | DepEd_3300 | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2019-12-16 |  |  |  | 2019-12-16 | 2020-02-06 |  |  |  | 2020-02-06 |  |  |  | 2019-12-19 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-02-24 | 2020-01-18 | [5 empty] | A | Jay Ochias | 5th Street, Mabini, Digos City | Davao del Sur | 125.36 | 6.7398 | Greenfield |  |  | 15 years | P25,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-25 | 2020-02-11 |  | 2020-02-24 | 2020-03-04 | 2020-02-01 | [16 empty] | 2020-02-22 | ok |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  | Awaiting MOC approval | 2020-02-08 | 2020-03-11 | 2020-02-18 |  |  | 2020-02-22 | 2020-03-12 | 2020-02-25 |  |  | 2020-03-10 |  |  |  | 2020-03-17 |  | JGT-30-340C-2NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100130 | 125.3661 | 6.7462 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Digos City | Aplaya | MIN | PH112403001 | 18485 | 30 | Monopole Tower | CO66 | 48.3392 | MIN-1100095 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-13 |  |  |  | 2019-12-13 |  |  |  | 2019-12-19 | [5 empty] | 2019-12-12 |  |  |  | 2019-12-12 |  | 2020-01-18 | [27 empty] | 2020-01-25 |  |  | 2020-02-24 |  | 2020-02-01 | [16 empty] | 2020-02-22 |  |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  |  | 2020-02-08 |  | 2020-02-18 |  |  | 2020-02-22 |  | 2020-02-25 |  |  | 2020-03-10 |  |  |  | 2020-03-17 |  | DGT-30-340C-2NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100131 | 125.7901 | 7.4632 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Mankilam | MIN | PH112319011 | 38963 | 30 | Three Legged Tubular Tower | CO65 | 2.8589 | MIN-1100096 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  | Enovell |  | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2019-12-12 | 2020-01-27 |  |  | 2019-12-12 | 2019-12-13 |  |  |  | 2019-12-13 |  |  |  | 2019-12-19 | 2019-12-13 |  |  |  | 2019-12-13 | 2019-12-12 | 2020-01-27 |  |  | 2019-12-12 | 2020-03-06 | 2020-01-18 | 2020-03-06 |  |  | 2020-03-06 | 2020-03-06 | B | Margareto Galang | Purok 1, Careg, Brgy. Mantilam, Tagum City | Davao del Norte | 125.7917 | 7.4632 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-25 |  |  | 2020-02-24 |  | 2020-02-01 | [11 empty] | 0906-1355356 |  |  |  |  | 2020-02-22 |  |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  |  | 2020-02-08 |  | 2020-02-18 |  |  | 2020-02-22 | 2020-02-24 | 2020-02-25 | 2020-02-24 | 2020-03-09 | 2020-03-10 |  |  |  | 2020-03-17 |  | DGT-30-340C-2NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100138 | 125.7962 | 7.4379 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Tagum City | San Miguel (Camp 4) | MIN | PH112319022 | 40297 | 30 | Three Legged Tubular Tower | CO65 | 1.505 | MIN-1100097 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-22 | 2019-12-22 | 2019-12-24 | 2019-12-23 |  |  |  | 2019-12-23 | 2020-01-11 |  |  |  | 2020-01-11 |  |  |  | 2019-12-29 | [5 empty] | 2019-12-23 |  |  |  | 2019-12-23 |  | 2020-01-28 | [27 empty] | 2020-02-04 |  |  | 2020-03-05 |  | 2020-02-11 | [16 empty] | 2020-03-03 |  |  | 2020-03-12 | [6 empty] | 2020-03-26 |  |  |  | 2020-03-26 |  |  |  |  | 2020-02-18 |  | 2020-02-28 |  |  | 2020-03-03 |  | 2020-03-06 |  |  | 2020-03-20 |  |  |  | 2020-03-27 |  | DGT-30-340C-2NPT |  |  | 2020-04-08 |  | 2020-03-17 | [6 empty] | 2020-04-16 | 2020-04-23 | [20 empty] | 2020-05-23 |  |  |  | 2020-05-26 | [8 empty] | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-04-26 |  |  |  | 2020-04-29 |  |  | 2020-05-14 |  |  |  | 2020-05-26 |  | 2020-05-29
PH1100139 | 125.8025 | 7.4558 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Magugpo West | MIN | PH112319026 | 13965 | 30 | Three Legged Tubular Tower | CO65 | 1.3843 | MIN-1100098 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2020-01-22 |  | 2019-12-12 |  | 2019-12-12 | 2020-01-23 |  | 2019-12-13 |  | 2019-12-13 |  |  |  | 2019-12-19 | 2020-01-23 |  |  |  | 2020-01-23 | 2020-01-22 |  | 2019-12-12 |  | 2019-12-12 |  | 2020-01-18 | [5 empty] | A |  |  |  | 125.8022 | 7.4559 | Greenfield | [15 empty] | 2020-01-25 | 2020-01-23 |  | 2020-02-24 |  | 2020-02-01 | [16 empty] | 2020-02-22 |  |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  |  | 2020-02-08 |  | 2020-02-18 |  |  | 2020-02-22 |  | 2020-02-25 |  |  | 2020-03-10 |  |  |  | 2020-03-17 |  | DGT-30-340C-2NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [8 empty] | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100145 | 125.8077 | 7.444 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Magugpo Poblacion | MIN | PH112319022 | 40297 | 30 | Three Legged Tubular Tower | CO65 | 0.077856 | MIN-1100099 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-29 | 2019-12-29 | 2019-12-31 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-05 |  |  |  | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-24 | 2020-02-04 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Samuel T. Paracha | Purok Bayan, Visayan Village, Tagum City | Davao del Norte | 125.8075 | 7.4431 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-11 | 2020-01-23 |  | 2020-03-12 |  | 2020-02-18 | [16 empty] | 2020-03-10 |  |  | 2020-03-19 | [6 empty] | 2020-04-02 |  |  |  | 2020-04-02 |  |  |  |  | 2020-02-25 |  | 2020-03-06 |  |  | 2020-03-10 |  | 2020-03-13 |  |  | 2020-03-27 |  |  |  | 2020-04-03 |  | DGT-30-340C-2NPT |  |  | 2020-04-15 |  | 2020-03-24 | [6 empty] | 2020-04-23 | 2020-04-30 | [20 empty] | 2020-05-30 |  |  |  | 2020-06-02 | [8 empty] | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-21 |  |  |  | 2020-06-02 |  | 2020-06-05
PH1100147 | 125.8087 | 7.4306 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Visayan Village | MIN | PH112319022 | 40297 | 30 | Three Legged Tubular Tower | CO65 | 1.5666 | MIN-1100100 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2020-01-05 |  |  |  | 2020-01-05 |  |  |  | 2019-12-13 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-04 |  |  |  | 2020-01-04 | 2020-01-24 | 2020-01-12 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-11 | A | Marie Stella | Mangga, Visayan Village, Kapagingan, Tagum City | Davao del Norte | 125.8091 | 7.431 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-02-03 |  | 2020-02-18 |  | 2020-01-26 |  |  | 2020-03-05 | [13 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100148 | 125.8151 | 7.4558 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Magugpo West | MIN | PH112319024 | 9344 | 30 | Three Legged Tubular Tower | CO65 | 1.4698 | MIN-1100101 | Level 4 (220) | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  | Enovell |  | 2019-11-27 | 2019-11-28 | 2019-11-28 | 2019-11-30 | 2019-12-10 | 2020-01-27 |  |  | 2019-12-10 | 2019-12-10 |  |  |  | 2019-12-10 |  |  |  | 2019-12-05 | 2019-12-10 |  |  |  | 2019-12-10 | 2019-12-06 | 2020-01-27 |  |  | 2019-12-06 | 2020-01-24 | 2020-01-04 | 2020-01-08 |  |  | 2020-01-09 | 2020-02-06 | B | Phoebe Hernaez | 3553 North Park, Camia, Mirafuentes Subdivision, Tagum City | Davao del Norte | 125.8138 | 7.4558 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-11 | 2020-01-28 |  | 2020-02-10 |  | 2020-01-18 | [16 empty] | 2020-02-08 |  |  | 2020-02-17 | [6 empty] | 2020-03-02 |  |  |  | 2020-03-02 |  |  |  |  | 2020-01-25 |  | 2020-02-04 |  |  | 2020-02-08 | 2020-02-24 | 2020-02-11 | 2020-02-24 |  | 2020-02-25 |  |  |  | 2020-03-03 |  | DGT-30-340C-2NPT |  |  | 2020-03-15 |  | 2020-02-22 | [6 empty] | 2020-03-23 | 2020-03-30 | [20 empty] | 2020-04-29 |  |  |  | 2020-05-02 | [8 empty] | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-23 |  |  |  | 2020-03-26 |  |  | 2020-04-02 |  |  |  | 2020-04-05 |  |  | 2020-04-20 |  |  |  | 2020-05-02 |  | 2020-05-05
PH1100152 | 125.8212 | 7.4305 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Apokon | MIN | PH112319001 | 29743 | 30 | Three Legged Tubular Tower | CO65 | 2.1448 | MIN-1100102 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-01-05 | 2020-01-04 | 2020-01-07 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-05 |  |  |  | 2020-01-05 |  |  |  | 2020-01-12 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-02-07 | 2020-02-11 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-11 | A | Gemma A. Havikhorst | U-3 Purok 3, Apokon, Tagum City | Davao del Norte | 125.8212 | 7.4305 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-18 | 2020-01-17 |  | 2020-03-19 |  | 2020-02-25 | [16 empty] | 2020-03-17 |  |  | 2020-03-26 | [6 empty] | 2020-04-09 |  |  |  | 2020-04-09 |  |  |  |  | 2020-03-03 |  | 2020-03-13 |  |  | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-03 |  |  |  | 2020-04-10 |  | DGT-30-340C-2NPT |  |  | 2020-04-22 |  | 2020-03-31 | [6 empty] | 2020-04-30 | 2020-05-07 | [20 empty] | 2020-06-06 |  |  |  | 2020-06-09 | [8 empty] | 2020-04-15 |  | 2020-04-18 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-10 |  |  |  | 2020-05-13 |  |  | 2020-05-28 |  |  |  | 2020-06-09 |  | 2020-06-12
PH1100169 | 125.5954 | 7.0523 | Urban | Greenfield | Greenfield | Y1 | L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Bucana | MIN | PH112402020 | 83964 | 30 | Three Legged Tubular Tower | CO66 | 5.9582 | MIN-1100103 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M05 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2020-02-03 | 2020-01-08 | 2020-01-20 |  | 2020-01-08 | 2020-02-05 |  | 2020-01-20 |  | 2020-01-20 |  |  |  | 2019-12-13 | 2020-02-05 |  |  |  | 2020-02-05 | 2020-02-03 | 2020-01-08 | 2020-01-20 |  | 2020-01-08 | 2020-03-05 | 2020-01-12 | 2020-03-06 |  |  | 2020-03-05 | 2020-03-06 | A | Hiram Enrico Magtoto | Quimpo Blvd., Ecoland, Davao City | Davao del Sur | 125.5941 | 7.0525 | Greenfield |  |  | 10 years | P30,000 exclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 | 2020-03-10 | 2020-02-19 | 2020-03-12 |  | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100170 | 125.5828 | 7.0524 | Urban | Greenfield | Greenfield | Y1 | L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Aplaya | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 6.7571 | MIN-1100104 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2020-04-16 |  | 2020-04-18 | [13 empty] | 2020-04-23 | [11 empty] | 2020-05-23 | [27 empty] | 2020-05-30 |  |  | 2020-06-29 |  | 2020-06-06 | [16 empty] | 2020-06-27 |  |  | 2020-07-06 | [6 empty] | 2020-07-20 |  |  |  | 2020-07-20 |  |  |  |  | 2020-06-13 |  | 2020-06-23 |  |  | 2020-06-27 |  | 2020-06-30 |  |  | 2020-07-14 |  |  |  | 2020-07-21 |  | ZCG-12-340D-1NPT |  |  | 2020-08-02 |  | 2020-07-11 | [6 empty] | 2020-08-10 | 2020-08-17 | [20 empty] | 2020-09-16 |  |  |  | 2020-09-19 | [8 empty] | 2020-07-26 |  | 2020-07-29 |  |  | 2020-08-10 |  |  |  | 2020-08-13 |  |  | 2020-08-20 |  |  |  | 2020-08-23 |  |  | 2020-09-07 |  |  |  | 2020-09-19 |  | 2020-09-22
PH1100172 | 125.5703 | 7.0525 | Urban | Greenfield | Greenfield | Y1 | L21+L26 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402074 | 33384 | 30 | Three Legged Tubular Tower | CO66 | 7.7229 | MIN-1100105 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-15 | 2019-12-15 | 2019-12-17 | 2019-12-16 |  |  |  | 2019-12-16 | 2019-12-17 |  |  |  | 2019-12-17 |  |  |  | 2019-12-22 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-16 |  |  |  | 2019-12-16 | 2020-03-06 | 2020-01-21 | 2019-12-27 |  |  | 2020-03-06 |  | A | Arish Espaldon | Fatima Village, Matina Crossing, Davao City | Davao del Sur | 125.5703 | 7.0528 | Greenfield | 18m |  | 15 years | P20,000 exclusive of VAT and withholding tax | monthly | 100sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-28 |  |  | 2020-02-27 |  | 2020-02-04 | [16 empty] | 2020-02-25 |  |  | 2020-03-05 | [6 empty] | 2020-03-19 |  |  |  | 2020-03-19 |  |  |  |  | 2020-02-11 |  | 2020-02-21 |  |  | 2020-02-25 |  | 2020-02-28 |  |  | 2020-03-13 |  |  |  | 2020-03-20 |  | DGT-30-340C-2NPT |  |  | 2020-04-01 |  | 2020-03-10 | [6 empty] | 2020-04-09 | 2020-04-16 | [20 empty] | 2020-05-16 |  |  |  | 2020-05-19 | [8 empty] | 2020-03-25 |  | 2020-03-28 |  |  | 2020-04-09 |  |  |  | 2020-04-12 |  |  | 2020-04-19 |  |  |  | 2020-04-22 |  |  | 2020-05-07 |  |  |  | 2020-05-19 |  | 2020-05-22
PH1100175 | 125.6017 | 7.0559 | Urban | Greenfield | Greenfield | Y1 | L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Bucana | MIN | PH112402020 | 83964 | 30 | Three Legged Tubular Tower | CO66 | 5.2742 | MIN-1100106 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-04-07 | 2020-01-08 | 2020-04-09 | [13 empty] | 2020-04-14 | [11 empty] | 2020-05-14 | [27 empty] | 2020-05-21 |  |  | 2020-06-20 |  | 2020-05-28 | [16 empty] | 2020-06-18 |  |  | 2020-06-27 | [6 empty] | 2020-07-11 |  |  |  | 2020-07-11 |  |  |  |  | 2020-06-04 |  | 2020-06-14 |  |  | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-05 |  |  |  | 2020-07-12 |  | ZCG-12-340D-1NPT |  |  | 2020-07-24 |  | 2020-07-02 | [6 empty] | 2020-08-01 | 2020-08-08 | [20 empty] | 2020-09-07 |  |  |  | 2020-09-10 | [8 empty] | 2020-07-17 |  | 2020-07-20 |  |  | 2020-08-01 |  |  |  | 2020-08-04 |  |  | 2020-08-11 |  |  |  | 2020-08-14 |  |  | 2020-08-29 |  |  |  | 2020-09-10 |  | 2020-09-13
PH1100176 | 125.5891 | 7.056 | Urban | Greenfield | Greenfield | Y1 | L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 6.0097 | MIN-1100107 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-15 | 2019-12-15 | 2019-12-17 | 2019-12-16 |  |  |  | 2019-12-16 | 2019-12-25 |  |  |  | 2019-12-25 |  |  |  | 2019-12-22 | [5 empty] | 2019-12-16 |  |  |  | 2019-12-16 |  | 2020-01-21 | [27 empty] | 2020-01-28 |  |  | 2020-02-27 |  | 2020-02-04 | [16 empty] | 2020-02-25 |  |  | 2020-03-05 | [6 empty] | 2020-03-19 |  |  |  | 2020-03-19 |  |  |  |  | 2020-02-11 |  | 2020-02-21 |  |  | 2020-02-25 |  | 2020-02-28 |  |  | 2020-03-13 |  |  |  | 2020-03-20 |  | ZCG-12-340D-1NPT |  |  | 2020-04-01 |  | 2020-03-10 | [6 empty] | 2020-04-09 | 2020-04-16 | [20 empty] | 2020-05-16 |  |  |  | 2020-05-19 | [8 empty] | 2020-03-25 |  | 2020-03-28 |  |  | 2020-04-09 |  |  |  | 2020-04-12 |  |  | 2020-04-19 |  |  |  | 2020-04-22 |  |  | 2020-05-07 |  |  |  | 2020-05-19 |  | 2020-05-22
PH1100177 | 125.5766 | 7.056 | Urban | Greenfield | Greenfield | Y1 | L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 6.9417 | MIN-1100108 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2020-01-22 | 2020-01-13 | 2020-01-24 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-01-25 |  |  |  | 2020-01-25 |  |  |  | 2020-01-29 | 2020-01-25 |  |  |  | 2020-01-25 | 2020-01-24 |  |  |  | 2020-01-24 |  | 2020-02-28 | [5 empty] | A |  |  |  | 125.5748 | 7.056 | Rooftop | 39m | 12m | [13 empty] | 2020-03-06 | 2020-02-19 |  | 2020-04-05 |  | 2020-03-13 | [16 empty] | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 |  | 2020-03-30 |  |  | 2020-04-03 | 2020-02-28 | 2020-04-06 | 2020-02-29 | 2020-03-03 | 2020-04-20 |  |  |  | 2020-04-27 |  | ZCG-12-340D-1NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1100178 | 125.5447 | 7.049 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402116 | 59678 | 30 | Three Legged Tubular Tower | CO66 | 10.2115 | MIN-1100109 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 | DepEd_3230 | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-01-16 | 2020-01-14 | 2020-01-18 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-23 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-24 | 2020-02-22 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Melita Lagumbay | Blk 6, Lot 2 St., JS Francisco Village, Talomo, Davao City | Davao del Sur | 125.5458 | 7.0485 | Greenfield | 20m |  | 15 years | P25,000 exclusive of VAT and withholding tax | quarterly | 200sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-29 | 2020-02-04 |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 |  | 2020-03-24 |  |  | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-14 |  |  |  | 2020-04-21 |  | DGT-30-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1100180 | 125.5954 | 7.0595 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 5.2799 | MIN-1100110 | Level 2 (Davao City) - U | phase3 | phase3 | P1_630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD |  | Gaskie |  | 2019-12-13 | 2019-12-21 | 2019-12-21 | 2019-12-23 | 2019-12-22 | 2019-12-30 | 2020-01-13 |  | 2019-12-22 | 2019-12-23 | 2020-01-05 |  |  | 2019-12-23 |  |  |  | 2019-12-28 |  | 2020-01-03 |  |  | 2020-01-03 | 2019-12-22 | 2019-12-30 | 2020-01-13 |  | 2019-12-22 | 2020-02-24 | 2020-01-27 | [5 empty] | A | Paul Borromeo | 13 Juna Subdivision, Matina, Davao City | Davao del Sur | 125.594 | 7.0604 | Rooftop |  | 15m | 15 years | P35,000 inclusive of VAT and withholding tax | monthly | 250sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-23 | n/a |  |  |  | n/a | 2020-02-03 | 2020-01-09 |  | 2020-03-04 | 2020-03-06 | 2020-02-10 | 2020-01-22 |  | 2020-01-22 | [13 empty] | 2020-03-02 |  |  | 2020-03-11 | [6 empty] | 2020-03-25 |  |  |  | 2020-03-25 |  |  |  | Awaiting MOC approval | 2020-02-17 |  | 2020-02-27 |  |  | 2020-03-02 | 2020-02-04 | 2020-03-05 | 2020-02-04 | 2020-02-05 | 2020-03-19 | 2020-02-10 |  |  | 2020-03-26 |  | ZCG-12-340D-1NPT |  |  | 2020-04-07 |  | 2020-03-16 | [6 empty] | 2020-04-15 | 2020-04-22 | [20 empty] | 2020-05-22 |  |  |  | 2020-05-25 | [8 empty] | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-04-25 |  |  |  | 2020-04-28 |  |  | 2020-05-13 |  |  |  | 2020-05-25 |  | 2020-05-28
PH1100181 | 125.5829 | 7.0596 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402061 | 59803 | 30 | Three Legged Tubular Tower | CO66 | 6.1653 | MIN-1100111 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-12 | 2020-04-19 | 2020-03-05 | 2020-04-21 | 2020-03-11 |  |  |  | 2020-03-11 | [8 empty] | 2020-04-26 | 2020-03-09 |  |  |  | 2020-03-09 | 2020-03-06 |  |  |  | 2020-03-06 |  | 2020-05-26 | [5 empty] | A |  |  |  | 125.5826 | 7.0601 | [16 empty] | 2020-06-02 |  |  | 2020-07-02 |  | 2020-06-09 | [16 empty] | 2020-06-30 |  |  | 2020-07-09 | [6 empty] | 2020-07-23 |  |  |  | 2020-07-23 |  |  |  |  | 2020-06-16 |  | 2020-06-26 |  |  | 2020-06-30 |  | 2020-07-03 |  |  | 2020-07-17 |  |  |  | 2020-07-24 |  | ZCG-12-340D-1NPT |  |  | 2020-08-05 |  | 2020-07-14 | [6 empty] | 2020-08-13 | 2020-08-20 | [20 empty] | 2020-09-19 |  |  |  | 2020-09-22 | [8 empty] | 2020-07-29 |  | 2020-08-01 |  |  | 2020-08-13 |  |  |  | 2020-08-16 |  |  | 2020-08-23 |  |  |  | 2020-08-26 |  |  | 2020-09-10 |  |  |  | 2020-09-22 |  | 2020-09-25
PH1100182 | 125.5703 | 7.0597 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 7.2107 | MIN-1100112 | Level 2 (Davao City) - U | phase3 | phase1_630 | P1_630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 | 2020-01-24 | 2020-01-29 |  | 2019-12-07 |  |  | 2020-02-07 |  | 2020-02-07 |  |  |  | 2019-12-13 |  |  | 2020-02-07 |  | 2020-02-07 | 2019-12-09 | 2020-01-24 | 2020-01-27 |  | 2019-12-09 |  | 2020-01-12 | [27 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 | 2020-02-21 | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100183 | 125.5578 | 7.0598 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402116 | 59678 | 30 | Three Legged Tubular Tower | CO66 | 8.355 | MIN-1100113 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 | Philcom_272 | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-27 | 2019-12-27 | 2019-12-29 | 2019-12-29 |  |  |  | 2019-12-29 | 2019-12-30 |  |  |  | 2019-12-30 |  |  |  | 2020-01-03 | [5 empty] | 2019-12-29 |  |  |  | 2019-12-29 |  | 2020-02-02 | [27 empty] | 2020-02-09 |  |  | 2020-03-10 |  | 2020-02-16 | [16 empty] | 2020-03-08 |  |  | 2020-03-17 | [6 empty] | 2020-03-31 |  |  |  | 2020-03-31 |  |  |  |  | 2020-02-23 |  | 2020-03-04 |  |  | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-25 |  |  |  | 2020-04-01 |  | ZCG-12-340D-1NPT |  |  | 2020-04-13 |  | 2020-03-22 | [6 empty] | 2020-04-21 | 2020-04-28 | [20 empty] | 2020-05-28 |  |  |  | 2020-05-31 | [8 empty] | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-01 |  |  |  | 2020-05-04 |  |  | 2020-05-19 |  |  |  | 2020-05-31 |  | 2020-06-03
PH1100184 | 125.5892 | 7.0632 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402061 | 59803 | 30 | Three Legged Tubular Tower | CO66 | 5.3958 | MIN-1100114 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-06 | 2020-01-08 | 2019-12-08 | 2020-01-09 |  |  |  | 2020-01-09 | 2020-01-09 |  |  |  | 2020-01-09 |  |  |  | 2019-12-13 | 2020-01-09 |  |  |  | 2020-01-09 | 2020-01-09 |  |  |  | 2020-01-09 |  | 2020-01-12 |  | y | MOC Submitted is Fritz Vilchez, Need to submit new MOC for approved Coordinates. |  |  | A |  |  |  | 125.5892 | 7.0635 | Greenfield | 14m | [14 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100185 | 125.5766 | 7.0633 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Matina Crossing | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 6.4175 | MIN-1100115 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2020-04-22 | 2020-03-06 | 2020-04-24 | 2020-03-11 |  |  |  | 2020-03-11 | [8 empty] | 2020-04-29 | [5 empty] | 2020-03-07 |  |  |  | 2020-03-07 |  | 2020-05-29 | [27 empty] | 2020-06-05 |  |  | 2020-07-05 |  | 2020-06-12 | [16 empty] | 2020-07-03 |  |  | 2020-07-12 | [6 empty] | 2020-07-26 |  |  |  | 2020-07-26 |  |  |  |  | 2020-06-19 |  | 2020-06-29 |  |  | 2020-07-03 |  | 2020-07-06 |  |  | 2020-07-20 |  |  |  | 2020-07-27 |  | ZCG-12-340D-1NPT |  |  | 2020-08-08 |  | 2020-07-17 | [6 empty] | 2020-08-16 | 2020-08-23 | [20 empty] | 2020-09-22 |  |  |  | 2020-09-25 | [8 empty] | 2020-08-01 |  | 2020-08-04 |  |  | 2020-08-16 |  |  |  | 2020-08-19 |  |  | 2020-08-26 |  |  |  | 2020-08-29 |  |  | 2020-09-13 |  |  |  | 2020-09-25 |  | 2020-09-28
PH1100186 | 125.5641 | 7.0633 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Talomo | MIN | PH112402075 | 32436 | 30 | Three Legged Tubular Tower | CO66 | 7.5553 | MIN-1100116 | Level 2 (Davao City) - U | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | [8 empty] | 2019-12-13 | [11 empty] | 2020-01-12 | [27 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | ZCG-12-340D-1NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100188 | 125.6077 | 7.0663 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Barangay 10-A | MIN | PH112402136 | 370 | 30 | Three Legged Tubular Tower | CO66 | 3.949 | MIN-1100117 | Level 2 (Davao City) - U | phase3 | phase2_1231 | First Call |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | MJV |  | 2019-12-12 | 2019-12-27 | 2019-12-27 | 2019-12-29 | 2019-12-29 |  |  | 2020-02-12 | 2019-12-29 | 2019-12-30 |  |  | 2020-02-13 | 2019-12-30 |  |  |  | 2020-01-03 |  |  |  | 2020-02-13 | 2020-02-13 | 2019-12-29 | 2020-02-05 |  | 2020-02-12 | 2019-12-29 | 2020-02-21 | 2020-02-02 | [5 empty] | D | Enrico Valencia | 2-B San Pedro City Hall, Davao City | Davao del Sur | 125.6076 | 7.0649 | Greenfield |  |  | 5 years | P35,000 inclusive of VAT and withholding tax | quarterly | 250sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-09 | 2020-02-14 |  | 2020-03-10 |  | 2020-02-16 | [16 empty] | 2020-03-08 |  |  | 2020-03-17 | [6 empty] | 2020-03-31 |  |  |  | 2020-03-31 |  |  |  |  | 2020-02-23 | 2020-02-12 | 2020-03-04 | 2020-02-10 | 2020-02-28 | 2020-03-08 | 2020-02-12 | 2020-03-11 | 2020-02-14 | 2020-02-15 | 2020-03-25 | 2020-02-12 | 2020-02-12 | 2020-02-12 | 2020-04-01 | 2020-02-28 | DGT-30-340C-2NPT |  |  | 2020-04-13 |  | 2020-03-22 | [6 empty] | 2020-04-21 | 2020-04-28 | [20 empty] | 2020-05-28 |  |  |  | 2020-05-31 | [7 empty] | 2020-02-26 | 2020-04-06 | 2020-03-02 | 2020-04-09 | 2020-03-02 |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-01 |  |  |  | 2020-05-04 |  |  | 2020-05-19 |  |  |  | 2020-05-31 |  | 2020-06-03
PH1100192 | 125.6143 | 7.0703 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Agdao | MIN | PH112402165 | 1985 | 30 | Three Legged Tubular Tower | CO66 | 3.2773 | MIN-1100118 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-12 | 2020-04-10 | 2020-01-27 | 2020-04-12 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-01-31 |  |  |  | 2020-01-31 |  |  |  | 2020-04-17 | 2020-01-31 |  |  |  | 2020-01-31 | [6 empty] | 2020-05-17 | [5 empty] | A |  |  |  | 125.6131 | 7.0693 | [16 empty] | 2020-05-24 |  |  | 2020-06-23 |  | 2020-05-31 | [16 empty] | 2020-06-21 |  |  | 2020-06-30 | [6 empty] | 2020-07-14 |  |  |  | 2020-07-14 |  |  |  |  | 2020-06-07 |  | 2020-06-17 |  |  | 2020-06-21 | 2020-03-10 | 2020-06-24 | 2020-03-12 |  | 2020-07-08 |  |  |  | 2020-07-15 |  | DGT-30-340C-2NPT |  |  | 2020-07-27 |  | 2020-07-05 | [6 empty] | 2020-08-04 | 2020-08-11 | [20 empty] | 2020-09-10 |  |  |  | 2020-09-13 | [8 empty] | 2020-07-20 |  | 2020-07-23 |  |  | 2020-08-04 |  |  |  | 2020-08-07 |  |  | 2020-08-14 |  |  |  | 2020-08-17 |  |  | 2020-09-01 |  |  |  | 2020-09-13 |  | 2020-09-16
PH1100196 | 125.6207 | 7.0739 | Urban | Greenfield | Greenfield | Y1 | L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Leon Garcia, Sr. | MIN | PH112402161 | 2270 | 30 | Three Legged Tubular Tower | CO66 | 2.7548 | MIN-1100119 | Level 2 (Davao City) - U | phase3 | phase1_630 | P1_630 | DepEd_3328 | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-12-12 | 2019-12-17 | 2019-12-17 | 2019-12-19 | [13 empty] | 2019-12-24 | [11 empty] | 2020-01-23 | [27 empty] | 2020-01-30 |  |  | 2020-02-29 |  | 2020-02-06 | [16 empty] | 2020-02-27 |  |  | 2020-03-07 | [6 empty] | 2020-03-21 |  |  |  | 2020-03-21 |  |  |  |  | 2020-02-13 |  | 2020-02-23 |  |  | 2020-02-27 |  | 2020-03-01 |  |  | 2020-03-15 |  |  |  | 2020-03-22 |  | DGT-30-340C-2NPT |  |  | 2020-04-03 |  | 2020-03-12 | [6 empty] | 2020-04-11 | 2020-04-18 | [20 empty] | 2020-05-18 |  |  |  | 2020-05-21 | [8 empty] | 2020-03-27 |  | 2020-03-30 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-09 |  |  |  | 2020-05-21 |  | 2020-05-24
PH1100197 | 125.6081 | 7.0739 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Barangay 19-B | MIN | PH112402142 | 5698 | 30 | Three Legged Tubular Tower | CO66 | 3.1826 | MIN-1100120 | Level 2 (Davao City) - U | phase3 | phase1_630 | P1_630 | DepEd_3442 | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-12-12 | 2019-12-17 | 2019-12-17 | 2019-12-19 | 2020-01-07 |  |  |  | 2020-01-07 | 2020-03-04 |  |  |  | 2020-03-04 |  |  |  | 2019-12-24 | 2020-03-04 |  |  |  | 2020-03-04 | 2020-01-07 |  |  |  | 2020-01-07 |  | 2020-01-23 | [5 empty] | A |  |  |  | 125.6078 | 7.0743 | [16 empty] | 2020-01-30 |  |  | 2020-02-29 |  | 2020-02-06 | [16 empty] | 2020-02-27 |  |  | 2020-03-07 | [6 empty] | 2020-03-21 |  |  |  | 2020-03-21 |  |  |  |  | 2020-02-13 |  | 2020-02-23 |  |  | 2020-02-27 |  | 2020-03-01 |  |  | 2020-03-15 |  |  |  | 2020-03-22 |  | DGT-30-340C-2NPT |  |  | 2020-04-03 |  | 2020-03-12 | [6 empty] | 2020-04-11 | 2020-04-18 | [20 empty] | 2020-05-18 |  |  |  | 2020-05-21 | [8 empty] | 2020-03-27 |  | 2020-03-30 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-09 |  |  |  | 2020-05-21 |  | 2020-05-24
PH1100198 | 125.6143 | 7.0775 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Wilfredo Aquino | MIN | PH112402146 | 427 | 30 | Three Legged Tubular Tower | CO66 | 2.5146 | MIN-1100121 | Level 2 (Davao City) - U | phase3 | phase1_630 | P1_630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-12-12 | 2019-12-26 | 2019-12-26 | 2019-12-28 | 2019-12-27 |  |  |  | 2019-12-27 | 2019-12-28 |  |  |  | 2019-12-28 |  |  |  | 2020-01-02 | [5 empty] | 2019-12-27 |  |  |  | 2019-12-27 |  | 2020-02-01 | [27 empty] | 2020-02-08 |  |  | 2020-03-09 |  | 2020-02-15 | [16 empty] | 2020-03-07 |  |  | 2020-03-16 | [6 empty] | 2020-03-30 |  |  |  | 2020-03-30 |  |  |  |  | 2020-02-22 |  | 2020-03-03 |  |  | 2020-03-07 |  | 2020-03-10 |  |  | 2020-03-24 |  |  |  | 2020-03-31 |  | DGT-30-340C-2NPT |  |  | 2020-04-12 |  | 2020-03-21 | [6 empty] | 2020-04-20 | 2020-04-27 | [20 empty] | 2020-05-27 |  |  |  | 2020-05-30 | [8 empty] | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-18 |  |  |  | 2020-05-30 |  | 2020-06-02
PH1100199 | 125.6039 | 7.0811 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | n.a. ( 39395) | MIN | PH112402143 | 6764 | 30 | Three Legged Tubular Tower | CO66 | 2.8337 | MIN-1100122 | Level 2 (Davao City) - U | phase2_add | phase1_630 | P1_630 |  | Cluster M05 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2019-12-17 | 2019-12-17 | 2019-12-19 | 2019-12-27 | 2020-01-13 |  |  | 2019-12-27 | 2019-12-28 |  |  |  | 2019-12-28 |  |  |  | 2019-12-24 | [5 empty] | 2019-12-27 | 2020-01-13 |  |  | 2019-12-27 |  | 2020-01-23 | [27 empty] | 2020-01-30 |  |  | 2020-02-29 |  | 2020-02-06 | [16 empty] | 2020-02-27 |  |  | 2020-03-07 | [6 empty] | 2020-03-21 |  |  |  | 2020-03-21 |  |  |  |  | 2020-02-13 |  | 2020-02-23 |  |  | 2020-02-27 |  | 2020-03-01 |  |  | 2020-03-15 |  |  |  | 2020-03-22 |  | DGT-30-340C-2NPT |  |  | 2020-04-03 |  | 2020-03-12 | [6 empty] | 2020-04-11 | 2020-04-18 | [20 empty] | 2020-05-18 |  |  |  | 2020-05-21 | [8 empty] | 2020-03-27 |  | 2020-03-30 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-09 |  |  |  | 2020-05-21 |  | 2020-05-24
PH1100200 | 125.6164 | 7.0811 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Wilfredo Aquino | MIN | PH112402148 | 2891 | 30 | Three Legged Tubular Tower | CO66 | 2.0588 | MIN-1100123 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-17 | 2019-12-17 | 2019-12-19 | [13 empty] | 2019-12-24 | [11 empty] | 2020-01-23 | [27 empty] | 2020-01-30 |  |  | 2020-02-29 |  | 2020-02-06 | [16 empty] | 2020-02-27 |  |  | 2020-03-07 | [6 empty] | 2020-03-21 |  |  |  | 2020-03-21 |  |  |  |  | 2020-02-13 |  | 2020-02-23 |  |  | 2020-02-27 |  | 2020-03-01 |  |  | 2020-03-15 |  |  |  | 2020-03-22 |  | ZCG-12-340D-1NPT |  |  | 2020-04-03 |  | 2020-03-12 | [6 empty] | 2020-04-11 | 2020-04-18 | [20 empty] | 2020-05-18 |  |  |  | 2020-05-21 | [8 empty] | 2020-03-27 |  | 2020-03-30 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-09 |  |  |  | 2020-05-21 |  | 2020-05-24
PH1100202 | 125.6143 | 7.0847 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Wilfredo Aquino | MIN | PH112402151 | 1832 | 30 | Three Legged Tubular Tower | CO66 | 1.7929 | MIN-1100124 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2020-01-09 |  |  |  | 2020-01-09 | 2020-03-06 |  |  |  | 2020-03-06 |  |  |  | 2019-12-25 | 2020-03-06 |  |  |  | 2020-03-06 | 2020-01-09 |  |  |  | 2020-01-09 |  | 2020-01-24 | [5 empty] | A |  |  |  | 125.6139 | 7.0845 | [16 empty] | 2020-01-31 |  |  | 2020-03-01 |  | 2020-02-07 | [16 empty] | 2020-02-28 |  |  | 2020-03-08 | [6 empty] | 2020-03-22 |  |  |  | 2020-03-22 |  |  |  |  | 2020-02-14 |  | 2020-02-24 |  |  | 2020-02-28 |  | 2020-03-02 |  |  | 2020-03-16 |  |  |  | 2020-03-23 |  | ZCG-12-340D-1NPT |  |  | 2020-04-04 |  | 2020-03-13 | [6 empty] | 2020-04-12 | 2020-04-19 | [20 empty] | 2020-05-19 |  |  |  | 2020-05-22 | [8 empty] | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-10 |  |  |  | 2020-05-22 |  | 2020-05-25
PH1100205 | 125.6206 | 7.0883 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Ubalde | MIN | PH112402181 | 8816 | 30 | Three Legged Tubular Tower | CO66 | 1.1573 | MIN-1100125 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | MJV |  | 2019-12-12 | 2019-12-16 | 2019-12-16 | 2019-12-18 | 2019-12-17 | 2020-02-18 |  |  | 2019-12-17 | 2019-12-18 | 2020-02-21 |  |  | 2019-12-18 |  |  |  | 2019-12-23 |  | 2020-02-22 |  |  | 2020-02-22 | 2019-12-17 | 2020-02-18 |  |  | 2019-12-17 | 2019-12-23 | 2020-01-22 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-22 | B | Carl Olano | Subrecarey, Sta. Ana Ave., Davao City | Davao del Sur | 125.6203 | 7.0896 | Rooftop | 23m | 15m | 15 years | P34,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | n/a | [6 empty] | 2020-01-29 | 2020-02-26 |  | 2020-02-28 |  | 2020-02-05 | [16 empty] | 2020-02-26 |  |  | 2020-03-06 | [6 empty] | 2020-03-20 |  |  |  | 2020-03-20 |  |  |  |  | 2020-02-12 |  | 2020-02-22 |  |  | 2020-02-26 | 2020-03-06 | 2020-02-29 | 2020-03-10 |  | 2020-03-14 |  |  |  | 2020-03-21 |  | ZCG-9-340D-1NPT |  |  | 2020-04-02 |  | 2020-03-11 | [6 empty] | 2020-04-10 | 2020-04-17 | [20 empty] | 2020-05-17 |  |  |  | 2020-05-20 | [7 empty] | 2020-02-28 | 2020-03-26 |  | 2020-03-29 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-05-08 |  |  |  | 2020-05-20 |  | 2020-05-23
PH1100208 | 125.6269 | 7.0919 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Centro (San Juan) | MIN | PH112402196 | 9903 | 30 | Three Legged Tubular Tower | CO66 | 0.87899 | MIN-1100126 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 | DepEd_3327 | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 |  | 2019-12-09 |  |  | 2019-12-09 |  |  |  | 2019-12-13 |  | 2019-12-09 |  |  | 2019-12-09 | [6 empty] | 2020-01-12 | [5 empty] | B |  |  |  | 125.6266 | 7.0912 | [16 empty] | 2020-01-19 | 2020-01-14 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 | 2020-03-02 | 2020-02-19 | 2020-03-10 | 2020-03-10 | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100211 | 125.6207 | 7.0955 | Urban | Greenfield | Greenfield | Y1 | L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Rafael Castillo | MIN | PH112402181 | 8816 | 30 | Three Legged Tubular Tower | CO66 | 0.39862 | MIN-1100127 | Level 2 (Davao City) - U | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2019-12-13 | 2019-12-13 | 2019-12-15 | 2020-01-10 | 2020-02-07 |  |  | 2020-01-10 | 2020-01-12 |  |  |  | 2020-01-12 |  |  |  | 2019-12-20 | 2020-01-12 | 2020-02-09 |  |  | 2020-01-12 | 2020-01-10 | 2020-02-07 |  |  | 2020-01-10 |  | 2020-01-19 |  | y | Above Lease Cap, Need to Renego or Change candidates |  |  | A |  |  |  | 125.6207 | 7.0969 | Greenfield | 71m | [14 empty] | 2020-01-26 |  |  | 2020-02-25 |  | 2020-02-02 | [16 empty] | 2020-02-23 |  |  | 2020-03-03 | [6 empty] | 2020-03-17 |  |  |  | 2020-03-17 |  |  |  |  | 2020-02-09 |  | 2020-02-19 |  |  | 2020-02-23 |  | 2020-02-26 |  |  | 2020-03-11 |  |  |  | 2020-03-18 |  | DGT-30-340C-2NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [8 empty] | 2020-03-23 |  | 2020-03-26 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100212 | 125.6081 | 7.0956 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 1.6324 | MIN-1100128 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-11 | 2019-12-11 | 2019-12-13 | 2020-01-03 |  |  |  | 2020-01-03 | 2020-01-04 |  |  |  | 2020-01-04 |  |  |  | 2019-12-18 | 2020-02-19 |  |  |  | 2020-02-19 | 2020-01-03 |  |  |  | 2020-01-03 | 2020-02-24 | 2020-01-17 | [6 empty] | Nena Cahucom | SAN ANTONIO KLM 4, BUHANGIN 19-B, BAJADA, DAVAO CITY | Davao del Sur | 125.6097 | 7.0946 | Rooftop |  |  | 15 years | P35,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-24 | 2020-03-04 |  | 2020-02-23 |  | 2020-01-31 | [16 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  |  | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 |  | 2020-02-24 |  |  | 2020-03-09 |  |  |  | 2020-03-16 |  | DGT-30-340C-2NPT |  |  | 2020-03-28 |  | 2020-03-06 | [6 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [8 empty] | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100213 | 125.627 | 7.0991 | Urban | Greenfield | Greenfield | Y1 | L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Rafael Castillo | MIN | PH112402196 | 9903 | 30 | Three Legged Tubular Tower | CO66 | 0.48182 | MIN-1100129 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630_First Call |  | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | RW |  | MJV |  | 2019-11-27 | 2019-12-13 | 2019-12-13 | 2019-12-15 | 2020-01-07 |  |  |  | 2020-01-07 | 2020-01-08 |  |  |  | 2020-01-08 |  |  |  | 2019-12-20 | 2020-01-08 |  |  |  | 2020-01-08 | 2020-01-07 |  |  |  | 2020-01-07 |  | 2020-01-19 |  | y | MOC Submitted is Melvin Suganan, Need to submit new MOC for approved Coordinates. |  |  | A |  |  |  | 125.6272 | 7.0992 | Rooftop | 41m | 20m | [13 empty] | 2020-01-26 |  |  | 2020-02-25 |  | 2020-02-02 | [16 empty] | 2020-02-23 |  |  | 2020-03-03 | [6 empty] | 2020-03-17 |  |  |  | 2020-03-17 |  |  |  |  | 2020-02-09 |  | 2020-02-19 |  |  | 2020-02-23 | 2020-01-13 | 2020-02-26 | 2020-01-13 | 2020-01-14 | 2020-03-11 | 2020-01-21 | 2020-01-27 |  | 2020-03-18 |  | ZCG-9-340D-1NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [8 empty] | 2020-03-23 |  | 2020-03-26 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100215 | 125.6144 | 7.0992 | Urban | Greenfield | Greenfield | Y1 | L21+L26 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 0.90824 | MIN-1100130 | Level 2 (Davao City) - U | phase3 | phase2_1231 | P1_630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD |  | MJV |  | 2019-12-12 | 2019-12-21 | 2019-12-21 | 2019-12-23 | 2019-12-22 |  |  |  | 2019-12-22 | 2019-12-23 |  |  |  | 2019-12-23 |  |  |  | 2019-12-28 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-22 |  |  |  | 2019-12-22 | 2020-01-10 | 2020-01-27 | [5 empty] | A | Vincent C. Manalili | KM5, Buhangin, Davao City | Davao del Sur | 125.6144 | 7.0998 | Rooftop | 30m | 6m | 15 years | P35,000 exclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-03 |  |  | 2020-03-04 |  | 2020-02-10 | [16 empty] | 2020-03-02 |  |  | 2020-03-11 | [6 empty] | 2020-03-25 |  |  |  | 2020-03-25 |  |  |  |  | 2020-02-17 |  | 2020-02-27 |  |  | 2020-03-02 |  | 2020-03-05 |  |  | 2020-03-19 |  |  |  | 2020-03-26 |  | ZCG-12-340D-1NPT |  |  | 2020-04-07 |  | 2020-03-16 | [6 empty] | 2020-04-15 | 2020-04-22 | [20 empty] | 2020-05-22 |  |  |  | 2020-05-25 | [8 empty] | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-04-25 |  |  |  | 2020-04-28 |  |  | 2020-05-13 |  |  |  | 2020-05-25 |  | 2020-05-28
PH1100217 | 125.6333 | 7.1027 | Urban | Greenfield | Greenfield | Y1 | L21+L26+NR | Davao Region (Region XI) | Davao Del Sur | Davao City | Pampanga | MIN | PH112402197 | 13539 | 30 | Three Legged Tubular Tower | CO66 | 1.2619 | MIN-1100131 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-04-11 | 2020-01-08 | 2020-04-13 | [13 empty] | 2020-04-18 | [11 empty] | 2020-05-18 | [27 empty] | 2020-05-25 | 2020-01-14 |  | 2020-06-24 |  | 2020-06-01 | [16 empty] | 2020-06-22 |  |  | 2020-07-01 | [6 empty] | 2020-07-15 |  |  |  | 2020-07-15 |  |  |  |  | 2020-06-08 |  | 2020-06-18 |  |  | 2020-06-22 |  | 2020-06-25 |  |  | 2020-07-09 |  |  |  | 2020-07-16 |  | ZCG-12-340D-1NPT |  |  | 2020-07-28 |  | 2020-07-06 | [6 empty] | 2020-08-05 | 2020-08-12 | [20 empty] | 2020-09-11 |  |  |  | 2020-09-14 | [8 empty] | 2020-07-21 |  | 2020-07-24 |  |  | 2020-08-05 |  |  |  | 2020-08-08 |  |  | 2020-08-15 |  |  |  | 2020-08-18 |  |  | 2020-09-02 |  |  |  | 2020-09-14 |  | 2020-09-17
PH1100218 | 125.6207 | 7.1027 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 0.50376 | MIN-1100132 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2019-12-18 |  |  |  | 2019-12-18 | 2019-12-19 |  |  |  | 2019-12-19 |  |  |  | 2019-12-25 | [5 empty] | 2019-12-18 | 2020-02-11 |  |  | 2019-12-18 |  | 2020-01-24 | [27 empty] | 2020-01-31 |  |  | 2020-03-01 |  | 2020-02-07 | [16 empty] | 2020-02-28 |  |  | 2020-03-08 | [6 empty] | 2020-03-22 |  |  |  | 2020-03-22 |  |  |  |  | 2020-02-14 |  | 2020-02-24 |  |  | 2020-02-28 |  | 2020-03-02 |  |  | 2020-03-16 |  |  |  | 2020-03-23 |  | ZCG-12-340D-1NPT |  |  | 2020-04-04 |  | 2020-03-13 | [6 empty] | 2020-04-12 | 2020-04-19 | [20 empty] | 2020-05-19 |  |  |  | 2020-05-22 | [8 empty] | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-10 |  |  |  | 2020-05-22 |  | 2020-05-25
PH1100219 | 125.6082 | 7.1028 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 1.6645 | MIN-1100133 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M05 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-12 | 2020-04-13 |  | 2020-04-15 | [13 empty] | 2020-04-20 | [11 empty] | 2020-05-20 | [27 empty] | 2020-05-27 |  |  | 2020-06-26 |  | 2020-06-03 | [16 empty] | 2020-06-24 |  |  | 2020-07-03 | [6 empty] | 2020-07-17 |  |  |  | 2020-07-17 |  |  |  |  | 2020-06-10 |  | 2020-06-20 |  |  | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-11 |  |  |  | 2020-07-18 |  | ZCG-12-340D-1NPT |  |  | 2020-07-30 |  | 2020-07-08 | [6 empty] | 2020-08-07 | 2020-08-14 | [20 empty] | 2020-09-13 |  |  |  | 2020-09-16 | [8 empty] | 2020-07-23 |  | 2020-07-26 |  |  | 2020-08-07 |  |  |  | 2020-08-10 |  |  | 2020-08-17 |  |  |  | 2020-08-20 |  |  | 2020-09-04 |  |  |  | 2020-09-16 |  | 2020-09-19
PH1100220 | 125.6353 | 7.1064 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Pampanga | MIN | PH112402197 | 13539 | 30 | Three Legged Tubular Tower | CO66 | 1.6473 | MIN-1100134 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | First Call |  | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | RW |  | MJV |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 | 2019-12-12 | 2020-02-07 |  | 2019-12-07 | 2019-12-13 |  |  |  | 2019-12-13 |  |  |  | 2019-12-13 | 2020-01-09 |  |  |  | 2020-01-09 | 2019-12-09 | 2019-12-12 | 2020-02-07 |  | 2019-12-09 | 2020-02-05 | 2020-01-12 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-10 | A | Rey A. Masing | 208 San Francisco St., Liceralde Subd., Lanang, Davao City | Davao del Sur | 125.6337 | 7.1052 | Greenfield | 15m |  | 15 years | P30,000 exclusive of VAT and withholding tax | quarterly | 176sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-01-10 |  | 2020-02-18 | 2020-01-20 | 2020-01-26 | 2020-01-22 | 2020-01-22 | 2020-01-22 | [9 empty] | 208 Liceralde Village, Lanang, Davao City |  |  |  | 2020-02-16 | ok |  | 2020-02-25 | [6 empty] | 2020-03-10 |  | 2020-02-11 | 2020-02-17 | 2020-03-10 | 2020-02-24 | 2020-02-27 | 2020-02-28 | Cheque released | 2020-02-02 | 2020-01-16 | 2020-02-12 | 2020-01-27 | 2020-01-27 | 2020-02-16 | 2020-01-13 | 2020-02-19 | 2020-01-13 | 2020-01-14 | 2020-03-04 | 2020-01-21 | 2020-01-22 | 2020-01-20 | 2020-03-11 | 2020-01-30 | JGT-36-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | 2020-01-29 | [5 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [7 empty] | 2020-01-21 | 2020-03-16 | 2020-01-22 | 2020-03-19 | 2020-02-12 | 2020-02-16 | 2020-03-31 | 2020-02-17 |  | 2020-02-20 | 2020-04-03 | 2020-02-29 |  | 2020-04-10 | 2020-03-03 |  |  | 2020-04-13 |  | 2020-03-06 | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100221 | 125.6145 | 7.1064 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Buhangin | MIN | PH112402021 | 65461 | 30 | Three Legged Tubular Tower | CO66 | 1.2558 | MIN-1100135 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-09 | 2019-12-09 | 2019-12-11 | 2020-02-28 | 2020-01-03 |  |  | 2020-01-03 |  | 2020-02-25 |  |  | 2020-02-25 |  |  |  | 2019-12-16 |  | 2020-02-25 |  |  | 2020-02-25 | 2019-12-10 | 2020-01-03 |  |  | 2019-12-10 |  | 2020-01-15 | [9 empty] | 125.6148 | 7.1073 | [16 empty] | 2020-01-22 | 2020-03-04 |  | 2020-02-21 |  | 2020-01-29 | [16 empty] | 2020-02-19 |  |  | 2020-02-28 | [6 empty] | 2020-03-13 |  |  |  | 2020-03-13 |  |  |  |  | 2020-02-05 |  | 2020-02-15 |  |  | 2020-02-19 |  | 2020-02-22 |  |  | 2020-03-07 |  |  |  | 2020-03-14 |  | ZCG-12-340D-1NPT |  |  | 2020-03-26 |  | 2020-03-04 | [6 empty] | 2020-04-03 | 2020-04-10 | [20 empty] | 2020-05-10 |  |  |  | 2020-05-13 | [8 empty] | 2020-03-19 |  | 2020-03-22 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-05-01 |  |  |  | 2020-05-13 |  | 2020-05-16
PH1100226 | 125.6484 | 7.1142 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402198 | 11265 | 30 | Three Legged Tubular Tower | CO66 | 3.3275 | MIN-1100136 | Level 2 (Davao City) - U | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2019-12-18 | 2019-12-18 | 2019-12-20 | 2019-12-18 |  |  |  | 2019-12-18 | [8 empty] | 2019-12-25 | [5 empty] | 2019-12-18 |  |  |  | 2019-12-18 |  | 2020-01-24 | [27 empty] | 2020-01-31 |  |  | 2020-03-01 |  | 2020-02-07 | [16 empty] | 2020-02-28 |  |  | 2020-03-08 | [6 empty] | 2020-03-22 |  |  |  | 2020-03-22 |  |  |  |  | 2020-02-14 |  | 2020-02-24 |  |  | 2020-02-28 |  | 2020-03-02 |  |  | 2020-03-16 |  |  |  | 2020-03-23 |  | ZCG-12-340D-1NPT |  |  | 2020-04-04 |  | 2020-03-13 | [6 empty] | 2020-04-12 | 2020-04-19 | [20 empty] | 2020-05-19 |  |  |  | 2020-05-22 | [8 empty] | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-10 |  |  |  | 2020-05-22 |  | 2020-05-25
PH1100227 | 125.6308 | 7.1129 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402197 | 13539 | 30 | Three Legged Tubular Tower | CO66 | 1.8382 | MIN-1100137 | Level 2 (Davao City) - U | phase2_add | phase2_1231 | PO Issued not 630 | DepEd_3463 | Cluster M04 | JXD | PO2019121801PH_WLS | Proposed PO 2 |  |  |  |  | 2019-11-27 | 2020-04-14 |  | 2020-04-16 | [13 empty] | 2020-04-21 | [11 empty] | 2020-05-21 | [27 empty] | 2020-05-28 |  |  | 2020-06-27 |  | 2020-06-04 | [16 empty] | 2020-06-25 |  |  | 2020-07-04 | [6 empty] | 2020-07-18 |  |  |  | 2020-07-18 |  |  |  |  | 2020-06-11 |  | 2020-06-21 |  |  | 2020-06-25 |  | 2020-06-28 |  |  | 2020-07-12 |  |  |  | 2020-07-19 |  | ZCG-12-340D-1NPT |  |  | 2020-07-31 |  | 2020-07-09 | [6 empty] | 2020-08-08 | 2020-08-15 | [20 empty] | 2020-09-14 |  |  |  | 2020-09-17 | [8 empty] | 2020-07-24 |  | 2020-07-27 |  |  | 2020-08-08 |  |  |  | 2020-08-11 |  |  | 2020-08-18 |  |  |  | 2020-08-21 |  |  | 2020-09-05 |  |  |  | 2020-09-17 |  | 2020-09-20
PH1100228 | 125.6381 | 7.1153 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402198 | 11265 | 30 | Three Legged Tubular Tower | CO66 | 2.5295 | MIN-1100138 | Level 2 (Davao City) - U | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2020-04-17 | 2020-01-05 | 2020-04-19 | 2020-01-06 |  |  |  | 2020-01-06 | 2020-01-08 |  |  |  | 2020-01-08 |  |  |  | 2020-04-24 | 2020-02-25 |  |  |  | 2020-02-25 | 2020-01-06 |  |  |  | 2020-01-06 | 2020-03-12 | 2020-05-24 | 2020-03-12 |  |  | 2020-03-12 |  |  | STEWART MADRANGCA | 80 BELIN ROAD, PAMPANGA, SASA, DAVAO CITY | Davao Del Sur | 125.6407 | 7.1162 | Rooftop |  |  | 15 years | P35,000 Inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-31 | 2020-03-04 |  | 2020-06-30 |  | 2020-06-07 | [16 empty] | 2020-06-28 |  |  | 2020-07-07 | [6 empty] | 2020-07-21 |  |  |  | 2020-07-21 |  |  |  |  | 2020-06-14 |  | 2020-06-24 |  |  | 2020-06-28 |  | 2020-07-01 |  |  | 2020-07-15 |  |  |  | 2020-07-22 |  | ZCG-12-340D-1NPT |  |  | 2020-08-03 |  | 2020-07-12 | [6 empty] | 2020-08-11 | 2020-08-18 | [20 empty] | 2020-09-17 |  |  |  | 2020-09-20 | [8 empty] | 2020-07-27 |  | 2020-07-30 |  |  | 2020-08-11 |  |  |  | 2020-08-14 |  |  | 2020-08-21 |  |  |  | 2020-08-24 |  |  | 2020-09-08 |  |  |  | 2020-09-20 |  | 2020-09-23
PH1100229 | 125.6226 | 7.1172 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Communal | MIN | PH112402023 | 43758 | 30 | Three Legged Tubular Tower | CO66 | 2.0748 | MIN-1100139 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-26 | 2019-12-26 | 2019-12-28 | 2019-12-27 |  |  |  | 2019-12-27 | 2019-12-28 |  |  |  | 2019-12-28 |  |  |  | 2020-01-02 | 2020-03-06 |  |  |  | 2020-03-06 | 2019-12-27 |  |  |  | 2019-12-27 | 2020-03-13 | 2020-02-01 | 2020-03-13 |  |  | 2020-03-13 |  | B | JOSEPHINE DAUZ | BLK 1 LOT 22 PHASE 1 DIHO SUBD., CABANTIAN, BUHANGIN, DAVAO CITY | Davao Del Sur | 125.6245 | 7.1176 | Rooftop |  |  | 10 YEARS | P25,000 inclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-08 |  |  | 2020-03-09 |  | 2020-02-15 | [16 empty] | 2020-03-07 |  |  | 2020-03-16 | [6 empty] | 2020-03-30 |  |  |  | 2020-03-30 |  |  |  |  | 2020-02-22 |  | 2020-03-03 |  |  | 2020-03-07 |  | 2020-03-10 |  |  | 2020-03-24 |  |  |  | 2020-03-31 |  | ZCG-12-340D-1NPT |  |  | 2020-04-12 |  | 2020-03-21 | [6 empty] | 2020-04-20 | 2020-04-27 | [20 empty] | 2020-05-27 |  |  |  | 2020-05-30 | [8 empty] | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-18 |  |  |  | 2020-05-30 |  | 2020-06-02
PH1100231 | 125.6444 | 7.1189 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402086 | 14381 | 30 | Three Legged Tubular Tower | CO66 | 3.3008 | MIN-1100140 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2020-01-20 | 2020-01-13 | 2020-01-22 | 2020-01-23 | 2020-01-23 | 2020-02-28 |  | 2020-01-23 | 2020-01-24 |  |  |  | 2020-01-24 |  |  |  | 2020-01-27 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-01-23 | 2020-01-23 |  |  | 2020-01-23 | 2020-03-13 | 2020-02-26 | 2020-03-13 |  |  | 2020-03-13 |  | A | VERANIO DIGAL PACATANG | PHASE 7, SEVMOAN ST., DONA ASUNCION, PAMPANGA, LANANG, DAVAO CITY | Davao Del Sur | 125.6448 | 7.1173 | Greenfield | 20m |  | 10 years | P18,000 inclusive of VAT and withholding tax | quarterly | 100sqm | 3 months | 2 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-04 | 2020-02-28 |  | 2020-04-03 |  | 2020-03-11 | [16 empty] | 2020-04-01 |  |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  |  | 2020-03-18 |  | 2020-03-28 |  |  | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-18 |  |  |  | 2020-04-25 |  | DGT-30-340C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1100233 | 125.6361 | 7.1259 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402023 | 43758 | 30 | Three Legged Tubular Tower | CO66 | 3.3838 | MIN-1100141 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-04-20 | 2020-01-08 | 2020-04-22 | 2020-02-28 |  |  |  | 2020-02-28 | 2020-03-06 |  |  |  | 2020-03-06 |  |  |  | 2020-04-27 | 2020-03-06 |  |  |  | 2020-03-06 | 2020-02-28 |  |  |  | 2020-02-28 | 2020-03-13 | 2020-05-27 | 2020-03-13 |  |  | 2020-03-13 |  | A | MARIA CECILLA MENDOZA | LAVERNA SUBD., CABANTIAN, BUHANGIN, DAVAO CITY | Davao Del Sur | 125.6356 | 7.1244 | Rooftop |  |  | 10 years | P25,000 inclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-06-03 |  |  | 2020-07-03 |  | 2020-06-10 | [16 empty] | 2020-07-01 |  |  | 2020-07-10 | [6 empty] | 2020-07-24 |  |  |  | 2020-07-24 |  |  |  |  | 2020-06-17 |  | 2020-06-27 |  |  | 2020-07-01 |  | 2020-07-04 |  |  | 2020-07-18 |  |  |  | 2020-07-25 |  | ZCG-12-340D-1NPT |  |  | 2020-08-06 |  | 2020-07-15 | [6 empty] | 2020-08-14 | 2020-08-21 | [20 empty] | 2020-09-20 |  |  |  | 2020-09-23 | [8 empty] | 2020-07-30 |  | 2020-08-02 |  |  | 2020-08-14 |  |  |  | 2020-08-17 |  |  | 2020-08-24 |  |  |  | 2020-08-27 |  |  | 2020-09-11 |  |  |  | 2020-09-23 |  | 2020-09-26
PH1100234 | 125.6235 | 7.126 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Communal | MIN | PH112402023 | 43758 | 30 | Three Legged Tubular Tower | CO66 | 3.0517 | MIN-1100142 | Level 2 (Davao City) - U | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019121801PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2020-01-16 | 2020-01-13 | 2020-01-18 |  | 2020-01-15 |  |  | 2020-01-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-23 | 2020-01-16 |  |  |  | 2020-01-16 |  | 2020-01-15 |  |  | 2020-01-15 | 2020-02-21 | 2020-02-22 | 2020-03-13 |  |  | 2020-03-13 |  | A | Patrisio dela Pena | Blk 18 Lot 9, Country Vill Subd., Cabantian, Davao City | Davao del Sur | 125.6241 | 7.1244 | Greenfield | 46m |  | 15 years | P30,000 inclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-29 | 2020-02-28 |  | 2020-03-30 | 2020-03-09 | 2020-03-07 | [16 empty] | 2020-03-28 | ok |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  | Awaiting MOC approval | 2020-03-14 | 2020-03-11 | 2020-03-24 |  |  | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-14 |  |  |  | 2020-04-21 |  | DGT-30-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1100235 | 125.6298 | 7.1296 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Communal | MIN | PH112402023 | 43758 | 30 | Three Legged Tubular Tower | CO66 | 3.5379 | MIN-1100143 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-04-23 | 2020-01-16 | 2020-04-25 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-01-18 |  |  |  | 2020-01-18 |  |  |  | 2020-04-30 | 2020-01-18 |  |  |  | 2020-01-18 | 2020-01-17 |  |  |  | 2020-01-17 |  | 2020-05-30 | [5 empty] | A |  |  |  | 125.6298 | 7.1295 | Rooftop | 42m | 6m | [13 empty] | 2020-06-06 |  |  | 2020-07-06 |  | 2020-06-13 | [16 empty] | 2020-07-04 |  |  | 2020-07-13 | [6 empty] | 2020-07-27 |  |  |  | 2020-07-27 |  |  |  |  | 2020-06-20 |  | 2020-06-30 |  |  | 2020-07-04 |  | 2020-07-07 |  |  | 2020-07-21 |  |  |  | 2020-07-28 |  | ZCG-12-340D-1NPT |  |  | 2020-08-09 |  | 2020-07-18 | [6 empty] | 2020-08-17 | 2020-08-24 | [20 empty] | 2020-09-23 |  |  |  | 2020-09-26 | [8 empty] | 2020-08-02 |  | 2020-08-05 |  |  | 2020-08-17 |  |  |  | 2020-08-20 |  |  | 2020-08-27 |  |  |  | 2020-08-30 |  |  | 2020-09-14 |  |  |  | 2020-09-26 |  | 2020-09-29
PH1100239 | 125.6424 | 7.1367 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402101 | 52386 | 30 | Three Legged Tubular Tower | CO66 | 4.7711 | MIN-1100144 | Level 2 (Davao City) - U | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-04-26 | 2020-01-09 | 2020-04-28 | 2020-01-10 |  |  |  | 2020-01-10 | [8 empty] | 2020-05-03 | [5 empty] | 2020-01-10 |  |  |  | 2020-01-10 |  | 2020-06-02 | [27 empty] | 2020-06-09 |  |  | 2020-07-09 |  | 2020-06-16 | [16 empty] | 2020-07-07 |  |  | 2020-07-16 | [6 empty] | 2020-07-30 |  |  |  | 2020-07-30 |  |  |  |  | 2020-06-23 |  | 2020-07-03 |  |  | 2020-07-07 |  | 2020-07-10 |  |  | 2020-07-24 |  |  |  | 2020-07-31 |  | ZCG-12-340D-1NPT |  |  | 2020-08-12 |  | 2020-07-21 | [6 empty] | 2020-08-20 | 2020-08-27 | [20 empty] | 2020-09-26 |  |  |  | 2020-09-29 | [8 empty] | 2020-08-05 |  | 2020-08-08 |  |  | 2020-08-20 |  |  |  | 2020-08-23 |  |  | 2020-08-30 |  |  |  | 2020-09-02 |  |  | 2020-09-17 |  |  |  | 2020-09-29 |  | 2020-10-02
PH1100240 | 125.6517 | 7.1352 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402101 | 52386 | 30 | Three Legged Tubular Tower | CO66 | 5.185 | MIN-1100145 | Level 2 (Davao City) - U | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M04 | JXD | PO2019121801PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2019-11-27 | 2020-01-22 | 2020-01-13 | 2020-01-24 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-03-04 |  |  |  | 2020-03-04 |  |  |  | 2020-01-29 | 2020-03-04 |  |  |  | 2020-03-04 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-03-10 | 2020-02-28 | 2020-03-11 |  |  | 2020-03-10 | 2020-03-11 | A | JENNIFER S. DEL ROSARIO | BEL AIR HOMES SUBD., KM 11, SASA, DAVAO CITY | Davao Del Sur | 125.6497 | 7.1344 | Rooftop |  |  | 10 years | P30,000 exclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-06 |  |  | 2020-04-05 |  | 2020-03-13 | [16 empty] | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 |  | 2020-03-30 |  |  | 2020-04-03 | 2020-03-10 | 2020-04-06 | 2020-03-12 |  | 2020-04-20 |  |  |  | 2020-04-27 |  | DGT-30-340C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1100243 | 125.655 | 7.1439 | Urban | Greenfield | Greenfield | Y1 | L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402087 | 35806 | 30 | Three Legged Tubular Tower | CO66 | 6.1748 | MIN-1100146 | Level 2 (Davao City) - U | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-29 | 2019-12-29 | 2019-12-31 | 2019-12-30 |  |  |  | 2019-12-30 | [8 empty] | 2020-01-05 | [5 empty] | 2020-01-23 |  |  |  | 2020-01-23 | 2020-01-24 | 2020-02-04 | 2020-01-09 |  |  | 2020-01-10 | 2020-02-04 |  | Leo Belandoy | Lot 109, Brgy. Cannery, Polomolok | South Cotabato |  |  | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-11 |  |  | 2020-03-12 |  | 2020-02-18 | [16 empty] | 2020-03-10 |  |  | 2020-03-19 | [6 empty] | 2020-04-02 |  |  |  | 2020-04-02 |  |  |  |  | 2020-02-25 |  | 2020-03-06 |  |  | 2020-03-10 |  | 2020-03-13 |  |  | 2020-03-27 |  |  |  | 2020-04-03 |  | ZCG-12-340D-1NPT |  |  | 2020-04-15 |  | 2020-03-24 | [6 empty] | 2020-04-23 | 2020-04-30 | [20 empty] | 2020-05-30 |  |  |  | 2020-06-02 | [8 empty] | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-21 |  |  |  | 2020-06-02 |  | 2020-06-05
PH1100263 | 125.3673 | 6.7381 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Digos City | Aplaya | MIN | PH112403007 | 4959 | 40 | Three Legged Tubular Tower | CO66 | 49.0004 | MIN-1100147 | Level 4 (220) | phase1_220_20% | phase2_1231 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019121803PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2019-12-04 | 2019-12-04 | 2019-12-06 | 2019-12-05 | 2019-12-05 |  |  | 2019-12-05 |  | 2019-12-23 | 2019-12-22 |  | 2019-12-22 |  |  |  | 2019-12-11 | [5 empty] | 2019-12-02 |  |  |  | 2019-12-02 |  | 2020-01-10 | [27 empty] | 2020-01-17 | 2020-01-23 |  | 2020-02-16 |  | 2020-01-24 | [16 empty] | 2020-02-14 |  |  | 2020-02-23 | [6 empty] | 2020-03-08 |  |  |  | 2020-03-08 |  |  |  |  | 2020-01-31 |  | 2020-02-10 |  |  | 2020-02-14 |  | 2020-02-17 |  |  | 2020-03-02 |  |  |  | 2020-03-09 |  | JGT-36-340C-2NPT |  |  | 2020-03-21 |  | 2020-02-28 | [6 empty] | 2020-03-29 | 2020-04-05 | [20 empty] | 2020-05-05 |  |  |  | 2020-05-08 | [8 empty] | 2020-03-14 |  | 2020-03-17 |  |  | 2020-03-29 |  |  |  | 2020-04-01 |  |  | 2020-04-08 |  |  |  | 2020-04-11 |  |  | 2020-04-26 |  |  |  | 2020-05-08 |  | 2020-05-11
PH1100264 | 125.377 | 6.7436 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Digos City | Aplaya | MIN | PH112403001 | 18485 | 40 | Three Legged Tubular Tower | CO66 | 47.8796 | MIN-1100148 | Level 4 (220) | phase1_220_20% | phase2_1231 | P1_630 |  | Cluster M14 | EPC | PO2019121803PH_WLS | Batch 1 (333) | EPC |  | EPC |  | 2019-11-27 | 2019-11-30 | 2019-11-30 | 2019-12-02 | 2019-12-07 | 2020-02-05 |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-07 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-11-29 | 2019-12-02 |  |  | 2019-11-29 | 2020-01-20 | 2020-01-06 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-22 | A | Maha M. Cacananta | Chapter 4, Brgy. Aplaya, Digos City | Davao del Sur | 125.3773 | 6.7427 | Greenfield | 8m |  | 15 years | P15,000 exclusive of VAT and withholding tax | quarterly | 195sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-01-23 | n/a |  |  |  | n/a | 2020-01-13 | 2020-01-13 |  | 2020-02-12 | 2020-01-29 | 2020-01-20 | 2020-02-26 | 2020-03-02 | [14 empty] | 2020-02-10 | ok |  | 2020-02-19 | 2020-02-26 | [5 empty] | 2020-03-04 |  | 2020-02-20 | 2020-02-26 | 2020-03-04 | 2020-03-02 | 2020-03-09 | 2020-03-11 | Cheque released | 2020-01-27 | 2020-02-03 | 2020-02-06 | 2020-02-07 | 2020-02-07 | 2020-02-10 | 2020-01-31 | 2020-02-13 | 2020-01-31 | 2020-02-08 | 2020-02-27 | 2020-02-01 | 2020-02-04 | 2020-02-11 | 2020-03-05 | 2020-02-14 | JGT-36-340C-2NPT |  |  | 2020-03-17 |  | 2020-02-24 | 2020-02-11 | [5 empty] | 2020-03-25 | 2020-04-01 | [20 empty] | 2020-05-01 |  |  |  | 2020-05-04 | [7 empty] | 2020-01-30 | 2020-03-10 | 2020-01-31 | 2020-03-13 | 2020-02-20 | 2020-02-28 | 2020-03-25 | 2020-03-07 |  |  | 2020-03-28 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-22 |  |  |  | 2020-05-04 |  | 2020-05-07
PH1100266 | 125.4537 | 7.1932 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Calinan | MIN | PH112402026 | 23052 | 15 | Pole | CO66 | 21.4047 | MIN-1100149 | Level 3 (Davao City) - R | phase1_220_20% | phase2_1231 | PO Issued not 630 |  | Cluster M09 | JXD |  | Batch 2 (333) |  |  | JXD |  | 2020-01-15 | 2020-02-01 | 2020-01-17 | 2020-02-03 | 2020-01-22 | 2020-01-24 |  |  | 2020-01-22 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2020-02-08 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-22 | 2020-01-24 | 2020-01-24 |  | 2020-01-22 | 2020-02-24 | 2020-03-09 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | A | Gershwin S. Matsuo | Lot 7H, Calinan, Davao City | Davao del Sur | 125.4527 | 7.1929 | Greenfield | 206m |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-02-24 | n/a |  |  |  |  | 2020-03-16 | 2020-02-20 |  | 2020-04-15 | 2020-02-28 | 2020-03-23 | [11 empty] | 0917-3121868 |  |  |  |  | 2020-04-13 | ok |  | 2020-04-22 | [6 empty] | 2020-05-06 |  | 2020-03-04 | 2020-03-07 | 2020-05-06 | 2020-03-12 | 2020-03-10 | 2020-03-12 | Cheque released | 2020-03-30 | 2020-03-03 | 2020-04-09 |  |  | 2020-04-13 | 2020-02-29 | 2020-04-16 | 2020-03-02 | 2020-03-03 | 2020-04-30 |  |  |  | 2020-05-07 |  | JGT-30-340C-2NPT |  |  | 2020-05-19 |  | 2020-04-27 | [6 empty] | 2020-05-27 | 2020-06-03 | [20 empty] | 2020-07-03 |  |  |  | 2020-07-06 | [7 empty] | 2020-03-03 | 2020-05-12 |  | 2020-05-15 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-06 |  |  |  | 2020-06-09 |  |  | 2020-06-24 |  |  |  | 2020-07-06 |  | 2020-07-09
PH1100267 | 125.4668 | 7.1766 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Riverside | MIN | PH112402026 | 23052 | 15 | Pole | CO66 | 19.2604 | MIN-1100150 | Level 3 (Davao City) - R | phase1_220_20% | phase2_1231 | PO Issued not 630 |  | Cluster M09 | JXD |  | Batch 2 (333) |  |  | JXD |  | 2020-01-15 | 2020-02-04 | 2020-01-19 | 2020-02-06 | 2020-01-19 | 2020-01-20 | 2020-01-20 |  | 2020-01-19 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2020-02-11 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-20 | 2020-01-20 | 2020-01-20 |  | 2020-01-20 | 2020-03-06 | 2020-03-12 | 2020-03-06 |  |  | 2020-03-06 | 2020-03-06 | A | Manuel Yogue | Purok 22, Robello Compound, Calinan, Davao City | Davao del Sur | 125.4665 | 7.1763 | Greenfield | 186m |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-02-24 | n/a |  |  |  |  | 2020-03-19 | 2020-02-20 |  | 2020-04-18 | 2020-02-28 | 2020-03-26 | [16 empty] | 2020-04-16 | ok |  | 2020-04-25 | [6 empty] | 2020-05-09 |  | 2020-03-08 |  | 2020-05-09 |  |  |  | RFP submitted, ongoing review | 2020-04-02 | 2020-03-03 | 2020-04-12 |  |  | 2020-04-16 | 2020-02-29 | 2020-04-19 | 2020-03-02 | 2020-03-02 | 2020-05-03 |  |  |  | 2020-05-10 |  | JGT-36-340C-2NPT |  |  | 2020-05-22 |  | 2020-04-30 | [6 empty] | 2020-05-30 | 2020-06-06 | [20 empty] | 2020-07-06 |  |  |  | 2020-07-09 | [7 empty] | 2020-03-03 | 2020-05-15 |  | 2020-05-18 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-09 |  |  |  | 2020-06-12 |  |  | 2020-06-27 |  |  |  | 2020-07-09 |  | 2020-07-12
PH1100268 | 125.4956 | 7.1149 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Ula | MIN | PH112402127 | 15115 | 40 | Angular Steel Tower | CO66 | 14.1304 | MIN-1100151 | Level 3 (Davao City) - R | phase1_220_20% | phase2_1231 | PO Issued not 630 |  | Cluster M09 | JXD |  | Batch 2 (333) |  |  |  |  | 2020-01-15 | 2020-02-07 | 2020-01-20 | 2020-02-09 | 2020-01-22 | 2020-01-22 |  |  | 2020-01-22 | 2020-01-22 | 2020-01-22 |  |  | 2020-01-22 |  |  |  | 2020-02-14 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-24 | 2020-01-22 | 2020-01-22 |  | 2020-01-22 | 2020-03-06 | 2020-03-15 | 2020-03-07 |  |  | 2020-03-06 | 2020-03-07 | A | Lao Concordio | Purok 18, Upper Mintal Davao City | Davao del Sur | 125.4977 | 7.1049 | Greenfield | 157m |  | 10 years | P25,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-22 |  |  | 2020-04-21 |  | 2020-03-29 | [16 empty] | 2020-04-19 |  |  | 2020-04-28 | [6 empty] | 2020-05-12 |  |  |  | 2020-05-12 |  |  |  |  | 2020-04-05 |  | 2020-04-15 |  |  | 2020-04-19 |  | 2020-04-22 |  |  | 2020-05-06 |  |  |  | 2020-05-13 |  | JGT-36-340C-2NPT |  |  | 2020-05-25 |  | 2020-05-03 | [6 empty] | 2020-06-02 | 2020-06-09 | [20 empty] | 2020-07-09 |  |  |  | 2020-07-12 | [8 empty] | 2020-05-18 |  | 2020-05-21 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-12 |  |  |  | 2020-06-15 |  |  | 2020-06-30 |  |  |  | 2020-07-12 |  | 2020-07-15
PH1100271 | 125.4952 | 7.0364 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Lubogan | MIN | PH112402059 | 12156 | 40 | Three Legged Tubular Tower | CO66 | 15.6679 | MIN-1100152 | Level 3 (Davao City) - R | phase3 | phase2_1231 | P1_630 | DepEd_3423 | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-12 | 2019-12-24 | 2019-12-24 | 2019-12-26 | 2019-12-26 |  |  |  | 2019-12-26 | 2019-12-26 |  |  |  | 2019-12-26 |  |  |  | 2019-12-31 | 2019-12-27 |  |  |  | 2019-12-27 | 2019-12-26 |  |  |  | 2019-12-26 | 2020-01-24 | 2020-01-30 | 2020-01-10 |  |  | 2020-01-10 | 2020-02-04 | A | Buenaventura M. Barnes | Purok 19, Lubogan, Toril, Davao City | Davao del Sur | 125.4961 | 7.0367 | Greenfield | 54m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-23 | n/a |  |  |  | n/a | 2020-02-06 | 2020-01-06 |  | 2020-03-07 | 2020-01-22 | 2020-02-13 | 2020-01-24 |  | 2020-01-24 | [13 empty] | 2020-03-05 | ok |  | 2020-03-14 | 2020-02-26 | [5 empty] | 2020-03-28 |  | 2020-02-25 | 2020-03-03 | 2020-03-28 | 2020-03-05 | 2020-03-10 |  | Cheque released | 2020-02-20 | 2020-02-18 | 2020-03-01 | 2020-02-27 | 2020-02-27 | 2020-03-05 | 2020-01-30 | 2020-03-08 | 2020-01-30 | 2020-01-31 | 2020-03-22 | 2020-01-31 | 2020-02-01 | 2020-02-28 | 2020-03-29 | 2020-02-28 | JGT-36-340C-2NPT |  |  | 2020-04-10 |  | 2020-03-19 | 2020-02-11 | [5 empty] | 2020-04-18 | 2020-04-25 | [20 empty] | 2020-05-25 |  |  |  | 2020-05-28 | [8 empty] | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-18 |  |  |  | 2020-04-21 |  |  | 2020-04-28 |  |  |  | 2020-05-01 |  |  | 2020-05-16 |  |  |  | 2020-05-28 |  | 2020-05-31
PH1100277 | 125.5052 | 7.0868 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Mintal | MIN | PH112402079 | 13227 | 40 | Monopole Tower | CO66 | 13.0249 | MIN-1100153 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-14 | [5 empty] | 2019-12-08 |  |  |  | 2019-12-08 |  | 2020-01-13 | [27 empty] | 2020-01-20 |  |  | 2020-02-19 |  | 2020-01-27 | [16 empty] | 2020-02-17 |  |  | 2020-02-26 | [6 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  |  | 2020-02-03 |  | 2020-02-13 |  |  | 2020-02-17 |  | 2020-02-20 |  |  | 2020-03-05 |  |  |  | 2020-03-12 |  | JGT-36-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 | [20 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [8 empty] | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1100278 | 125.5051 | 7.0756 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Santo Nino | MIN | PH112402193 | 20103 | 40 | Angular Steel Tower | CO66 | 13.2151 | MIN-1100154 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M12 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2020-04-25 |  | 2020-04-27 | [13 empty] | 2020-05-02 | [11 empty] | 2020-06-01 | [27 empty] | 2020-06-08 |  |  | 2020-07-08 |  | 2020-06-15 | [16 empty] | 2020-07-06 |  |  | 2020-07-15 | [6 empty] | 2020-07-29 |  |  |  | 2020-07-29 |  |  |  |  | 2020-06-22 |  | 2020-07-02 |  |  | 2020-07-06 |  | 2020-07-09 |  |  | 2020-07-23 |  |  |  | 2020-07-30 |  | JGT-36-340C-2NPT |  |  | 2020-08-11 |  | 2020-07-20 | [6 empty] | 2020-08-19 | 2020-08-26 | [20 empty] | 2020-09-25 |  |  |  | 2020-09-28 | [8 empty] | 2020-08-04 |  | 2020-08-07 |  |  | 2020-08-19 |  |  |  | 2020-08-22 |  |  | 2020-08-29 |  |  |  | 2020-09-01 |  |  | 2020-09-16 |  |  |  | 2020-09-28 |  | 2020-10-01
PH1100280 | 125.505 | 7.042 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Baliok | MIN | PH112402010 | 16140 | 40 | Angular Steel Tower | CO66 | 14.4308 | MIN-1100155 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-04-10 | 2020-01-15 | 2020-04-12 | [13 empty] | 2020-04-17 | [11 empty] | 2020-05-17 | [27 empty] | 2020-05-24 |  |  | 2020-06-23 |  | 2020-05-31 | [16 empty] | 2020-06-21 |  |  | 2020-06-30 | [6 empty] | 2020-07-14 |  |  |  | 2020-07-14 |  |  |  |  | 2020-06-07 |  | 2020-06-17 |  |  | 2020-06-21 |  | 2020-06-24 |  |  | 2020-07-08 |  |  |  | 2020-07-15 |  | JGT-36-340C-2NPT |  |  | 2020-07-27 |  | 2020-07-05 | [6 empty] | 2020-08-04 | 2020-08-11 | [20 empty] | 2020-09-10 |  |  |  | 2020-09-13 | [8 empty] | 2020-07-20 |  | 2020-07-23 |  |  | 2020-08-04 |  |  |  | 2020-08-07 |  |  | 2020-08-14 |  |  |  | 2020-08-17 |  |  | 2020-09-01 |  |  |  | 2020-09-13 |  | 2020-09-16
PH1100282 | 125.4982 | 7.0214 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Toril | MIN | PH112402036 | 11490 | 15 | Pole | CO66 | 16.1958 | MIN-1100156 | Level 3 (Davao City) - R | phase1_220_20% | phase2_1231 | PO Issued not 630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-11-27 | 2020-04-13 | 2020-01-11 | 2020-04-15 | 2020-01-13 |  |  |  | 2020-01-13 | [8 empty] | 2020-04-20 | [5 empty] | 2020-01-13 |  |  |  | 2020-01-13 |  | 2020-05-20 | [27 empty] | 2020-05-27 |  |  | 2020-06-26 |  | 2020-06-03 | [16 empty] | 2020-06-24 |  |  | 2020-07-03 | [6 empty] | 2020-07-17 |  |  |  | 2020-07-17 |  |  |  |  | 2020-06-10 |  | 2020-06-20 |  |  | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-11 |  |  |  | 2020-07-18 |  | JGT-30-340C-2NPT |  |  | 2020-07-30 |  | 2020-07-08 | [6 empty] | 2020-08-07 | 2020-08-14 | [20 empty] | 2020-09-13 |  |  |  | 2020-09-16 | [8 empty] | 2020-07-23 |  | 2020-07-26 |  |  | 2020-08-07 |  |  |  | 2020-08-10 |  |  | 2020-08-17 |  |  |  | 2020-08-20 |  |  | 2020-09-04 |  |  |  | 2020-09-16 |  | 2020-09-19
PH1100283 | 125.4981 | 7.0102 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Toril | MIN | PH112402040 | 21124 | 40 | Monopole Tower | CO66 | 16.8949 | MIN-1100157 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-21 | 2019-12-21 | 2019-12-23 | 2020-01-16 |  |  |  | 2020-01-16 | [8 empty] | 2019-12-28 | [5 empty] | 2020-01-16 |  |  |  | 2020-01-16 |  | 2020-01-27 | [27 empty] | 2020-02-03 |  |  | 2020-03-04 |  | 2020-02-10 | [16 empty] | 2020-03-02 |  |  | 2020-03-11 | [6 empty] | 2020-03-25 |  |  |  | 2020-03-25 |  |  |  |  | 2020-02-17 |  | 2020-02-27 |  |  | 2020-03-02 |  | 2020-03-05 |  |  | 2020-03-19 |  |  |  | 2020-03-26 |  | JGT-36-340C-2NPT |  |  | 2020-04-07 |  | 2020-03-16 | [6 empty] | 2020-04-15 | 2020-04-22 | [20 empty] | 2020-05-22 |  |  |  | 2020-05-25 | [8 empty] | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-04-25 |  |  |  | 2020-04-28 |  |  | 2020-05-13 |  |  |  | 2020-05-25 |  | 2020-05-28
PH1100285 | 125.5149 | 7.0811 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Santo Nino | MIN | PH112402031 | 22809 | 15 | Pole | CO66 | 12.0472 | MIN-1100158 | Level 3 (Davao City) - R | phase3 | phase3 | P1_630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  |  |  | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-15 | 2019-12-13 |  |  |  | 2019-12-13 | 2019-12-14 |  |  |  | 2019-12-14 |  |  |  | 2019-12-20 | 2019-12-13 |  |  |  | 2019-12-13 | [5 empty] | 2020-03-13 | 2020-01-19 | 2020-03-13 |  |  | 2020-03-13 |  | A | Emilio Jondit | Pequino 1, Catalunan, Davao City | Davao Del Sur | 125.5163 | 7.0827 | Greenfield |  |  | 15 years | P15,000 Exclusive of VAT and withholding tax | monthly | 100sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-26 | 2020-02-03 |  | 2020-02-25 |  | 2020-02-02 | [16 empty] | 2020-02-23 |  |  | 2020-03-03 | [6 empty] | 2020-03-17 |  |  |  | 2020-03-17 |  |  |  |  | 2020-02-09 |  | 2020-02-19 |  |  | 2020-02-23 |  | 2020-02-26 |  |  | 2020-03-11 |  |  |  | 2020-03-18 |  | JGT-36-340C-2NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [8 empty] | 2020-03-23 |  | 2020-03-26 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100287 | 125.5148 | 7.0587 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bago Gallera | MIN | PH112402005 | 17378 | 30 | Three Legged Tubular Tower | CO66 | 12.7016 | MIN-1100159 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-15 | 2019-12-21 |  |  |  | 2019-12-21 | [8 empty] | 2019-12-20 | [5 empty] | 2020-01-17 |  |  |  | 2020-01-17 |  | 2020-01-19 | [27 empty] | 2020-01-26 |  |  | 2020-02-25 |  | 2020-02-02 | [16 empty] | 2020-02-23 |  |  | 2020-03-03 | [6 empty] | 2020-03-17 |  |  |  | 2020-03-17 |  |  |  |  | 2020-02-09 |  | 2020-02-19 |  |  | 2020-02-23 |  | 2020-02-26 |  |  | 2020-03-11 |  |  |  | 2020-03-18 |  | JGT-36-340C-2NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [8 empty] | 2020-03-23 |  | 2020-03-26 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100288 | 125.5147 | 7.0475 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Baliok | MIN | PH112402005 | 17378 | 30 | Three Legged Tubular Tower | CO66 | 13.1942 | MIN-1100160 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  | EPC |  | 2019-12-13 | 2019-12-28 | 2019-12-28 | 2019-12-30 | 2019-12-29 |  |  |  | 2019-12-29 | 2019-12-30 |  |  |  | 2019-12-30 |  |  |  | 2020-01-04 | 2019-12-30 |  |  |  | 2019-12-30 | 2019-12-29 |  |  |  | 2019-12-29 | 2020-01-24 | 2020-02-03 | 2020-01-10 |  |  | 2020-01-10 | 2020-02-04 | A | Lorna N. Arrubio | Purok 6, Bago Galera, Talomo, Davao City | Davao del Sur | 125.5181 | 7.0504 | Greenfield | 23m |  | 15 years | P25,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-02-11 | n/a |  |  |  | n/a | 2020-02-10 | 2020-01-10 |  | 2020-03-11 | 2020-02-19 | 2020-02-17 | [16 empty] | 2020-03-09 | ok |  | 2020-03-18 | [6 empty] | 2020-04-01 |  | 2020-02-27 | 2020-03-05 | 2020-04-01 | 2020-03-06 | 2020-03-10 |  | Cheque released | 2020-02-24 |  | 2020-03-05 |  |  | 2020-03-09 |  | 2020-03-12 |  |  | 2020-03-26 |  |  |  | 2020-04-02 |  | JGT-36-340C-2NPT |  |  | 2020-04-14 |  | 2020-03-23 | [6 empty] | 2020-04-22 | 2020-04-29 | [20 empty] | 2020-05-29 |  |  |  | 2020-06-01 | [7 empty] | 2020-03-03 | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-02 |  |  |  | 2020-05-05 |  |  | 2020-05-20 |  |  |  | 2020-06-01 |  | 2020-06-04
PH1100289 | 125.5146 | 7.0363 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Dumoy | MIN | PH112402043 | 18622 | 45 | Three Legged Tubular Tower | CO66 | 13.7821 | MIN-1100161 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-11-27 | 2019-12-24 | 2019-12-24 | 2019-12-26 | 2019-12-25 |  |  |  | 2019-12-25 | 2019-12-26 |  |  |  | 2019-12-26 |  |  |  | 2019-12-31 | 2020-01-16 |  |  |  | 2020-01-16 | 2019-12-25 |  |  |  | 2019-12-25 | 2020-01-24 | 2020-01-30 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Vilma D. Bulan | Vergul Village, Dumoy, Davao City | Davao del Sur | 125.5136 | 7.0367 | Greenfield | 23m |  | 15 years | P25,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-06 | 2020-01-23 |  | 2020-03-07 |  | 2020-02-13 | [16 empty] | 2020-03-05 |  |  | 2020-03-14 | [6 empty] | 2020-03-28 |  |  |  | 2020-03-28 |  |  |  |  | 2020-02-20 | 2020-03-04 | 2020-03-01 |  |  | 2020-03-05 | 2020-02-06 | 2020-03-08 | 2020-02-06 | 2020-02-07 | 2020-03-22 | 2020-02-06 |  |  | 2020-03-29 |  | JGT-36-340C-2NPT |  |  | 2020-04-10 |  | 2020-03-19 | [6 empty] | 2020-04-18 | 2020-04-25 | [20 empty] | 2020-05-25 |  |  |  | 2020-05-28 | [8 empty] | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-18 |  |  |  | 2020-04-21 |  |  | 2020-04-28 |  |  |  | 2020-05-01 |  |  | 2020-05-16 |  |  |  | 2020-05-28 |  | 2020-05-31
PH1100292 | 125.5246 | 7.0867 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Tacunan | MIN | PH112402030 | 32461 | 45 | Three Legged Tubular Tower | CO66 | 10.8953 | MIN-1100162 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2020-01-16 | 2020-01-13 | 2020-01-18 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-23 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-02-19 | 2020-02-22 | 2020-02-26 |  |  | 2020-02-26 | 2020-03-02 | A | Feliciano v. Enriquez III | Sitio Ubat, Catalunan Grande Rd., Davao City | Davao del Sur | 125.5267 | 7.0867 | Greenfield | 23m |  | 15 years | P14,868 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-29 | 2020-02-03 |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 |  | 2020-03-24 |  |  | 2020-03-28 | 2020-03-02 | 2020-03-31 | 2020-03-03 | 2020-03-03 | 2020-04-14 |  |  |  | 2020-04-21 |  | JGT-36-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1100293 | 125.5246 | 7.0755 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Catalunan Pequeno | MIN | PH112402031 | 22809 | 15 | Pole | CO66 | 11.1221 | MIN-1100163 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-16 | 2019-12-16 | 2019-12-18 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-18 |  |  |  | 2019-12-18 |  |  |  | 2019-12-23 | [5 empty] | 2019-12-17 |  |  |  | 2019-12-17 |  | 2020-01-22 | [27 empty] | 2020-01-29 | 2020-02-19 |  | 2020-02-28 |  | 2020-02-05 | [16 empty] | 2020-02-26 |  |  | 2020-03-06 | [6 empty] | 2020-03-20 |  |  |  | 2020-03-20 |  |  |  |  | 2020-02-12 |  | 2020-02-22 |  |  | 2020-02-26 |  | 2020-02-29 |  |  | 2020-03-14 |  |  |  | 2020-03-21 |  | ZCG-9-340D-1NPT |  |  | 2020-04-02 |  | 2020-03-11 | [6 empty] | 2020-04-10 | 2020-04-17 | [20 empty] | 2020-05-17 |  |  |  | 2020-05-20 | [8 empty] | 2020-03-26 |  | 2020-03-29 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-05-08 |  |  |  | 2020-05-20 |  | 2020-05-23
PH1100294 | 125.5245 | 7.0643 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bago Gallera | MIN | PH112402005 | 17378 | 40 | Three Legged Tubular Tower | CO66 | 11.4802 | MIN-1100164 | Level 3 (Davao City) - R | phase1_220_20% | phase2_1231 | PO Issued not 630 |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2019-12-21 | 2019-12-21 | 2019-12-23 | 2019-12-22 |  |  |  | 2019-12-22 | 2019-12-23 |  |  |  | 2019-12-23 |  |  |  | 2019-12-28 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-22 |  |  |  | 2019-12-22 | 2020-01-24 | 2020-01-27 | 2020-01-10 |  |  | 2020-01-10 | 2020-02-04 | A | Willie Batalla | Purok 18, Batalla Village, Catalunan Pequeno, Davao City | Davao del Sur | 125.524 | 7.0661 | Greenfield | 49m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 100sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-23 | n/a |  |  |  | n/a | 2020-02-03 | 2020-02-03 |  | 2020-03-04 |  | 2020-02-10 | 2020-01-22 |  | 2020-01-22 | [13 empty] | 2020-03-02 |  |  | 2020-03-11 | [6 empty] | 2020-03-25 |  |  |  | 2020-03-25 |  |  |  |  | 2020-02-17 |  | 2020-02-27 |  |  | 2020-03-02 |  | 2020-03-05 |  |  | 2020-03-19 |  |  |  | 2020-03-26 |  | JGT-36-340C-2NPT |  |  | 2020-04-07 |  | 2020-03-16 | [6 empty] | 2020-04-15 | 2020-04-22 | [20 empty] | 2020-05-22 |  |  |  | 2020-05-25 | [8 empty] | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-04-25 |  |  |  | 2020-04-28 |  |  | 2020-05-13 |  |  |  | 2020-05-25 |  | 2020-05-28
PH1100295 | 125.5244 | 7.0531 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bago Gallera | MIN | PH112402005 | 17378 | 45 | Three Legged Tubular Tower | CO66 | 11.9583 | MIN-1100165 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-19 | 2019-12-19 | 2019-12-21 | 2019-12-20 |  |  |  | 2019-12-20 | [8 empty] | 2019-12-26 | [5 empty] | 2019-12-20 |  |  |  | 2019-12-20 |  | 2020-01-25 | [27 empty] | 2020-02-01 |  |  | 2020-03-02 |  | 2020-02-08 | [16 empty] | 2020-02-29 |  |  | 2020-03-09 | [6 empty] | 2020-03-23 |  |  |  | 2020-03-23 |  |  |  |  | 2020-02-15 |  | 2020-02-25 |  |  | 2020-02-29 |  | 2020-03-03 |  |  | 2020-03-17 |  |  |  | 2020-03-24 |  | JGT-36-340C-2NPT |  |  | 2020-04-05 |  | 2020-03-14 | [6 empty] | 2020-04-13 | 2020-04-20 | [20 empty] | 2020-05-20 |  |  |  | 2020-05-23 | [8 empty] | 2020-03-29 |  | 2020-04-01 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-11 |  |  |  | 2020-05-23 |  | 2020-05-26
PH1100297 | 125.5243 | 7.0307 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Dumoy | MIN | PH112402043 | 18622 | 30 | Three Legged Tubular Tower | CO66 | 13.2182 | MIN-1100166 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-04-19 | 2020-01-18 | 2020-04-21 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2020-04-26 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-02-13 | 2020-05-26 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Joselito Villamor | Dumuy, Sto Rosario, Tolomo Dist. Davao City | Davao del Sur | 125.5237 | 7.0362 | Greenfield | 12m |  | 15 years | P16,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-06-02 | 2020-01-23 |  | 2020-07-02 |  | 2020-06-09 | [16 empty] | 2020-06-30 |  |  | 2020-07-09 | [6 empty] | 2020-07-23 |  |  |  | 2020-07-23 |  |  |  |  | 2020-06-16 |  | 2020-06-26 |  |  | 2020-06-30 |  | 2020-07-03 |  |  | 2020-07-17 |  |  |  | 2020-07-24 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-08-05 |  | 2020-07-14 | [6 empty] | 2020-08-13 | 2020-08-20 | [20 empty] | 2020-09-19 |  |  |  | 2020-09-22 | [8 empty] | 2020-07-29 |  | 2020-08-01 |  |  | 2020-08-13 |  |  |  | 2020-08-16 |  |  | 2020-08-23 |  |  |  | 2020-08-26 |  |  | 2020-09-10 |  |  |  | 2020-09-22 |  | 2020-09-25
PH1100298 | 125.5343 | 7.081 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Catalunan Grande | MIN | PH112402030 | 32461 | 45 | Three Legged Tubular Tower | CO66 | 9.9394 | MIN-1100167 | Level 3 (Davao City) - R | phase3 | phase3 | P1_630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD |  | JXD |  | 2019-12-13 | 2019-12-21 | 2019-12-21 | 2019-12-23 | 2019-12-22 |  |  |  | 2019-12-22 | 2019-12-23 |  |  |  | 2019-12-23 |  |  |  | 2019-12-28 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-22 |  |  |  | 2019-12-22 | 2020-01-24 | 2020-01-27 | 2020-01-10 |  |  | 2020-01-10 | 2020-02-04 | A | Alena G. Campur | Sitio Aura, Catalunan Grande, Davao City | Davao del Sur | 125.5352 | 7.0808 | Greenfield | 70m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-03 | 2020-02-05 |  | 2020-03-04 |  | 2020-02-10 | [16 empty] | 2020-03-02 |  |  | 2020-03-11 | [6 empty] | 2020-03-25 |  |  |  | 2020-03-25 |  |  |  |  | 2020-02-17 | 2020-02-13 | 2020-02-27 | 2020-02-22 | 2020-02-23 | 2020-03-02 | 2020-02-08 | 2020-03-05 | 2020-02-15 | 2020-02-16 | 2020-03-19 | 2020-02-17 | 2020-02-26 | 2020-02-17 | 2020-03-26 | 2020-02-26 | JGT-36-340C-2NPT |  |  | 2020-04-07 |  | 2020-03-16 | [6 empty] | 2020-04-15 | 2020-04-22 | [20 empty] | 2020-05-22 |  |  |  | 2020-05-25 | [8 empty] | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-04-25 |  |  |  | 2020-04-28 |  |  | 2020-05-13 |  |  |  | 2020-05-25 |  | 2020-05-28
PH1100300 | 125.5342 | 7.0586 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bago Gallera | MIN | PH112402005 | 17378 | 6 | Wall Mounted Pole | CO66 | 10.7234 | MIN-1100168 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M12 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2020-01-01 |  |  |  | 2020-01-01 | [8 empty] | 2019-12-13 | [5 empty] | 2020-01-01 |  |  |  | 2020-01-01 |  | 2020-01-12 | [27 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | POLE-3-340C-RF & POLE-3-340C-MW |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100301 | 125.5341 | 7.0474 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bago Aplaya | MIN | PH112402176 | 15918 | 45 | Three Legged Tubular Tower | CO66 | 11.3025 | MIN-1100169 | Level 3 (Davao City) - R | phase1_220_20% | phase2_1231 | P1_630 |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD |  | JXD |  | 2019-11-27 | 2019-12-11 | 2019-12-11 | 2019-12-13 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-13 |  |  |  | 2019-12-13 |  |  |  | 2019-12-18 | 2019-12-13 |  |  |  | 2019-12-13 | 2019-12-18 |  |  |  | 2019-12-18 | 2019-12-23 | 2020-01-17 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | A | Bethoven | Bago Aplaya, Talomo District, Davao City | Davao del Sur | 125.5355 | 7.0482 | Greenfield |  |  | 15 years | P18,000 inclusive of VAT and withholding tax | monthly | 100sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-20 | n/a |  |  |  | n/a | 2020-01-24 |  |  | 2020-02-23 |  | 2020-01-31 |  |  | 2020-01-22 | [13 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  |  | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 | 2020-02-15 | 2020-02-24 | 2020-02-15 | 2020-02-16 | 2020-03-09 | 2020-02-15 |  |  | 2020-03-16 |  | JGT-36-340C-2NPT |  |  | 2020-03-28 |  | 2020-03-06 | [6 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [8 empty] | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100303 | 125.544 | 7.0754 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Catalunan Grande | MIN | PH112402030 | 32461 | 45 | Three Legged Tubular Tower | CO66 | 9.0528 | MIN-1100170 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M12 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2020-04-28 | 2020-02-10 | 2020-04-30 | 2020-02-11 |  |  |  | 2020-02-11 | 2020-02-12 |  |  |  | 2020-02-12 |  |  |  | 2020-05-05 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-11 |  |  |  | 2020-02-11 | 2020-02-28 | 2020-06-04 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 | A | Virginia Nacamura | 105 Libra St., Pag-ibig Homes, Catalunan Grande, Davao City | Davao del Sur | 125.545 | 7.0761 | Rooftop |  |  | 10 years | P30,000 Exclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-06-11 | 2020-02-27 |  | 2020-07-11 |  | 2020-06-18 | [16 empty] | 2020-07-09 |  |  | 2020-07-18 | [6 empty] | 2020-08-01 |  |  |  | 2020-08-01 |  |  |  |  | 2020-06-25 |  | 2020-07-05 |  |  | 2020-07-09 |  | 2020-07-12 |  |  | 2020-07-26 |  |  |  | 2020-08-02 |  | JGT-36-340C-2NPT |  |  | 2020-08-14 |  | 2020-07-23 | [6 empty] | 2020-08-22 | 2020-08-29 | [20 empty] | 2020-09-28 |  |  |  | 2020-10-01 | [8 empty] | 2020-08-07 |  | 2020-08-10 |  |  | 2020-08-22 |  |  |  | 2020-08-25 |  |  | 2020-09-01 |  |  |  | 2020-09-04 |  |  | 2020-09-19 |  |  |  | 2020-10-01 |  | 2020-10-04
PH1100304 | 125.583 | 7.0976 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Magtuod | MIN | PH112402061 | 59803 | 15 | Pole | CO66 | 4.3776 | MIN-1100171 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-21 | 2019-12-21 | 2019-12-23 | 2019-12-22 | 2020-02-13 |  |  | 2019-12-22 | 2019-12-23 | 2020-02-15 |  |  | 2019-12-23 |  |  |  | 2019-12-28 |  | 2020-02-15 |  |  | 2020-02-15 | 2019-12-22 | 2020-02-05 |  |  | 2019-12-22 |  | 2020-01-27 | [5 empty] | B |  |  |  | 125.5831 | 7.0989 | [16 empty] | 2020-02-03 | 2020-01-26 |  | 2020-03-04 |  | 2020-02-10 | [16 empty] | 2020-03-02 |  |  | 2020-03-11 | [6 empty] | 2020-03-25 |  |  |  | 2020-03-25 |  |  |  |  | 2020-02-17 |  | 2020-02-27 |  |  | 2020-03-02 |  | 2020-03-05 |  |  | 2020-03-19 |  |  |  | 2020-03-26 |  | ZCG-12-340D-1NPT |  |  | 2020-04-07 |  | 2020-03-16 | [6 empty] | 2020-04-15 | 2020-04-22 | [20 empty] | 2020-05-22 |  |  |  | 2020-05-25 | [8 empty] | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-04-25 |  |  |  | 2020-04-28 |  |  | 2020-05-13 |  |  |  | 2020-05-25 |  | 2020-05-28
PH1100305 | 125.5829 | 7.0864 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Magtuod | MIN | PH112402061 | 59803 | 40 | Three Legged Tubular Tower | CO66 | 4.5882 | MIN-1100172 | Level 3 (Davao City) - R | phase1_220_20% | phase2_1231 | PO Issued not 630 |  | Cluster M05 | Richworld | PO2019121801PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-07 |  |  |  | 2019-12-07 |  |  |  | 2019-12-14 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-07 | 2020-02-05 |  |  | 2019-12-07 | 2020-02-26 | 2020-01-13 | 2020-03-09 |  |  | 2020-03-09 |  | A | Liza Labuan | Lot 4, Purok 23, Pantinople Village, Ma-a, Davao City | Davao del Sur | 125.5811 | 7.0862 | Rooftop |  | 6m | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-20 | 2020-02-28 |  | 2020-02-19 |  | 2020-01-27 |  |  | 2020-01-22 | [13 empty] | 2020-02-17 |  |  | 2020-02-26 | [6 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  |  | 2020-02-03 | 2020-03-12 | 2020-02-13 | 2020-03-12 | 2020-03-12 | 2020-02-17 | 2020-03-13 | 2020-02-20 |  |  | 2020-03-05 |  |  |  | 2020-03-12 |  | ZCG-12-340D-1NPT |  |  | 2020-03-24 |  | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 | [20 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [8 empty] | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1100307 | 125.5871 | 7.1088 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Waan | MIN | PH112402195 | 3925 | 45 | Three Legged Tubular Tower | CO66 | 4.0824 | MIN-1100173 | Level 3 (Davao City) - R | phase3 | phase3 | P1_630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  |  |  | 2019-12-13 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-18 |  |  |  | 2019-12-18 |  |  |  | 2019-12-13 | 2019-12-18 |  |  |  | 2019-12-18 | 2019-12-07 | 2019-12-10 |  |  | 2019-12-07 | 2019-12-23 | 2020-01-12 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | A | Joel M. Restante | Sitio Camamara, Brgy. Waan, Davao City | Davao del Sur | 125.589 | 7.1075 | Greenfield |  |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 330sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-02-05 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-36-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100309 | 125.597 | 7.1368 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Cabantian | MIN | PH112402125 | 36387 | 45 | Three Legged Tubular Tower | CO66 | 5.1057 | MIN-1100174 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  |  |  | 2019-12-12 | 2019-12-10 | 2019-12-10 | 2019-12-12 | 2019-12-21 | 2019-12-11 |  |  | 2019-12-11 |  | 2019-12-12 |  |  | 2019-12-12 |  |  |  | 2019-12-17 | 2019-12-22 |  |  |  | 2019-12-22 | 2019-12-11 | 2019-12-11 |  |  | 2019-12-11 | 2020-01-24 | 2020-01-16 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | B | Angel Orayle | Purok 5, KM11, Cabantian, Davao City | Davao del Sur | 125.6003 | 7.1425 | Greenfield | 105m |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 100sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-23 | 2020-02-28 |  | 2020-02-22 |  | 2020-01-30 | [16 empty] | 2020-02-20 |  |  | 2020-02-29 | [6 empty] | 2020-03-14 |  |  |  | 2020-03-14 |  |  |  |  | 2020-02-06 |  | 2020-02-16 |  |  | 2020-02-20 |  | 2020-02-23 |  |  | 2020-03-08 |  |  |  | 2020-03-15 |  | JGT-36-340C-2NPT |  |  | 2020-03-27 |  | 2020-03-05 | [6 empty] | 2020-04-04 | 2020-04-11 | [20 empty] | 2020-05-11 |  |  |  | 2020-05-14 | [8 empty] | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-05-02 |  |  |  | 2020-05-14 |  | 2020-05-17
PH1100312 | 125.6146 | 7.5176 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Santo Tomas | Tibal-Og | MIN | PH112318017 | 2716 | 45 | Three Legged Tubular Tower | CO65 | 22.8176 | MIN-1100175 | Level 5 | phase2_add | phase2_1231 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  | Enovell |  | 2019-12-12 | 2019-12-13 | 2019-12-13 | 2019-12-15 | 2019-12-14 |  |  |  | 2019-12-14 | 2019-12-15 |  |  |  | 2019-12-15 |  |  |  | 2019-12-20 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-14 |  |  |  | 2019-12-14 | 2019-12-27 | 2020-01-19 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Bebeth G. Estrada | Purok Mahogany, New Visayas, Sto. Tomas | Davao del Norte | 125.6131 | 7.5181 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-26 | 2020-01-25 |  | 2020-02-25 | 2020-02-28 | 2020-02-02 | [11 empty] | 0915-4621974 |  |  |  |  | 2020-02-23 | ok |  | 2020-03-03 | [6 empty] | 2020-03-17 |  | 2020-03-04 |  | 2020-03-17 |  |  |  | RFP rejected, need to correct Lessor ID | 2020-02-09 | 2020-02-13 | 2020-02-19 | 2020-02-27 | 2020-02-27 | 2020-02-23 | 2020-02-24 | 2020-02-26 | 2020-02-24 | 2020-02-28 | 2020-03-11 | 2020-02-28 | 2020-02-28 | 2020-02-28 | 2020-03-18 | 2020-02-28 | JGT-36-340C-2NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [7 empty] | 2020-02-20 | 2020-03-23 |  | 2020-03-26 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100313 | 125.6123 | 7.1254 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Cabantian | MIN | PH112402023 | 43758 | 45 | Three Legged Tubular Tower | CO66 | 3.1975 | MIN-1100176 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M04 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2019-12-13 | 2020-04-29 |  | 2020-05-01 | [13 empty] | 2020-05-06 | [11 empty] | 2020-06-05 | [27 empty] | 2020-06-12 |  |  | 2020-07-12 |  | 2020-06-19 | [16 empty] | 2020-07-10 |  |  | 2020-07-19 | [6 empty] | 2020-08-02 |  |  |  | 2020-08-02 |  |  |  |  | 2020-06-26 |  | 2020-07-06 |  |  | 2020-07-10 |  | 2020-07-13 |  |  | 2020-07-27 |  |  |  | 2020-08-03 |  | JGT-36-340C-2NPT |  |  | 2020-08-15 |  | 2020-07-24 | [6 empty] | 2020-08-23 | 2020-08-30 | [20 empty] | 2020-09-29 |  |  |  | 2020-10-02 | [8 empty] | 2020-08-08 |  | 2020-08-11 |  |  | 2020-08-23 |  |  |  | 2020-08-26 |  |  | 2020-09-02 |  |  |  | 2020-09-05 |  |  | 2020-09-20 |  |  |  | 2020-10-02 |  | 2020-10-05
PH1100314 | 125.6244 | 7.5343 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Santo Tomas | Tibal-Og | MIN | PH112318011 | 41354 | 45 | Three Legged Tubular Tower | CO65 | 22.5674 | MIN-1100177 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 | DICT_68 | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  | Enovell |  | 2019-12-12 | 2019-12-13 | 2019-12-13 | 2019-12-15 | 2019-12-14 |  |  |  | 2019-12-14 | 2019-12-15 |  |  |  | 2019-12-15 |  |  |  | 2019-12-20 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-14 |  |  |  | 2019-12-14 | 2019-12-27 | 2020-01-19 | 2020-03-09 |  |  | 2020-03-09 | 2020-03-09 | A | Meliton Alamillo, Jr. | FDR 3, Santo Tomas | Davao del Norte | 125.6244 | 7.5337 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-26 | 2020-01-25 |  | 2020-02-25 | 2020-02-21 | 2020-02-02 | [11 empty] | 0910-1060168 |  |  |  |  | 2020-02-23 | ok |  | 2020-03-03 | [6 empty] | 2020-03-17 |  | 2020-03-02 | 2020-03-11 | 2020-03-17 |  |  |  | RFP approved, follow up cheque release | 2020-02-09 | 2020-02-27 | 2020-02-19 | 2020-02-27 | 2020-02-27 | 2020-02-23 | 2020-02-18 | 2020-02-26 | 2020-02-28 | 2020-02-28 | 2020-03-11 | 2020-02-28 | 2020-02-28 | 2020-02-28 | 2020-03-18 |  | JGT-36-340C-2NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [7 empty] | 2020-02-24 | 2020-03-23 |  | 2020-03-26 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100315 | 125.6243 | 7.5231 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Santo Tomas | Tibal-Og | MIN | PH112318011 | 41354 | 45 | Three Legged Tubular Tower | CO65 | 22.0521 | MIN-1100178 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  | Enovell |  | 2019-12-12 | 2019-11-29 | 2019-11-29 | 2019-12-01 | 2019-12-14 | 2020-01-23 |  |  | 2019-12-14 | 2019-12-15 | 2020-01-25 |  |  | 2019-12-15 |  |  |  | 2019-12-06 |  | 2020-01-25 |  |  | 2020-01-25 | 2019-12-14 | 2020-01-23 |  |  | 2019-12-14 | 2020-02-10 | 2020-01-05 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | B | Nanette Dazon | Purok 3, Feeder Road 1, Tibal-og, Sto. Tomas | Davao del Norte | 125.6261 | 7.5221 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | Monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | 2020-02-08 | n/a |  |  |  | n/a | 2020-01-12 | 2020-01-25 |  | 2020-02-11 | 2020-02-21 | 2020-01-19 | 2020-02-28 | 2020-02-28 | 2020-02-28 | [13 empty] | 2020-02-09 | ok |  | 2020-02-18 | 2020-03-05 | [5 empty] | 2020-03-03 |  | 2020-03-04 |  | 2020-03-03 |  |  |  | RFP rejected, align Lessor signature | 2020-01-26 | 2020-03-09 | 2020-02-05 | 2020-03-09 | 2020-03-09 | 2020-02-09 | 2020-03-03 | 2020-02-12 | 2020-03-04 | 2020-03-04 | 2020-02-26 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-03-09 | JGT-36-340C-2NPT |  |  | 2020-03-16 |  | 2020-02-23 | [6 empty] | 2020-03-24 | 2020-03-31 | [20 empty] | 2020-04-30 |  |  |  | 2020-05-03 | [7 empty] | 2020-02-24 | 2020-03-09 | 2020-03-12 | 2020-03-12 | 2020-03-12 |  | 2020-03-24 |  |  |  | 2020-03-27 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-21 |  |  |  | 2020-05-03 |  | 2020-05-06
PH1100317 | 125.6438 | 7.523 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Santo Tomas | Tibal-Og | MIN | PH112318011 | 41354 | 45 | Three Legged Tubular Tower | CO65 | 20.0955 | MIN-1100179 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  | Enovell | PH20200302002 | 2019-12-12 | 2019-12-13 | 2019-12-13 | 2019-12-15 | 2019-12-14 |  |  |  | 2019-12-14 | 2019-12-15 |  |  |  | 2019-12-15 |  |  |  | 2019-12-20 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-14 |  |  |  | 2019-12-14 | 2019-12-27 | 2020-01-19 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Julio Eugenio, Jr. | Brgy. Tibal-og, Santo Tomas | Davao del Norte | 125.6438 | 7.5234 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | 2020-02-08 | n/a |  |  |  | n/a | 2020-01-26 | 2020-01-25 |  | 2020-02-25 | 2020-02-21 | 2020-02-02 | [11 empty] | 0908-7000150 |  |  |  |  | 2020-02-23 | ok |  | 2020-03-03 | [6 empty] | 2020-03-17 |  | 2020-03-10 | 2020-03-11 | 2020-03-17 |  |  |  | RFP approved, follow up cheque release | 2020-02-09 | 2020-02-12 | 2020-02-19 | 2020-02-27 | 2020-02-27 | 2020-02-23 | 2020-02-24 | 2020-02-26 | 2020-02-24 | 2020-02-25 | 2020-03-11 | 2020-02-25 | 2020-02-27 | 2020-02-27 | 2020-03-18 | 2020-02-27 | JGT-36-340C-2NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [7 empty] | 2020-02-20 | 2020-03-23 | 2020-03-09 | 2020-03-26 | 2020-03-09 |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100320 | 125.6515 | 7.1812 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402049 | 24947 | 15 | Pole | CO66 | 9.7259 | MIN-1100180 | Level 3 (Davao City) - R | phase3 | phase1_630 | P1_630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  |  |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-08 | 2019-12-08 |  |  | 2019-12-08 |  | 2019-12-08 |  |  | 2019-12-08 |  |  |  | 2019-12-13 |  | 2019-12-08 |  |  | 2019-12-08 | 2019-12-07 | 2019-12-07 |  |  | 2019-12-07 | 2019-12-23 | 2020-01-12 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-22 | B | Julie Ronaliza Martinez | Brgy. Ilang, Davao City | Davao del Sur | 125.6493 | 7.183 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-02-28 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 | 2020-03-03 | 2020-02-19 | 2020-03-05 | 2020-03-08 | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-30-340C-2NPT（340KPH/D） |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100321 | 125.6514 | 7.17 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Sasa | MIN | PH112402049 | 24947 | 15 | Pole | CO66 | 8.5555 | MIN-1100181 | Level 3 (Davao City) - R | phase1_220_20% | phase2_1231 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-05-02 | 2020-01-16 | 2020-05-04 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-01-18 |  |  |  | 2020-01-18 |  |  |  | 2020-05-09 | 2020-01-18 |  |  |  | 2020-01-18 | 2020-01-17 |  |  |  | 2020-01-17 |  | 2020-06-08 | [5 empty] | A |  |  |  | 125.6446 | 7.1706 | Greenfield | 25m | [14 empty] | 2020-06-15 | 2020-03-04 |  | 2020-07-15 |  | 2020-06-22 | [16 empty] | 2020-07-13 |  |  | 2020-07-22 | [6 empty] | 2020-08-05 |  |  |  | 2020-08-05 |  |  |  |  | 2020-06-29 |  | 2020-07-09 |  |  | 2020-07-13 |  | 2020-07-16 |  |  | 2020-07-30 |  |  |  | 2020-08-06 |  | JGT-36-340C-2NPT |  |  | 2020-08-18 |  | 2020-07-27 | [6 empty] | 2020-08-26 | 2020-09-02 | [20 empty] | 2020-10-02 |  |  |  | 2020-10-05 | [8 empty] | 2020-08-11 |  | 2020-08-14 |  |  | 2020-08-26 |  |  |  | 2020-08-29 |  |  | 2020-09-05 |  |  |  | 2020-09-08 |  |  | 2020-09-23 |  |  |  | 2020-10-05 |  | 2020-10-08
PH1100323 | 125.6588 | 7.1527 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | Panacan | MIN | PH112402087 | 35806 | 45 | Three Legged Tubular Tower | CO66 | 7.2193 | MIN-1100182 | Level 3 (Davao City) - R | phase3 | phase3 | First Call | AFP_23 | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  | MJV |  | 2019-12-13 | 2019-12-09 | 2019-12-09 | 2019-12-11 | 2019-12-10 |  |  |  | 2019-12-10 | 2019-12-10 |  |  |  | 2019-12-10 |  |  |  | 2019-12-16 | 2020-02-21 |  |  |  | 2020-02-21 | 2019-12-10 |  |  |  | 2019-12-10 | 2020-02-26 | 2020-01-15 | [5 empty] | A | Joanne Minoza Jabillo | Block 7 Lot 7, San Miguel Village, Panacan, Davao City | Davao del Sur | 125.6576 | 7.1516 | Rooftop |  |  | 10 years | P25,000 Exclusive of VAT and withholding tax | quarterly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-22 |  |  | 2020-02-21 |  | 2020-01-29 | [16 empty] | 2020-02-19 |  |  | 2020-02-28 | [6 empty] | 2020-03-13 |  |  |  | 2020-03-13 |  |  |  |  | 2020-02-05 | 2020-02-18 | 2020-02-15 | 2020-02-18 | 2020-02-18 | 2020-02-19 | 2020-02-18 | 2020-02-22 | 2020-02-18 | 2020-02-18 | 2020-03-07 | 2020-02-18 | 2020-02-18 | 2020-02-18 | 2020-03-14 | 2020-02-18 | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-03-26 |  | 2020-03-04 | [6 empty] | 2020-04-03 | 2020-04-10 | [20 empty] | 2020-05-10 |  |  |  | 2020-05-13 | [7 empty] | 2020-03-01 | 2020-03-19 | 2020-03-02 | 2020-03-22 | 2020-03-02 |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-05-01 |  |  |  | 2020-05-13 |  | 2020-05-16
PH1100324 | 125.6717 | 7.3268 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Panabo City | San Francisco | MIN | PH112315027 | 4649 | 45 | Three Legged Tubular Tower | CO65 | 19.9379 | MIN-1100183 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M08 | EPC | PO2019121803PH_WLS | Batch 1 (333) | EPC |  | EPC |  | 2019-11-27 | 2019-11-30 | 2019-11-30 | 2019-12-02 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-07 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-11-29 |  |  |  | 2019-11-29 | 2019-12-23 | 2020-01-06 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | A | Jaime C. Rule | Purok 7, New Visayas, Panabo City | Davao del Norte | 125.6699 | 7.3226 | Greenfield | 16m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 240sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-01-23 | n/a |  |  |  | n/a | 2020-01-13 | 2020-01-06 |  | 2020-02-12 |  | 2020-01-20 | 2020-01-17 | 2020-02-27 | 2020-01-13 | [8 empty] | 0909-9156064 |  |  |  |  | 2020-02-10 | ok |  | 2020-02-19 | 2020-01-13 | [5 empty] | 2020-03-04 |  |  |  | 2020-03-04 |  |  |  | Awaiting BR release | 2020-01-27 | 2020-01-15 | 2020-02-06 | 2020-01-25 | 2020-01-25 | 2020-02-10 | 2020-01-20 | 2020-02-13 | 2020-01-20 | 2020-01-21 | 2020-02-27 | 2020-01-21 | 2020-01-23 | 2020-02-19 | 2020-03-05 | 2020-02-19 | JGT-36-340C-2NPT |  |  | 2020-03-17 |  | 2020-02-24 | 2020-02-12 | [5 empty] | 2020-03-25 | 2020-04-01 | [20 empty] | 2020-05-01 |  |  |  | 2020-05-04 | [7 empty] | 2020-01-22 | 2020-03-10 | 2020-01-23 | 2020-03-13 |  |  | 2020-03-25 |  |  |  | 2020-03-28 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-22 |  |  |  | 2020-05-04 |  | 2020-05-07
PH1100327 | 125.6715 | 7.2932 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | n.a. ( 39395) | MIN | PH112315009 | 16543 | 45 | Three Legged Tubular Tower | CO66 | 22.3004 | MIN-1100184 | Level 3 (Davao City) - R | phase3 | phase3 | P1_630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-13 | 2019-12-03 | 2019-12-03 | 2019-12-05 | 2019-12-15 | 2020-02-03 |  |  | 2019-12-15 | 2019-12-16 |  |  |  | 2019-12-16 |  |  |  | 2019-12-10 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-15 | 2020-02-03 |  |  | 2019-12-15 | 2020-01-24 | 2020-01-09 | 2020-01-09 |  |  | 2020-01-10 | 2020-02-04 | A | Renato Royo, Jr. | Purok Cauliflower, Brgy.Gredu, Panabo City | Davao del Norte | 125.6689 | 7.2896 | Greenfield | 17m |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-03-03 | n/a |  |  |  |  | 2020-01-16 | 2020-02-27 |  | 2020-02-15 | 2020-03-12 | 2020-01-23 | 2020-03-13 | [15 empty] | 2020-02-13 | ok |  | 2020-02-22 | 2020-01-13 | [5 empty] | 2020-03-07 |  |  |  | 2020-03-07 |  |  |  | For RFP submission in DingTalk | 2020-01-30 |  | 2020-02-09 |  |  | 2020-02-13 |  | 2020-02-16 |  |  | 2020-03-01 |  |  |  | 2020-03-08 |  | JGT-36-340C-2NPT |  |  | 2020-03-20 |  | 2020-02-27 | [6 empty] | 2020-03-28 | 2020-04-04 | [20 empty] | 2020-05-04 |  |  |  | 2020-05-07 | [8 empty] | 2020-03-13 |  | 2020-03-16 |  |  | 2020-03-28 |  |  |  | 2020-03-31 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-25 |  |  |  | 2020-05-07 |  | 2020-05-10
PH1100329 | 125.6814 | 7.3211 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Panabo City | Santo Nino | MIN | PH112315029 | 12832 | 45 | Three Legged Tubular Tower | CO65 | 19.5821 | MIN-1100185 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M08 | EPC | PO2019121803PH_WLS | Batch 1 (333) | EPC |  | EPC |  | 2019-11-27 | 2019-11-30 | 2019-11-30 | 2019-12-02 | 2019-12-10 | 2019-12-24 |  |  | 2019-12-10 | 2019-12-10 | 2019-12-25 |  |  | 2019-12-10 |  |  |  | 2019-12-07 |  | 2019-12-26 |  |  | 2019-12-26 | 2019-12-10 | 2019-12-24 |  |  | 2019-12-10 | 2020-02-19 | 2020-01-06 | 2020-03-10 |  |  | 2020-03-10 | 2020-03-10 | B | Gondelina S. Comighog | Purok 1, Brgy Quezon Panabo City | Davao del Norte | 125.6867 | 7.3179 | Greenfield | 16m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-13 | 2020-01-22 |  | 2020-02-12 | 2020-02-07 | 2020-01-20 | 2020-03-13 | [15 empty] | 2020-02-10 | ok |  | 2020-02-19 | [6 empty] | 2020-03-04 |  | 2020-03-11 |  | 2020-03-04 |  |  |  | RFP submitted, ongoing review | 2020-01-27 | 2020-02-17 | 2020-02-06 | 2020-02-27 | 2020-02-27 | 2020-02-10 | 2020-02-07 | 2020-02-13 | 2020-02-14 | 2020-02-28 | 2020-02-27 | 2020-02-07 | 2020-02-28 | 2020-02-28 | 2020-03-05 | 2020-02-28 | JGT-36-340C-2NPT |  |  | 2020-03-17 |  | 2020-02-24 | 2020-02-11 | [5 empty] | 2020-03-25 | 2020-04-01 | [20 empty] | 2020-05-01 |  |  |  | 2020-05-04 | [7 empty] | 2020-02-24 | 2020-03-10 |  | 2020-03-13 |  |  | 2020-03-25 |  |  |  | 2020-03-28 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-22 |  |  |  | 2020-05-04 |  | 2020-05-07
PH1100330 | 125.6814 | 7.3099 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Panabo City | New Pandan | MIN | PH112315029 | 12832 | 45 | Three Legged Tubular Tower | CO65 | 20.4805 | MIN-1100186 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M08 | EPC | PO2019121803PH_WLS | Batch 1 (333) | EPC |  | Enovell |  | 2019-11-27 | 2019-11-29 | 2019-11-29 | 2019-12-01 | 2019-12-03 | 2019-12-20 |  |  | 2019-12-03 | 2019-12-04 | 2019-12-04 |  |  | 2019-12-04 |  |  |  | 2019-12-06 |  | 2019-12-05 |  |  | 2019-12-05 | 2019-11-29 | 2019-12-13 |  |  | 2019-11-29 | 2020-03-05 | 2020-01-05 | 2020-03-12 |  |  | 2020-03-12 |  | B | Magdalena Alfeche | Alfeche Bldg., Circumferential Rd., San Francisco, Panabo | Davao del Norte | 125.6835 | 7.3091 | Rooftop | 8m | 12m | 15 years | P30,000 inclusive of VAT and withholding tax | monthly | 81sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-12 | 2020-01-06 |  | 2020-02-11 | 2020-01-10 | 2020-01-19 | 2020-01-27 |  | 2020-01-13 | [9 empty] | 851 Cabaluna Gredu Bios, Panabo City |  |  |  | 2020-02-09 | ok |  | 2020-02-18 | 2020-02-26 | [5 empty] | 2020-03-03 |  |  |  | 2020-03-03 |  |  |  | Awaiting NRAF approval | 2020-01-26 |  | 2020-02-05 |  |  | 2020-02-09 | 2020-02-17 | 2020-02-12 | 2020-02-17 |  | 2020-02-26 |  |  |  | 2020-03-04 |  | ZCG-12-340D-1NPT |  |  | 2020-03-16 |  | 2020-02-23 | [6 empty] | 2020-03-24 | 2020-03-31 | [20 empty] | 2020-04-30 |  |  |  | 2020-05-03 | [8 empty] | 2020-03-09 |  | 2020-03-12 |  |  | 2020-03-24 |  |  |  | 2020-03-27 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-21 |  |  |  | 2020-05-03 |  | 2020-05-06
PH1100331 | 125.6813 | 7.2987 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | n.a. ( 39395) | MIN | PH112315025 | 6636 | 45 | Three Legged Tubular Tower | CO65 | 21.4136 | MIN-1100187 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-10 | 2019-12-10 | 2019-12-12 | 2019-12-11 |  |  |  | 2019-12-11 | [8 empty] | 2019-12-17 | [5 empty] | 2019-12-11 |  |  |  | 2019-12-11 |  | 2020-01-16 | [27 empty] | 2020-01-23 |  |  | 2020-02-22 |  | 2020-01-30 | [16 empty] | 2020-02-20 |  |  | 2020-02-29 | [6 empty] | 2020-03-14 |  |  |  | 2020-03-14 |  |  |  |  | 2020-02-06 |  | 2020-02-16 |  |  | 2020-02-20 |  | 2020-02-23 |  |  | 2020-03-08 |  |  |  | 2020-03-15 |  | JGT-36-340C-2NPT |  |  | 2020-03-27 |  | 2020-03-05 | [6 empty] | 2020-04-04 | 2020-04-11 | [20 empty] | 2020-05-11 |  |  |  | 2020-05-14 | [8 empty] | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-05-02 |  |  |  | 2020-05-14 |  | 2020-05-17
PH1100332 | 125.6812 | 7.2875 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | n.a. ( 39395) | MIN | PH112315005 | 13776 | 45 | Three Legged Tubular Tower | CO66 | 21.9805 | MIN-1100188 | Level 3 (Davao City) - R | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-03 | 2019-12-03 | 2019-12-05 |  |  | 2020-01-11 |  | 2020-01-11 |  |  | 2020-01-11 |  | 2020-01-11 |  |  |  | 2019-12-10 | 2020-01-13 |  |  |  | 2020-01-13 | 2019-12-06 | 2019-12-06 | 2020-01-11 |  | 2019-12-06 | 2020-02-21 | 2020-01-09 | 2019-12-27 |  |  | 2020-02-26 | 2020-03-02 | A | Alex Enguito | Purok Guyabano, Cagangohan, Panabo City | Davao del Norte | 125.6828 | 7.2849 | Greenfield | 14m |  | 15 years | P20,000 inclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-16 | 2020-02-24 |  | 2020-02-15 | 2020-03-12 | 2020-01-23 | [16 empty] | 2020-02-13 |  |  | 2020-02-22 | [6 empty] | 2020-03-07 |  |  |  | 2020-03-07 |  |  |  | Awaiting Lessor ID | 2020-01-30 | 2020-02-28 | 2020-02-09 |  |  | 2020-02-13 |  | 2020-02-16 |  |  | 2020-03-01 |  |  |  | 2020-03-08 |  | JGT-36-340C-2NPT |  |  | 2020-03-20 |  | 2020-02-27 | [6 empty] | 2020-03-28 | 2020-04-04 | [20 empty] | 2020-05-04 |  |  |  | 2020-05-07 | [8 empty] | 2020-03-13 |  | 2020-03-16 |  |  | 2020-03-28 |  |  |  | 2020-03-31 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-25 |  |  |  | 2020-05-07 |  | 2020-05-10
PH1100335 | 125.6911 | 7.3154 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Panabo City | Salvacion | MIN | PH112315028 | 9521 | 45 | Three Legged Tubular Tower | CO65 | 19.2996 | MIN-1100189 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M08 | EPC | PO2019121803PH_WLS | Batch 1 (333) |  |  | EPC |  | 2019-11-27 | 2019-11-30 | 2019-11-30 | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2019-12-03 |  | 2019-12-02 | 2019-12-03 | 2019-12-03 | 2019-12-04 |  | 2019-12-03 |  |  |  | 2019-12-07 | 2020-02-13 |  |  |  | 2020-02-13 | 2019-11-28 |  |  |  | 2019-11-28 | 2020-03-06 | 2020-01-06 | 2020-03-06 |  |  | 2020-03-06 | 2020-03-06 | A | Marion L. Lucedra | Purok 1, Adlaon St., Salvacion, Panabo City | Davao del Norte | 125.6912 | 7.3141 | Greenfield |  |  | 15 years | P20,000 inclusive of VAT and withholding tax | quarterly | 280sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-13 | 2020-02-01 |  | 2020-02-12 | 2020-02-10 | 2020-01-20 | 2020-01-17 |  | 2020-01-17 | [13 empty] | 2020-02-10 | ok |  | 2020-02-19 | [6 empty] | 2020-03-04 |  | 2020-03-10 |  | 2020-03-04 |  |  |  | RFP rejected, align Lessor signature | 2020-01-27 | 2020-02-17 | 2020-02-06 |  |  | 2020-02-10 | 2020-01-15 | 2020-02-13 | 2020-02-27 | 2020-02-27 | 2020-02-27 |  |  |  | 2020-03-05 |  | JGT-36-340C-2NPT |  |  | 2020-03-17 |  | 2020-02-24 | 2020-02-11 | [5 empty] | 2020-03-25 | 2020-04-01 | [20 empty] | 2020-05-01 |  |  |  | 2020-05-04 | [7 empty] | 2020-02-24 | 2020-03-10 |  | 2020-03-13 |  |  | 2020-03-25 |  |  |  | 2020-03-28 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-22 |  |  |  | 2020-05-04 |  | 2020-05-07
PH1100339 | 125.7009 | 7.3322 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Carmen | Santo Nino | MIN | PH112303019 | 5784 | 45 | Three Legged Tubular Tower | CO65 | 17.1958 | MIN-1100190 | Level 5 | phase2_add | phase2_1231 | P1_630 |  | Cluster M08 | EPC | PO2019121803PH_WLS | Batch 1 (333) | EPC |  | EPC |  | 2019-11-27 | 2019-11-30 | 2019-11-30 | 2019-12-02 | 2019-12-04 | 2019-12-04 |  |  | 2019-12-04 | 2019-12-05 | 2019-12-05 |  |  | 2019-12-05 |  |  |  | 2019-12-07 | 2019-12-06 |  |  |  | 2019-12-06 | 2019-11-28 | 2019-11-29 |  |  | 2019-11-28 | 2020-01-24 | 2020-01-06 | 2020-01-09 |  |  | 2020-01-10 | 2020-02-04 | A | Antonio Curay | Purok 7, Sto. Nino, Carmen | Davao del Norte | 125.702 | 7.3357 | Greenfield | 11m |  | 15 years | P16,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-13 | 2020-01-07 |  | 2020-02-12 | 2020-02-19 | 2020-01-20 | 2020-02-27 | 2020-02-27 | 2020-02-27 |  |  | 2020-02-28 |  |  | Antonio C. Curay | BDO/One Network Bank/Carmen | 040420004149 | [5 empty] | 2020-02-10 | ok | 2020-02-28 | 2020-02-19 | 2020-02-28 | [5 empty] | 2020-03-04 |  | 2020-02-25 | 2020-03-05 | 2020-03-04 | 2020-03-06 | 2020-03-10 |  | Cheque released | 2020-01-27 | 2020-02-10 | 2020-02-06 | 2020-02-21 | 2020-02-21 | 2020-02-10 | 2020-01-28 | 2020-02-13 | 2020-01-28 | 2020-01-29 | 2020-02-27 | 2020-01-28 | 2020-01-29 | 2020-02-22 | 2020-03-05 | 2020-02-22 | JGT-36-340C-2NPT |  |  | 2020-03-17 |  | 2020-02-24 | [6 empty] | 2020-03-25 | 2020-04-01 | [20 empty] | 2020-05-01 |  |  |  | 2020-05-04 | [7 empty] | 2020-03-13 | 2020-03-10 | 2020-03-13 | 2020-03-13 | 2020-03-13 |  | 2020-03-25 |  |  |  | 2020-03-28 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-22 |  |  |  | 2020-05-04 |  | 2020-05-07
PH1100341 | 125.7008 | 7.3098 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Panabo City | Salvacion | MIN | PH112315032 | 14449 | 15 | Pole | CO65 | 19.0937 | MIN-1100191 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 | DepEd_3426 | Cluster M08 | EPC | PO2019121803PH_WLS | Batch 1 (333) | EPC |  | EPC |  | 2019-11-27 | 2019-11-30 | 2019-11-30 | 2019-12-02 | 2019-12-03 | 2019-12-03 |  |  | 2019-12-03 | 2019-12-04 | 2019-12-04 |  |  | 2019-12-04 |  |  |  | 2019-12-07 | 2019-12-06 |  |  |  | 2019-12-06 | 2019-11-30 | 2019-11-30 |  |  | 2019-11-30 | 2020-01-24 | 2020-01-06 | 2019-12-27 |  |  | 2020-01-24 | 2020-02-06 | A | Mirra O. Merto | Purok 2, San Vicente, Panabo City | Davao del Norte | 125.7007 | 7.3094 | Greenfield | 16m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-01-23 | n/a |  |  |  | n/a | 2020-01-13 | 2020-01-06 |  | 2020-02-12 | 2020-02-12 | 2020-01-20 | 2020-01-23 | 2020-01-23 | 2020-01-23 | [13 empty] | 2020-02-10 | ok |  | 2020-02-19 | 2020-02-26 | [5 empty] | 2020-03-04 |  | 2020-03-04 | 2020-03-06 | 2020-03-04 | 2020-03-12 | 2020-03-10 | 2020-03-12 | Cheque released | 2020-01-27 |  | 2020-02-06 |  |  | 2020-02-10 | 2020-01-30 | 2020-02-13 | 2020-01-30 | 2020-01-31 | 2020-02-27 | 2020-01-31 |  |  | 2020-03-05 |  | DGT-30-340C-2NPT |  |  | 2020-03-17 |  | 2020-02-24 | [6 empty] | 2020-03-25 | 2020-04-01 | [20 empty] | 2020-05-01 |  |  |  | 2020-05-04 | [7 empty] | 2020-02-28 | 2020-03-10 |  | 2020-03-13 |  |  | 2020-03-25 |  |  |  | 2020-03-28 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-22 |  |  |  | 2020-05-04 |  | 2020-05-07
PH1100345 | 125.7105 | 7.3041 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Norte | Panabo City | Salvacion | MIN | PH112315041 | 4193 | 30 | Three Legged Tubular Tower | CO65 | 18.9666 | MIN-1100192 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M08 | EPC | PO2019121803PH_WLS | Batch 1 (333) | EPC |  | EPC |  | 2019-11-27 | 2019-11-29 | 2019-11-29 | 2019-12-01 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2019-12-06 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-24 | 2020-01-05 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Marjorie Soriano | Purok 17, Brgy. San Vicente, Panabo City | Davao del Norte | 125.7034 | 7.3045 | Greenfield | 7m |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-27 | n/a |  |  |  | n/a | 2020-01-12 | 2020-02-07 |  | 2020-02-11 | 2020-02-25 | 2020-01-19 | 2020-03-03 | [15 empty] | 2020-02-09 | ok |  | 2020-02-18 | [6 empty] | 2020-03-03 |  | 2020-03-04 |  | 2020-03-03 |  |  |  | RFP rejected, align Lessor signature | 2020-01-26 | 2020-03-05 | 2020-02-05 |  |  | 2020-02-09 |  | 2020-02-12 |  |  | 2020-02-26 |  |  |  | 2020-03-04 |  | JGT-30-340C-2NPT（340KPH/D） |  |  | 2020-03-16 |  | 2020-02-23 | [6 empty] | 2020-03-24 | 2020-03-31 | [20 empty] | 2020-04-30 |  |  |  | 2020-05-03 | [7 empty] | 2020-03-02 | 2020-03-09 |  | 2020-03-12 |  |  | 2020-03-24 |  |  |  | 2020-03-27 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-21 |  |  |  | 2020-05-03 |  | 2020-05-06
PH1100346 | 125.7117 | 7.292 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Del Sur | Davao City | n.a. ( 39395) | MIN | PH112315041 | 4193 | 30 | Three Legged Tubular Tower | CO65 | 20.019 | MIN-1100193 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-30 | 2019-12-30 | 2020-01-01 | 2020-01-02 |  |  |  | 2020-01-02 | 2020-02-06 |  |  |  | 2020-02-06 |  |  |  | 2020-01-06 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-01-02 |  |  |  | 2020-01-02 | 2020-03-06 | 2020-02-05 | 2020-03-06 |  |  | 2020-03-06 | 2020-03-06 | A | Ray Dano | Purok Baracuda, Brgy. San Pedro, Panabo City | Davao del Norte | 125.7075 | 7.296 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-02-12 | 2020-01-28 |  | 2020-03-13 | 2020-02-27 | 2020-02-19 | 2020-02-27 |  | 2020-02-27 | [13 empty] | 2020-03-11 | ok |  | 2020-03-20 | [6 empty] | 2020-04-03 |  |  |  | 2020-04-03 |  |  |  | For RFP submission in DingTalk | 2020-02-26 |  | 2020-03-07 |  |  | 2020-03-11 |  | 2020-03-14 |  |  | 2020-03-28 |  |  |  | 2020-04-04 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-04-16 |  | 2020-03-25 | [6 empty] | 2020-04-24 | 2020-05-01 | [20 empty] | 2020-05-31 |  |  |  | 2020-06-03 | [8 empty] | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-04 |  |  |  | 2020-05-07 |  |  | 2020-05-22 |  |  |  | 2020-06-03 |  | 2020-06-06
PH1100347 | 125.9652 | 7.605 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Compostela Valley | Nabunturan | Poblacion | MIN | PH118209019 | 18331 | 40 | Monopole Tower | CO65 | 24.8612 | MIN-1100194 | Level 1 (OA) | phase2_add | phase1_630 | OA_630 | DICT_18 | Cluster M07 | EPC | PO2019122103PH_WLS | Batch 2 | EPC |  | EPC |  | 2020-01-20 | 2020-01-16 | 2020-01-07 | 2020-01-18 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-23 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-24 | 2020-02-22 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Federico Arangcon | Purok 4, Brgy. Poblacion, Nabunturan, Davao de Oro | Compostela Valley | 125.9662 | 7.6048 | Greenfield | 105m |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-02-29 | 2020-01-12 |  | 2020-03-30 | 2020-02-22 | 2020-03-07 | 2020-02-26 | [10 empty] | 0910-7900382 |  |  |  |  | 2020-03-28 | ok |  | 2020-04-06 | 2020-03-11 | [5 empty] | 2020-04-20 |  | 2020-02-27 | 2020-03-05 | 2020-04-20 | 2020-03-06 | 2020-03-10 |  | Cheque released | 2020-03-14 | 2020-01-25 | 2020-03-24 | 2020-02-17 | 2020-02-17 | 2020-03-28 | 2020-02-05 | 2020-03-31 | 2020-02-05 | 2020-02-17 | 2020-04-14 | 2020-02-03 | 2020-02-17 | 2020-02-17 | 2020-04-21 | 2020-02-17 | JGT-36-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 |  |  |  | 2020-03-02 |  | 2020-03-06 | 2020-03-09 | [13 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [7 empty] | 2020-02-28 | 2020-04-26 | 2020-03-04 | 2020-04-29 | 2020-03-04 |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1100348 | 126.0823 | 7.6714 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Compostela Valley | Compostela | Poblacion | MIN | PH118201011 | 27261 | 45 | Three Legged Tubular Tower | CO65 | 39.369 | MIN-1100195 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M07 | EPC | PO2019122103PH_WLS | Batch 2 | EPC |  |  |  | 2020-01-20 | 2020-01-24 | 2020-01-03 | 2020-01-26 | 2020-01-04 |  |  |  | 2020-01-04 | 2020-01-12 |  |  |  | 2020-01-12 |  |  |  | 2020-01-31 | 2020-01-12 |  |  |  | 2020-01-12 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-03-02 | 2020-03-01 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 | A | Randy Gonzales | Purok 3, Poblacion, Compostela, Davao de Oro | Compostela Valley | 126.0822 | 7.6714 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-13 | n/a |  |  |  |  | 2020-03-08 | 2020-01-27 |  | 2020-04-07 | 2020-02-19 | 2020-03-15 | 2020-03-11 |  | 2020-02-27 | [13 empty] | 2020-04-05 | ok |  | 2020-04-14 | [6 empty] | 2020-04-28 |  | 2020-03-07 |  | 2020-04-28 |  |  |  | RFP rejected, align Lessor signature | 2020-03-22 | 2020-03-10 | 2020-04-01 |  |  | 2020-04-05 | 2020-03-09 | 2020-04-08 | 2020-03-09 | 2020-03-10 | 2020-04-22 |  |  |  | 2020-04-29 |  | JGT-36-340C-2NPT |  |  | 2020-05-11 |  | 2020-04-19 | [6 empty] | 2020-05-19 | 2020-05-26 | [20 empty] | 2020-06-25 |  |  |  | 2020-06-28 | [7 empty] | 2020-03-06 | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-05-29 |  |  |  | 2020-06-01 |  |  | 2020-06-16 |  |  |  | 2020-06-28 |  | 2020-07-01
PH1100350 | 126.092 | 7.6657 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Compostela Valley | Compostela | Poblacion | MIN | PH118201011 | 27261 | 45 | Three Legged Tubular Tower | CO65 | 39.8022 | MIN-1100196 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M07 | EPC | [7 empty] | 2020-03-02 | 2020-02-12 | 2020-03-04 | 2020-02-13 |  |  |  | 2020-02-13 | 2020-02-15 |  |  |  | 2020-02-15 |  |  |  | 2020-03-09 | 2020-02-15 |  |  |  | 2020-02-15 | 2020-02-13 |  |  |  | 2020-02-13 | 2020-02-25 | 2020-04-08 | [5 empty] | A | Ruel Boyose | Purok 7, Poblacion, Compostela Valley | Compostela Valley | 126.0918 | 7.6658 | Greenfield |  |  | 10 years | P18,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-15 | 2020-03-03 |  | 2020-05-15 |  | 2020-04-22 | [16 empty] | 2020-05-13 |  |  | 2020-05-22 | [6 empty] | 2020-06-05 |  |  |  | 2020-06-05 |  |  |  |  | 2020-04-29 |  | 2020-05-09 |  |  | 2020-05-13 |  | 2020-05-16 |  |  | 2020-05-30 |  |  |  | 2020-06-06 |  | JGT-36-340C-2NPT |  |  | 2020-06-18 |  | 2020-05-27 | [6 empty] | 2020-06-26 | 2020-07-03 | [20 empty] | 2020-08-02 |  |  |  | 2020-08-05 | [8 empty] | 2020-06-11 |  | 2020-06-14 |  |  | 2020-06-26 |  |  |  | 2020-06-29 |  |  | 2020-07-06 |  |  |  | 2020-07-09 |  |  | 2020-07-24 |  |  |  | 2020-08-05 |  | 2020-08-08
PH1100352 | 126.1284 | 7.3182 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Compostela Valley | Maragusan (San Mariano) | New Panay | MIN | PH118205003 | 14741 | 45 | Three Legged Tubular Tower | CO65 | 38.0255 | MIN-1100197 | Level 6 | phase3 | phase3 |  |  | Cluster M07 | EPC | [7 empty] | 2020-03-05 | 2020-02-11 | 2020-03-07 | 2020-02-14 |  |  |  | 2020-02-14 | 2020-02-19 |  |  |  | 2020-02-19 |  |  |  | 2020-03-12 | 2020-02-19 |  |  |  | 2020-02-19 | 2020-02-17 |  |  |  | 2020-02-17 |  | 2020-04-11 | [9 empty] | 126.1277 | 7.316 | [16 empty] | 2020-04-18 | 2020-03-02 |  | 2020-05-18 |  | 2020-04-25 | [16 empty] | 2020-05-16 |  |  | 2020-05-25 | [6 empty] | 2020-06-08 |  |  |  | 2020-06-08 |  |  |  |  | 2020-05-02 |  | 2020-05-12 |  |  | 2020-05-16 |  | 2020-05-19 |  |  | 2020-06-02 |  |  |  | 2020-06-09 |  | JGT-36-340C-2NPT |  |  | 2020-06-21 |  | 2020-05-30 | [6 empty] | 2020-06-29 | 2020-07-06 | [20 empty] | 2020-08-05 |  |  |  | 2020-08-08 | [8 empty] | 2020-06-14 |  | 2020-06-17 |  |  | 2020-06-29 |  |  |  | 2020-07-02 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-27 |  |  |  | 2020-08-08 |  | 2020-08-11
PH1100353 | 126.2036 | 6.9593 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Oriental | Mati City | Dahican | MIN | PH112509005 | 36485 | 45 | Three Legged Tubular Tower | CO66 | 65.9611 | MIN-1100198 | Level 6 | phase3 | phase3 |  |  | Cluster M01 | TBD | [7 empty] | 2020-03-01 |  | 2020-03-03 | [13 empty] | 2020-03-08 | [11 empty] | 2020-04-07 | [27 empty] | 2020-04-14 |  |  | 2020-05-14 |  | 2020-04-21 | [16 empty] | 2020-05-12 |  |  | 2020-05-21 | [6 empty] | 2020-06-04 |  |  |  | 2020-06-04 |  |  |  |  | 2020-04-28 |  | 2020-05-08 |  |  | 2020-05-12 |  | 2020-05-15 |  |  | 2020-05-29 |  |  |  | 2020-06-05 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-06-17 |  | 2020-05-26 | [6 empty] | 2020-06-25 | 2020-07-02 | [20 empty] | 2020-08-01 |  |  |  | 2020-08-04 | [8 empty] | 2020-06-10 |  | 2020-06-13 |  |  | 2020-06-25 |  |  |  | 2020-06-28 |  |  | 2020-07-05 |  |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  |  | 2020-08-04 |  | 2020-08-07
PH1100355 | 126.223 | 6.9592 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Oriental | Mati City | Dahican | MIN | PH112509022 | 10754 | 45 | Three Legged Tubular Tower | CO66 | 68.0489 | MIN-1100199 | Level 6 | phase3 | phase3 |  | DepEd_3247 | Cluster M01 | TBD | [7 empty] | 2020-03-04 |  | 2020-03-06 | [13 empty] | 2020-03-11 | [11 empty] | 2020-04-10 | [27 empty] | 2020-04-17 |  |  | 2020-05-17 |  | 2020-04-24 | [16 empty] | 2020-05-15 |  |  | 2020-05-24 | [6 empty] | 2020-06-07 |  |  |  | 2020-06-07 |  |  |  |  | 2020-05-01 |  | 2020-05-11 |  |  | 2020-05-15 |  | 2020-05-18 |  |  | 2020-06-01 |  |  |  | 2020-06-08 |  | JGT-36-340C-2NPT |  |  | 2020-06-20 |  | 2020-05-29 | [6 empty] | 2020-06-28 | 2020-07-05 | [20 empty] | 2020-08-04 |  |  |  | 2020-08-07 | [8 empty] | 2020-06-13 |  | 2020-06-16 |  |  | 2020-06-28 |  |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  |  | 2020-07-11 |  |  | 2020-07-26 |  |  |  | 2020-08-07 |  | 2020-08-10
PH1100356 | 126.2234 | 6.9477 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Oriental | Mati City | Dahican | MIN | PH112509005 | 36485 | 30 | Three Legged Tubular Tower | CO66 | 68.3872 | MIN-1100200 | Level 6 | phase3 | phase3 |  | DICT_76 | Cluster M01 | TBD | [7 empty] | 2020-03-07 |  | 2020-03-09 | [13 empty] | 2020-03-14 | [11 empty] | 2020-04-13 | [27 empty] | 2020-04-20 |  |  | 2020-05-20 |  | 2020-04-27 | [16 empty] | 2020-05-18 |  |  | 2020-05-27 | [6 empty] | 2020-06-10 |  |  |  | 2020-06-10 |  |  |  |  | 2020-05-04 |  | 2020-05-14 |  |  | 2020-05-18 |  | 2020-05-21 |  |  | 2020-06-04 |  |  |  | 2020-06-11 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-06-23 |  | 2020-06-01 | [6 empty] | 2020-07-01 | 2020-07-08 | [20 empty] | 2020-08-07 |  |  |  | 2020-08-10 | [8 empty] | 2020-06-16 |  | 2020-06-19 |  |  | 2020-07-01 |  |  |  | 2020-07-04 |  |  | 2020-07-11 |  |  |  | 2020-07-14 |  |  | 2020-07-29 |  |  |  | 2020-08-10 |  | 2020-08-13
PH1100360 | 126.252 | 6.931 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Oriental | Mati City | Dahican | MIN | PH112509007 | 16212 | 30 | Three Legged Tubular Tower | CO66 | 71.911 | MIN-1100201 | Level 6 | phase3 | phase3 |  |  | Cluster M01 | TBD | [7 empty] | 2020-03-10 |  | 2020-03-12 | [13 empty] | 2020-03-17 | [11 empty] | 2020-04-16 | [27 empty] | 2020-04-23 |  |  | 2020-05-23 |  | 2020-04-30 | [16 empty] | 2020-05-21 |  |  | 2020-05-30 | [6 empty] | 2020-06-13 |  |  |  | 2020-06-13 |  |  |  |  | 2020-05-07 |  | 2020-05-17 |  |  | 2020-05-21 |  | 2020-05-24 |  |  | 2020-06-07 |  |  |  | 2020-06-14 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-06-26 |  | 2020-06-04 | [6 empty] | 2020-07-04 | 2020-07-11 | [20 empty] | 2020-08-10 |  |  |  | 2020-08-13 | [8 empty] | 2020-06-19 |  | 2020-06-22 |  |  | 2020-07-04 |  |  |  | 2020-07-07 |  |  | 2020-07-14 |  |  |  | 2020-07-17 |  |  | 2020-08-01 |  |  |  | 2020-08-13 |  | 2020-08-16
PH1100362 | 126.2617 | 6.9365 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Davao Region (Region XI) | Davao Oriental | Mati City | Dahican | MIN | PH112509007 | 16212 | 30 | Three Legged Tubular Tower | CO66 | 72.7951 | MIN-1100202 | Level 6 | phase3 | phase3 |  |  | Cluster M01 | TBD | [7 empty] | 2020-03-13 |  | 2020-03-15 | [13 empty] | 2020-03-20 | [11 empty] | 2020-04-19 | [27 empty] | 2020-04-26 |  |  | 2020-05-26 |  | 2020-05-03 | [16 empty] | 2020-05-24 |  |  | 2020-06-02 | [6 empty] | 2020-06-16 |  |  |  | 2020-06-16 |  |  |  |  | 2020-05-10 |  | 2020-05-20 |  |  | 2020-05-24 |  | 2020-05-27 |  |  | 2020-06-10 |  |  |  | 2020-06-17 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-06-29 |  | 2020-06-07 | [6 empty] | 2020-07-07 | 2020-07-14 | [20 empty] | 2020-08-13 |  |  |  | 2020-08-16 | [8 empty] | 2020-06-22 |  | 2020-06-25 |  |  | 2020-07-07 |  |  |  | 2020-07-10 |  |  | 2020-07-17 |  |  |  | 2020-07-20 |  |  | 2020-08-04 |  |  |  | 2020-08-16 |  | 2020-08-19
PH1100365 | 125.3744 | 6.7601 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Digos City | Cogon | MIN | PH112403005 | 7998 | 40 | Three Legged Tubular Tower | CO66 | 46.5547 | MIN-1100203 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-17 | 2019-12-17 | 2019-12-19 | 2019-12-18 |  |  |  | 2019-12-18 | 2019-12-19 |  |  |  | 2019-12-19 |  |  |  | 2019-12-24 | [5 empty] | 2019-12-18 |  |  |  | 2019-12-18 |  | 2020-01-23 | [27 empty] | 2020-01-30 |  |  | 2020-02-29 |  | 2020-02-06 | [16 empty] | 2020-02-27 |  |  | 2020-03-07 | [6 empty] | 2020-03-21 |  |  |  | 2020-03-21 |  |  |  |  | 2020-02-13 |  | 2020-02-23 |  |  | 2020-02-27 |  | 2020-03-01 |  |  | 2020-03-15 |  |  |  | 2020-03-22 |  | JGT-36-340C-2NPT |  |  | 2020-04-03 |  | 2020-03-12 | [6 empty] | 2020-04-11 | 2020-04-18 | [20 empty] | 2020-05-18 |  |  |  | 2020-05-21 | [8 empty] | 2020-03-27 |  | 2020-03-30 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-09 |  |  |  | 2020-05-21 |  | 2020-05-24
PH1100367 | 125.4474 | 7.188 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Calinan | MIN | PH112402026 | 23052 | 40 | Three Legged Tubular Tower | CO66 | 21.7359 | MIN-1100204 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M09 | JXD |  | Batch 2 (333) | JXD-2 |  |  |  | 2020-01-15 | 2020-01-17 | 2020-01-14 | 2020-01-19 | 2020-01-15 | 2020-01-16 | 2020-01-18 |  | 2020-01-15 | 2020-01-16 | 2020-01-19 | 2020-02-14 |  | 2020-01-16 |  |  |  | 2020-01-24 |  |  | 2020-02-14 |  | 2020-02-14 | 2020-01-16 | 2020-01-16 | 2020-01-20 |  | 2020-01-16 | 2020-03-06 | 2020-02-23 | 2020-03-06 |  |  | 2020-03-06 | 2020-03-06 | A | HECTOR SALDANA | BRGY. POBLACION, CALINAN, DAVAO CITY | Davao del Sur | 125.4505 | 7.1858 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-02-24 | n/a |  |  |  |  | 2020-03-01 | 2020-02-20 |  | 2020-03-31 | 2020-02-28 | 2020-03-08 | [16 empty] | 2020-03-29 | ok |  | 2020-04-07 | [6 empty] | 2020-04-21 |  | 2020-03-11 |  | 2020-04-21 |  |  |  | RFP submitted, ongoing review | 2020-03-15 |  | 2020-03-25 |  |  | 2020-03-29 | 2020-02-29 | 2020-04-01 | 2020-03-02 | 2020-03-03 | 2020-04-15 |  |  |  | 2020-04-22 |  | JGT-36-340C-2NPT |  |  | 2020-05-04 |  | 2020-04-12 | [6 empty] | 2020-05-12 | 2020-05-19 | [20 empty] | 2020-06-18 |  |  |  | 2020-06-21 | [8 empty] | 2020-04-27 |  | 2020-04-30 |  |  | 2020-05-12 |  |  |  | 2020-05-15 |  |  | 2020-05-22 |  |  |  | 2020-05-25 |  |  | 2020-06-09 |  |  |  | 2020-06-21 |  | 2020-06-24
PH1100368 | 125.4605 | 7.1843 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Calinan | MIN | PH112402026 | 23052 | 40 | Monopole Tower | CO66 | 20.271 | MIN-1100205 | Level 3 (Davao City) - R | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M09 | JXD |  | Batch 2 (333) |  |  |  |  | 2020-01-15 | 2020-02-10 | 2020-01-17 | 2020-02-12 | 2020-02-19 |  |  |  | 2020-02-19 | 2020-02-26 |  |  |  | 2020-02-26 |  |  |  | 2020-02-17 | 2020-02-26 |  |  |  | 2020-02-26 | 2020-03-02 |  |  |  | 2020-03-02 | 2020-03-02 | 2020-03-18 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 |  | JUVELYN VILLAMERO | PRK 17, LANZONA VILLAGE, CALINAN, DAVAO CITY | Davao Del Sur | 125.4599 | 7.1899 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-25 | 2020-02-28 |  | 2020-04-24 | 2020-03-11 | 2020-04-01 | [16 empty] | 2020-04-22 |  |  | 2020-05-01 | [6 empty] | 2020-05-15 |  |  |  | 2020-05-15 |  |  |  | Awaiting Lessor ID | 2020-04-08 |  | 2020-04-18 |  |  | 2020-04-22 | 2020-03-13 | 2020-04-25 |  |  | 2020-05-09 |  |  |  | 2020-05-16 |  | JGT-36-340C-2NPT |  |  | 2020-05-28 |  | 2020-05-06 | [6 empty] | 2020-06-05 | 2020-06-12 | [20 empty] | 2020-07-12 |  |  |  | 2020-07-15 | [8 empty] | 2020-05-21 |  | 2020-05-24 |  |  | 2020-06-05 |  |  |  | 2020-06-08 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-07-03 |  |  |  | 2020-07-15 |  | 2020-07-18
PH1100369 | 125.4703 | 7.1875 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Calinan | MIN | PH112402117 | 6846 | 40 | Three Legged Tubular Tower | CO66 | 19.4962 | MIN-1100206 | Level 3 (Davao City) - R | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M09 | JXD |  | Batch 2 (333) |  |  | JXD |  | 2020-01-15 | 2020-02-13 | 2020-01-17 | 2020-02-15 | 2020-01-18 | 2020-01-18 |  |  | 2020-01-18 | 2020-01-19 |  |  |  | 2020-01-19 |  |  |  | 2020-02-20 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-20 | 2020-01-20 |  |  | 2020-01-20 | 2020-02-28 | 2020-03-21 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 | A | Tita Agravante | Riverside, Calinan, Davao City | Davao del Sur | 125.4766 | 7.1671 | Greenfield | 206m |  | 10 years | P15,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-02-29 | n/a |  |  |  | n/a | 2020-03-28 | 2020-02-14 |  | 2020-04-27 | 2020-03-06 | 2020-04-04 | 2020-03-11 | [15 empty] | 2020-04-25 | ok |  | 2020-05-04 | 2020-03-11 | [5 empty] | 2020-05-18 |  | 2020-03-11 |  | 2020-05-18 |  |  |  | RFP submitted, ongoing review | 2020-04-11 | 2020-02-18 | 2020-04-21 | 2020-02-28 | 2020-02-28 | 2020-04-25 | 2020-02-12 | 2020-04-28 | 2020-02-12 | 2020-02-21 | 2020-05-12 | 2020-02-17 | 2020-03-02 | 2020-02-17 | 2020-05-19 | 2020-03-02 | JGT-36-340C-2NPT |  |  | 2020-05-31 |  | 2020-05-09 | [6 empty] | 2020-06-08 | 2020-06-15 | [20 empty] | 2020-07-15 |  |  |  | 2020-07-18 | [7 empty] | 2020-03-11 | 2020-05-24 | 2020-03-11 | 2020-05-27 | 2020-03-11 |  | 2020-06-08 |  |  |  | 2020-06-11 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-07-06 |  |  |  | 2020-07-18 |  | 2020-07-21
PH1100372 | 125.4859 | 7.1093 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Tugbok | MIN | PH112402127 | 15115 | 40 | Three Legged Tubular Tower | CO66 | 15.1364 | MIN-1100207 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 | DepEd_5032 | Cluster M09 | JXD |  | Batch 2 (333) | JXD-2 |  |  |  | 2020-01-15 | 2020-01-18 | 2020-01-15 | 2020-01-20 | 2020-01-15 | 2020-01-15 |  |  | 2020-01-15 | 2020-02-08 |  |  |  | 2020-02-08 |  |  |  | 2020-01-25 | 2020-02-08 |  |  |  | 2020-02-08 | 2020-01-16 | 2020-01-16 |  |  | 2020-01-16 | 2020-02-19 | 2020-02-24 | [5 empty] | A | Anselma Saliwas | Pomelo St., Poblacion, Tugbok Proper, Davao City | Davao del Sur | 125.4866 | 7.1077 | Greenfield |  |  | 15 years | P30,000 inclusive of VAT and withholding tax | quarterly | 144sqm | n/a | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-03-02 |  |  | 2020-04-01 |  | 2020-03-09 | [16 empty] | 2020-03-30 |  |  | 2020-04-08 | [6 empty] | 2020-04-22 |  |  |  | 2020-04-22 |  |  |  |  | 2020-03-16 |  | 2020-03-26 |  |  | 2020-03-30 |  | 2020-04-02 |  |  | 2020-04-16 |  |  |  | 2020-04-23 |  | JGT-36-340C-2NPT |  |  | 2020-05-05 |  | 2020-04-13 | [6 empty] | 2020-05-13 | 2020-05-20 | [20 empty] | 2020-06-19 |  |  |  | 2020-06-22 | [8 empty] | 2020-04-28 |  | 2020-05-01 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-10 |  |  |  | 2020-06-22 |  | 2020-06-25
PH1100376 | 125.4837 | 7.0275 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Crossing Bayabas | MIN | PH112402014 | 10007 | 40 | Three Legged Tubular Tower | CO66 | 17.2537 | MIN-1100208 | Level 3 (Davao City) - R | phase3 | phase2_1231 | P1_630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2019-12-22 | 2019-12-22 | 2019-12-24 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-25 |  |  |  | 2019-12-25 |  |  |  | 2019-12-29 | 2019-12-26 |  |  |  | 2019-12-26 | 2019-12-23 |  |  |  | 2019-12-23 | 2020-03-06 | 2020-01-28 | 2020-03-06 |  |  | 2020-03-06 | 2020-03-06 | A | Angelita C. Romero | Upper Piedad, Brgy. Bato, Toril, Davao City | Davao del Sur | 125.482 | 7.0269 | Greenfield | 44m |  | 15 years | P10,500 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-02-04 | 2020-02-05 |  | 2020-03-05 |  | 2020-02-11 | 2020-02-27 |  | 2020-02-27 | [13 empty] | 2020-03-03 |  |  | 2020-03-12 | [6 empty] | 2020-03-26 |  |  |  | 2020-03-26 |  |  |  |  | 2020-02-18 |  | 2020-02-28 |  |  | 2020-03-03 | 2020-03-05 | 2020-03-06 | 2020-03-05 | 2020-03-06 | 2020-03-20 | 2020-02-18 |  |  | 2020-03-27 |  | 4GT-42-340C-2NPT |  |  | 2020-04-08 |  | 2020-03-17 | [6 empty] | 2020-04-16 | 2020-04-23 | [20 empty] | 2020-05-23 |  |  |  | 2020-05-26 | [8 empty] | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-04-26 |  |  |  | 2020-04-29 |  |  | 2020-05-14 |  |  |  | 2020-05-26 |  | 2020-05-29
PH1100378 | 125.515 | 7.1035 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Tacunan | MIN | PH112402030 | 32461 | 40 | Three Legged Tubular Tower | CO66 | 11.8895 | MIN-1100209 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M12 | Richworld | PO2019121801PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-11-27 | 2019-12-19 | 2019-12-19 | 2019-12-21 | 2019-12-20 |  |  |  | 2019-12-20 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2019-12-26 | 2020-02-21 |  |  |  | 2020-02-21 | 2019-12-20 |  | 2020-02-20 |  | 2019-12-20 |  | 2020-01-25 | [5 empty] | C |  |  |  | 125.5196 | 7.1054 | [16 empty] | 2020-02-01 | 2020-02-19 |  | 2020-03-02 |  | 2020-02-08 | [16 empty] | 2020-02-29 |  |  | 2020-03-09 | [6 empty] | 2020-03-23 |  |  |  | 2020-03-23 |  |  |  |  | 2020-02-15 |  | 2020-02-25 |  |  | 2020-02-29 | 2020-03-05 | 2020-03-03 | 2020-03-09 | 2020-03-09 | 2020-03-17 |  |  |  | 2020-03-24 |  | 4GT-42-340C-2NPT |  |  | 2020-04-05 |  | 2020-03-14 | [6 empty] | 2020-04-13 | 2020-04-20 | [20 empty] | 2020-05-20 |  |  |  | 2020-05-23 | [8 empty] | 2020-03-29 |  | 2020-04-01 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-11 |  |  |  | 2020-05-23 |  | 2020-05-26
PH1100381 | 125.5662 | 7.0832 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Langub | MIN | PH112402077 | 18081 | 45 | Three Legged Tubular Tower | CO66 | 6.4523 | MIN-1100210 | Level 3 (Davao City) - R | phase2_add | phase2_1231 | P1_630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD |  | MJV |  | 2019-12-12 | 2019-12-19 | 2019-12-19 | 2019-12-21 | 2019-12-21 |  |  |  | 2019-12-21 | 2019-12-21 |  |  |  | 2019-12-21 |  |  |  | 2019-12-26 | 2019-12-22 |  |  |  | 2019-12-22 | 2019-12-21 |  |  |  | 2019-12-21 | 2020-01-24 | 2020-01-25 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Gabriel V. Jose | Purok 7-A, KM8, Matina Pangi, Davao City | Davao del Sur | 125.5592 | 7.0804 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-01 | 2020-02-01 |  | 2020-03-02 | 2020-02-13 | 2020-02-08 | [16 empty] | 2020-02-29 | ok |  | 2020-03-09 | [6 empty] | 2020-03-23 |  | 2020-03-10 | 2020-03-11 | 2020-03-23 |  |  |  | RFP approved, follow up cheque release | 2020-02-15 | 2020-02-13 | 2020-02-25 | 2020-02-22 | 2020-02-23 | 2020-02-29 | 2020-02-12 | 2020-03-03 | 2020-02-12 | 2020-03-02 | 2020-03-17 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 2020-03-24 | 2020-03-02 | 4GT-42-340C-2NPT |  |  | 2020-04-05 |  | 2020-03-14 | [6 empty] | 2020-04-13 | 2020-04-20 | [20 empty] | 2020-05-20 |  |  |  | 2020-05-23 | [7 empty] | 2020-03-02 | 2020-03-29 | 2020-03-05 | 2020-04-01 | 2020-03-06 |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-11 |  |  |  | 2020-05-23 |  | 2020-05-26
PH1100387 | 125.5774 | 7.1145 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Waan | MIN | PH112402195 | 3925 | 40 | Three Legged Tubular Tower | CO66 | 5.2929 | MIN-1100211 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M05 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  |  |  | 2019-12-12 | 2020-01-22 | 2020-01-26 | 2020-01-24 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-02-10 |  |  |  | 2020-02-10 |  |  |  | 2020-01-29 | 2020-02-10 |  |  |  | 2020-02-10 | 2020-01-27 |  |  |  | 2020-01-27 |  | 2020-02-28 | [5 empty] | A |  |  |  | 125.5814 | 7.1087 | [16 empty] | 2020-03-06 | 2020-02-28 |  | 2020-04-05 |  | 2020-03-13 | [16 empty] | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 |  | 2020-03-30 |  |  | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-20 |  |  |  | 2020-04-27 |  | 4GT-42-340C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1100388 | 125.5874 | 7.1536 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Mandug | MIN | PH112402069 | 13594 | 40 | Three Legged Tubular Tower | CO66 | 7.2564 | MIN-1100212 | Level 3 (Davao City) - R | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-10 |  |  |  | 2019-12-10 |  |  |  | 2019-12-14 | [5 empty] | 2019-12-11 | 2019-12-08 |  |  | 2019-12-08 |  | 2020-01-13 | [27 empty] | 2020-01-20 | 2020-02-19 |  | 2020-02-19 |  | 2020-01-27 | [16 empty] | 2020-02-17 |  |  | 2020-02-26 | [6 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  |  | 2020-02-03 |  | 2020-02-13 |  |  | 2020-02-17 |  | 2020-02-20 |  |  | 2020-03-05 |  |  |  | 2020-03-12 |  | JGT-36-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 | [20 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [8 empty] | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1100391 | 125.5971 | 7.1592 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Indangan | MIN | PH112402050 | 14867 | 40 | Three Legged Tubular Tower | CO66 | 7.306 | MIN-1100213 | Level 3 (Davao City) - R | phase2_add | phase2_1231 | P1_630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD |  | Richworld |  | 2019-12-12 | 2019-12-08 | 2019-12-08 | 2019-12-10 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-10 |  |  |  | 2019-12-10 |  |  |  | 2019-12-15 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-18 |  |  |  | 2019-12-18 | 2019-12-23 | 2020-01-14 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | A | Roland Monreal | Brgy. Indangan, Davao City | Davao del Sur | 125.5997 | 7.1576 | Greenfield |  |  | 15 years | P18,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-21 | 2020-02-05 |  | 2020-02-20 | 2020-03-12 | 2020-01-28 | 2020-01-22 |  | 2020-01-22 | [13 empty] | 2020-02-18 | ok |  | 2020-02-27 | [6 empty] | 2020-03-12 |  |  |  | 2020-03-12 |  |  |  | For RFP submission in DingTalk | 2020-02-04 | 2020-02-21 | 2020-02-14 | 2020-02-27 | 2020-02-27 | 2020-02-18 | 2020-02-18 | 2020-02-21 | 2020-02-18 | 2020-02-21 | 2020-03-06 | 2020-02-19 | 2020-02-28 | 2020-02-28 | 2020-03-13 | 2020-02-28 | JGT-36-340C-2NPT |  |  | 2020-03-25 | 2020-02-28 | 2020-03-03 | [6 empty] | 2020-04-02 | 2020-04-09 | [20 empty] | 2020-05-09 |  |  |  | 2020-05-12 | [7 empty] | 2020-02-26 | 2020-03-18 | 2020-03-06 | 2020-03-21 | 2020-03-06 |  | 2020-04-02 |  |  |  | 2020-04-05 |  |  | 2020-04-12 |  |  |  | 2020-04-15 |  |  | 2020-04-30 |  |  |  | 2020-05-12 |  | 2020-05-15
PH1100394 | 125.6224 | 7.5548 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Santo Tomas | Tibal-Og | MIN | PH112318011 | 41354 | 40 | Three Legged Tubular Tower | CO65 | 23.8487 | MIN-1100214 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  | Enovell |  | 2019-12-12 | 2019-12-13 | 2019-12-13 | 2019-12-15 | 2019-12-14 | 2020-01-15 | 2020-01-23 |  | 2019-12-14 |  | 2020-01-16 | 2020-01-25 |  | 2020-01-16 |  |  |  | 2019-12-20 |  |  | 2020-01-25 |  | 2020-01-25 | 2019-12-14 | 2020-01-15 | 2020-01-23 |  | 2019-12-14 | 2020-02-25 | 2020-01-19 | [5 empty] | A | Yen Yen Perez | Purok 9, FD Rd., Tibal-og, Sto. Tomas | Davao del Norte | 125.6173 | 7.5307 | Greenfield |  |  | 10 years | P20,000 Exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-26 | 2020-01-25 |  | 2020-02-25 | 2020-02-21 | 2020-02-02 | [16 empty] | 2020-02-23 |  |  | 2020-03-03 | [6 empty] | 2020-03-17 |  |  |  | 2020-03-17 |  |  |  | Awaiting MOC approval | 2020-02-09 | 2020-02-13 | 2020-02-19 | 2020-02-28 | 2020-02-28 | 2020-02-23 | 2020-02-19 | 2020-02-26 | 2020-03-04 |  | 2020-03-11 | 2020-02-28 |  |  | 2020-03-18 |  | 4GT-42-340C-2NPT |  |  | 2020-03-30 |  | 2020-03-08 | [6 empty] | 2020-04-07 | 2020-04-14 | [20 empty] | 2020-05-14 |  |  |  | 2020-05-17 | [7 empty] | 2020-03-01 | 2020-03-23 |  | 2020-03-26 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-05-05 |  |  |  | 2020-05-17 |  | 2020-05-20
PH1100396 | 125.6168 | 7.1485 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Indangan | MIN | PH112402023 | 43758 | 40 | Three Legged Tubular Tower | CO66 | 5.5884 | MIN-1100215 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD-2 |  | Richworld |  | 2019-12-12 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-09 | 2019-12-09 |  |  | 2019-12-09 |  | 2019-12-10 |  |  | 2019-12-10 |  |  |  | 2019-12-14 |  | 2019-12-17 |  |  | 2019-12-17 | 2019-12-08 | 2019-12-08 |  |  | 2019-12-08 | 2019-12-23 | 2020-01-13 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | B | Maria Jurnaliza Sumilhig | Communal, Buhangin, Davao City | Davao del Sur | 125.6159 | 7.1494 | Greenfield |  |  | 15 years | P15,000 exclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-20 | 2020-02-05 |  | 2020-02-19 | 2020-02-21 | 2020-01-27 | [16 empty] | 2020-02-17 | ok |  | 2020-02-26 | [6 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  | For MOC/NRAF resubmission (different option approved) | 2020-02-03 | 2020-02-17 | 2020-02-13 | 2020-02-28 | 2020-02-28 | 2020-02-17 | 2020-02-17 | 2020-02-20 | 2020-02-22 | 2020-02-27 | 2020-03-05 | 2020-02-26 | 2020-02-28 | 2020-02-28 | 2020-03-12 | 2020-02-28 | JGT-36-340C-2NPT |  |  | 2020-03-24 | 2020-02-28 | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 | [20 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [7 empty] | 2020-02-26 | 2020-03-17 | 2020-03-08 | 2020-03-20 | 2020-03-08 |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1100399 | 125.6289 | 7.1482 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Panacan | MIN | PH112402035 | 16740 | 40 | Three Legged Tubular Tower | CO66 | 5.5577 | MIN-1100216 | Level 3 (Davao City) - R | phase2_add | phase2_1231 | P1_630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) | JXD |  | Richworld | PH20200309001 | 2019-12-12 | 2019-12-10 | 2019-12-10 | 2019-12-12 | 2019-12-11 |  |  |  | 2019-12-11 | 2019-12-12 |  |  |  | 2019-12-12 |  |  |  | 2019-12-17 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-11 |  |  |  | 2019-12-11 | 2020-01-24 | 2020-01-16 | 2020-01-09 |  |  | 2020-01-10 | 2020-02-04 | A | Marcial Orogo | Purok 6, Communal, Davao City | Davao del Sur | 125.6279 | 7.1495 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 100sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-23 | 2020-02-05 |  | 2020-02-22 | 2020-02-21 | 2020-01-30 | [16 empty] | 2020-02-20 | ok |  | 2020-02-29 | [6 empty] | 2020-03-14 |  |  |  | 2020-03-14 |  |  |  | For RFP submission in DingTalk | 2020-02-06 | 2020-02-14 | 2020-02-16 | 2020-02-28 | 2020-02-28 | 2020-02-20 | 2020-02-15 | 2020-02-23 | 2020-02-17 |  | 2020-03-08 | 2020-02-15 | 2020-02-28 | 2020-02-28 | 2020-03-15 | 2020-02-28 | 4GT-42-340C-2NPT |  |  | 2020-03-27 | 2020-02-28 | 2020-03-05 | [6 empty] | 2020-04-04 | 2020-04-11 | [20 empty] | 2020-05-11 |  |  |  | 2020-05-14 | [7 empty] | 2020-03-08 | 2020-03-20 | 2020-03-08 | 2020-03-23 | 2020-03-08 |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-05-02 |  |  |  | 2020-05-14 |  | 2020-05-17
PH1100401 | 125.6457 | 7.2029 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Mahayag | MIN | PH112402124 | 41864 | 40 | Three Legged Tubular Tower | CO66 | 11.8793 | MIN-1100217 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2019-12-23 | 2019-12-23 | 2019-12-25 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-01-27 |  |  |  | 2020-01-27 |  |  |  | 2019-12-30 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-02-04 | 2020-01-29 | [5 empty] | A | Erlinda Escasinas | KM 19, San Juan Tibungco, Davao City | Davao del Sur | 125.6467 | 7.1978 | Greenfield | 23m |  | 10 years | P20,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-05 | 2020-02-26 |  | 2020-03-06 |  | 2020-02-12 | [16 empty] | 2020-03-04 |  |  | 2020-03-13 | [6 empty] | 2020-03-27 |  |  |  | 2020-03-27 |  |  |  |  | 2020-02-19 |  | 2020-02-29 |  |  | 2020-03-04 |  | 2020-03-07 |  |  | 2020-03-21 |  |  |  | 2020-03-28 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-04-09 |  | 2020-03-18 | [6 empty] | 2020-04-17 | 2020-04-24 | [20 empty] | 2020-05-24 |  |  |  | 2020-05-27 | [8 empty] | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-04-27 |  |  |  | 2020-04-30 |  |  | 2020-05-15 |  |  |  | 2020-05-27 |  | 2020-05-30
PH1100402 | 125.6416 | 7.1645 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Mudiang | MIN | PH112402087 | 35806 | 40 | Three Legged Tubular Tower | CO66 | 7.6229 | MIN-1100218 | Level 3 (Davao City) - R | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-20 | 2019-12-20 | 2019-12-22 | 2019-12-21 | 2019-12-29 |  |  | 2019-12-21 | 2020-01-15 | 2020-02-21 |  |  | 2020-01-15 |  |  |  | 2019-12-27 |  | 2020-02-21 |  |  | 2020-02-21 | 2019-12-21 | 2019-12-29 | 2020-02-20 |  | 2019-12-21 |  | 2020-01-26 | [5 empty] | C |  |  |  | 125.6346 | 7.1631 | [16 empty] | 2020-02-02 | 2020-02-19 |  | 2020-03-03 |  | 2020-02-09 | [16 empty] | 2020-03-01 |  |  | 2020-03-10 | [6 empty] | 2020-03-24 |  |  |  | 2020-03-24 |  |  |  |  | 2020-02-16 |  | 2020-02-26 |  |  | 2020-03-01 |  | 2020-03-04 |  |  | 2020-03-18 |  |  |  | 2020-03-25 |  | JGT-36-340C-2NPT |  |  | 2020-04-06 |  | 2020-03-15 | [6 empty] | 2020-04-14 | 2020-04-21 | [20 empty] | 2020-05-21 |  |  |  | 2020-05-24 | [8 empty] | 2020-03-30 |  | 2020-04-02 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-12 |  |  |  | 2020-05-24 |  | 2020-05-27
PH1100406 | 125.6563 | 7.2899 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Panabo City | Maduao | MIN | PH112315019 | 3114 | 40 | Three Legged Tubular Tower | CO66 | 21.5985 | MIN-1100219 | Level 5 | phase3 | phase3 | PO Issued not 630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-04-22 | 2020-02-11 | 2020-04-24 | [13 empty] | 2020-04-29 | [11 empty] | 2020-05-29 | [27 empty] | 2020-06-05 |  |  | 2020-07-05 |  | 2020-06-12 | [16 empty] | 2020-07-03 |  |  | 2020-07-12 | [6 empty] | 2020-07-26 |  |  |  | 2020-07-26 |  |  |  |  | 2020-06-19 |  | 2020-06-29 |  |  | 2020-07-03 |  | 2020-07-06 |  |  | 2020-07-20 |  |  |  | 2020-07-27 |  | JGT-36-340C-2NPT |  |  | 2020-08-08 |  | 2020-07-17 | [6 empty] | 2020-08-16 | 2020-08-23 | [20 empty] | 2020-09-22 |  |  |  | 2020-09-25 | [8 empty] | 2020-08-01 |  | 2020-08-04 |  |  | 2020-08-16 |  |  |  | 2020-08-19 |  |  | 2020-08-26 |  |  |  | 2020-08-29 |  |  | 2020-09-13 |  |  |  | 2020-09-25 |  | 2020-09-28
PH1100407 | 125.6653 | 7.2669 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | n.a. ( 39395) | MIN | PH112402056 | 10223 | 40 | Three Legged Tubular Tower | CO66 | 19.302 | MIN-1100220 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 | DepEd_3236 | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2020-01-16 | 2020-01-15 | 2020-01-18 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-23 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-24 | 2020-02-22 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Teresita S. Dadole | Purok Pantukan, J.P. Laurel, Panabo City | Davao del Norte | 125.6691 | 7.2682 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-29 | 2020-02-26 |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 | ok |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 | 2020-03-07 | 2020-03-24 |  |  | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-14 |  |  |  | 2020-04-21 |  | JGT-36-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1100412 | 125.7107 | 7.3377 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Carmen | Santo Nino | MIN | PH112303019 | 5784 | 40 | Three Legged Tubular Tower | CO65 | 16.0133 | MIN-1100221 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2019-12-02 | 2019-12-02 | 2019-12-04 | 2019-12-10 | 2020-01-06 | 2020-01-13 |  | 2019-12-10 | 2019-12-10 | 2020-01-07 |  |  | 2019-12-10 |  |  |  | 2019-12-09 |  | 2020-01-07 |  |  | 2020-01-07 | 2019-12-02 | 2019-12-02 | 2020-01-13 |  | 2019-12-02 | 2020-01-24 | 2020-01-08 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | B | Michael Arado | Brgy. Ising, Carmen | Davao del Norte | 125.702 | 7.3582 | Greenfield | 9m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 240sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-15 | 2020-01-10 |  | 2020-02-14 |  | 2020-01-22 | [16 empty] | 2020-02-12 |  |  | 2020-02-21 | [6 empty] | 2020-03-06 |  |  |  | 2020-03-06 |  |  |  |  | 2020-01-29 |  | 2020-02-08 |  |  | 2020-02-12 |  | 2020-02-15 |  |  | 2020-02-29 |  |  |  | 2020-03-07 |  | JGT-36-340C-2NPT |  |  | 2020-03-19 |  | 2020-02-26 | [6 empty] | 2020-03-27 | 2020-04-03 | [20 empty] | 2020-05-03 |  |  |  | 2020-05-06 | [8 empty] | 2020-03-12 |  | 2020-03-15 |  |  | 2020-03-27 |  |  |  | 2020-03-30 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-24 |  |  |  | 2020-05-06 |  | 2020-05-09
PH1100418 | 125.9736 | 7.624 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Nabunturan | Magsaysay | MIN | PH118209010 | 5301 | 40 | Three Legged Tubular Tower | CO65 | 27.0317 | MIN-1100222 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M07 | EPC | PO2019122103PH_WLS | Batch 2 | EPC |  | EPC |  | 2020-01-20 | 2019-12-30 | 2019-12-30 | 2020-01-01 | 2020-01-01 |  |  |  | 2020-01-01 | 2020-01-05 |  |  |  | 2020-01-05 |  |  |  | 2020-01-06 | 2020-01-03 |  |  |  | 2020-01-03 | 2020-01-01 |  |  |  | 2020-01-01 | 2020-01-24 | 2020-02-05 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Ernie B. Cartera | Purok 1, Recto Magsaysay, Nabunturan, Davao de Oro | Compostela Valley | 125.9732 | 7.625 | Greenfield | 92m |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-02-19 | n/a |  |  |  |  | 2020-02-12 | 2020-01-23 |  | 2020-03-13 | 2020-02-19 | 2020-02-19 | 2020-02-26 | 2020-02-26 | 2020-02-26 |  |  | 2020-03-04 | [10 empty] | 2020-03-11 | ok | 2020-03-04 | 2020-03-20 | 2020-02-26 | [5 empty] | 2020-04-03 |  |  |  | 2020-04-03 |  |  |  | Incorrect DITO information on BR | 2020-02-26 | 2020-02-06 | 2020-03-07 | 2020-02-21 | 2020-02-21 | 2020-03-11 | 2020-02-14 | 2020-03-14 | 2020-02-25 | 2020-02-25 | 2020-03-28 | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-04-04 | 2020-02-25 | 4GT-42-340C-2NPT |  |  | 2020-04-16 |  | 2020-03-25 | [6 empty] | 2020-04-24 | 2020-05-01 | [20 empty] | 2020-05-31 |  |  |  | 2020-06-03 | [7 empty] | 2020-02-27 | 2020-04-09 | 2020-03-07 | 2020-04-12 | 2020-03-07 |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-04 |  |  |  | 2020-05-07 |  |  | 2020-05-22 |  |  |  | 2020-06-03 |  | 2020-06-06
PH1100421 | 126.0824 | 7.6826 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Compostela | Bagongon | MIN | PH118201001 | 2025 | 40 | Three Legged Tubular Tower | CO65 | 40.1844 | MIN-1100223 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M07 | EPC | [7 empty] | 2020-03-08 | 2020-01-16 | 2020-03-10 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-01-22 |  |  |  | 2020-01-22 |  |  |  | 2020-03-15 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-02-24 | 2020-04-14 | [5 empty] | A | Roberto Villegas | P-10, Poblacion, Compostela, Davao de Oro | Compostela Valley | 126.0862 | 7.6779 | Greenfield | 84m |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 240sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-04-21 | 2020-02-26 |  | 2020-05-21 |  | 2020-04-28 | [16 empty] | 2020-05-19 | ok |  | 2020-05-28 | 2020-03-11 | [5 empty] | 2020-06-11 |  |  |  | 2020-06-11 |  |  |  |  | 2020-05-05 |  | 2020-05-15 |  |  | 2020-05-19 |  | 2020-05-22 |  |  | 2020-06-05 |  |  |  | 2020-06-12 |  | JGT-36-340C-2NPT |  |  | 2020-06-24 |  | 2020-06-02 | [6 empty] | 2020-07-02 | 2020-07-09 | [20 empty] | 2020-08-08 |  |  |  | 2020-08-11 | [8 empty] | 2020-06-17 |  | 2020-06-20 |  |  | 2020-07-02 |  |  |  | 2020-07-05 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-30 |  |  |  | 2020-08-11 |  | 2020-08-14
PH1100422 | 126.0822 | 7.6602 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Compostela | Lagab | MIN | PH118201009 | 5602 | 40 | Three Legged Tubular Tower | CO65 | 38.5766 | MIN-1100224 | Level 6 | phase3 | phase3 |  |  | Cluster M07 | EPC | [7 empty] | 2020-03-11 | 2020-01-16 | 2020-03-13 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-01-22 |  |  |  | 2020-01-22 |  |  |  | 2020-03-18 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-02-13 | 2020-04-17 | [5 empty] | A | Alicia Antonio | Purok 2, Poblacion Campostela, Davao De oro | Compostela Valley | 126.0865 | 7.6649 | Greenfield | 80m |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 200sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-04-24 | 2020-02-26 |  | 2020-05-24 |  | 2020-05-01 | [16 empty] | 2020-05-22 | ok |  | 2020-05-31 | [6 empty] | 2020-06-14 |  |  |  | 2020-06-14 |  |  |  |  | 2020-05-08 |  | 2020-05-18 |  |  | 2020-05-22 |  | 2020-05-25 |  |  | 2020-06-08 |  |  |  | 2020-06-15 |  | JGT-36-340C-2NPT |  |  | 2020-06-27 |  | 2020-06-05 | [6 empty] | 2020-07-05 | 2020-07-12 | [20 empty] | 2020-08-11 |  |  |  | 2020-08-14 | [8 empty] | 2020-06-20 |  | 2020-06-23 |  |  | 2020-07-05 |  |  |  | 2020-07-08 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-08-02 |  |  |  | 2020-08-14 |  | 2020-08-17
PH1100438 | 126.2796 | 6.921 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Oriental | Mati City | Dahican | MIN | PH112509007 | 16212 | 40 | Three Legged Tubular Tower | CO66 | 75.1496 | MIN-1100225 | Level 6 | phase3 | phase3 |  |  | Cluster M01 | TBD | [7 empty] | 2020-03-16 |  | 2020-03-18 | [13 empty] | 2020-03-23 | [11 empty] | 2020-04-22 | [27 empty] | 2020-04-29 |  |  | 2020-05-29 |  | 2020-05-06 | [16 empty] | 2020-05-27 |  |  | 2020-06-05 | [6 empty] | 2020-06-19 |  |  |  | 2020-06-19 |  |  |  |  | 2020-05-13 |  | 2020-05-23 |  |  | 2020-05-27 |  | 2020-05-30 |  |  | 2020-06-13 |  |  |  | 2020-06-20 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-07-02 |  | 2020-06-10 | [6 empty] | 2020-07-10 | 2020-07-17 | [20 empty] | 2020-08-16 |  |  |  | 2020-08-19 | [8 empty] | 2020-06-25 |  | 2020-06-28 |  |  | 2020-07-10 |  |  |  | 2020-07-13 |  |  | 2020-07-20 |  |  |  | 2020-07-23 |  |  | 2020-08-07 |  |  |  | 2020-08-19 |  | 2020-08-22
PH1100440 | 125.4504 | 7.1201 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Tagakpan | MIN | PH112402112 | 4208 | 40 | Three Legged Tubular Tower | CO66 | 19.1512 | MIN-1100226 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M09 | JXD |  | Batch 2 (333) | JXD-2 |  |  |  | 2020-01-15 | 2020-01-16 | 2020-01-15 | 2020-01-18 | 2020-01-16 | 2020-01-16 | 2020-01-16 |  | 2020-01-16 |  | 2020-01-16 |  |  | 2020-01-16 |  |  |  | 2020-01-23 |  | 2020-01-16 |  |  | 2020-01-16 | 2020-01-16 | 2020-01-16 | 2020-01-16 |  | 2020-01-16 | 2020-02-19 | 2020-02-22 | [5 empty] | B | Florencio Abnera | Purok 5 Naming Ngalan, Tugbok Davao City | Davao del Sur | 125.4511 | 7.1198 | Greenfield | 362m |  | 15 years | P30,000 inclusive of VAT and withholding tax | quarterly | 144sqm | n/a | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-29 | 2020-02-21 |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 |  | 2020-03-24 |  |  | 2020-03-28 | 2020-02-29 | 2020-03-31 | 2020-03-02 | 2020-03-02 | 2020-04-14 |  |  |  | 2020-04-21 |  | JGT-36-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1100443 | 125.6403 | 7.2241 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bunawan | MIN | PH112402022 | 23495 | 40 | Monopole Tower | CO66 | 14.0953 | MIN-1100227 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 | DepEd_3307 | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2019-12-21 | 2019-12-21 | 2019-12-23 | 2019-12-22 |  |  |  | 2019-12-22 | 2019-12-23 |  |  |  | 2019-12-23 |  |  |  | 2019-12-28 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-22 |  |  |  | 2019-12-22 | 2020-01-24 | 2020-01-27 | 2020-01-10 |  |  | 2020-01-10 | 2020-02-04 | A | Gilda Cabangangan | Purok 11-B, Brgy. Bunawan Proper, Bunawan, Davao City | Davao del Sur | 125.6389 | 7.2245 | Greenfield | 31m |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-27 | n/a |  |  |  | n/a | 2020-02-03 | 2020-01-06 |  | 2020-03-04 |  | 2020-02-10 | 2020-01-27 | 2020-02-27 | 2020-01-27 | [13 empty] | 2020-03-02 |  |  | 2020-03-11 | 2020-01-13 | [5 empty] | 2020-03-25 |  |  |  | 2020-03-25 |  |  |  |  | 2020-02-17 | 2020-02-28 | 2020-02-27 | 2020-03-05 | 2020-03-05 | 2020-03-02 | 2020-03-06 | 2020-03-05 | 2020-03-06 | 2020-03-06 | 2020-03-19 | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2020-03-26 | 2020-03-06 | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-04-07 |  | 2020-03-16 | [6 empty] | 2020-04-15 | 2020-04-22 | [20 empty] | 2020-05-22 |  |  |  | 2020-05-25 | [8 empty] | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-04-25 |  |  |  | 2020-04-28 |  |  | 2020-05-13 |  |  |  | 2020-05-25 |  | 2020-05-28
PH1100445 | 125.7965 | 7.5095 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Cuambogan | MIN | PH112319006 | 10612 | 45 | Three Legged Tubular Tower | CO65 | 7.3215 | MIN-1100228 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | JXD-2 |  | Enovell |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 | 2020-02-11 |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-13 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-07 | 2019-12-07 | 2019-12-07 |  | 2019-12-07 | 2019-12-23 | 2020-01-12 | 2020-03-11 |  |  | 2020-03-09 | 2020-03-11 | A | Efrin Pitogo | San Antonio Baca, Cuambugan, Tagum City | Davao del Norte | 125.7939 | 7.5104 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-01-23 | 2020-02-13 | 2020-02-18 | 2020-02-13 | 2020-01-26 | 2020-02-28 | 2020-02-28 | 2020-02-28 | [13 empty] | 2020-02-16 | ok |  | 2020-02-25 | [6 empty] | 2020-03-10 |  | 2020-03-10 |  | 2020-03-10 |  |  |  | RFP submitted, ongoing review | 2020-02-02 | 2020-02-12 | 2020-02-12 | 2020-02-28 | 2020-02-28 | 2020-02-16 | 2020-02-14 | 2020-02-19 | 2020-02-14 | 2020-02-21 | 2020-03-04 | 2020-02-15 | 2020-03-05 | 2020-03-05 | 2020-03-11 | 2020-03-05 | JGT-36-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [7 empty] | 2020-02-24 | 2020-03-16 | 2020-03-10 | 2020-03-19 | 2020-03-10 |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100448 | 125.8068 | 7.3831 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Madaum | MIN | PH112319009 | 10721 | 45 | Three Legged Tubular Tower | CO65 | 6.8477 | MIN-1100229 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | JXD-2 |  | Padccon |  | 2019-11-27 | 2019-11-29 | 2019-11-29 | 2019-12-01 | 2019-12-06 |  |  |  | 2019-12-06 | 2019-12-07 |  |  |  | 2019-12-07 |  |  |  | 2019-12-06 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-06 | 2019-12-06 | 2019-12-06 | 2019-12-06 | 2019-12-06 | 2020-02-13 | 2020-01-05 | 2020-01-08 |  |  | 2020-01-09 | 2020-02-04 | B | Adjumar Quitab | Ladia St., Madaum, Tagum City | Davao del Norte | 125.807 | 7.3831 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | 2020-01-25 | n/a |  |  |  |  | 2020-01-12 | 2020-01-25 |  | 2020-02-11 | 2020-02-07 | 2020-01-19 | [16 empty] | 2020-02-09 | ok |  | 2020-02-18 | [6 empty] | 2020-03-03 |  | 2020-02-19 |  | 2020-03-03 |  |  |  | RFP rejected, incorrect DITO information on BR | 2020-01-26 | 2020-01-15 | 2020-02-05 | 2020-01-25 | 2020-01-25 | 2020-02-09 | 2020-01-29 | 2020-02-12 | 2020-01-29 | 2020-01-30 | 2020-02-26 | 2020-01-30 | 2020-01-31 | 2020-02-10 | 2020-03-04 | 2020-02-20 | JGT-36-340C-2NPT |  |  | 2020-03-16 |  | 2020-02-23 | [6 empty] | 2020-03-24 | 2020-03-31 | [20 empty] | 2020-04-30 |  |  |  | 2020-05-03 | [7 empty] | 2020-02-26 | 2020-03-09 | 2020-01-31 | 2020-03-12 |  |  | 2020-03-24 |  |  |  | 2020-03-27 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-21 |  |  |  | 2020-05-03 |  | 2020-05-06
PH1100449 | 125.8059 | 7.4792 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Tagum City | La Filipina | MIN | PH112319007 | 15390 | 45 | Three Legged Tubular Tower | CO65 | 3.8536 | MIN-1100230 | Level 5 | phase2_add | phase2_1231 | P1_630 |  | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  | Enovell |  | 2019-11-27 | 2019-11-28 | 2019-11-28 | 2019-11-30 | 2019-12-06 | 2020-01-27 |  |  | 2019-12-06 |  | 2019-12-17 |  |  | 2019-12-17 |  |  |  | 2019-12-05 |  | 2019-12-17 |  |  | 2019-12-17 | 2019-12-06 | 2020-01-27 |  |  | 2019-12-06 | 2020-01-24 | 2020-01-04 | 2020-01-09 |  |  | 2020-01-10 | 2020-02-06 | B | Tirso G. Magdoza | Purok 2, La Filipina, Tagum City | Davao del Norte | 125.8058 | 7.4788 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-11 | 2020-02-04 |  | 2020-02-10 |  | 2020-01-18 | [16 empty] | 2020-02-08 | ok |  | 2020-02-17 | [6 empty] | 2020-03-02 |  |  |  | 2020-03-02 |  |  |  |  | 2020-01-25 | 2020-02-19 | 2020-02-04 | 2020-02-28 | 2020-02-28 | 2020-02-08 | 2020-02-25 | 2020-02-11 | 2020-02-25 | 2020-03-07 | 2020-02-25 | 2020-03-07 | 2020-03-07 | 2020-03-07 | 2020-03-03 | 2020-03-07 | JGT-36-340C-2NPT |  |  | 2020-03-15 |  | 2020-02-22 | [6 empty] | 2020-03-23 | 2020-03-30 | [20 empty] | 2020-04-29 |  |  |  | 2020-05-02 | [7 empty] | 2020-02-24 | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-23 |  |  |  | 2020-03-26 |  |  | 2020-04-02 |  |  |  | 2020-04-05 |  |  | 2020-04-20 |  |  |  | 2020-05-02 |  | 2020-05-05
PH1100451 | 125.8426 | 7.474 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Magdum | MIN | PH112319010 | 10216 | 45 | Three Legged Tubular Tower | CO65 | 5.0152 | MIN-1100231 | Level 5 | phase2_add | phase2_1231 | P1_630 | DepEd_3290 | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  | Enovell | PH20200302004 | 2019-11-27 | 2019-11-28 | 2019-11-28 | 2019-11-30 | 2019-12-03 | 2019-12-03 | 2019-12-03 |  | 2019-12-03 | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2019-12-04 |  |  |  | 2019-12-05 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-07 | 2019-12-07 | 2019-12-07 |  | 2019-12-07 | 2020-03-04 | 2020-01-04 | 2020-03-05 |  |  | 2020-03-04 | 2020-03-05 | A | Richie L. Ragudo | Purok 2, Magdum, Tagum City | Davao del Norte | 125.8426 | 7.4739 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-11 | 2020-01-28 |  | 2020-02-10 | 2020-02-24 | 2020-01-18 | [16 empty] | 2020-02-08 | ok |  | 2020-02-17 | [6 empty] | 2020-03-02 |  | 2020-03-02 | 2020-03-11 | 2020-03-02 | 2020-03-13 |  |  | Cheque released | 2020-01-25 | 2020-02-14 | 2020-02-04 | 2020-03-01 | 2020-03-01 | 2020-02-08 | 2020-02-24 | 2020-02-11 | 2020-02-26 | 2020-03-03 | 2020-02-25 | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-03-03 | JGT-36-340C-2NPT |  |  | 2020-03-15 |  | 2020-02-22 | [6 empty] | 2020-03-23 | 2020-03-30 | [20 empty] | 2020-04-29 |  |  |  | 2020-05-02 | [7 empty] | 2020-02-24 | 2020-03-08 | 2020-03-08 | 2020-03-11 | 2020-03-08 |  | 2020-03-23 |  |  |  | 2020-03-26 |  |  | 2020-04-02 |  |  |  | 2020-04-05 |  |  | 2020-04-20 |  |  |  | 2020-05-02 |  | 2020-05-05
PH1100453 | 125.6127 | 7.2765 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Panabo City | San Nicolas | MIN | PH112315030 | 2071 | 45 | Three Legged Tubular Tower | CO66 | 19.8215 | MIN-1100232 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2020-01-16 | 2020-01-15 | 2020-01-18 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-23 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-24 | 2020-02-22 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Antonio G. Delica | Purok 3-A, Brgy. San Isidro, Bunawan | Davao del Norte | 125.6333 | 7.2468 | Greenfield | 20m |  | 15 years | P25,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-02-29 | 2020-01-23 |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 | ok |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 | 2020-03-06 | 2020-03-24 |  |  | 2020-03-28 | 2020-02-19 | 2020-03-31 | 2020-03-10 |  | 2020-04-14 |  |  |  | 2020-04-21 |  | JGT-36-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1100454 | 125.5734 | 7.1678 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Mandug | MIN | PH112402082 | 2626 | 40 | Three Legged Tubular Tower | CO66 | 9.425 | MIN-1100233 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M04 | Richworld | PO2019122101PH_WLS | Batch 1 (333) | JXD-2 |  |  |  | 2019-12-12 | 2020-01-25 | 2019-12-07 | 2020-01-27 | 2019-12-09 | 2020-02-05 | 2020-02-05 |  | 2019-12-09 | 2019-12-10 |  |  |  | 2019-12-10 |  |  |  | 2020-02-01 | 2020-01-29 |  |  |  | 2020-01-29 | 2019-12-08 | 2020-01-27 | 2020-01-29 | 2020-02-05 | 2019-12-08 |  | 2020-03-02 | [5 empty] | A |  |  |  | 125.5752 | 7.1657 | [16 empty] | 2020-03-09 | 2020-02-26 |  | 2020-04-08 |  | 2020-03-16 | [11 empty] | 0920-9534181 |  |  |  |  | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 |  | 2020-04-02 |  |  | 2020-04-06 | 2020-03-02 | 2020-04-09 | 2020-03-03 | 2020-03-04 | 2020-04-23 |  |  |  | 2020-04-30 |  | JGT-36-340C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1100455 | 125.7177 | 7.4837 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Santo Tomas | San Vicente | MIN | PH112318018 | 3493 | 45 | Three Legged Tubular Tower | CO65 | 10.8619 | MIN-1100234 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_3410 | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  | Enovell |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-13 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-07 | 2019-12-07 | 2019-12-07 |  | 2019-12-07 | 2019-12-23 | 2020-01-12 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | A | Fulgencio Jarison | Salvacion, Sto. Tomas | Davao del Norte | 125.7174 | 7.4835 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-01-30 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 | ok |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 | 2020-02-24 | 2020-02-12 | 2020-02-28 | 2020-02-28 | 2020-02-16 | 2020-02-24 | 2020-02-19 | 2020-02-26 | 2020-02-27 | 2020-03-04 | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-03-11 | 2020-02-27 | 4GT-42-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [7 empty] | 2020-02-24 | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100456 | 125.5803 | 7.3431 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Panabo City | Katipunan | MIN | PH112315021 | 5406 | 30 | Three Legged Tubular Tower | CO65 | 27.5347 | MIN-1100235 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-15 |  |  |  | 2019-12-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2019-12-13 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-16 | 2020-02-05 |  |  | 2020-01-16 | 2020-02-05 | 2020-01-12 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-10 | A | Gregorio C. Bainticulo | Purok 4, Brgy. Manay, Panabo City | Davao del Norte | 125.579 | 7.3428 | Greenfield | 47m |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-02-13 | n/a |  |  |  |  | 2020-01-19 | 2020-01-23 |  | 2020-02-18 | 2020-02-13 | 2020-01-26 | [16 empty] | 2020-02-16 | ok |  | 2020-02-25 | 2020-03-11 | [5 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  | Incorrect DITO information on BR | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 | 2020-02-13 | 2020-02-19 | 2020-03-03 | 2020-03-04 | 2020-03-04 |  |  |  | 2020-03-11 |  | 4GT-42-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [7 empty] | 2020-03-02 | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100458 | 125.3113 | 6.7684 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Digos City | Matti | MIN | PH112403014 | 6016 | 40 | Three Legged Tubular Tower | CO66 | 50.2859 | MIN-1100236 | Level 5 | phase2_add | phase2_1231 | P1_630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-06 | 2020-01-28 |  |  | 2019-12-06 | 2019-12-07 |  |  |  | 2019-12-07 |  |  |  | 2019-12-13 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-11 | 2020-01-28 |  |  | 2019-12-11 | 2019-12-27 | 2020-01-12 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Ester N. Carpio | Purok 3, Matti, Digos City | Davao del Sur | 125.3127 | 7.1752 | Greenfield | 50m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-01-13 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 | 2020-03-09 | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | 4GT-42-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100464 | 125.6457 | 7.2387 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bunawan | MIN | PH112402022 | 23495 | 40 | Monopole Tower | CO66 | 15.7948 | MIN-1100237 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2020-01-08 |  |  |  | 2020-01-08 | [8 empty] | 2019-12-13 | [5 empty] | 2020-01-08 |  |  |  | 2020-01-08 |  | 2020-01-12 | [27 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100465 | 125.3921 | 7.1738 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Malagos | MIN | PH112402007 | 4655 | 40 | Monopole Tower | CO66 | 26.7818 | MIN-1100238 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M09 | JXD |  | Batch 2 (333) | JXD-2 |  |  |  | 2020-01-15 | 2020-01-16 | 2020-01-15 | 2020-01-18 | 2020-01-15 | 2020-01-15 |  |  | 2020-01-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-23 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-16 | 2020-01-16 | 2020-02-03 |  | 2020-01-16 | 2020-02-10 | 2020-02-22 | 2020-03-09 |  |  | 2020-03-09 | 2020-03-09 | A | Bunifer Bulig | Purok Everlasting Brgy. Baguio Davao City | Davao del Sur | 125.3932 | 7.1752 | Greenfield |  |  | 15 years | P25,000 inclusive of VAT and withholding tax | quarterly | 144sqm | n/a | 3 months | 4.5% increase on the 4th year | 2020-02-24 | n/a |  |  |  |  | 2020-02-29 | 2020-02-24 |  | 2020-03-30 | 2020-03-03 | 2020-03-07 | [16 empty] | 2020-03-28 | ok |  | 2020-04-06 | [6 empty] | 2020-04-20 |  | 2020-03-11 |  | 2020-04-20 |  |  |  | RFP submitted, ongoing review | 2020-03-14 | 2020-03-04 | 2020-03-24 |  |  | 2020-03-28 | 2020-02-29 | 2020-03-31 | 2020-03-03 | 2020-03-04 | 2020-04-14 | 2020-03-04 | 2020-03-04 |  | 2020-04-21 |  | 4GT-42-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1100468 | 125.7697 | 7.4446 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Tagum City | San Miguel (Camp 4) | MIN | PH112319020 | 17317 | 45 | Three Legged Tubular Tower | CO65 | 4.225 | MIN-1100239 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  | Enovell | PH20200302005 | 2019-11-27 | 2019-11-29 | 2019-11-29 | 2019-12-01 | 2019-12-07 | 2020-01-15 |  |  | 2019-12-07 |  | 2019-12-08 |  |  | 2019-12-08 |  |  |  | 2019-12-06 |  | 2019-12-08 |  |  | 2019-12-08 | 2019-12-06 | 2019-12-06 | 2019-12-06 |  | 2019-12-06 | 2020-02-12 | 2020-01-05 | 2020-01-08 |  |  | 2020-01-09 | 2020-02-04 | B | Aida Lepiten | Purok 7, San Miguel, Tagum City | Davao del Norte | 125.7692 | 7.4433 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-12 | 2020-01-15 |  | 2020-02-11 | 2020-02-10 | 2020-01-19 | 2020-02-28 | 2020-02-28 | 2020-01-27 | [13 empty] | 2020-02-09 | ok |  | 2020-02-18 | [6 empty] | 2020-03-03 |  | 2020-02-19 | 2020-02-26 | 2020-03-03 | 2020-02-28 |  |  | Cheque released | 2020-01-26 | 2020-01-15 | 2020-02-05 | 2020-01-25 | 2020-01-25 | 2020-02-09 | 2020-01-31 | 2020-02-12 | 2020-01-31 |  | 2020-02-26 | 2020-01-27 | 2020-01-29 | 2020-02-18 | 2020-03-04 | 2020-02-18 | JGT-36-340C-2NPT |  |  | 2020-03-16 |  | 2020-02-23 | [6 empty] | 2020-03-24 | 2020-03-31 | [20 empty] | 2020-04-30 |  |  |  | 2020-05-03 | [7 empty] | 2020-01-29 | 2020-03-09 | 2020-01-31 | 2020-03-12 | 2020-03-04 |  | 2020-03-24 |  |  |  | 2020-03-27 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-21 |  |  |  | 2020-05-03 |  | 2020-05-06
PH1100470 | 125.3916 | 7.2491 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Malamba | MIN | PH112402120 | 8351 | 45 | Three Legged Tubular Tower | CO66 | 30.488 | MIN-1100240 | Level 3 (Davao City) - R | phase3 | phase3 | OA_630 |  | Cluster M09 | JXD |  | Batch 2 (333) | JXD |  | JXD |  | 2020-01-15 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-20 | 2020-01-20 | 2020-01-20 |  | 2020-01-20 | 2020-02-07 |  |  |  | 2020-02-07 |  |  |  | 2020-01-26 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-01-22 | 2020-01-22 | 2020-01-22 |  | 2020-01-22 | 2020-03-04 | 2020-02-25 | 2020-03-04 |  |  | 2020-03-05 | 2020-03-05 |  | Melchor Emperado | Purok 1, Lower Tamugan, Marilog District, Davao City | Davao Del Sur | 125.3931 | 7.2534 | Greenfield | 263m |  | 10 years | P15,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-03 | 2020-02-24 |  | 2020-04-02 |  | 2020-03-10 | [16 empty] | 2020-03-31 |  |  | 2020-04-09 | [6 empty] | 2020-04-23 |  |  |  | 2020-04-23 |  |  |  |  | 2020-03-17 |  | 2020-03-27 |  |  | 2020-03-31 | 2020-01-31 | 2020-04-03 | 2020-01-31 |  | 2020-04-17 | 2020-02-12 |  |  | 2020-04-24 |  | 4GT-42-340C-2NPT |  |  | 2020-05-06 |  | 2020-04-14 | [6 empty] | 2020-05-14 | 2020-05-21 | [20 empty] | 2020-06-20 |  |  |  | 2020-06-23 | [8 empty] | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-11 |  |  |  | 2020-06-23 |  | 2020-06-26
PH1100472 | 125.7424 | 7.02 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Anonang | MIN | PH112317002 | 2493 | 40 | Three Legged Tubular Tower | CO66 | 15.8458 | MIN-1100241 | Level 6 | phase3 | phase3 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-02-01 |  | 2020-02-03 | [13 empty] | 2020-02-08 | [11 empty] | 2020-03-09 | [27 empty] | 2020-03-16 |  |  | 2020-04-15 |  | 2020-03-23 | [16 empty] | 2020-04-13 |  |  | 2020-04-22 | [6 empty] | 2020-05-06 |  |  |  | 2020-05-06 |  |  |  |  | 2020-03-30 |  | 2020-04-09 |  |  | 2020-04-13 |  | 2020-04-16 |  |  | 2020-04-30 |  |  |  | 2020-05-07 |  | 4GT-42-340C-2NPT |  |  | 2020-05-19 |  | 2020-04-27 | [6 empty] | 2020-05-27 | 2020-06-03 | [20 empty] | 2020-07-03 |  |  |  | 2020-07-06 | [8 empty] | 2020-05-12 |  | 2020-05-15 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-06 |  |  |  | 2020-06-09 |  |  | 2020-06-24 |  |  |  | 2020-07-06 |  | 2020-07-09
PH1100473 | 125.6986 | 7.1727 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Camudmud | MIN | PH112317008 | 2564 | 40 | Three Legged Tubular Tower | CO66 | 11.7553 | MIN-1100242 | Level 6 | phase3 | phase2_1231 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-02-04 |  | 2020-02-06 | [13 empty] | 2020-02-11 | [11 empty] | 2020-03-12 | [27 empty] | 2020-03-19 |  |  | 2020-04-18 |  | 2020-03-26 | [16 empty] | 2020-04-16 |  |  | 2020-04-25 | [6 empty] | 2020-05-09 |  |  |  | 2020-05-09 |  |  |  |  | 2020-04-02 |  | 2020-04-12 |  |  | 2020-04-16 |  | 2020-04-19 |  |  | 2020-05-03 |  |  |  | 2020-05-10 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-05-22 |  | 2020-04-30 | [6 empty] | 2020-05-30 | 2020-06-06 | [20 empty] | 2020-07-06 |  |  |  | 2020-07-09 | [8 empty] | 2020-05-15 |  | 2020-05-18 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-09 |  |  |  | 2020-06-12 |  |  | 2020-06-27 |  |  |  | 2020-07-09 |  | 2020-07-12
PH1100474 | 125.6675 | 7.1024 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Caliclic (Dangca-An) | MIN | PH112317021 | 2497 | 40 | Three Legged Tubular Tower | CO66 | 4.9636 | MIN-1100243 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M03 | JXD | PO2019122101PH_WLS | Proposed PO 1 | JXD-2 |  |  |  | 2020-01-20 | 2020-01-25 | 2020-01-16 | 2020-01-27 | 2020-01-29 |  |  |  | 2020-01-29 | [8 empty] | 2020-02-01 | [5 empty] | 2020-01-28 |  |  |  | 2020-01-28 |  | 2020-03-02 | [27 empty] | 2020-03-09 |  |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 |  | 2020-04-02 |  |  | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-23 |  |  |  | 2020-04-30 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1100475 | 125.7201 | 7.0603 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Cawag | MIN | PH112317010 | 2585 | 40 | Three Legged Tubular Tower | CO66 | 11.5701 | MIN-1100244 | Level 6 | phase2_add | phase3 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-02-07 |  | 2020-02-09 | [13 empty] | 2020-02-14 | [11 empty] | 2020-03-15 | [27 empty] | 2020-03-22 |  |  | 2020-04-21 |  | 2020-03-29 | [16 empty] | 2020-04-19 |  |  | 2020-04-28 | [6 empty] | 2020-05-12 |  |  |  | 2020-05-12 |  |  |  |  | 2020-04-05 |  | 2020-04-15 |  |  | 2020-04-19 |  | 2020-04-22 |  |  | 2020-05-06 |  |  |  | 2020-05-13 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-05-25 |  | 2020-05-03 | [6 empty] | 2020-06-02 | 2020-06-09 | [20 empty] | 2020-07-09 |  |  |  | 2020-07-12 | [8 empty] | 2020-05-18 |  | 2020-05-21 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-12 |  |  |  | 2020-06-15 |  |  | 2020-06-30 |  |  |  | 2020-07-12 |  | 2020-07-15
PH1100479 | 125.7309 | 7.0023 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Adecor | MIN | PH112317001 | 1884 | 40 | Three Legged Tubular Tower | CO66 | 16.0389 | MIN-1100245 | Level 6 | phase3 | phase3 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-02-10 |  | 2020-02-12 | [13 empty] | 2020-02-17 | [11 empty] | 2020-03-18 | [27 empty] | 2020-03-25 |  |  | 2020-04-24 |  | 2020-04-01 | [16 empty] | 2020-04-22 |  |  | 2020-05-01 | [6 empty] | 2020-05-15 |  |  |  | 2020-05-15 |  |  |  |  | 2020-04-08 |  | 2020-04-18 |  |  | 2020-04-22 |  | 2020-04-25 |  |  | 2020-05-09 |  |  |  | 2020-05-16 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-05-28 |  | 2020-05-06 | [6 empty] | 2020-06-05 | 2020-06-12 | [20 empty] | 2020-07-12 |  |  |  | 2020-07-15 | [8 empty] | 2020-05-21 |  | 2020-05-24 |  |  | 2020-06-05 |  |  |  | 2020-06-08 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-07-03 |  |  |  | 2020-07-15 |  | 2020-07-18
PH1100481 | 125.7102 | 7.0767 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Penaplata | MIN | PH112317028 | 6097 | 40 | Three Legged Tubular Tower | CO66 | 9.9657 | MIN-1100246 | Level 6 | phase3 | phase3 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-02-13 |  | 2020-02-15 | [13 empty] | 2020-02-20 | [11 empty] | 2020-03-21 | [27 empty] | 2020-03-28 |  |  | 2020-04-27 |  | 2020-04-04 | [16 empty] | 2020-04-25 |  |  | 2020-05-04 | [6 empty] | 2020-05-18 |  |  |  | 2020-05-18 |  |  |  |  | 2020-04-11 |  | 2020-04-21 |  |  | 2020-04-25 |  | 2020-04-28 |  |  | 2020-05-12 |  |  |  | 2020-05-19 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-05-31 |  | 2020-05-09 | [6 empty] | 2020-06-08 | 2020-06-15 | [20 empty] | 2020-07-15 |  |  |  | 2020-07-18 | [8 empty] | 2020-05-24 |  | 2020-05-27 |  |  | 2020-06-08 |  |  |  | 2020-06-11 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-07-06 |  |  |  | 2020-07-18 |  | 2020-07-21
PH1100484 | 125.463 | 6.9149 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Santa Cruz | Astorga | MIN | PH112412001 | 12041 | 40 | Monopole Tower | CO66 | 26.9702 | MIN-1100247 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-13 | 2020-02-10 |  |  |  | 2020-02-10 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-02-25 | 2020-01-12 | [5 empty] | A | Fontojan Amado Jr | Dablo Compound, Astorga, Sta Cruz | Davao del Sur | 125.4615 | 6.916 | Greenfield |  |  | 15 years | P18,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-02-20 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-36-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100485 | 125.3895 | 6.7932 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Santa Cruz | Bato | MIN | PH112412002 | 6965 | 40 | Monopole Tower | CO66 | 42.5963 | MIN-1100248 | Level 4 (220) | phase1_220_20% | phase2_1231 | P1_630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2019-12-22 |  |  |  | 2019-12-22 |  | 2019-12-19 |  |  | 2019-12-19 |  |  |  | 2019-12-19 |  | 2019-12-21 |  |  | 2019-12-21 | 2019-12-18 |  |  |  | 2019-12-18 | 2020-02-10 | 2020-01-18 | 2020-01-09 |  |  | 2020-01-10 | 2020-02-19 | B | Rhodora Calacat | Purok Sampaguita, Bato, Sta. Cruz | Davao del Sur | 125.3885 | 6.7933 | Greenfield | 35m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 240sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-25 | 2020-01-08 |  | 2020-02-24 | 2020-02-21 | 2020-02-01 | 2020-02-26 |  | 2020-02-26 | [8 empty] | 0910-5476314 |  |  |  |  | 2020-02-22 | ok |  | 2020-03-02 | 2020-02-26 | [5 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  | Incorrect DITO information on BR | 2020-02-08 | 2020-02-03 | 2020-02-18 | 2020-02-17 | 2020-02-17 | 2020-02-22 | 2020-01-23 | 2020-02-25 | 2020-01-23 | 2020-02-17 | 2020-03-10 | 2020-01-22 | 2020-01-24 | 2020-02-17 | 2020-03-17 | 2020-02-17 | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [7 empty] | 2020-01-30 | 2020-03-22 | 2020-01-31 | 2020-03-25 | 2020-03-09 |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100486 | 125.8761 | 7.2149 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Pantukan | Bongabong | MIN | PH118211001 | 4647 | 40 | Three Legged Tubular Tower | CO65 | 26.6262 | MIN-1100249 | Level 5 | phase3 | phase3 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-20 | 2019-12-20 | 2019-12-22 | 2020-01-20 | 2019-12-21 |  |  | 2019-12-21 | 2020-01-21 | 2019-12-22 |  |  | 2019-12-22 |  |  |  | 2019-12-27 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-01-20 | 2019-12-21 |  |  | 2019-12-21 | 2020-02-10 | 2020-01-26 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Kerwin Ross Aujero Chiva | Purok 5 Pagakpak, Brgy. Bangabong, Pantukan, Davao de Oro | Compostela Valley | 125.8751 | 7.2141 | Greenfield |  |  | 10 years | P15,000 inclusive of VAT and withholding tax | Monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | 2020-01-17 | n/a |  |  |  | n/a | 2020-02-02 |  |  | 2020-03-03 |  | 2020-02-09 | [16 empty] | 2020-03-01 |  |  | 2020-03-10 | [6 empty] | 2020-03-24 |  |  |  | 2020-03-24 |  |  |  |  | 2020-02-16 | 2020-01-15 | 2020-02-26 |  |  | 2020-03-01 |  | 2020-03-04 |  |  | 2020-03-18 |  |  |  | 2020-03-25 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-04-06 |  | 2020-03-15 | [6 empty] | 2020-04-14 | 2020-04-21 | [20 empty] | 2020-05-21 |  |  |  | 2020-05-24 | [8 empty] | 2020-03-30 |  | 2020-04-02 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-12 |  |  |  | 2020-05-24 |  | 2020-05-27
PH1100487 | 125.9941 | 7.5729 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Nabunturan | Cabidianan | MIN | PH118209005 | 2937 | 40 | Three Legged Tubular Tower | CO65 | 24.9797 | MIN-1100250 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M07 | EPC | PO2019122103PH_WLS | Batch 2 | EPC |  |  |  | 2020-01-20 | 2020-01-05 | 2020-01-04 | 2020-01-07 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-05 |  |  |  | 2020-01-05 |  |  |  | 2020-01-12 | 2020-01-06 |  |  |  | 2020-01-06 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-24 | 2020-02-11 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Teresita A. Masin | Purok 1, Cabidianan, Nabunturan, Davao de Oro | Compostela Valley | 125.9945 | 7.5712 | Greenfield | 89m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-02-18 | 2020-01-23 |  | 2020-03-19 |  | 2020-02-25 | [16 empty] | 2020-03-17 |  |  | 2020-03-26 | [6 empty] | 2020-04-09 |  |  |  | 2020-04-09 |  |  |  |  | 2020-03-03 | 2020-01-28 | 2020-03-13 | 2020-02-21 | 2020-02-21 | 2020-03-17 | 2020-01-24 | 2020-03-20 | 2020-02-24 | 2020-02-24 | 2020-04-03 | 2020-01-24 | 2020-02-26 | 2020-02-26 | 2020-04-10 | 2020-02-26 | JGT-36-340C-2NPT |  |  | 2020-04-22 |  | 2020-03-31 | [6 empty] | 2020-04-30 | 2020-05-07 | [20 empty] | 2020-06-06 |  |  |  | 2020-06-09 | [8 empty] | 2020-04-15 |  | 2020-04-18 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-10 |  |  |  | 2020-05-13 |  |  | 2020-05-28 |  |  |  | 2020-06-09 |  | 2020-06-12
PH1100490 | 125.4525 | 6.8775 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Santa Cruz | Coronon | MIN | PH112412003 | 8979 | 45 | Three Legged Tubular Tower | CO66 | 30.9322 | MIN-1100251 | Level 4 (220) | phase1_220_20% | phase2_1231 | P1_630 | DepEd_3293 | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-15 |  |  |  | 2019-12-15 | 2019-12-16 |  |  |  | 2019-12-16 |  |  |  | 2019-12-13 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-18 | 2019-12-07 |  |  | 2019-12-07 | 2020-01-24 | 2020-01-12 | 2020-01-03 |  |  | 2020-01-24 | 2020-02-06 | A | Annie Rose Omblero | Purok Kumintang, Brgy. Coronon, Sta. Cruz | Davao del Sur | 125.4518 | 6.876 | Greenfield | 18m |  | 15 years | P16,000 inclusive of VAT and withholding tax | monthly | 225sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-01-06 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 | ok |  | 2020-02-25 | 2020-01-20 | [5 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 | 2020-03-13 | 2020-02-19 | 2020-03-13 |  | 2020-03-04 |  |  |  | 2020-03-11 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100494 | 125.4733 | 6.9606 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Santa Cruz | Inawayan | MIN | PH112412005 | 6309 | 40 | Three Legged Tubular Tower | CO66 | 22.5186 | MIN-1100252 | Level 5 | phase2_add | phase2_1231 | P1_630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-13 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-27 | 2020-01-12 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Efren T. Bibat | Purok Parrot, Inawayan, Sta. Cruz | Davao del Sur | 125.4741 | 6.96 | Greenfield | 28m |  | 15 years | P25,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-19 | 2020-01-08 |  | 2020-02-18 |  | 2020-01-26 | [11 empty] | 0907-5532276 |  |  |  |  | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 | 2020-02-19 | 2020-02-12 | 2020-02-28 | 2020-02-28 | 2020-02-16 | 2020-01-29 | 2020-02-19 | 2020-01-29 | 2020-01-30 | 2020-03-04 | 2020-01-29 | 2020-01-29 | 2020-02-28 | 2020-03-11 | 2020-02-28 | JGT-36-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100496 | 125.6757 | 7.5642 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Kapalong | Luna | MIN | PH112318004 | 7411 | 40 | Three Legged Tubular Tower | CO65 | 19.7311 | MIN-1100253 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  | Enovell |  | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-14 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-13 |  |  |  | 2019-12-13 |  |  |  | 2019-12-19 | 2019-12-13 |  |  |  | 2019-12-13 | 2019-12-12 |  |  |  | 2019-12-12 | 2020-01-24 | 2020-01-18 | 2019-12-27 |  |  | 2020-01-24 | 2020-02-06 | A | Ruel Robledo | Purok 2, Luna Kapalong, Tagum City | Davao del Norte | 125.6759 | 7.5646 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-01-16 | n/a |  |  |  | n/a | 2020-01-25 | 2020-01-15 |  | 2020-02-24 | 2020-03-02 | 2020-02-01 | [16 empty] | 2020-02-22 | ok |  | 2020-03-02 | [6 empty] | 2020-03-16 |  |  |  | 2020-03-16 |  |  |  | For MOC/NRAF resubmission (different option approved) | 2020-02-08 | 2020-03-10 | 2020-02-18 | 2020-03-10 | 2020-03-10 | 2020-02-22 | 2020-01-26 | 2020-02-25 | 2020-02-29 | 2020-03-11 | 2020-03-10 | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2020-03-17 | 2020-03-11 | JGT-36-340C-2NPT |  |  | 2020-03-29 |  | 2020-03-07 | [6 empty] | 2020-04-06 | 2020-04-13 | [20 empty] | 2020-05-13 |  |  |  | 2020-05-16 | [7 empty] | 2020-03-01 | 2020-03-22 |  | 2020-03-25 |  |  | 2020-04-06 |  |  |  | 2020-04-09 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-05-04 |  |  |  | 2020-05-16 |  | 2020-05-19
PH1100498 | 125.6743 | 7.5003 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Santo Tomas | Kinamayan | MIN | PH112318005 | 5890 | 40 | Three Legged Tubular Tower | CO65 | 15.9928 | MIN-1100254 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2019-12-30 | 2019-12-30 | 2020-01-01 | 2020-01-02 | 2020-01-20 |  |  | 2020-01-02 | 2020-01-02 | 2020-01-21 |  |  | 2020-01-02 |  |  |  | 2020-01-06 | 2020-03-05 |  |  |  | 2020-03-05 | 2020-01-02 | 2020-01-20 |  |  | 2020-01-02 | 2020-03-13 | 2020-02-05 | 2020-03-13 |  |  | 2020-03-12 | 2020-03-13 | A | BERNABE SERENTAS | PUROK 1 KINAMAYAN, STO TOMAS | Davao Del Norte | 125.6714 | 7.4999 | Greenfield |  |  | 10 years | P17,000 Exclusive of VAT and withholding tax | quarterly | 225sqm | n/a | 3 months | 4.5% increase on the 4th year | 2020-01-16 | n/a |  |  |  | n/a | 2020-02-12 | 2020-01-25 |  | 2020-03-13 |  | 2020-02-19 | [16 empty] | 2020-03-11 |  |  | 2020-03-20 | [6 empty] | 2020-04-03 |  |  |  | 2020-04-03 |  |  |  |  | 2020-02-26 |  | 2020-03-07 |  |  | 2020-03-11 |  | 2020-03-14 |  |  | 2020-03-28 |  |  |  | 2020-04-04 |  | JGT-36-340C-2NPT |  |  | 2020-04-16 |  | 2020-03-25 | [6 empty] | 2020-04-24 | 2020-05-01 | [20 empty] | 2020-05-31 |  |  |  | 2020-06-03 | [8 empty] | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-04 |  |  |  | 2020-05-07 |  |  | 2020-05-22 |  |  |  | 2020-06-03 |  | 2020-06-06
PH1100501 | 125.86 | 7.3708 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Maco | Binuangan | MIN | PH118204003 | 6017 | 40 | Three Legged Tubular Tower | CO65 | 10.0149 | MIN-1100255 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2019-12-20 | 2019-12-20 | 2019-12-22 | 2019-12-21 | 2020-01-10 |  |  | 2019-12-21 | 2019-12-22 | 2020-01-11 |  |  | 2019-12-22 |  |  |  | 2019-12-27 | [5 empty] | 2019-12-21 | 2020-01-10 |  |  | 2019-12-21 | 2020-02-19 | 2020-01-26 | [6 empty] | Adonis Atablanco | Brgy Binuagan, Maco, Compostela Valley | Compostela Valley |  |  | Greenfield |  |  | 10 years | P17,000 exclusive of VAT and withholding tax | quarterly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-02 | 2020-01-16 |  | 2020-03-03 |  | 2020-02-09 | [16 empty] | 2020-03-01 |  |  | 2020-03-10 | [6 empty] | 2020-03-24 |  |  |  | 2020-03-24 |  |  |  |  | 2020-02-16 |  | 2020-02-26 |  |  | 2020-03-01 |  | 2020-03-04 |  |  | 2020-03-18 |  |  |  | 2020-03-25 |  | 4GT-42-340C-2NPT |  |  | 2020-04-06 |  | 2020-03-15 | [6 empty] | 2020-04-14 | 2020-04-21 |  |  |  | 2020-03-02 |  | 2020-03-02 | [14 empty] | 2020-05-21 |  |  |  | 2020-05-24 | [8 empty] | 2020-03-30 |  | 2020-04-02 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-12 |  |  |  | 2020-05-24 |  | 2020-05-27
PH1100502 | 125.6125 | 6.411 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Occidental | Malita | Poblacion | MIN | PH118603032 | 17787 | 45 | Three Legged Tubular Tower | CO67 | 58.133 | MIN-1100256 | Level 5 | phase3 | phase3 | P1_630_废站 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-13 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-08 | 2019-12-25 |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-14 |  | 2019-12-26 |  |  | 2019-12-26 |  | 2019-12-25 |  |  | 2019-12-25 | 2020-01-24 | 2020-01-13 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | B | Benedict Barcelona | Peralta St., Poblacion, Malita | Davao Occidental | 125.604 | 6.4101 | Greenfield | 12m |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-20 | 2020-01-15 |  | 2020-02-19 | 2020-01-29 | 2020-01-27 | 2020-02-26 |  | 2020-02-26 | [13 empty] | 2020-02-17 | ok |  | 2020-02-26 | 2020-02-26 | [5 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  | RFP submission on-hold, transmission not ready | 2020-02-03 | 2020-03-09 | 2020-02-13 |  |  | 2020-02-17 | 2020-02-07 | 2020-02-20 | 2020-02-27 | 2020-02-27 | 2020-03-05 | 2020-02-07 |  |  | 2020-03-12 |  | 4GT-42-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 | [20 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [7 empty] | 2020-02-22 | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1100503 | 125.275 | 6.3766 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Malita | Demoloc | MIN | PH128007023 | 9895 | 40 | Three Legged Tubular Tower | CO67 | 29.6341 | MIN-1100257 | Level 5 | phase3 | phase3 | P1_630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-13 | 2019-12-09 | 2019-12-09 | 2019-12-11 |  | 2019-12-21 |  |  | 2019-12-21 |  | 2019-12-11 |  |  | 2019-12-11 |  |  |  | 2019-12-16 |  | 2019-12-22 |  |  | 2019-12-22 | 2019-12-11 | 2019-12-21 |  |  | 2019-12-11 | 2020-01-24 | 2020-01-15 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | B | Eva F. Padernilla | Purok Talaytay, Malungon | Sarangani | 125.276 | 6.377 | Greenfield | 139m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-22 | 2020-01-09 |  | 2020-02-21 |  | 2020-01-29 | [16 empty] | 2020-02-19 | ok |  | 2020-02-28 | 2020-01-27 | [5 empty] | 2020-03-13 |  |  |  | 2020-03-13 |  |  |  |  | 2020-02-05 | 2020-02-03 | 2020-02-15 |  |  | 2020-02-19 | 2020-01-29 | 2020-02-22 | 2020-01-29 | 2020-01-30 | 2020-03-07 | 2020-01-29 | 2020-01-29 |  | 2020-03-14 |  | 4GT-42-340C-2NPT |  |  | 2020-03-26 |  | 2020-03-04 | 2020-02-12 | [5 empty] | 2020-04-03 | 2020-04-10 | [20 empty] | 2020-05-10 |  |  |  | 2020-05-13 | [8 empty] | 2020-03-19 |  | 2020-03-22 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-05-01 |  |  |  | 2020-05-13 |  | 2020-05-16
PH1100504 | 125.8944 | 7.1687 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Pantukan | Magnaga | MIN | PH118211005 | 9762 | 40 | Three Legged Tubular Tower | CO66 | 30.9807 | MIN-1100258 | Level 5 | phase3 | phase3 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-20 | 2019-12-20 | 2019-12-22 | 2019-12-21 | 2020-01-10 |  |  | 2019-12-21 | 2019-12-22 | 2020-01-10 |  |  | 2019-12-22 |  |  |  | 2019-12-27 |  | 2020-01-10 |  |  | 2020-01-10 | 2019-12-21 | 2020-01-10 |  |  | 2019-12-21 | 2020-01-24 | 2020-01-26 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | B | Nestor Pulido | Brgy. Magnaga, Pantukan, Davao de Oro | Compostela Valley | 125.8932 | 7.1687 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-02 | 2020-01-17 |  | 2020-03-03 |  | 2020-02-09 | [16 empty] | 2020-03-01 |  |  | 2020-03-10 | [6 empty] | 2020-03-24 |  |  |  | 2020-03-24 |  |  |  |  | 2020-02-16 |  | 2020-02-26 |  |  | 2020-03-01 |  | 2020-03-04 |  |  | 2020-03-18 |  |  |  | 2020-03-25 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-04-06 |  | 2020-03-15 | [6 empty] | 2020-04-14 | 2020-04-21 | [20 empty] | 2020-05-21 |  |  |  | 2020-05-24 | [8 empty] | 2020-03-30 |  | 2020-04-02 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-12 |  |  |  | 2020-05-24 |  | 2020-05-27
PH1100505 | 126.0512 | 7.8236 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Monkayo | Poblacion | MIN | PH118207013 | 19434 | 40 | Three Legged Tubular Tower | CO65 | 49.939 | MIN-1100259 | Level 6 | phase3 | phase3 |  | DepEd_3384 | Cluster M07 | EPC | [7 empty] | 2020-03-14 | 2020-02-12 | 2020-03-16 | 2020-02-17 |  |  |  | 2020-02-17 | 2020-02-19 |  |  |  | 2020-02-19 |  |  |  | 2020-03-21 | 2020-02-19 |  |  |  | 2020-02-19 | 2020-02-17 |  |  |  | 2020-02-17 | 2020-02-25 | 2020-04-20 | [6 empty] | Esteban Maglajos | P-10, Poblacion, Monkayo | Compostela Valley | 126.0512 | 7.8215 | Greenfield |  |  | 10 years | P18,000 exclusive of VAT and withholding tax | quarterly | 240sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-27 |  |  | 2020-05-27 |  | 2020-05-04 | [16 empty] | 2020-05-25 |  |  | 2020-06-03 | [6 empty] | 2020-06-17 |  |  |  | 2020-06-17 |  |  |  |  | 2020-05-11 |  | 2020-05-21 |  |  | 2020-05-25 |  | 2020-05-28 |  |  | 2020-06-11 |  |  |  | 2020-06-18 |  | 4GT-42-340C-2NPT |  |  | 2020-06-30 |  | 2020-06-08 | [6 empty] | 2020-07-08 | 2020-07-15 | [20 empty] | 2020-08-14 |  |  |  | 2020-08-17 | [8 empty] | 2020-06-23 |  | 2020-06-26 |  |  | 2020-07-08 |  |  |  | 2020-07-11 |  |  | 2020-07-18 |  |  |  | 2020-07-21 |  |  | 2020-08-05 |  |  |  | 2020-08-17 |  | 2020-08-20
PH1100508 | 126.0236 | 7.7874 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Monkayo | Olaycon | MIN | PH118207011 | 2383 | 40 | Three Legged Tubular Tower | CO65 | 44.9169 | MIN-1100260 | Level 6 | phase3 | phase3 |  |  | Cluster M07 | EPC | [7 empty] | 2020-03-17 | 2020-02-12 | 2020-03-19 | 2020-03-06 |  |  |  | 2020-03-06 | [8 empty] | 2020-03-24 | [5 empty] | 2020-03-06 |  |  |  | 2020-03-06 |  | 2020-04-23 | [27 empty] | 2020-04-30 |  |  | 2020-05-30 |  | 2020-05-07 | [16 empty] | 2020-05-28 |  |  | 2020-06-06 | [6 empty] | 2020-06-20 |  |  |  | 2020-06-20 |  |  |  |  | 2020-05-14 |  | 2020-05-24 |  |  | 2020-05-28 |  | 2020-05-31 |  |  | 2020-06-14 |  |  |  | 2020-06-21 |  | 4GT-42-340C-2NPT |  |  | 2020-07-03 |  | 2020-06-11 | [6 empty] | 2020-07-11 | 2020-07-18 | [20 empty] | 2020-08-17 |  |  |  | 2020-08-20 | [8 empty] | 2020-06-26 |  | 2020-06-29 |  |  | 2020-07-11 |  |  |  | 2020-07-14 |  |  | 2020-07-21 |  |  |  | 2020-07-24 |  |  | 2020-08-08 |  |  |  | 2020-08-20 |  | 2020-08-23
PH1100510 | 125.4101 | 6.8468 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Santa Cruz | Zone I | MIN | PH112412019 | 5004 | 40 | Three Legged Tubular Tower | CO66 | 36.5213 | MIN-1100261 | Level 1 (OA) | phase1_220_20% | phase2_1231 | OA_630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2020-01-28 | 2019-12-08 |  |  | 2019-12-08 | 2020-01-13 |  |  |  | 2020-01-13 |  |  |  | 2019-12-13 | 2020-01-13 |  |  |  | 2020-01-13 | 2020-01-28 |  |  |  | 2020-01-28 | 2020-02-25 | 2020-01-12 | [5 empty] | A | Mary Grace Cornilla Amaquin | Purok Pag asa, Zone 3, Sta Cruz | Davao del Sur | 125.4102 | 6.8382 | Greenfield | 96m |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-01-23 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 | ok |  | 2020-02-25 | 2020-03-13 | [5 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 | 2020-02-21 | 2020-02-12 | 2020-02-28 | 2020-02-28 | 2020-02-16 | 2020-02-12 | 2020-02-19 | 2020-02-12 | 2020-02-13 | 2020-03-04 | 2020-02-12 | 2020-02-28 | 2020-02-28 | 2020-03-11 | 2020-02-28 | 4GT-42-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100513 | 125.662 | 7.3848 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Carmen | Alejal | MIN | PH112303001 | 8148 | 40 | Three Legged Tubular Tower | CO65 | 17.4168 | MIN-1100262 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M08 | EPC | PO2019121803PH_WLS | Batch 1 (333) | EPC |  | EPC |  | 2019-11-27 | 2019-11-30 | 2019-11-30 | 2019-12-02 | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2019-12-04 | 2019-12-05 | 2019-12-05 | 2019-12-05 |  | 2019-12-05 |  |  |  | 2019-12-07 | 2019-12-05 | 2019-12-06 | 2019-12-05 |  | 2019-12-05 | 2019-12-05 | 2019-11-28 | 2019-12-05 |  | 2019-11-28 | 2020-02-24 | 2020-01-06 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | A | Roda Ancheta | Purok 1, Alejal, Carmen | Davao del Norte | 125.6626 | 7.3852 | Greenfield | 28m |  | 10 years | P18,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-13 | 2020-01-09 |  | 2020-02-12 |  | 2020-01-20 | [16 empty] | 2020-02-10 |  |  | 2020-02-19 | 2020-01-23 | [5 empty] | 2020-03-04 |  |  |  | 2020-03-04 |  |  |  |  | 2020-01-27 | 2020-01-22 | 2020-02-06 | 2020-02-07 | 2020-02-07 | 2020-02-10 | 2020-01-27 | 2020-02-13 | 2020-01-27 | 2020-01-28 | 2020-02-27 | 2020-01-27 | 2020-01-27 | 2020-02-21 | 2020-03-05 | 2020-02-21 | 4GT-42-340C-2NPT |  |  | 2020-03-17 |  | 2020-02-24 | 2020-02-12 | [5 empty] | 2020-03-25 | 2020-04-01 | [20 empty] | 2020-05-01 |  |  |  | 2020-05-04 | [8 empty] | 2020-03-10 |  | 2020-03-13 |  |  | 2020-03-25 |  |  |  | 2020-03-28 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-22 |  |  |  | 2020-05-04 |  | 2020-05-07
PH1100515 | 125.6884 | 7.4495 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Carmen | San Isidro | MIN | PH112323002 | 7438 | 40 | Three Legged Tubular Tower | CO65 | 13.1964 | MIN-1100263 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_3304 | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  | Enovell | PH20200302006 | 2019-11-27 | 2019-12-16 | 2019-12-16 | 2019-12-18 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-17 |  |  |  | 2019-12-17 |  |  |  | 2019-12-23 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-27 | 2020-01-22 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Ella Tautho | Purok 5-A, Brgy. Dujai, Braulio E. Dujali | Davao del Norte | 125.6884 | 7.45 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 225sqm | 1 month | n/a | 4.5% increase on the 4th year | 2020-01-26 | n/a |  |  |  | n/a | 2020-01-29 | 2020-01-15 | 2020-02-13 | 2020-02-28 | 2020-01-26 | 2020-02-05 |  |  | 2020-01-26 | [8 empty] | 0966-1798324 |  |  |  |  | 2020-02-26 | ok |  | 2020-03-06 | 2020-03-11 | [5 empty] | 2020-03-20 |  | 2020-02-05 | 2020-02-17 | 2020-03-20 | 2020-02-24 | 2020-02-27 | 2020-03-05 | Cheque released | 2020-02-12 | 2020-01-15 | 2020-02-22 | 2020-01-22 | 2020-01-22 | 2020-02-26 | 2020-01-31 | 2020-02-29 | 2020-01-31 |  | 2020-03-14 | 2020-01-24 | 2020-01-29 | 2020-02-18 | 2020-03-21 | 2020-02-18 | 4GT-42-340C-2NPT |  |  | 2020-04-02 |  | 2020-03-11 | [6 empty] | 2020-04-10 | 2020-04-17 | [20 empty] | 2020-05-17 |  |  |  | 2020-05-20 | [7 empty] | 2020-02-24 | 2020-03-26 | 2020-01-30 | 2020-03-29 | 2020-03-02 |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-05-08 |  |  |  | 2020-05-20 |  | 2020-05-23
PH1100516 | 125.7061 | 7.5842 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Kapalong | Pag-Asa | MIN | PH112305021 | 19175 | 40 | Three Legged Tubular Tower | CO65 | 19.1616 | MIN-1100264 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DICT_20 | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | JXD |  | Enovell |  | 2019-12-12 | 2019-12-16 | 2019-12-16 | 2019-12-18 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-17 |  |  |  | 2019-12-17 |  |  |  | 2019-12-23 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-17 | 2020-01-29 |  |  | 2019-12-17 | 2019-12-27 | 2020-01-22 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Evelyn Malno | Purok 2, Brgy. Maniki, Kapalong | Davao del Norte | 125.707 | 7.5837 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-29 |  |  | 2020-02-28 |  | 2020-02-05 | [11 empty] | 0955-9302740 |  |  |  |  | 2020-02-26 |  |  | 2020-03-06 | [6 empty] | 2020-03-20 |  |  |  | 2020-03-20 |  |  |  |  | 2020-02-12 | 2020-02-21 | 2020-02-22 | 2020-02-28 | 2020-02-28 | 2020-02-26 | 2020-02-19 | 2020-02-29 | 2020-02-19 | 2020-02-21 | 2020-03-14 | 2020-02-19 | 2020-02-27 | 2020-02-27 | 2020-03-21 | 2020-02-27 | JGT-36-340C-2NPT |  |  | 2020-04-02 |  | 2020-03-11 | [6 empty] | 2020-04-10 | 2020-04-17 | [20 empty] | 2020-05-17 |  |  |  | 2020-05-20 | [7 empty] | 2020-02-28 | 2020-03-26 |  | 2020-03-29 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-05-08 |  |  |  | 2020-05-20 |  | 2020-05-23
PH1100519 | 125.7042 | 7.6248 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Kapalong | Tiburcia | MIN | PH112305008 | 5146 | 40 | Three Legged Tubular Tower | CO65 | 23.0677 | MIN-1100265 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | JXD-2 |  | MJV |  | 2019-12-12 | 2020-01-08 | 2020-01-08 | 2020-01-10 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-01-10 |  |  |  | 2020-01-10 |  |  |  | 2020-01-15 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-02-07 | 2020-02-14 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Aldrin G. Siegue | Purok 3-B, Brgy. Capangagan, Kapalong | Davao del Norte | 125.7031 | 7.6248 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-02-21 | 2020-01-20 |  | 2020-03-22 | 2020-01-27 | 2020-02-28 | 2020-02-28 | 2020-02-28 | 2020-02-28 | [13 empty] | 2020-03-20 | ok |  | 2020-03-29 | [6 empty] | 2020-04-12 |  | 2020-02-20 | 2020-02-26 | 2020-04-12 | 2020-02-28 | 2020-03-09 | 2020-03-11 | Cheque released | 2020-03-06 | 2020-01-21 | 2020-03-16 | 2020-02-01 | 2020-02-01 | 2020-03-20 | 2020-02-11 | 2020-03-23 | 2020-01-29 | 2020-02-13 | 2020-04-06 | 2020-01-30 | 2020-01-31 | 2020-02-10 | 2020-04-13 | 2020-02-14 | 4GT-42-340C-2NPT |  |  | 2020-04-25 |  | 2020-04-03 | [6 empty] | 2020-05-03 | 2020-05-10 | [20 empty] | 2020-06-09 |  |  |  | 2020-06-12 | [7 empty] | 2020-02-26 | 2020-04-18 | 2020-01-29 | 2020-04-21 | 2020-03-06 |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-31 |  |  |  | 2020-06-12 |  | 2020-06-15
PH1100526 | 125.2101 | 6.7839 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Bansalan | Tubod | MIN | PH112401025 | 9031 | 40 | Three Legged Tubular Tower | CO66 | 57.4283 | MIN-1100266 | Level 5 | phase3 | phase2_1231 | P1_630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-12 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-26 | 2019-12-08 |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-14 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-26 |  |  |  | 2019-12-26 | 2019-12-27 | 2020-01-13 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Giselle Suagan | Nebrada St., Purok 2, Bansalan | Davao del Sur | 125.2105 | 6.7819 | Greenfield | 155m |  | 15 years | P17,000 inclusive of VAT and withholding tax | quarterly | 240sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-20 | 2020-01-12 |  | 2020-02-19 | 2020-01-29 | 2020-01-27 | 2020-02-26 | 2020-02-26 | [9 empty] | 0910-4884440 |  |  |  |  | 2020-02-17 | ok |  | 2020-02-26 | 2020-02-26 | [5 empty] | 2020-03-11 |  | 2020-02-06 | 2020-02-11 | 2020-03-11 | 2020-02-12 | 2020-02-17 |  | Cheque released | 2020-02-03 | 2020-02-03 | 2020-02-13 | 2020-02-07 | 2020-02-07 | 2020-02-17 | 2020-01-24 | 2020-02-20 | 2020-01-24 | 2020-02-19 | 2020-03-05 | 2020-01-24 | 2020-01-27 | 2020-02-19 | 2020-03-12 | 2020-02-19 | 4GT-42-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | 2020-02-11 | [5 empty] | 2020-04-01 | 2020-04-08 |  |  |  | 2020-03-03 |  | 2020-03-02 | [14 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [7 empty] | 2020-01-30 | 2020-03-17 | 2020-01-31 | 2020-03-20 | 2020-02-27 | 2020-03-10 | 2020-04-01 | 2020-03-13 |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1100536 | 125.4246 | 7.2004 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Lacson | MIN | PH112402066 | 6524 | 40 | Three Legged Tubular Tower | CO66 | 24.612 | MIN-1100267 | Level 3 (Davao City) - R | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M09 | JXD |  | Batch 2 (333) |  |  |  |  | 2020-01-15 | 2020-02-16 | 2020-01-21 | 2020-02-18 | 2020-01-23 |  |  |  | 2020-01-23 | 2020-01-23 |  |  |  | 2020-01-23 |  |  |  | 2020-02-23 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-03-10 | 2020-03-24 | 2020-03-11 |  |  | 2020-03-10 | 2020-03-11 | A | HELEN DIAZ MAHILUM | PUROK 2, LOWER LACSON, CALINAN, DAVAO CITY | Davao Del Sur | 125.443 | 7.2047 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-31 | 2020-02-24 |  | 2020-04-30 |  | 2020-04-07 | [16 empty] | 2020-04-28 |  |  | 2020-05-07 | [6 empty] | 2020-05-21 |  |  |  | 2020-05-21 |  |  |  |  | 2020-04-14 |  | 2020-04-24 |  |  | 2020-04-28 | 2020-03-13 | 2020-05-01 |  |  | 2020-05-15 |  |  |  | 2020-05-22 |  | 4GT-42-340C-2NPT |  |  | 2020-06-03 |  | 2020-05-12 | [6 empty] | 2020-06-11 | 2020-06-18 | [20 empty] | 2020-07-18 |  |  |  | 2020-07-21 | [8 empty] | 2020-05-27 |  | 2020-05-30 |  |  | 2020-06-11 |  |  |  | 2020-06-14 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-09 |  |  |  | 2020-07-21 |  | 2020-07-24
PH1100538 | 125.4559 | 6.9989 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Catigan | MIN | PH112402104 | 7140 | 40 | Three Legged Tubular Tower | CO66 | 21.479 | MIN-1100268 | Level 3 (Davao City) - R | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-04 | 2019-12-04 | 2019-12-06 | 2019-12-19 | 2019-12-06 |  |  | 2019-12-06 | 2020-01-13 | 2019-12-06 |  |  | 2019-12-06 |  |  |  | 2019-12-11 | 2020-01-13 |  |  |  | 2020-01-13 | 2019-12-05 |  |  |  | 2019-12-05 | 2020-01-24 | 2020-01-10 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | D | Ramil Janraque | Purok 15, Sirawan, Toril, Davao City | Davao del Sur | 125.4798 | 6.9911 | Greenfield | 245m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-17 | 2020-01-23 |  | 2020-02-16 |  | 2020-01-24 | [16 empty] | 2020-02-14 |  |  | 2020-02-23 | [6 empty] | 2020-03-08 |  |  |  | 2020-03-08 |  |  |  |  | 2020-01-31 |  | 2020-02-10 |  |  | 2020-02-14 |  | 2020-02-17 |  |  | 2020-03-02 |  |  |  | 2020-03-09 |  | 4GT-42-340C-2NPT |  |  | 2020-03-21 |  | 2020-02-28 | [6 empty] | 2020-03-29 | 2020-04-05 | [20 empty] | 2020-05-05 |  |  |  | 2020-05-08 | [8 empty] | 2020-03-14 |  | 2020-03-17 |  |  | 2020-03-29 |  |  |  | 2020-04-01 |  |  | 2020-04-08 |  |  |  | 2020-04-11 |  |  | 2020-04-26 |  |  |  | 2020-05-08 |  | 2020-05-11
PH1100539 | 125.4671 | 7.0669 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Alambre | MIN | PH112402081 | 2477 | 40 | Three Legged Tubular Tower | CO66 | 17.5198 | MIN-1100269 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2019-12-24 | 2019-12-24 | 2019-12-26 | 2019-12-25 | 2020-01-28 |  |  | 2019-12-25 | 2019-12-26 | 2020-02-07 |  |  | 2019-12-26 |  |  |  | 2019-12-31 |  | 2020-02-07 |  |  | 2020-02-07 | 2019-12-25 | 2020-01-28 |  |  | 2019-12-25 | 2020-03-05 | 2020-01-30 | 2020-03-05 |  |  | 2020-03-05 | 2020-03-05 | B | Mario Ferrer | Purok 2, Bangkas Heights, Toril, Davao City | Davao Del Sur | 125.4845 | 7.0509 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 240sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-02-06 | 2020-02-27 |  | 2020-03-07 |  | 2020-02-13 | [16 empty] | 2020-03-05 | ok |  | 2020-03-14 | 2020-03-11 | [5 empty] | 2020-03-28 |  |  |  | 2020-03-28 |  |  |  |  | 2020-02-20 | 2020-03-10 | 2020-03-01 |  |  | 2020-03-05 |  | 2020-03-08 |  |  | 2020-03-22 |  |  |  | 2020-03-29 |  | JGT-36-340C-2NPT |  |  | 2020-04-10 |  | 2020-03-19 | [6 empty] | 2020-04-18 | 2020-04-25 | [20 empty] | 2020-05-25 |  |  |  | 2020-05-28 | [8 empty] | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-18 |  |  |  | 2020-04-21 |  |  | 2020-04-28 |  |  |  | 2020-05-01 |  |  | 2020-05-16 |  |  |  | 2020-05-28 |  | 2020-05-31
PH1100542 | 125.4672 | 7.2172 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Dacudao | MIN | PH112402037 | 4418 | 40 | Three Legged Tubular Tower | CO66 | 21.6371 | MIN-1100270 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M09 | JXD |  | Batch 2 (333) | JXD-2 |  |  |  | 2020-01-15 | 2020-01-20 | 2020-01-14 | 2020-01-22 | 2020-01-17 | 2020-01-17 | 2020-01-17 |  | 2020-01-17 | 2020-01-18 |  |  |  | 2020-01-18 |  |  |  | 2020-01-27 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-01-17 | 2020-01-17 | 2020-01-17 |  | 2020-01-17 | 2020-02-19 | 2020-02-26 | 2020-02-26 |  |  | 2020-02-26 | 2020-03-03 | A | Linda Banaston | Purok 6 Dacudao, Calinan, Davao City | Davao del Sur | 125.4787 | 7.2151 | Greenfield | 243m |  | 10 years | P20,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-02-19 | n/a |  |  |  | n/a | 2020-03-04 | 2020-02-14 |  | 2020-04-03 | 2020-03-13 | 2020-03-11 | [16 empty] | 2020-04-01 | ok |  | 2020-04-10 | 2020-03-11 | [5 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  | For RFP submission in DingTalk | 2020-03-18 | 2020-02-19 | 2020-03-28 | 2020-02-28 | 2020-02-28 | 2020-04-01 | 2020-02-04 | 2020-04-04 | 2020-02-04 | 2020-02-05 | 2020-04-18 | 2020-02-16 | 2020-02-28 | 2020-02-28 | 2020-04-25 | 2020-02-28 | 4GT-42-340C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1100543 | 125.4799 | 7.1511 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Los Amigos | MIN | PH112402058 | 9722 | 40 | Three Legged Tubular Tower | CO66 | 16.7925 | MIN-1100271 | Level 3 (Davao City) - R | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M09 | JXD |  | Batch 2 (333) | JXD |  | JXD |  | 2020-01-15 | 2020-01-21 | 2020-01-14 | 2020-01-23 | 2020-01-17 | 2020-01-18 |  |  | 2020-01-17 | 2020-01-19 |  |  |  | 2020-01-19 |  |  |  | 2020-01-28 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-17 | 2020-01-20 |  |  | 2020-01-17 | 2020-02-19 | 2020-02-27 | 2020-02-26 |  |  | 2020-02-26 | 2020-03-03 | A | Jean V. Polison | Purok 6-C, Los Amigos, Tugbok District, Davao City | Davao del Sur | 125.4802 | 7.1427 | Greenfield | 184m |  | 10 years | P20,000 Exclusive of VAT and withholding tax | quarterly | 150sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-05 |  |  | 2020-04-04 |  | 2020-03-12 | [16 empty] | 2020-04-02 |  |  | 2020-04-11 | [6 empty] | 2020-04-25 |  |  |  | 2020-04-25 |  |  |  |  | 2020-03-19 |  | 2020-03-29 |  |  | 2020-04-02 | 2020-01-31 | 2020-04-05 | 2020-01-31 | 2020-02-01 | 2020-04-19 | 2020-02-01 | 2020-02-02 |  | 2020-04-26 |  | JGT-36-340C-2NPT |  |  | 2020-05-08 |  | 2020-04-16 | [6 empty] | 2020-05-16 | 2020-05-23 | [20 empty] | 2020-06-22 |  |  |  | 2020-06-25 | [8 empty] | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-16 |  |  |  | 2020-05-19 |  |  | 2020-05-26 |  |  |  | 2020-05-29 |  |  | 2020-06-13 |  |  |  | 2020-06-25 |  | 2020-06-28
PH1100546 | 125.438 | 7.1685 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Subasta | MIN | PH112402131 | 5821 | 40 | Three Legged Tubular Tower | CO66 | 21.8084 | MIN-1100272 | Level 3 (Davao City) - R | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M09 | JXD |  | Batch 2 (333) |  |  | JXD |  | 2020-01-15 | 2020-02-19 | 2020-01-18 | 2020-02-21 | 2020-01-18 |  |  |  | 2020-01-18 | 2020-01-23 |  |  |  | 2020-01-23 |  |  |  | 2020-02-26 | 2020-01-23 |  |  |  | 2020-01-23 | 2020-01-20 | 2020-01-22 |  |  | 2020-01-20 | 2020-02-10 | 2020-03-27 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Elmira Aranas | Purok 2, Subasta, Calinan, Davao City | Davao del Sur | 125.4387 | 7.152 | Greenfield | 316m |  | 10 years | P20,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-02-19 | n/a |  |  |  | n/a | 2020-04-03 | 2020-02-14 |  | 2020-05-03 | 2020-03-05 | 2020-04-10 | 2020-03-11 | 2020-03-11 | 2020-03-11 |  |  | 2020-03-13 | [5 empty] | 0946-9068489 |  |  |  |  | 2020-05-01 | ok | 2020-03-13 | 2020-05-10 | 2020-03-13 | [5 empty] | 2020-05-24 |  | 2020-03-13 |  | 2020-05-24 |  |  |  | RFP submitted, ongoing review | 2020-04-17 | 2020-02-19 | 2020-04-27 | 2020-02-28 | 2020-02-28 | 2020-05-01 | 2020-02-12 | 2020-05-04 | 2020-02-12 | 2020-02-13 | 2020-05-18 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 2020-05-25 | 2020-03-02 | JGT-36-340C-2NPT |  |  | 2020-06-06 |  | 2020-05-15 | [6 empty] | 2020-06-14 | 2020-06-21 | [20 empty] | 2020-07-21 |  |  |  | 2020-07-24 | [7 empty] | 2020-02-21 | 2020-05-30 | 2020-03-13 | 2020-06-02 | 2020-03-13 |  | 2020-06-14 |  |  |  | 2020-06-17 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-12 |  |  |  | 2020-07-24 |  | 2020-07-27
PH1100548 | 125.951 | 7.4986 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Mawab | Nuevo Iloco | MIN | PH118206006 | 4543 | 40 | Three Legged Tubular Tower | CO65 | 16.8714 | MIN-1100273 | Level 6 | phase3 | phase2_1231 |  | DepEd_3392 | Cluster M07 | EPC | [7 empty] | 2020-03-20 | 2020-02-05 | 2020-03-22 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-02-09 |  |  |  | 2020-02-09 |  |  |  | 2020-03-27 | 2020-02-09 |  |  |  | 2020-02-09 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-03-13 | 2020-04-26 | 2020-03-13 |  |  | 2020-03-12 | 2020-03-13 | A | Jose Peralta Delos Reyes | Purok 1-A, Nuevo Iloco, Mawab, Davao de Oro | Compostela Valley | 125.95 | 7.4989 | Greenfield |  |  | 10 years | P18,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-05-03 | 2020-02-26 |  | 2020-06-02 |  | 2020-05-10 | [16 empty] | 2020-05-31 |  |  | 2020-06-09 | [6 empty] | 2020-06-23 |  |  |  | 2020-06-23 |  |  |  |  | 2020-05-17 |  | 2020-05-27 |  |  | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-17 |  |  |  | 2020-06-24 |  | 4GT-42-340C-2NPT |  |  | 2020-07-06 |  | 2020-06-14 | [6 empty] | 2020-07-14 | 2020-07-21 | [20 empty] | 2020-08-20 |  |  |  | 2020-08-23 | [8 empty] | 2020-06-29 |  | 2020-07-02 |  |  | 2020-07-14 |  |  |  | 2020-07-17 |  |  | 2020-07-24 |  |  |  | 2020-07-27 |  |  | 2020-08-11 |  |  |  | 2020-08-23 |  | 2020-08-26
PH1100552 | 125.3469 | 6.677 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Hagonoy | Paligue | MIN | PH112404007 | 10845 | 40 | Three Legged Tubular Tower | CO66 | 55.8928 | MIN-1100274 | Level 4 (220) | phase1_220_20% | phase2_1231 | P1_630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2019-12-10 | 2019-12-10 | 2019-12-12 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-13 |  |  |  | 2019-12-13 |  |  |  | 2019-12-17 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-12 |  |  |  | 2019-12-12 |  | 2020-01-16 | [5 empty] | A |  |  |  | 125.3489 | 6.6798 | Greenfield | 15m | [14 empty] | 2020-01-23 | 2020-02-28 |  | 2020-02-22 |  | 2020-01-30 | [16 empty] | 2020-02-20 |  |  | 2020-02-29 | [6 empty] | 2020-03-14 |  |  |  | 2020-03-14 |  |  |  |  | 2020-02-06 | 2020-03-09 | 2020-02-16 |  |  | 2020-02-20 |  | 2020-02-23 |  |  | 2020-03-08 |  |  |  | 2020-03-15 |  | JGT-36-340C-2NPT |  |  | 2020-03-27 |  | 2020-03-05 | [6 empty] | 2020-04-04 | 2020-04-11 | [20 empty] | 2020-05-11 |  |  |  | 2020-05-14 | [8 empty] | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-05-02 |  |  |  | 2020-05-14 |  | 2020-05-17
PH1100556 | 125.47 | 6.5564 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Occidental | Santa Maria | Poblacion | MIN | PH118604009 | 8108 | 40 | Three Legged Tubular Tower | CO67 | 57.794 | MIN-1100275 | Level 5 | phase3 | phase3 | P1_630_废站 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-13 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-13 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-27 | 2020-01-12 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Ruben P. Satur | Lambino Village, Poblacio, Sta. Maria | Davao del Sur | 125.4703 | 6.5565 | Greenfield | 23m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-01-10 |  | 2020-02-18 |  | 2020-01-26 | [11 empty] | 0946-8886866 |  |  |  |  | 2020-02-16 |  |  | 2020-02-25 | 2020-03-03 | [5 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 | 2020-02-01 | 2020-02-19 | 2020-02-01 | 2020-02-02 | 2020-03-04 | 2020-02-03 | 2020-02-04 |  | 2020-03-11 |  | 4GT-42-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100558 | 125.9854 | 7.0209 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Oriental | Banaybanay | Punta Linao | MIN | PH112502005 | 2958 | 40 | Three Legged Tubular Tower | CO66 | 40.9492 | MIN-1100276 | Level 6 | phase3 | phase3 |  |  | Cluster M01 | TBD | [7 empty] | 2020-03-19 |  | 2020-03-21 | [13 empty] | 2020-03-26 | [11 empty] | 2020-04-25 | [27 empty] | 2020-05-02 |  |  | 2020-06-01 |  | 2020-05-09 | [16 empty] | 2020-05-30 |  |  | 2020-06-08 | [6 empty] | 2020-06-22 |  |  |  | 2020-06-22 |  |  |  |  | 2020-05-16 |  | 2020-05-26 |  |  | 2020-05-30 |  | 2020-06-02 |  |  | 2020-06-16 |  |  |  | 2020-06-23 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-07-05 |  | 2020-06-13 | [6 empty] | 2020-07-13 | 2020-07-20 | [20 empty] | 2020-08-19 |  |  |  | 2020-08-22 | [8 empty] | 2020-06-28 |  | 2020-07-01 |  |  | 2020-07-13 |  |  |  | 2020-07-16 |  |  | 2020-07-23 |  |  |  | 2020-07-26 |  |  | 2020-08-10 |  |  |  | 2020-08-22 |  | 2020-08-25
PH1100562 | 125.4014 | 6.5976 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Malalag | Baybay | MIN | PH112408016 | 6208 | 40 | Three Legged Tubular Tower | CO67 | 57.8193 | MIN-1100277 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-11 | 2019-12-11 | 2019-12-13 | 2019-12-12 | 2019-12-22 |  |  | 2019-12-12 | 2019-12-13 | 2020-02-15 |  |  | 2019-12-13 |  |  |  | 2019-12-18 |  | 2020-02-15 |  |  | 2020-02-15 | 2020-02-06 |  |  |  | 2020-02-06 | 2020-02-24 | 2020-01-17 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | B | Jerrard Leo Titong | San Roque, Brgy. Baybay, Malalag | Davao del Sur | 125.4041 | 6.5984 | Greenfield |  |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-24 | 2020-02-24 |  | 2020-02-23 | 2020-03-10 | 2020-01-31 | 2020-03-02 | 2020-03-02 | 2020-03-02 | [13 empty] | 2020-02-21 |  |  | 2020-03-01 | [6 empty] | 2020-03-15 |  |  |  | 2020-03-15 |  |  |  | Awaiting Lessor ID | 2020-02-07 |  | 2020-02-17 |  |  | 2020-02-21 |  | 2020-02-24 |  |  | 2020-03-09 |  |  |  | 2020-03-16 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-03-28 |  | 2020-03-06 | [6 empty] | 2020-04-05 | 2020-04-12 | [20 empty] | 2020-05-12 |  |  |  | 2020-05-15 | [8 empty] | 2020-03-21 |  | 2020-03-24 |  |  | 2020-04-05 |  |  |  | 2020-04-08 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-05-03 |  |  |  | 2020-05-15 |  | 2020-05-18
PH1100567 | 125.644 | 7.3511 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Panabo City | Southern Davao | MIN | PH112315022 | 3847 | 40 | Three Legged Tubular Tower | CO65 | 20.8609 | MIN-1100278 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-06 | 2020-01-28 |  |  | 2019-12-06 | 2020-01-28 |  |  |  | 2020-01-28 |  |  |  | 2019-12-13 | 2020-01-28 |  |  |  | 2020-01-28 | 2019-12-06 | 2020-01-28 |  |  | 2019-12-06 | 2020-02-24 | 2020-01-12 | [5 empty] | B | Cornelio Rabago | Purok 1, Southern Davao, Pilar, Panabo City | Davao del Norte | 125.6376 | 7.4006 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-02-13 |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 | 2020-03-05 | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-36-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100573 | 125.6943 | 7.1383 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Miranda | MIN | PH112317025 | 7113 | 40 | Three Legged Tubular Tower | CO66 | 9.0562 | MIN-1100279 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M03 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2020-01-20 | 2020-02-16 |  | 2020-02-18 | [13 empty] | 2020-02-23 | [11 empty] | 2020-03-24 | [27 empty] | 2020-03-31 |  |  | 2020-04-30 |  | 2020-04-07 | [16 empty] | 2020-04-28 |  |  | 2020-05-07 | [6 empty] | 2020-05-21 |  |  |  | 2020-05-21 |  |  |  |  | 2020-04-14 |  | 2020-04-24 |  |  | 2020-04-28 |  | 2020-05-01 |  |  | 2020-05-15 |  |  |  | 2020-05-22 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-06-03 |  | 2020-05-12 | [6 empty] | 2020-06-11 | 2020-06-18 | [20 empty] | 2020-07-18 |  |  |  | 2020-07-21 | [8 empty] | 2020-05-27 |  | 2020-05-30 |  |  | 2020-06-11 |  |  |  | 2020-06-14 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-09 |  |  |  | 2020-07-21 |  | 2020-07-24
PH1100575 | 125.7642 | 6.9791 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Sion (Zion) | MIN | PH112317006 | 1748 | 40 | Three Legged Tubular Tower | CO66 | 20.502 | MIN-1100280 | Level 6 | phase3 | phase3 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-02-19 |  | 2020-02-21 | [13 empty] | 2020-02-26 | [11 empty] | 2020-03-27 | [27 empty] | 2020-04-03 |  |  | 2020-05-03 |  | 2020-04-10 | [16 empty] | 2020-05-01 |  |  | 2020-05-10 | [6 empty] | 2020-05-24 |  |  |  | 2020-05-24 |  |  |  |  | 2020-04-17 |  | 2020-04-27 |  |  | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-18 |  |  |  | 2020-05-25 |  | 4GT-42-340C-2NPT |  |  | 2020-06-06 |  | 2020-05-15 | [6 empty] | 2020-06-14 | 2020-06-21 | [20 empty] | 2020-07-21 |  |  |  | 2020-07-24 | [8 empty] | 2020-05-30 |  | 2020-06-02 |  |  | 2020-06-14 |  |  |  | 2020-06-17 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-12 |  |  |  | 2020-07-24 |  | 2020-07-27
PH1100576 | 125.7584 | 7.5078 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Asuncion | Buclad | MIN | PH112301007 | 2479 | 40 | Three Legged Tubular Tower | CO65 | 8.9048 | MIN-1100281 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  | Enovell |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 |  |  | 2019-12-08 |  | 2019-12-08 |  |  |  | 2019-12-13 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-07 | 2019-12-07 | 2019-12-07 |  | 2019-12-07 | 2019-12-23 | 2020-01-12 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | C | Pedro Torres | Bucad, Asuncion, Tagum City | Davao del Norte | 125.7582 | 7.508 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-02-03 |  | 2020-02-18 | 2020-03-11 | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  | Awaiting Lessor ID | 2020-02-02 | 2020-02-22 | 2020-02-12 | 2020-02-28 | 2020-02-28 | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-36-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [7 empty] | 2020-02-24 | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100577 | 125.728 | 7.5781 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Asuncion | Camoning | MIN | PH112301010 | 3158 | 40 | Three Legged Tubular Tower | CO65 | 17.2572 | MIN-1100282 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-26 | 2019-12-26 | 2019-12-28 | 2019-12-28 |  |  |  | 2019-12-28 | [8 empty] | 2020-01-02 | [5 empty] | 2019-12-28 |  |  |  | 2019-12-28 |  | 2020-02-01 | [27 empty] | 2020-02-08 |  |  | 2020-03-09 |  | 2020-02-15 |  |  | 2020-03-05 | [13 empty] | 2020-03-07 |  |  | 2020-03-16 | [6 empty] | 2020-03-30 |  |  |  | 2020-03-30 |  |  |  |  | 2020-02-22 |  | 2020-03-03 |  |  | 2020-03-07 |  | 2020-03-10 |  |  | 2020-03-24 |  |  |  | 2020-03-31 |  | JGT-36-340C-2NPT |  |  | 2020-04-12 |  | 2020-03-21 | [6 empty] | 2020-04-20 | 2020-04-27 | [20 empty] | 2020-05-27 |  |  |  | 2020-05-30 | [8 empty] | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-18 |  |  |  | 2020-05-30 |  | 2020-06-02
PH1100578 | 125.7546 | 7.5394 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Asuncion | Cambanogoy | MIN | PH112301032 | 9857 | 40 | Three Legged Tubular Tower | CO65 | 12.0656 | MIN-1100283 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 | DICT_19 | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  | Enovell |  | 2019-12-12 | 2019-12-26 | 2019-12-26 | 2019-12-28 | 2019-12-28 | 2020-01-23 |  |  | 2019-12-28 |  | 2020-01-25 |  |  | 2020-01-25 |  |  |  | 2020-01-02 |  | 2020-01-25 |  |  | 2020-01-25 | 2019-12-28 | 2020-01-23 |  |  | 2019-12-28 | 2020-02-24 | 2020-02-01 | [5 empty] | A | Dra. Lovette F. Uy | Purok 4-A, Cambanogoy, Asuncion | Davao del Norte | 125.7524 | 7.5405 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 400sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-08 | 2020-01-22 |  | 2020-03-09 |  | 2020-02-15 | [16 empty] | 2020-03-07 |  |  | 2020-03-16 | [6 empty] | 2020-03-30 |  |  |  | 2020-03-30 |  |  |  |  | 2020-02-22 |  | 2020-03-03 |  |  | 2020-03-07 |  | 2020-03-10 |  |  | 2020-03-24 |  |  |  | 2020-03-31 |  | JGT-36-340C-2NPT |  |  | 2020-04-12 |  | 2020-03-21 | [6 empty] | 2020-04-20 | 2020-04-27 | [20 empty] | 2020-05-27 |  |  |  | 2020-05-30 | [7 empty] | 2020-02-28 | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-18 |  |  |  | 2020-05-30 |  | 2020-06-02
PH1100585 | 125.7481 | 7.452 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Braulio E. Dujali | Magupising | MIN | PH112323003 | 2194 | 40 | Three Legged Tubular Tower | CO65 | 6.6496 | MIN-1100284 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 | DepEd_3366 | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-29 | 2019-12-29 | 2019-12-31 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-06 |  |  |  | 2020-01-06 |  |  |  | 2020-01-05 | 2020-01-06 |  |  |  | 2020-01-06 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-24 | 2020-02-04 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Filomena Secuya | Purok GoldenShower, Magupising, Dujali | Davao del Norte | 125.7477 | 7.4398 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-11 |  |  | 2020-03-12 |  | 2020-02-18 | [16 empty] | 2020-03-10 |  |  | 2020-03-19 | [6 empty] | 2020-04-02 |  |  |  | 2020-04-02 |  |  |  |  | 2020-02-25 |  | 2020-03-06 |  |  | 2020-03-10 |  | 2020-03-13 |  |  | 2020-03-27 |  |  |  | 2020-04-03 |  | JGT-36-340C-2NPT |  |  | 2020-04-15 |  | 2020-03-24 | [6 empty] | 2020-04-23 | 2020-04-30 | [20 empty] | 2020-05-30 |  |  |  | 2020-06-02 | [8 empty] | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-21 |  |  |  | 2020-06-02 |  | 2020-06-05
PH1100589 | 125.9608 | 7.5699 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Mawab | Saosao | MIN | PH118209025 | 597 | 40 | Three Legged Tubular Tower | CO65 | 21.8574 | MIN-1100285 | Level 6 | phase2_add | phase1_630 | P1_630 |  | Cluster M07 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  |  |  |  | 2020-01-16 | 2020-01-15 | 2020-01-18 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-23 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-03-05 | 2020-02-22 | 2020-03-11 |  |  | 2020-03-09 | 2020-03-11 | A | Martin Cabuga | P-7 Poblacion, Nabunturan, Davao de Oro | Compostela Valley | 125.965 | 7.598 | Greenfield | 87m |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-02-29 | 2020-01-15 |  | 2020-03-30 | 2020-02-22 | 2020-03-07 | 2020-02-27 | [15 empty] | 2020-03-28 | ok |  | 2020-04-06 | 2020-03-11 | [5 empty] | 2020-04-20 |  | 2020-03-13 |  | 2020-04-20 |  |  |  | RFP submitted, ongoing review | 2020-03-14 | 2020-01-27 | 2020-03-24 | 2020-02-17 | 2020-02-17 | 2020-03-28 | 2020-02-19 | 2020-03-31 | 2020-02-19 | 2020-02-20 | 2020-04-14 | 2020-02-19 | 2020-02-19 | 2020-02-19 | 2020-04-21 | 2020-02-19 | JGT-36-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 |  |  |  | 2020-03-02 |  | 2020-03-05 | 2020-03-09 | [13 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [7 empty] | 2020-03-05 | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1100594 | 125.8609 | 7.4439 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Maco | Anibongan | MIN | PH118204009 | 3408 | 40 | Three Legged Tubular Tower | CO65 | 5.8322 | MIN-1100286 | Level 5 | phase2_add | phase2_1231 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | JXD |  | Enovell |  | 2019-12-12 | 2019-12-27 | 2019-12-27 | 2019-12-29 | 2019-12-29 |  |  |  | 2019-12-29 | 2019-12-30 |  |  |  | 2019-12-30 |  |  |  | 2020-01-03 | 2019-12-31 |  |  |  | 2019-12-31 | 2019-12-29 |  |  |  | 2019-12-29 | 2020-01-24 | 2020-02-02 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Adela Recrio | Purok 6, Tayma Anibangan, Maco, Davao de Oro | Compostela Valley | 125.8608 | 7.4437 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-09 | 2020-02-05 |  | 2020-03-10 | 2020-02-19 | 2020-02-16 | 2020-02-28 | 2020-02-28 | 2020-02-28 | [13 empty] | 2020-03-08 | ok |  | 2020-03-17 | [6 empty] | 2020-03-31 |  | 2020-02-25 |  | 2020-03-31 |  |  |  | RFP rejected, incorrect DITO information on BR | 2020-02-23 | 2020-02-28 | 2020-03-04 | 2020-02-28 | 2020-02-28 | 2020-03-08 | 2020-02-19 | 2020-03-11 | 2020-02-19 | 2020-02-21 | 2020-03-25 | 2020-02-19 | 2020-02-28 | 2020-02-28 | 2020-04-01 | 2020-02-28 | 4GT-42-340C-2NPT |  |  | 2020-04-13 |  | 2020-03-22 | [6 empty] | 2020-04-21 | 2020-04-28 | [20 empty] | 2020-05-28 |  |  |  | 2020-05-31 | [7 empty] | 2020-03-08 | 2020-04-06 | 2020-03-11 | 2020-04-09 | 2020-03-11 |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-01 |  |  |  | 2020-05-04 |  |  | 2020-05-19 |  |  |  | 2020-05-31 |  | 2020-06-03
PH1100596 | 125.7029 | 7.5226 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Santo Tomas | Talomo | MIN | PH112318007 | 3598 | 40 | Three Legged Tubular Tower | CO65 | 14.4755 | MIN-1100287 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  | Enovell | PH20200307001 | 2019-11-27 | 2019-12-16 | 2019-12-16 | 2019-12-18 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-17 |  |  |  | 2019-12-17 |  |  |  | 2019-12-23 | 2020-01-23 |  |  |  | 2020-01-23 | 2019-12-17 |  |  |  | 2019-12-17 | 2020-03-06 | 2020-01-22 | 2020-03-06 |  |  | 2020-03-06 | 2020-03-06 | A | Mary Jane Gallo | Purok Macopa, Talomo, Davao City | Davao del Sur | 125.7031 | 7.5236 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-29 | 2020-01-15 |  | 2020-02-28 | 2020-02-19 | 2020-02-05 | [16 empty] | 2020-02-26 |  |  | 2020-03-06 | [6 empty] | 2020-03-20 |  |  |  | 2020-03-20 |  |  |  | Awaiting Lessor ID | 2020-02-12 | 2020-02-27 | 2020-02-22 | 2020-03-04 | 2020-03-04 | 2020-02-26 | 2020-03-05 | 2020-02-29 | 2020-03-05 |  | 2020-03-14 |  |  |  | 2020-03-21 |  | JGT-36-340C-2NPT |  |  | 2020-04-02 |  | 2020-03-11 | [6 empty] | 2020-04-10 | 2020-04-17 | [20 empty] | 2020-05-17 |  |  |  | 2020-05-20 | [7 empty] | 2020-03-01 | 2020-03-26 | 2020-03-08 | 2020-03-29 | 2020-03-08 |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-20 |  |  |  | 2020-04-23 |  |  | 2020-05-08 |  |  |  | 2020-05-20 |  | 2020-05-23
PH1100601 | 125.8378 | 7.3936 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Maco | Hijo | MIN | PH118204011 | 3775 | 40 | Three Legged Tubular Tower | CO65 | 6.557 | MIN-1100288 | Level 5 | phase2_add | phase2_1231 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | JXD-2 |  | Padccon |  | 2019-12-12 | 2019-12-22 | 2019-12-22 | 2019-12-24 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-23 |  |  |  | 2019-12-23 |  |  |  | 2019-12-29 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-27 | 2020-01-28 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Maribeth Obenza | Purok 5, Sta. Catalina, Hijo Maco | Compostela Valley | 125.8375 | 7.3953 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-04 | 2020-01-15 | 2020-02-13 | 2020-03-05 | 2020-02-10 | 2020-02-11 | 2020-02-28 | 2020-02-28 | 2020-02-28 | [13 empty] | 2020-03-03 | ok |  | 2020-03-12 | [6 empty] | 2020-03-26 |  | 2020-02-11 | 2020-02-17 | 2020-03-26 | 2020-02-26 | 2020-02-27 |  | Cheque released | 2020-02-18 | 2020-01-16 | 2020-02-28 | 2020-02-01 | 2020-02-01 | 2020-03-03 | 2020-01-29 | 2020-03-06 | 2020-01-29 | 2020-02-08 | 2020-03-20 | 2020-01-31 | 2020-02-03 | 2020-02-10 | 2020-03-27 | 2020-02-14 | JGT-36-340C-2NPT |  |  | 2020-04-08 |  | 2020-03-17 | [6 empty] | 2020-04-16 | 2020-04-23 | [20 empty] | 2020-05-23 |  |  |  | 2020-05-26 | [7 empty] | 2020-02-26 | 2020-04-01 | 2020-01-31 | 2020-04-04 | 2020-03-06 |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-04-26 |  |  |  | 2020-04-29 |  |  | 2020-05-14 |  |  |  | 2020-05-26 |  | 2020-05-29
PH1100604 | 125.7519 | 7.3971 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Carmen | Mabaus | MIN | PH112319003 | 4227 | 40 | Three Legged Tubular Tower | CO65 | 8.1319 | MIN-1100289 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  | Enovell |  | 2019-11-27 | 2019-12-27 | 2019-12-27 | 2019-12-29 | 2020-01-07 | 2020-01-23 |  |  | 2020-01-07 | 2020-01-08 | 2020-01-25 |  |  | 2020-01-08 |  |  |  | 2020-01-03 |  | 2020-01-25 |  |  | 2020-01-25 | 2020-01-07 | 2020-01-23 |  |  | 2020-01-07 | 2020-02-19 | 2020-02-02 | 2020-02-17 |  |  | 2020-02-19 | 2020-02-21 | B | Emily Pendon | Purok Orchids, Bincungan, Tagum City | Davao del Norte | 125.755 | 7.3774 | Greenfield |  |  | 10 years | P17,000 exclusive of VAT and withholding tax | quarterly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-09 | 2020-02-04 |  | 2020-03-10 |  | 2020-02-16 | [16 empty] | 2020-03-08 |  |  | 2020-03-17 | [6 empty] | 2020-03-31 |  |  |  | 2020-03-31 |  |  |  |  | 2020-02-23 | 2020-02-27 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-03-08 | 2020-02-24 | 2020-03-11 | 2020-02-24 | 2020-02-25 | 2020-03-25 |  |  |  | 2020-04-01 |  | 4GT-42-340C-2NPT |  |  | 2020-04-13 |  | 2020-03-22 | [6 empty] | 2020-04-21 | 2020-04-28 | [20 empty] | 2020-05-28 |  |  |  | 2020-05-31 | [8 empty] | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-01 |  |  |  | 2020-05-04 |  |  | 2020-05-19 |  |  |  | 2020-05-31 |  | 2020-06-03
PH1100605 | 125.4689 | 6.9376 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Santa Cruz | Darong | MIN | PH112412004 | 4576 | 40 | Three Legged Tubular Tower | CO66 | 24.6629 | MIN-1100290 | Level 4 (220) | phase1_220_20% | phase2_1231 | P1_630 |  | Cluster M13 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-08 | 2020-01-23 |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-13 | 2019-12-09 | 2020-01-31 |  |  | 2019-12-09 |  | 2020-01-25 |  |  | 2020-01-25 | 2020-02-13 | 2020-01-12 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | B | Rene Oboza | Brgy. Darung, Sta. Cruz Davao Del Sur | Davao del Sur | 125.4665 | 6.9309 | Greenfield | 30m |  | 10 years | P15,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-01-30 |  | 2020-02-18 | 2020-02-13 | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  | Awaiting Lessor ID | 2020-02-02 | 2020-01-19 | 2020-02-12 | 2020-03-05 | 2020-03-05 | 2020-02-16 | 2020-03-06 | 2020-02-19 | 2020-03-06 | 2020-03-06 | 2020-03-04 | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2020-03-11 | 2020-03-06 | JGT-36-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [7 empty] | 2020-03-04 | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100611 | 125.8913 | 7.5046 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Mawab | Tuboran | MIN | PH118206011 | 2766 | 40 | Three Legged Tubular Tower | CO65 | 11.3457 | MIN-1100291 | Level 5 | phase3 | phase3 | PO Issued not 630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-02-10 | 2020-01-05 | 2020-02-12 | 2020-01-23 | 2020-01-07 |  |  | 2020-01-07 | 2020-01-25 | 2020-01-08 |  |  | 2020-01-08 |  |  |  | 2020-02-17 | 2020-01-25 |  |  |  | 2020-01-25 | 2020-01-23 | 2020-01-07 |  |  | 2020-01-07 | 2020-02-10 | 2020-03-18 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Zenaida Magbanua | Purok 7 Poblacion Mawab Davao De Oro | Compostela Valley | 125.9217 | 7.507 | Greenfield |  |  | 10 years | P17,000 inclusive of VAT and withholding tax | Monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-25 |  |  | 2020-04-24 |  | 2020-04-01 |  |  | 2020-03-05 | [13 empty] | 2020-04-22 |  |  | 2020-05-01 | [6 empty] | 2020-05-15 |  |  |  | 2020-05-15 |  |  |  |  | 2020-04-08 |  | 2020-04-18 |  |  | 2020-04-22 |  | 2020-04-25 |  |  | 2020-05-09 |  |  |  | 2020-05-16 |  | 4GT-42-340C-2NPT |  |  | 2020-05-28 |  | 2020-05-06 | [6 empty] | 2020-06-05 | 2020-06-12 | [20 empty] | 2020-07-12 |  |  |  | 2020-07-15 | [8 empty] | 2020-05-21 |  | 2020-05-24 |  |  | 2020-06-05 |  |  |  | 2020-06-08 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-07-03 |  |  |  | 2020-07-15 |  | 2020-07-18
PH1100612 | 126.0018 | 7.7489 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Montevista | Tapia | MIN | PH118208003 | 1166 | 40 | Three Legged Tubular Tower | CO65 | 40.0082 | MIN-1100292 | Level 6 | phase3 | phase1_630 | P1_630 |  | Cluster M07 | EPC | PO2020011303PH_WLS | PO Batch 3 | EPC |  | EPC |  |  | 2020-01-25 | 2020-01-16 | 2020-01-27 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2020-02-01 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-02-17 | 2020-03-02 | 2020-02-17 |  |  | 2020-02-19 | 2020-02-21 | A | Emilio Sigaton | Purok 5, Poblacion, Montevista, Davao De oro | Compostela Valley | 125.9921 | 7.7097 | Greenfield | 71m |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-03-09 | 2020-01-24 |  | 2020-04-08 | 2020-02-11 | 2020-03-16 | 2020-02-26 | [15 empty] | 2020-04-06 | ok |  | 2020-04-15 | 2020-02-26 | [5 empty] | 2020-04-29 |  | 2020-02-25 | 2020-03-03 | 2020-04-29 | 2020-03-05 | 2020-03-10 |  | Cheque released | 2020-03-23 | 2020-02-05 | 2020-04-02 | 2020-02-21 | 2020-02-21 | 2020-04-06 | 2020-02-25 | 2020-04-09 | 2020-02-25 | 2020-02-25 | 2020-04-23 | 2020-02-25 | 2020-02-26 | 2020-02-25 | 2020-04-30 | 2020-02-26 | 4GT-42-340C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [7 empty] | 2020-03-05 | 2020-05-05 | 2020-03-11 | 2020-05-08 | 2020-03-11 |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1100618 | 125.3211 | 6.478 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Malalag | Tagansule | MIN | PH128007005 | 4134 | 40 | Three Legged Tubular Tower | CO67 | 42.0017 | MIN-1100293 | Level 1 (OA) | phase3 | phase3 | OA_630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-13 | 2019-12-09 | 2019-12-09 | 2019-12-11 | 2019-12-13 | 2019-12-27 | 2020-02-01 |  | 2019-12-13 | 2019-12-14 | 2020-01-16 |  |  | 2019-12-14 |  |  |  | 2019-12-16 | [5 empty] | 2019-12-13 | 2019-12-27 | 2020-02-01 |  | 2019-12-13 |  | 2020-01-15 | [27 empty] | 2020-01-22 |  |  | 2020-02-21 |  | 2020-01-29 | [16 empty] | 2020-02-19 |  |  | 2020-02-28 | [6 empty] | 2020-03-13 |  |  |  | 2020-03-13 |  |  |  |  | 2020-02-05 |  | 2020-02-15 |  |  | 2020-02-19 |  | 2020-02-22 |  |  | 2020-03-07 |  |  |  | 2020-03-14 |  | 4GT-42-340C-2NPT |  |  | 2020-03-26 |  | 2020-03-04 | [6 empty] | 2020-04-03 | 2020-04-10 | [20 empty] | 2020-05-10 |  |  |  | 2020-05-13 | [8 empty] | 2020-03-19 |  | 2020-03-22 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-05-01 |  |  |  | 2020-05-13 |  | 2020-05-16
PH1100621 | 125.3465 | 6.6448 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Padada | Palili | MIN | PH112411002 | 606 | 40 | Three Legged Tubular Tower | CO66 | 58.9558 | MIN-1100294 | Level 5 | phase3 | phase2_1231 | P1_630 | DepEd_3379 | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2020-01-30 | 2019-12-08 |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-14 | 2019-12-09 |  |  |  | 2019-12-09 | 2020-01-30 |  |  |  | 2020-01-30 | 2020-02-25 | 2020-01-13 | [5 empty] | A | Victor Semilla | Southern Pauague, Padada | Davao del Sur | 125.3488 | 6.6434 | Greenfield | 16m |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-20 | 2020-02-24 |  | 2020-02-19 |  | 2020-01-27 | [16 empty] | 2020-02-17 |  |  | 2020-02-26 | [6 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  |  | 2020-02-03 |  | 2020-02-13 |  |  | 2020-02-17 |  | 2020-02-20 |  |  | 2020-03-05 |  |  |  | 2020-03-12 |  | 4GT-42-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 | [20 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [8 empty] | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1100623 | 125.3445 | 6.6039 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Sulop | Poblacion | MIN | PH112414018 | 7274 | 40 | Three Legged Tubular Tower | CO67 | 55.9431 | MIN-1100295 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-03 | 2019-12-03 | 2019-12-05 | 2019-12-11 | 2019-12-22 | 2019-12-28 |  | 2019-12-11 | 2019-12-12 |  | 2020-01-12 |  | 2019-12-12 |  |  |  | 2019-12-10 |  |  | 2020-01-12 |  | 2020-01-12 | 2019-12-06 | 2019-12-03 | 2019-12-29 |  | 2019-12-03 | 2020-03-06 | 2020-01-09 | 2020-03-07 |  |  | 2020-03-06 | 2020-03-07 | C | Alexis Arobo | Purok 7, Poblacion, Sulop | Davao del Sur | 125.3414 | 6.5987 | Greenfield | 15m |  | 15 years | P20,000 inclusive of VAT and withholding tax | quarterly | 240sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-01-16 | 2020-01-23 |  | 2020-02-15 | 2020-02-27 | 2020-01-23 | 2020-02-27 | [15 empty] | 2020-02-13 | ok |  | 2020-02-22 | [6 empty] | 2020-03-07 |  | 2020-03-10 |  | 2020-03-07 |  |  |  | RFP submitted, ongoing review | 2020-01-30 |  | 2020-02-09 |  |  | 2020-02-13 |  | 2020-02-16 |  |  | 2020-03-01 |  |  |  | 2020-03-08 |  | 4GT-42-340C-2NPT |  |  | 2020-03-20 |  | 2020-02-27 | [6 empty] | 2020-03-28 | 2020-04-04 | [20 empty] | 2020-05-04 |  |  |  | 2020-05-07 | [8 empty] | 2020-03-13 |  | 2020-03-16 |  |  | 2020-03-28 |  |  |  | 2020-03-31 |  |  | 2020-04-07 |  |  |  | 2020-04-10 |  |  | 2020-04-25 |  |  |  | 2020-05-07 |  | 2020-05-10
PH1100631 | 125.9893 | 7.7008 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Montevista | Bankerohan Sur | MIN | PH118208020 | 9080 | 40 | Three Legged Tubular Tower | CO65 | 34.7969 | MIN-1100296 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_5033 | Cluster M07 | EPC | PO2019122103PH_WLS | Batch 2 | EPC |  |  |  | 2020-01-20 | 2019-12-30 | 2019-12-30 | 2020-01-01 | 2020-01-02 | 2020-02-01 |  |  | 2020-01-02 | 2020-01-16 | 2020-02-06 |  |  | 2020-01-16 |  |  |  | 2020-01-06 |  | 2020-02-06 |  |  | 2020-02-06 | 2020-01-02 | 2020-02-01 |  |  | 2020-01-02 | 2020-02-24 | 2020-02-05 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | B | Dante Santoyo | Purok 8, Poblacion, Montevista, Davao de Oro | Compostela Valley | 125.9941 | 7.7009 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-12 | 2020-02-28 |  | 2020-03-13 | 2020-03-04 | 2020-02-19 | [16 empty] | 2020-03-11 | ok |  | 2020-03-20 | [6 empty] | 2020-04-03 |  | 2020-03-07 |  | 2020-04-03 |  |  |  | RFP rejected, align Lessor signature | 2020-02-26 |  | 2020-03-07 |  |  | 2020-03-11 |  | 2020-03-14 |  |  | 2020-03-28 |  |  |  | 2020-04-04 |  | 4GT-42-340C-2NPT |  |  | 2020-04-16 |  | 2020-03-25 | [6 empty] | 2020-04-24 | 2020-05-01 | [20 empty] | 2020-05-31 |  |  |  | 2020-06-03 | [8 empty] | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-04 |  |  |  | 2020-05-07 |  |  | 2020-05-22 |  |  |  | 2020-06-03 |  | 2020-06-06
PH1100632 | 125.2969 | 6.6897 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Hagonoy | Lapulabao | MIN | PH112404021 | 4437 | 40 | Three Legged Tubular Tower | CO66 | 57.9635 | MIN-1100297 | Level 4 (220) | phase1_220_20% | phase2_1231 | P1_630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  |  |  | 2019-12-12 | 2019-12-05 | 2019-12-05 | 2019-12-07 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-12 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-05 |  |  |  | 2019-12-05 |  | 2020-01-11 | [5 empty] | A |  |  |  | 125.2993 | 6.6908 | Greenfield | 28m | [14 empty] | 2020-01-18 |  |  | 2020-02-17 |  | 2020-01-25 | [16 empty] | 2020-02-15 |  |  | 2020-02-24 | [6 empty] | 2020-03-09 |  |  |  | 2020-03-09 |  |  |  |  | 2020-02-01 |  | 2020-02-11 |  |  | 2020-02-15 |  | 2020-02-18 |  |  | 2020-03-03 |  |  |  | 2020-03-10 |  | 4GT-42-340C-2NPT |  |  | 2020-03-22 |  | 2020-02-29 | [6 empty] | 2020-03-30 | 2020-04-06 | [20 empty] | 2020-05-06 |  |  |  | 2020-05-09 | [8 empty] | 2020-03-15 |  | 2020-03-18 |  |  | 2020-03-30 |  |  |  | 2020-04-02 |  |  | 2020-04-09 |  |  |  | 2020-04-12 |  |  | 2020-04-27 |  |  |  | 2020-05-09 |  | 2020-05-12
PH1100634 | 125.3542 | 6.5185 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Malalag | Mabini | MIN | PH128007020 | 2963 | 40 | Three Legged Tubular Tower | CO67 | 47.6239 | MIN-1100298 | Level 5 | phase3 | phase3 | P1_630 | DepEd_5069 | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-13 | 2019-12-09 | 2019-12-09 | 2019-12-11 | 2019-12-10 |  |  |  | 2019-12-10 | 2019-12-11 |  |  |  | 2019-12-11 |  |  |  | 2019-12-16 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-18 |  |  |  | 2019-12-18 | 2020-01-24 | 2020-01-15 | 2020-01-09 |  |  | 2020-01-10 | 2020-02-04 | A | Reliosa Dela Pena | Purok 4, Malungon Gamay, Malungon | Sarangani | 125.3671 | 6.5603 | Greenfield | 316m |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 240sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-27 | n/a |  |  |  | n/a | 2020-01-22 | 2020-01-09 |  | 2020-02-21 | 2020-03-13 | 2020-01-29 | [16 empty] | 2020-02-19 |  |  | 2020-02-28 | 2020-01-27 | [5 empty] | 2020-03-13 |  |  |  | 2020-03-13 |  |  |  | Awaiting Lessor ID | 2020-02-05 | 2020-01-27 | 2020-02-15 | 2020-02-17 | 2020-02-17 | 2020-02-19 | 2020-01-24 | 2020-02-22 | 2020-01-24 | 2020-01-25 | 2020-03-07 | 2020-01-27 | 2020-01-25 | 2020-02-20 | 2020-03-14 | 2020-02-19 | 4GT-42-340C-2NPT |  |  | 2020-03-26 |  | 2020-03-04 | [6 empty] | 2020-04-03 | 2020-04-10 | [20 empty] | 2020-05-10 |  |  |  | 2020-05-13 | [8 empty] | 2020-03-19 |  | 2020-03-22 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-05-01 |  |  |  | 2020-05-13 |  | 2020-05-16
PH1100639 | 125.298 | 6.7492 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Digos City | Colorado | MIN | PH112403006 | 2732 | 40 | Three Legged Tubular Tower | CO66 | 52.8492 | MIN-1100299 | Level 4 (220) | phase1_220_20% | phase2_1231 | P1_630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-12 | 2019-12-09 | 2019-12-09 | 2019-12-11 | 2019-12-13 | 2020-01-28 |  |  | 2019-12-13 | 2019-12-14 |  |  |  | 2019-12-14 |  |  |  | 2019-12-16 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-13 | 2020-01-28 |  |  | 2019-12-13 | 2019-12-23 | 2020-01-15 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | A | Edwin Bastatas | Purok Anahaw Colorado, Digos City | Davao del Sur | 125.2979 | 6.7473 | Greenfield | 30m |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-22 | 2020-02-18 |  | 2020-02-21 | 2020-03-06 | 2020-01-29 | [16 empty] | 2020-02-19 | ok |  | 2020-02-28 | [6 empty] | 2020-03-13 |  |  |  | 2020-03-13 |  |  |  | For RFP submission in DingTalk | 2020-02-05 |  | 2020-02-15 |  |  | 2020-02-19 |  | 2020-02-22 |  |  | 2020-03-07 |  |  |  | 2020-03-14 |  | 4GT-42-340C-2NPT |  |  | 2020-03-26 |  | 2020-03-04 | [6 empty] | 2020-04-03 | 2020-04-10 | [20 empty] | 2020-05-10 |  |  |  | 2020-05-13 | [8 empty] | 2020-03-19 |  | 2020-03-22 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-05-01 |  |  |  | 2020-05-13 |  | 2020-05-16
PH1100644 | 125.7195 | 7.1001 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Mambago-A | MIN | PH112317043 | 765 | 40 | Three Legged Tubular Tower | CO66 | 10.6936 | MIN-1100300 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M03 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2020-01-20 | 2020-02-22 |  | 2020-02-24 | [13 empty] | 2020-02-29 | [11 empty] | 2020-03-30 | [27 empty] | 2020-04-06 |  |  | 2020-05-06 |  | 2020-04-13 | [16 empty] | 2020-05-04 |  |  | 2020-05-13 | [6 empty] | 2020-05-27 |  |  |  | 2020-05-27 |  |  |  |  | 2020-04-20 |  | 2020-04-30 |  |  | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-21 |  |  |  | 2020-05-28 |  | JGT-36-340C-2NPT |  |  | 2020-06-09 |  | 2020-05-18 | [6 empty] | 2020-06-17 | 2020-06-24 | [20 empty] | 2020-07-24 |  |  |  | 2020-07-27 | [8 empty] | 2020-06-02 |  | 2020-06-05 |  |  | 2020-06-17 |  |  |  | 2020-06-20 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-15 |  |  |  | 2020-07-27 |  | 2020-07-30
PH1100646 | 125.7785 | 7.4858 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Pagsabangan | MIN | PH112319011 | 38963 | 40 | Three Legged Tubular Tower | CO65 | 5.6186 | MIN-1100301 | Level 4 (220) | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 | 2020-01-04 | 2020-01-20 |  | 2019-12-07 | 2020-01-04 |  | 2020-01-21 |  | 2020-01-04 |  |  |  | 2019-12-13 |  |  | 2020-01-21 |  | 2020-01-21 | 2019-12-09 | 2020-01-04 | 2020-01-20 |  | 2019-12-09 | 2020-03-05 | 2020-01-12 | 2020-03-05 |  |  | 2020-03-05 | 2020-03-05 | A | Sergio E. Isaal, Sr. | Purok Bagani, Brgy. Cuambogan, Tagum City | Davao del Norte | 125.7872 | 7.4933 | Greenfield |  |  | 10 years | P18,000 exclusive of VAT and withholding tax | quarterly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-01-16 |  | 2020-02-18 | 2020-03-05 | 2020-01-26 | 2020-03-05 | 2020-03-05 | [14 empty] | 2020-02-16 | ok |  | 2020-02-25 | 2020-03-05 | [5 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  | For RFP submission in DingTalk | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-36-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100647 | 125.6768 | 7.0695 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Catagman | MIN | PH112317021 | 2497 | 40 | Three Legged Tubular Tower | CO66 | 6.7942 | MIN-1100302 | Level 6 | phase3 | phase3 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-02-25 |  | 2020-02-27 | [13 empty] | 2020-03-03 | [11 empty] | 2020-04-02 | [27 empty] | 2020-04-09 |  |  | 2020-05-09 |  | 2020-04-16 | [16 empty] | 2020-05-07 |  |  | 2020-05-16 | [6 empty] | 2020-05-30 |  |  |  | 2020-05-30 |  |  |  |  | 2020-04-23 |  | 2020-05-03 |  |  | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-24 |  |  |  | 2020-05-31 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-06-12 |  | 2020-05-21 | [6 empty] | 2020-06-20 | 2020-06-27 | [20 empty] | 2020-07-27 |  |  |  | 2020-07-30 | [8 empty] | 2020-06-05 |  | 2020-06-08 |  |  | 2020-06-20 |  |  |  | 2020-06-23 |  |  | 2020-06-30 |  |  |  | 2020-07-03 |  |  | 2020-07-18 |  |  |  | 2020-07-30 |  | 2020-08-02
PH1100648 | 125.6258 | 7.3058 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Panabo City | n.a. ( 38686) | MIN | PH112315012 | 1836 | 40 | Three Legged Tubular Tower | CO66 | 23.0427 | MIN-1100303 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M08 | EPC | PO2019122103PH_WLS | Batch 2 (333) | EPC |  | EPC |  | 2019-12-12 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-14 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-18 |  |  |  | 2019-12-18 | 2019-12-27 | 2020-01-13 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Rosello Cabardo | Purok 3, Brgy. Katipunan, Panabo City | Davao del Norte | 125.6261 | 7.3051 | Greenfield | 55m |  | 15 years | P16,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-22 | n/a |  |  |  | n/a | 2020-01-20 | 2020-01-09 |  | 2020-02-19 | 2020-02-06 | 2020-01-27 | 2020-01-17 | 2020-03-02 | 2020-01-13 |  |  | 2020-03-03 | [5 empty] | 0938-7280135 |  |  |  |  | 2020-02-17 | ok | 2020-03-03 | 2020-02-26 | 2020-02-26 | [5 empty] | 2020-03-11 |  | 2020-02-06 | 2020-02-11 | 2020-03-11 | 2020-02-12 | 2020-02-17 | 2020-03-11 | Cheque released | 2020-02-03 | 2020-01-15 | 2020-02-13 | 2020-01-25 | 2020-01-25 | 2020-02-17 | 2020-01-22 | 2020-02-20 | 2020-01-22 | 2020-01-23 | 2020-03-05 | 2020-01-23 | 2020-01-23 | 2020-02-11 | 2020-03-12 | 2020-02-24 | 4GT-42-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | 2020-02-11 | [5 empty] | 2020-04-01 | 2020-04-08 |  |  |  | 2020-03-09 | [16 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [7 empty] | 2020-01-29 | 2020-03-17 | 2020-01-30 | 2020-03-20 | 2020-03-07 |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1100652 | 125.7754 | 7.3589 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Liboganon | MIN | PH112319003 | 4227 | 45 | Three Legged Tubular Tower | CO65 | 10.1865 | MIN-1100304 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  | Enovell |  | 2019-12-12 | 2020-01-08 | 2020-01-05 | 2020-01-10 | 2020-01-07 |  |  |  | 2020-01-07 | 2020-01-08 |  |  |  | 2020-01-08 |  |  |  | 2020-01-15 | 2020-01-08 |  |  |  | 2020-01-08 | 2020-01-07 |  |  |  | 2020-01-07 | 2020-01-24 | 2020-02-14 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Rosito P. Ballesteros | Purok 3, Liboganon, Tagum City | Davao del Norte | 125.7785 | 7.3478 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-21 | 2020-02-28 |  | 2020-03-22 | 2020-03-02 | 2020-02-28 | [16 empty] | 2020-03-20 | ok |  | 2020-03-29 | [6 empty] | 2020-04-12 |  | 2020-03-07 |  | 2020-04-12 |  |  |  | RFP rejected, align Lessor signature | 2020-03-06 | 2020-02-22 | 2020-03-16 | 2020-02-27 | 2020-02-27 | 2020-03-20 | 2020-02-24 | 2020-03-23 | 2020-02-27 | 2020-02-28 | 2020-04-06 | 2020-02-28 | 2020-02-28 | 2020-02-28 | 2020-04-13 | 2020-02-28 | JGT-36-340C-2NPT |  |  | 2020-04-25 |  | 2020-04-03 | [6 empty] | 2020-05-03 | 2020-05-10 | [20 empty] | 2020-06-09 |  |  |  | 2020-06-12 | [7 empty] | 2020-02-21 | 2020-04-18 |  | 2020-04-21 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-31 |  |  |  | 2020-06-12 |  | 2020-06-15
PH1100654 | 125.7652 | 7.4672 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Tagum City | Pagsabangan | MIN | PH112319011 | 38963 | 45 | Three Legged Tubular Tower | CO65 | 5.3465 | MIN-1100305 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2020-01-06 |  |  |  | 2020-01-06 |  |  |  | 2019-12-13 | 2020-01-06 |  |  |  | 2020-01-06 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-02-13 | 2020-01-12 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Ranny Manla | Purok Banana, Brgy. Banana, Mankilan, Tagum City | Davao del Norte | 125.764 | 7.4663 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 | 2020-02-03 |  | 2020-02-18 | 2020-02-20 | 2020-01-26 | 2020-02-28 |  | 2020-02-28 | [13 empty] | 2020-02-16 | ok |  | 2020-02-25 | [6 empty] | 2020-03-10 |  | 2020-02-22 | 2020-02-26 | 2020-03-10 | 2020-03-02 |  |  | Cheque released | 2020-02-02 | 2020-02-27 | 2020-02-12 | 2020-03-04 | 2020-03-04 | 2020-02-16 | 2020-02-24 | 2020-02-19 | 2020-02-26 | 2020-02-26 | 2020-03-04 |  |  |  | 2020-03-11 |  | JGT-36-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [7 empty] | 2020-03-01 | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1100655 | 125.6852 | 7.1174 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Kinawitnon | MIN | PH112317017 | 1973 | 45 | Three Legged Tubular Tower | CO66 | 7.214 | MIN-1100306 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-02-28 |  | 2020-03-01 | [13 empty] | 2020-03-06 | [11 empty] | 2020-04-05 | [27 empty] | 2020-04-12 |  |  | 2020-05-12 |  | 2020-04-19 | [16 empty] | 2020-05-10 |  |  | 2020-05-19 | [6 empty] | 2020-06-02 |  |  |  | 2020-06-02 |  |  |  |  | 2020-04-26 |  | 2020-05-06 |  |  | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-27 |  |  |  | 2020-06-03 |  | 4GT-42-340C-2NPT |  |  | 2020-06-15 |  | 2020-05-24 | [6 empty] | 2020-06-23 | 2020-06-30 | [20 empty] | 2020-07-30 |  |  |  | 2020-08-02 | [8 empty] | 2020-06-08 |  | 2020-06-11 |  |  | 2020-06-23 |  |  |  | 2020-06-26 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-21 |  |  |  | 2020-08-02 |  | 2020-08-05
PH1100658 | 126.1313 | 7.6927 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Compostela | Ngan | MIN | PH118201008 | 8348 | 45 | Three Legged Tubular Tower | CO65 | 45.0606 | MIN-1100307 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M07 | EPC | [7 empty] | 2020-03-23 | 2020-02-17 | 2020-03-25 | 2020-02-18 |  |  |  | 2020-02-18 | 2020-02-21 |  |  |  | 2020-02-21 |  |  |  | 2020-03-30 | 2020-02-21 |  |  |  | 2020-02-21 | 2020-03-02 |  |  |  | 2020-03-02 | 2020-02-26 | 2020-04-29 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 | A | Vicente Damalerio | Brgy. Ngan, Compostela | Compostela Valley | 126.1316 | 7.6956 | Greenfield |  |  | 10 years | P18,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-06 | 2020-03-02 |  | 2020-06-05 |  | 2020-05-13 | [16 empty] | 2020-06-03 |  |  | 2020-06-12 | [6 empty] | 2020-06-26 |  |  |  | 2020-06-26 |  |  |  |  | 2020-05-20 |  | 2020-05-30 |  |  | 2020-06-03 |  | 2020-06-06 |  |  | 2020-06-20 |  |  |  | 2020-06-27 |  | 4GT-42-340C-2NPT |  |  | 2020-07-09 |  | 2020-06-17 | [6 empty] | 2020-07-17 | 2020-07-24 | [20 empty] | 2020-08-23 |  |  |  | 2020-08-26 | [8 empty] | 2020-07-02 |  | 2020-07-05 |  |  | 2020-07-17 |  |  |  | 2020-07-20 |  |  | 2020-07-27 |  |  |  | 2020-07-30 |  |  | 2020-08-14 |  |  |  | 2020-08-26 |  | 2020-08-29
PH1100659 | 126.1276 | 7.6459 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Compostela | San Jose | MIN | PH118201013 | 7286 | 45 | Three Legged Tubular Tower | CO65 | 41.736 | MIN-1100308 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M07 | EPC | PO2019122103PH_WLS | Batch 2 | EPC |  | EPC |  | 2020-01-20 | 2020-01-08 | 2020-01-10 | 2020-01-10 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-01-12 |  |  |  | 2020-01-12 |  |  |  | 2020-01-15 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-01-24 | 2020-02-14 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Diosdado Castil | Brgy. San Miguel, Compostela, Davao de Oro | Compostela Valley | 126.1218 | 7.6377 | Greenfield | 92m |  | 15 years | P16,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | n/a | 4.5% increase on the 4th year | 2020-02-10 | n/a |  |  |  | n/a | 2020-02-21 | 2020-01-29 | 2020-02-13 | 2020-03-22 | 2020-02-14 | 2020-02-28 | 2020-02-26 | 2020-02-26 | 2020-02-26 | [13 empty] | 2020-03-20 | ok |  | 2020-03-29 | 2020-03-13 | [5 empty] | 2020-04-12 |  | 2020-02-25 | 2020-03-03 | 2020-04-12 | 2020-03-05 | 2020-03-10 |  | Cheque released | 2020-03-06 | 2020-02-07 | 2020-03-16 | 2020-02-21 | 2020-02-21 | 2020-03-20 | 2020-02-24 | 2020-03-23 | 2020-02-24 | 2020-02-24 | 2020-04-06 | 2020-02-26 | 2020-02-26 | 2020-02-26 | 2020-04-13 | 2020-02-26 | 4GT-42-340C-2NPT |  |  | 2020-04-25 |  | 2020-04-03 | [6 empty] | 2020-05-03 | 2020-05-10 | [20 empty] | 2020-06-09 |  |  |  | 2020-06-12 | [7 empty] | 2020-02-27 | 2020-04-18 |  | 2020-04-21 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-31 |  |  |  | 2020-06-12 |  | 2020-06-15
PH1100661 | 126.035 | 7.645 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Compostela | Maparat | MIN | PH118201014 | 3517 | 45 | Three Legged Tubular Tower | CO65 | 33.5007 | MIN-1100309 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_5041 | Cluster M07 | EPC | PO2019122103PH_WLS | Batch 2 | EPC |  | EPC |  | 2020-01-20 | 2020-01-08 | 2020-01-10 | 2020-01-10 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-01-12 |  |  |  | 2020-01-12 |  |  |  | 2020-01-15 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-01-24 | 2020-02-14 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Benita V. Ladica | Purok 9, Siocon, Compostela, Davao de Oro | Compostela Valley | 126.0353 | 7.646 | Greenfield | 73m |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 240sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-02-21 | 2020-01-27 |  | 2020-03-22 | 2020-02-14 | 2020-02-28 | 2020-02-26 |  | 2020-02-26 | [13 empty] | 2020-03-20 | ok |  | 2020-03-29 | 2020-03-11 | [5 empty] | 2020-04-12 |  | 2020-02-22 | 2020-02-26 | 2020-04-12 | 2020-03-02 |  |  | Cheque released | 2020-03-06 |  | 2020-03-16 |  |  | 2020-03-20 | 2020-02-20 | 2020-03-23 | 2020-03-03 | 2020-03-03 | 2020-04-06 | 2020-03-03 | 2020-03-03 |  | 2020-04-13 |  | JGT-36-340C-2NPT |  |  | 2020-04-25 |  | 2020-04-03 | [6 empty] | 2020-05-03 | 2020-05-10 |  |  |  | 2020-03-09 |  |  | 2020-03-11 | [13 empty] | 2020-06-09 |  |  |  | 2020-06-12 | [7 empty] | 2020-02-27 | 2020-04-18 |  | 2020-04-21 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-31 |  |  |  | 2020-06-12 |  | 2020-06-15
PH1100665 | 126.1176 | 7.3475 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Maragusan (San Mariano) | Maragusan | MIN | PH118205003 | 14741 | 45 | Three Legged Tubular Tower | CO65 | 35.8109 | MIN-1100310 | Level 6 | phase3 | phase3 |  |  | Cluster M07 | EPC | [7 empty] | 2020-03-26 |  | 2020-03-28 | [13 empty] | 2020-04-02 | [11 empty] | 2020-05-02 | [27 empty] | 2020-05-09 |  |  | 2020-06-08 |  | 2020-05-16 | [16 empty] | 2020-06-06 |  |  | 2020-06-15 | [6 empty] | 2020-06-29 |  |  |  | 2020-06-29 |  |  |  |  | 2020-05-23 |  | 2020-06-02 |  |  | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-23 |  |  |  | 2020-06-30 |  | 4GT-42-340C-2NPT |  |  | 2020-07-12 |  | 2020-06-20 | [6 empty] | 2020-07-20 | 2020-07-27 | [20 empty] | 2020-08-26 |  |  |  | 2020-08-29 | [8 empty] | 2020-07-05 |  | 2020-07-08 |  |  | 2020-07-20 |  |  |  | 2020-07-23 |  |  | 2020-07-30 |  |  |  | 2020-08-02 |  |  | 2020-08-17 |  |  |  | 2020-08-29 |  | 2020-09-01
PH1100667 | 126.1301 | 7.2669 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Pantukan | Araibo | MIN | PH118205024 | 1635 | 45 | Three Legged Tubular Tower | CO65 | 40.6503 | MIN-1100311 | Level 6 | phase3 | phase3 |  |  | Cluster M07 | EPC | [7 empty] | 2020-03-29 | 2020-02-11 | 2020-03-31 | 2020-02-14 |  |  |  | 2020-02-14 | 2020-02-19 |  |  |  | 2020-02-19 |  |  |  | 2020-04-05 | 2020-02-19 |  |  |  | 2020-02-19 | 2020-02-14 |  |  |  | 2020-02-14 | 2020-02-26 | 2020-05-05 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 |  | Renato Condole | Purok Gumamela, Tigbao, Maragusan | Compostela Valley | 126.1273 | 7.2609 | Greenfield |  |  | 10 years | P18,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-12 | 2020-03-02 |  | 2020-06-11 |  | 2020-05-19 | [16 empty] | 2020-06-09 |  |  | 2020-06-18 | [6 empty] | 2020-07-02 |  |  |  | 2020-07-02 |  |  |  |  | 2020-05-26 |  | 2020-06-05 |  |  | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-26 |  |  |  | 2020-07-03 |  | 4GT-42-340C-2NPT |  |  | 2020-07-15 |  | 2020-06-23 | [6 empty] | 2020-07-23 | 2020-07-30 | [20 empty] | 2020-08-29 |  |  |  | 2020-09-01 | [8 empty] | 2020-07-08 |  | 2020-07-11 |  |  | 2020-07-23 |  |  |  | 2020-07-26 |  |  | 2020-08-02 |  |  |  | 2020-08-05 |  |  | 2020-08-20 |  |  |  | 2020-09-01 |  | 2020-09-04
PH1100684 | 126.2031 | 7.0129 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Oriental | Mati City | Buso | MIN | PH112509022 | 10754 | 45 | Three Legged Tubular Tower | CO66 | 64.7594 | MIN-1100312 | Level 6 | phase3 | phase3 |  |  | Cluster M01 | TBD | [7 empty] | 2020-03-22 |  | 2020-03-24 | [13 empty] | 2020-03-29 | [11 empty] | 2020-04-28 | [27 empty] | 2020-05-05 |  |  | 2020-06-04 |  | 2020-05-12 | [16 empty] | 2020-06-02 |  |  | 2020-06-11 | [6 empty] | 2020-06-25 |  |  |  | 2020-06-25 |  |  |  |  | 2020-05-19 |  | 2020-05-29 |  |  | 2020-06-02 |  | 2020-06-05 |  |  | 2020-06-19 |  |  |  | 2020-06-26 |  | 4GT-42-340C-2NPT |  |  | 2020-07-08 |  | 2020-06-16 | [6 empty] | 2020-07-16 | 2020-07-23 | [20 empty] | 2020-08-22 |  |  |  | 2020-08-25 | [8 empty] | 2020-07-01 |  | 2020-07-04 |  |  | 2020-07-16 |  |  |  | 2020-07-19 |  |  | 2020-07-26 |  |  |  | 2020-07-29 |  |  | 2020-08-13 |  |  |  | 2020-08-25 |  | 2020-08-28
PH1100687 | 125.7628 | 7.136 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | San Antonio | MIN | PH112317031 | 2098 | 45 | Three Legged Tubular Tower | CO66 | 16.0145 | MIN-1100313 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M03 | JXD | PO2019122101PH_WLS | Proposed PO 2 |  |  |  |  | 2020-01-20 | 2020-03-02 |  | 2020-03-04 | [13 empty] | 2020-03-09 | [11 empty] | 2020-04-08 | [27 empty] | 2020-04-15 |  |  | 2020-05-15 |  | 2020-04-22 | [16 empty] | 2020-05-13 |  |  | 2020-05-22 | [6 empty] | 2020-06-05 |  |  |  | 2020-06-05 |  |  |  |  | 2020-04-29 |  | 2020-05-09 |  |  | 2020-05-13 |  | 2020-05-16 |  |  | 2020-05-30 |  |  |  | 2020-06-06 |  | 4GT-42-340C-2NPT |  |  | 2020-06-18 |  | 2020-05-27 | [6 empty] | 2020-06-26 | 2020-07-03 | [20 empty] | 2020-08-02 |  |  |  | 2020-08-05 | [8 empty] | 2020-06-11 |  | 2020-06-14 |  |  | 2020-06-26 |  |  |  | 2020-06-29 |  |  | 2020-07-06 |  |  |  | 2020-07-09 |  |  | 2020-07-24 |  |  |  | 2020-08-05 |  | 2020-08-08
PH1100701 | 125.6061 | 7.4947 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Santo Tomas | Bobongon | MIN | PH112318002 | 6551 | 45 | Three Legged Tubular Tower | CO65 | 22.9441 | MIN-1100314 | Level 5 | phase3 | phase3 | P1_630 |  | Cluster M02 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-13 | 2019-12-28 | 2019-12-28 | 2019-12-30 | 2019-12-31 |  |  |  | 2019-12-31 | 2019-12-31 |  |  |  | 2019-12-31 |  |  |  | 2020-01-04 | 2019-12-31 |  |  |  | 2019-12-31 | 2019-12-31 |  |  |  | 2019-12-31 | 2020-02-13 | 2020-02-03 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Eunora Tabajonda | Purok 2-A, Brgy. Bobongon, Sto. Tomas | Davao del Norte | 125.607 | 7.4954 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-10 | 2020-01-25 |  | 2020-03-11 |  | 2020-02-17 |  |  | 2020-03-05 | [13 empty] | 2020-03-09 |  |  | 2020-03-18 | [6 empty] | 2020-04-01 |  |  |  | 2020-04-01 |  |  |  |  | 2020-02-24 | 2020-02-25 | 2020-03-05 | 2020-02-27 | 2020-02-27 | 2020-03-09 | 2020-02-24 | 2020-03-12 | 2020-02-26 | 2020-02-26 | 2020-03-26 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-04-02 | 2020-03-04 | 4GT-42-340C-2NPT |  |  | 2020-04-14 |  | 2020-03-23 | [6 empty] | 2020-04-22 | 2020-04-29 | [20 empty] | 2020-05-29 |  |  |  | 2020-06-01 | [8 empty] | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-02 |  |  |  | 2020-05-05 |  |  | 2020-05-20 |  |  |  | 2020-06-01 |  | 2020-06-04
PH1100706 | 125.3353 | 6.8436 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Digos City | Binaton | MIN | PH112403004 | 2599 | 45 | Three Legged Tubular Tower | CO66 | 42.5376 | MIN-1100315 | Level 4 (220) | phase1_220_20% | phase3 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-21 | 2019-12-21 | 2019-12-23 | [13 empty] | 2019-12-28 | [11 empty] | 2020-01-27 | [27 empty] | 2020-02-03 |  |  | 2020-03-04 |  | 2020-02-10 | [16 empty] | 2020-03-02 |  |  | 2020-03-11 | [6 empty] | 2020-03-25 |  |  |  | 2020-03-25 |  |  |  |  | 2020-02-17 |  | 2020-02-27 |  |  | 2020-03-02 |  | 2020-03-05 |  |  | 2020-03-19 |  |  |  | 2020-03-26 |  | 4GT-42-340C-2NPT |  |  | 2020-04-07 |  | 2020-03-16 | [6 empty] | 2020-04-15 | 2020-04-22 | [20 empty] | 2020-05-22 |  |  |  | 2020-05-25 | [8 empty] | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-15 |  |  |  | 2020-04-18 |  |  | 2020-04-25 |  |  |  | 2020-04-28 |  |  | 2020-05-13 |  |  |  | 2020-05-25 |  | 2020-05-28
PH1100714 | 126.072 | 7.8649 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Monkayo | Baylo | MIN | PH118207004 | 3080 | 45 | Three Legged Tubular Tower | CO65 | 55.0538 | MIN-1100316 | Level 6 | phase3 | phase3 |  |  | Cluster M07 | EPC | [7 empty] | 2020-04-01 | 2020-01-21 | 2020-04-03 | 2020-02-12 |  |  |  | 2020-02-12 | 2020-02-14 |  |  |  | 2020-02-14 |  |  |  | 2020-04-08 | 2020-02-14 |  |  |  | 2020-02-14 | 2020-02-12 |  |  |  | 2020-02-12 |  | 2020-05-08 | [5 empty] | A |  |  |  | 126.0728 | 7.8486 | [16 empty] | 2020-05-15 | 2020-02-26 |  | 2020-06-14 |  | 2020-05-22 | [16 empty] | 2020-06-12 | ok |  | 2020-06-21 | [6 empty] | 2020-07-05 |  |  |  | 2020-07-05 |  |  |  |  | 2020-05-29 |  | 2020-06-08 |  |  | 2020-06-12 |  | 2020-06-15 |  |  | 2020-06-29 |  |  |  | 2020-07-06 |  | 4GT-42-340C-2NPT |  |  | 2020-07-18 |  | 2020-06-26 | [6 empty] | 2020-07-26 | 2020-08-02 | [20 empty] | 2020-09-01 |  |  |  | 2020-09-04 | [8 empty] | 2020-07-11 |  | 2020-07-14 |  |  | 2020-07-26 |  |  |  | 2020-07-29 |  |  | 2020-08-05 |  |  |  | 2020-08-08 |  |  | 2020-08-23 |  |  |  | 2020-09-04 |  | 2020-09-07
PH1100720 | 125.9863 | 7.46 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Mawab | Andili | MIN | PH118206001 | 4886 | 45 | Three Legged Tubular Tower | CO65 | 19.7282 | MIN-1100317 | Level 6 | phase3 | phase3 |  |  | Cluster M07 | EPC | [7 empty] | 2020-04-04 | 2020-02-05 | 2020-04-06 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-02-09 |  |  |  | 2020-02-09 |  |  |  | 2020-04-11 | 2020-02-09 |  |  |  | 2020-02-09 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-02-26 | 2020-05-11 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 | A | Leopoldo Valiente | Purok 7, Panibasan, Maco, Davao de Oro | Compostela Valley | 125.9726 | 7.4356 | Greenfield |  |  | 10 years | P18,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-05-18 | 2020-02-24 |  | 2020-06-17 |  | 2020-05-25 | [16 empty] | 2020-06-15 |  |  | 2020-06-24 | [6 empty] | 2020-07-08 |  |  |  | 2020-07-08 |  |  |  |  | 2020-06-01 |  | 2020-06-11 |  |  | 2020-06-15 |  | 2020-06-18 |  |  | 2020-07-02 |  |  |  | 2020-07-09 |  | 4GT-42-340C-2NPT |  |  | 2020-07-21 |  | 2020-06-29 | [6 empty] | 2020-07-29 | 2020-08-05 | [20 empty] | 2020-09-04 |  |  |  | 2020-09-07 | [8 empty] | 2020-07-14 |  | 2020-07-17 |  |  | 2020-07-29 |  |  |  | 2020-08-01 |  |  | 2020-08-08 |  |  |  | 2020-08-11 |  |  | 2020-08-26 |  |  |  | 2020-09-07 |  | 2020-09-10
PH1100724 | 125.4108 | 7.2996 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Davao City | Bantol | MIN | PH112402191 | 2112 | 45 | Three Legged Tubular Tower | CO66 | 32.3422 | MIN-1100318 | Level 3 (Davao City) - R | phase3 | phase3 | PO Issued not 630 |  | Cluster M09 | JXD |  | Batch 2 (333) |  |  |  |  | 2020-01-15 | 2020-02-22 | 2020-01-19 | 2020-02-24 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-20 |  |  |  | 2020-01-20 |  |  |  | 2020-02-29 | [5 empty] | 2020-01-20 |  |  |  | 2020-01-20 |  | 2020-03-30 | [27 empty] | 2020-04-06 |  |  | 2020-05-06 |  | 2020-04-13 | [16 empty] | 2020-05-04 |  |  | 2020-05-13 | [6 empty] | 2020-05-27 |  |  |  | 2020-05-27 |  |  |  |  | 2020-04-20 |  | 2020-04-30 |  |  | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-21 |  |  |  | 2020-05-28 |  | 4GT-42-340C-2NPT |  |  | 2020-06-09 |  | 2020-05-18 | [6 empty] | 2020-06-17 | 2020-06-24 | [20 empty] | 2020-07-24 |  |  |  | 2020-07-27 | [8 empty] | 2020-06-02 |  | 2020-06-05 |  |  | 2020-06-17 |  |  |  | 2020-06-20 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-15 |  |  |  | 2020-07-27 |  | 2020-07-30
PH1100727 | 126.1615 | 7.1967 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Oriental | Banaybanay | Mahayag | MIN | PH112507022 | 5767 | 45 | Three Legged Tubular Tower | CO65 | 47.7549 | MIN-1100319 | Level 6 | phase3 | phase3 |  |  | Cluster M07 | EPC | [7 empty] | 2020-04-07 |  | 2020-04-09 | [13 empty] | 2020-04-14 | [11 empty] | 2020-05-14 | [27 empty] | 2020-05-21 |  |  | 2020-06-20 |  | 2020-05-28 | [16 empty] | 2020-06-18 |  |  | 2020-06-27 | [6 empty] | 2020-07-11 |  |  |  | 2020-07-11 |  |  |  |  | 2020-06-04 |  | 2020-06-14 |  |  | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-05 |  |  |  | 2020-07-12 |  | 4GT-42-340C-2NPT |  |  | 2020-07-24 |  | 2020-07-02 | [6 empty] | 2020-08-01 | 2020-08-08 | [20 empty] | 2020-09-07 |  |  |  | 2020-09-10 | [8 empty] | 2020-07-17 |  | 2020-07-20 |  |  | 2020-08-01 |  |  |  | 2020-08-04 |  |  | 2020-08-11 |  |  |  | 2020-08-14 |  |  | 2020-08-29 |  |  |  | 2020-09-10 |  | 2020-09-13
PH1100745 | 126.0298 | 7.5923 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Nabunturan | Cabacungan | MIN | PH118209017 | 1540 | 45 | Three Legged Tubular Tower | CO65 | 29.4501 | MIN-1100320 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M07 | EPC | PO2019122103PH_WLS | Batch 2 | EPC |  | EPC |  | 2020-01-20 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-20 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-24 | 2020-02-19 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Amelita L. Ganade | Purok 18, Poblacion, Nabunturan, Davao de Oro | Compostela Valley | 125.9737 | 7.6075 | Greenfield | 88m |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-02-26 | 2020-01-15 |  | 2020-03-27 | 2020-02-22 | 2020-03-04 | 2020-02-26 | 2020-02-26 | 2020-02-26 |  |  | 2020-03-04 | [10 empty] | 2020-03-25 | ok | 2020-03-04 | 2020-04-03 | 2020-03-11 | [5 empty] | 2020-04-17 |  | 2020-02-27 | 2020-03-05 | 2020-04-17 | 2020-03-06 | 2020-03-10 |  | Cheque released | 2020-03-11 | 2020-02-13 | 2020-03-21 | 2020-02-21 | 2020-02-21 | 2020-03-25 | 2020-01-28 | 2020-03-28 | 2020-01-28 | 2020-01-29 | 2020-04-11 | 2020-01-28 | 2020-01-29 | 2020-02-21 | 2020-04-18 | 2020-02-21 | JGT-36-340C-2NPT |  |  | 2020-04-30 |  | 2020-04-08 | [6 empty] | 2020-05-08 | 2020-05-15 |  |  |  | 2020-03-02 |  | 2020-03-05 | 2020-03-09 | [13 empty] | 2020-06-14 |  |  |  | 2020-06-17 | [7 empty] | 2020-02-27 | 2020-04-23 | 2020-03-10 | 2020-04-26 | 2020-03-10 |  | 2020-05-08 |  |  |  | 2020-05-11 |  |  | 2020-05-18 |  |  |  | 2020-05-21 |  |  | 2020-06-05 |  |  |  | 2020-06-17 |  | 2020-06-20
PH1100757 | 125.29 | 6.823 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Sur | Digos City | Goma | MIN | PH112403009 | 4093 | 45 | Three Legged Tubular Tower | CO66 | 47.8173 | MIN-1100321 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M14 | EPC | PO2019122103PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-10 | 2019-12-10 | 2019-12-12 | 2019-12-12 |  |  |  | 2019-12-12 | [8 empty] | 2019-12-17 | [5 empty] | 2020-02-06 |  |  |  | 2020-02-06 |  | 2020-01-16 | [27 empty] | 2020-01-23 |  |  | 2020-02-22 |  | 2020-01-30 | [16 empty] | 2020-02-20 |  |  | 2020-02-29 | [6 empty] | 2020-03-14 |  |  |  | 2020-03-14 |  |  |  |  | 2020-02-06 |  | 2020-02-16 |  |  | 2020-02-20 |  | 2020-02-23 |  |  | 2020-03-08 |  |  |  | 2020-03-15 |  | 4GT-42-340C-2NPT |  |  | 2020-03-27 |  | 2020-03-05 | [6 empty] | 2020-04-04 | 2020-04-11 | [20 empty] | 2020-05-11 |  |  |  | 2020-05-14 | [8 empty] | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-05-02 |  |  |  | 2020-05-14 |  | 2020-05-17
PH1100759 | 125.7688 | 7.0765 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Aundanao | MIN | PH112317041 | 1407 | 45 | Three Legged Tubular Tower | CO66 | 16.3177 | MIN-1100322 | Level 6 | phase3 | phase3 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-03-05 |  | 2020-03-07 | [13 empty] | 2020-03-12 | [11 empty] | 2020-04-11 | [27 empty] | 2020-04-18 |  |  | 2020-05-18 |  | 2020-04-25 | [16 empty] | 2020-05-16 |  |  | 2020-05-25 | [6 empty] | 2020-06-08 |  |  |  | 2020-06-08 |  |  |  |  | 2020-05-02 |  | 2020-05-12 |  |  | 2020-05-16 |  | 2020-05-19 |  |  | 2020-06-02 |  |  |  | 2020-06-09 |  | 4GT-42-340C-2NPT |  |  | 2020-06-21 |  | 2020-05-30 | [6 empty] | 2020-06-29 | 2020-07-06 | [20 empty] | 2020-08-05 |  |  |  | 2020-08-08 | [8 empty] | 2020-06-14 |  | 2020-06-17 |  |  | 2020-06-29 |  |  |  | 2020-07-02 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-27 |  |  |  | 2020-08-08 |  | 2020-08-11
PH1100760 | 125.6791 | 6.9501 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Dadatan | MIN | PH112317013 | 1421 | 45 | Three Legged Tubular Tower | CO66 | 17.6428 | MIN-1100323 | Level 6 | phase3 | phase3 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-03-08 |  | 2020-03-10 | [13 empty] | 2020-03-15 | [11 empty] | 2020-04-14 | [27 empty] | 2020-04-21 |  |  | 2020-05-21 |  | 2020-04-28 | [16 empty] | 2020-05-19 |  |  | 2020-05-28 | [6 empty] | 2020-06-11 |  |  |  | 2020-06-11 |  |  |  |  | 2020-05-05 |  | 2020-05-15 |  |  | 2020-05-19 |  | 2020-05-22 |  |  | 2020-06-05 |  |  |  | 2020-06-12 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-06-24 |  | 2020-06-02 | [6 empty] | 2020-07-02 | 2020-07-09 | [20 empty] | 2020-08-08 |  |  |  | 2020-08-11 | [8 empty] | 2020-06-17 |  | 2020-06-20 |  |  | 2020-07-02 |  |  |  | 2020-07-05 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-30 |  |  |  | 2020-08-11 |  | 2020-08-14
PH1100761 | 125.7616 | 6.924 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Davao Del Norte | Island Garden City of Samal | Libertad | MIN | PH112317018 | 2382 | 45 | Three Legged Tubular Tower | CO66 | 24.7395 | MIN-1100324 | Level 6 | phase3 | phase3 |  |  | Cluster M03 | Richworld | [7 empty] | 2020-03-11 |  | 2020-03-13 | [13 empty] | 2020-03-18 | [11 empty] | 2020-04-17 | [27 empty] | 2020-04-24 |  |  | 2020-05-24 |  | 2020-05-01 | [16 empty] | 2020-05-22 |  |  | 2020-05-31 | [6 empty] | 2020-06-14 |  |  |  | 2020-06-14 |  |  |  |  | 2020-05-08 |  | 2020-05-18 |  |  | 2020-05-22 |  | 2020-05-25 |  |  | 2020-06-08 |  |  |  | 2020-06-15 |  | 4GT-42-340C-2NPT |  |  | 2020-06-27 |  | 2020-06-05 | [6 empty] | 2020-07-05 | 2020-07-12 | [20 empty] | 2020-08-11 |  |  |  | 2020-08-14 | [8 empty] | 2020-06-20 |  | 2020-06-23 |  |  | 2020-07-05 |  |  |  | 2020-07-08 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-08-02 |  |  |  | 2020-08-14 |  | 2020-08-17
PH1100766 | 126.0342 | 7.3849 | Rural | Greenfield | Greenfield | Y1 | L7 | Davao Region (Region XI) | Compostela Valley | Mabini (Do?a Alicia) | Golden Valley (Maraut) | MIN | PH118204033 | 2720 | 45 | Three Legged Tubular Tower | CO65 | 25.8106 | MIN-1100325 | Level 6 | phase3 | phase3 |  |  | Cluster M07 | EPC | [7 empty] | 2020-04-10 | 2020-02-18 | 2020-04-12 | [13 empty] | 2020-04-17 | [5 empty] | 2020-02-19 |  |  |  | 2020-02-19 |  | 2020-05-17 | [27 empty] | 2020-05-24 |  |  | 2020-06-23 |  | 2020-05-31 | [16 empty] | 2020-06-21 |  |  | 2020-06-30 | [6 empty] | 2020-07-14 |  |  |  | 2020-07-14 |  |  |  |  | 2020-06-07 |  | 2020-06-17 |  |  | 2020-06-21 |  | 2020-06-24 |  |  | 2020-07-08 |  |  |  | 2020-07-15 |  | 4GT-42-340C-2NPT |  |  | 2020-07-27 |  | 2020-07-05 | [6 empty] | 2020-08-04 | 2020-08-11 | [20 empty] | 2020-09-10 |  |  |  | 2020-09-13 | [8 empty] | 2020-07-20 |  | 2020-07-23 |  |  | 2020-08-04 |  |  |  | 2020-08-07 |  |  | 2020-08-14 |  |  |  | 2020-08-17 |  |  | 2020-09-01 |  |  |  | 2020-09-13 |  | 2020-09-16
PH1200001 | 125.0729 | 7.026 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Lanao | MIN | PH124704015 | 8271 | 30 | Three Legged Tubular Tower | CO66 | 61.1992 | MIN-1200001 | Level 5 | phase2_add | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-02-13 | 2020-02-03 | 2020-02-15 | 2020-02-04 |  |  |  | 2020-02-04 | 2020-02-07 |  |  |  | 2020-02-07 |  |  |  | 2020-02-20 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-02-04 |  |  |  | 2020-02-04 | 2020-02-28 | 2020-03-21 | 2020-03-12 |  |  | 2020-03-12 |  | A | Gerlie Bombeo | Brgy. Balindog, Kidapawan City | Cotabato (North Cotabato) | 125.0719 | 7.0276 | Greenfield |  |  | 10 years | P20,000 Exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-28 |  |  | 2020-04-27 |  | 2020-04-04 | [16 empty] | 2020-04-25 | ok |  | 2020-05-04 | [6 empty] | 2020-05-18 |  |  |  | 2020-05-18 |  |  |  |  | 2020-04-11 |  | 2020-04-21 |  |  | 2020-04-25 |  | 2020-04-28 |  |  | 2020-05-12 |  |  |  | 2020-05-19 |  | DGT-30-280C-2NPT（290KPH/C） |  |  | 2020-05-31 |  | 2020-05-09 | [6 empty] | 2020-06-08 | 2020-06-15 | [20 empty] | 2020-07-15 |  |  |  | 2020-07-18 | [8 empty] | 2020-05-24 |  | 2020-05-27 |  |  | 2020-06-08 |  |  |  | 2020-06-11 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-07-06 |  |  |  | 2020-07-18 |  | 2020-07-21
PH1200002 | 125.0729 | 7.0188 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Magsaysay | MIN | PH124704015 | 8271 | 30 | Three Legged Tubular Tower | CO66 | 61.3143 | MIN-1200002 | Level 5 | phase3 | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-02-16 | 2020-01-16 | 2020-02-18 | 2020-01-17 | 2020-01-28 |  |  | 2020-01-17 | 2020-01-18 |  |  |  | 2020-01-18 |  |  |  | 2020-02-23 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-01-17 | 2020-01-28 |  |  | 2020-01-17 | 2020-02-28 | 2020-03-24 | 2020-03-12 |  |  | 2020-03-12 |  | A | Eufrocina Labrado | Brgy. 4-B, Balindog, Kidapawan City | Cotabato (North Cotabato) | 125.0611 | 7.0278 | Greenfield |  |  | 10 years | P20,000 Exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-31 |  |  | 2020-04-30 |  | 2020-04-07 | [16 empty] | 2020-04-28 | ok |  | 2020-05-07 | [6 empty] | 2020-05-21 |  |  |  | 2020-05-21 |  |  |  |  | 2020-04-14 |  | 2020-04-24 |  |  | 2020-04-28 |  | 2020-05-01 |  |  | 2020-05-15 |  |  |  | 2020-05-22 |  | DGT-30-340C-2NPT |  |  | 2020-06-03 |  | 2020-05-12 | [6 empty] | 2020-06-11 | 2020-06-18 | [20 empty] | 2020-07-18 |  |  |  | 2020-07-21 | [8 empty] | 2020-05-27 |  | 2020-05-30 |  |  | 2020-06-11 |  |  |  | 2020-06-14 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-09 |  |  |  | 2020-07-21 |  | 2020-07-24
PH1200003 | 125.0728 | 7.0115 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Magsaysay | MIN | PH124704041 | 3541 | 30 | Three Legged Tubular Tower | CO66 | 61.4398 | MIN-1200003 | Level 5 | phase3 | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-02-19 | 2020-01-16 | 2020-02-21 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-01-18 |  |  |  | 2020-01-18 |  |  |  | 2020-02-26 | 2020-01-18 |  |  |  | 2020-01-18 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-03-06 | 2020-03-27 | 2020-03-07 |  |  | 2020-03-06 | 2020-03-07 | A | Nicanora Ortega | Purok 2, Magsaysay, Kidapawan City | Cotabato (North Cotabato) | 125.0731 | 7.0115 | Greenfield |  |  | 15 years | P15,000 Inclusive of VAT and withholding tax | monthly | 225sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-03 |  |  | 2020-05-03 |  | 2020-04-10 | [16 empty] | 2020-05-01 |  |  | 2020-05-10 | [6 empty] | 2020-05-24 |  |  |  | 2020-05-24 |  |  |  |  | 2020-04-17 |  | 2020-04-27 |  |  | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-18 |  |  |  | 2020-05-25 |  | JGT-30-340C-2NPT |  |  | 2020-06-06 |  | 2020-05-15 | [6 empty] | 2020-06-14 | 2020-06-21 | [20 empty] | 2020-07-21 |  |  |  | 2020-07-24 | [8 empty] | 2020-05-30 |  | 2020-06-02 |  |  | 2020-06-14 |  |  |  | 2020-06-17 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-12 |  |  |  | 2020-07-24 |  | 2020-07-27
PH1200004 | 125.0728 | 7.0043 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Singao | MIN | PH124704038 | 8041 | 30 | Three Legged Tubular Tower | CO66 | 61.5755 | MIN-1200004 | Level 5 | phase3 | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-02-22 | 2020-01-10 | 2020-02-24 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-19 |  |  |  | 2020-01-19 |  |  |  | 2020-02-29 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-03-06 | 2020-03-30 | 2020-03-07 |  |  | 2020-03-06 | 2020-03-07 | A | Elpidio/Susan Namoc | Purok 2, Magsaysay, Kidapawan City | Cotabato (North Cotabato) | 125.0725 | 7.0045 | Greenfield |  |  | 10 years | P15,000 inclusive of VAT and withholding tax | quarterly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | 2020-03-11 | n/a |  |  |  |  | 2020-04-06 |  |  | 2020-05-06 |  | 2020-04-13 | [16 empty] | 2020-05-04 |  |  | 2020-05-13 | [6 empty] | 2020-05-27 |  |  |  | 2020-05-27 |  |  |  |  | 2020-04-20 |  | 2020-04-30 |  |  | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-21 |  |  |  | 2020-05-28 |  | DGT-30-340C-2NPT |  |  | 2020-06-09 |  | 2020-05-18 | [6 empty] | 2020-06-17 | 2020-06-24 | [20 empty] | 2020-07-24 |  |  |  | 2020-07-27 | [8 empty] | 2020-06-02 |  | 2020-06-05 |  |  | 2020-06-17 |  |  |  | 2020-06-20 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-15 |  |  |  | 2020-07-27 |  | 2020-07-30
PH1200005 | 125.0726 | 6.9972 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Singao | MIN | PH124704032 | 31586 | 30 | Three Legged Tubular Tower | CO66 | 61.7308 | MIN-1200005 | Level 5 | phase2_add | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-20 | 2020-01-21 | 2020-01-09 | 2020-01-23 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-01-18 |  |  |  | 2020-01-18 |  |  |  | 2020-01-28 | 2020-01-18 |  |  |  | 2020-01-18 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-03-05 | 2020-02-27 | 2020-03-06 |  |  | 2020-03-05 | 2020-03-06 | A | Gregorio Andolana | Apo Sandawa Phase 3, Upper Singao, Kidapawan City | Cotabato (North Cotabato) | 125.0721 | 6.9973 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-05 | 2020-01-30 |  | 2020-04-04 | 2020-03-03 | 2020-03-12 | [16 empty] | 2020-04-02 |  |  | 2020-04-11 | [6 empty] | 2020-04-25 |  |  |  | 2020-04-25 |  |  |  | Awaiting Lessor ID | 2020-03-19 | 2020-03-04 | 2020-03-29 |  |  | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-19 |  |  |  | 2020-04-26 |  | 3GT-30-280C-2NPT（290KPH/C） |  |  | 2020-05-08 |  | 2020-04-16 | [6 empty] | 2020-05-16 | 2020-05-23 | [20 empty] | 2020-06-22 |  |  |  | 2020-06-25 | [8 empty] | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-16 |  |  |  | 2020-05-19 |  |  | 2020-05-26 |  |  |  | 2020-05-29 |  |  | 2020-06-13 |  |  |  | 2020-06-25 |  | 2020-06-28
PH1200006 | 125.0791 | 7.0224 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Lanao | MIN | PH124704015 | 8271 | 30 | Three Legged Tubular Tower | CO66 | 60.5708 | MIN-1200006 | Level 5 | phase3 | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-20 | 2020-01-22 | 2020-01-18 | 2020-01-24 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-19 |  |  |  | 2020-01-19 |  |  |  | 2020-01-29 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-02-19 | 2020-02-28 | 2020-02-17 |  |  | 2020-02-19 | 2020-02-21 | A | Rosendo E. Amores | Purok 4-B, Brgy. Lanao, Kidapawan City | Cotabato (North Cotabato) | 125.0787 | 7.0221 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-06 | 2020-01-30 |  | 2020-04-05 | 2020-03-03 | 2020-03-13 | [16 empty] | 2020-04-03 | ok |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  | For MOC/NRAF resubmission (different option approved) | 2020-03-20 |  | 2020-03-30 |  |  | 2020-04-03 |  | 2020-04-06 |  |  | 2020-04-20 |  |  |  | 2020-04-27 |  | JGT-30-340C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1200007 | 125.0791 | 7.0151 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Magsaysay | MIN | PH124704041 | 3541 | 30 | Three Legged Tubular Tower | CO66 | 60.6925 | MIN-1200007 | Level 5 | phase2_add | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-02-25 | 2020-01-16 | 2020-02-27 | 2020-01-17 | 2020-01-28 |  |  | 2020-01-17 | 2020-01-18 |  |  |  | 2020-01-18 |  |  |  | 2020-03-03 |  | 2020-02-03 |  |  | 2020-02-03 | 2020-01-17 | 2020-02-01 |  |  | 2020-01-17 | 2020-02-21 | 2020-04-02 | [5 empty] | A | Nikki Marasigan | Purok 2, Brgy. Magsaysay, Kidapawan City | Cotabato (North Cotabato) | 125.0813 | 7.0143 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-09 |  |  | 2020-05-09 |  | 2020-04-16 | [16 empty] | 2020-05-07 |  |  | 2020-05-16 | [6 empty] | 2020-05-30 |  |  |  | 2020-05-30 |  |  |  |  | 2020-04-23 |  | 2020-05-03 |  |  | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-24 |  |  |  | 2020-05-31 |  | DGT-30-280C-2NPT（290KPH/C） |  |  | 2020-06-12 |  | 2020-05-21 | [6 empty] | 2020-06-20 | 2020-06-27 | [20 empty] | 2020-07-27 |  |  |  | 2020-07-30 | [8 empty] | 2020-06-05 |  | 2020-06-08 |  |  | 2020-06-20 |  |  |  | 2020-06-23 |  |  | 2020-06-30 |  |  |  | 2020-07-03 |  |  | 2020-07-18 |  |  |  | 2020-07-30 |  | 2020-08-02
PH1200008 | 125.0791 | 7.0079 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Poblacion | MIN | PH124704041 | 3541 | 30 | Three Legged Tubular Tower | CO66 | 60.8246 | MIN-1200008 | Level 5 | phase2_add | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-20 | 2020-01-23 | 2020-01-18 | 2020-01-25 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-19 |  |  |  | 2020-01-19 |  |  |  | 2020-01-30 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-02-17 | 2020-02-29 | 2020-02-17 |  |  | 2020-02-19 | 2020-02-21 | A | Cromwell Kennedy Rabaya | Purok Pinya, Sinsuat Extension. Pblacion Kidapawan City | Cotabato (North Cotabato) | 125.0782 | 7.0068 | Greenfield |  |  | 10 years | P15,000 inclusive of VAT and withholding tax | quarterly | 225sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-07 | 2020-01-27 |  | 2020-04-06 | 2020-03-03 | 2020-03-14 | [16 empty] | 2020-04-04 |  |  | 2020-04-13 | [6 empty] | 2020-04-27 |  |  |  | 2020-04-27 |  |  |  | Awaiting Lessor ID | 2020-03-21 |  | 2020-03-31 |  |  | 2020-04-04 |  | 2020-04-07 |  |  | 2020-04-21 |  |  |  | 2020-04-28 |  | DGT-30-280C-2NPT（290KPH/C） |  |  | 2020-05-10 |  | 2020-04-18 | [6 empty] | 2020-05-18 | 2020-05-25 | [20 empty] | 2020-06-24 |  |  |  | 2020-06-27 | [8 empty] | 2020-05-03 |  | 2020-05-06 |  |  | 2020-05-18 |  |  |  | 2020-05-21 |  |  | 2020-05-28 |  |  |  | 2020-05-31 |  |  | 2020-06-15 |  |  |  | 2020-06-27 |  | 2020-06-30
PH1200009 | 125.079 | 7.0007 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Singao | MIN | PH124704032 | 31586 | 30 | Three Legged Tubular Tower | CO66 | 60.9669 | MIN-1200009 | Level 5 | phase3 | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-02-28 | 2020-01-18 | 2020-03-01 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-19 |  |  |  | 2020-01-19 |  |  |  | 2020-03-06 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-01-19 |  |  |  | 2020-01-19 | 2020-02-17 | 2020-04-05 | 2020-02-17 |  |  | 2020-02-19 | 2020-02-21 | A | Paterno Malicuban | Purok Guava, Brgy. Singao, Kidapawan City | Cotabato (North Cotabato) | 125.0785 | 7.0001 | Greenfield |  |  | 10 years | P15,000 inclusive of VAT and withholding tax | quarterly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-12 |  |  | 2020-05-12 |  | 2020-04-19 | [16 empty] | 2020-05-10 |  |  | 2020-05-19 | [6 empty] | 2020-06-02 |  |  |  | 2020-06-02 |  |  |  |  | 2020-04-26 |  | 2020-05-06 |  |  | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-27 |  |  |  | 2020-06-03 |  | DGT-30-340C-2NPT |  |  | 2020-06-15 |  | 2020-05-24 | [6 empty] | 2020-06-23 | 2020-06-30 | [20 empty] | 2020-07-30 |  |  |  | 2020-08-02 | [8 empty] | 2020-06-08 |  | 2020-06-11 |  |  | 2020-06-23 |  |  |  | 2020-06-26 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-21 |  |  |  | 2020-08-02 |  | 2020-08-05
PH1200010 | 125.0854 | 7.0259 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Sudapin | MIN | PH124704015 | 8271 | 30 | Three Legged Tubular Tower | CO66 | 59.8288 | MIN-1200010 | Level 5 | phase2_add | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-03-02 | 2020-01-14 | 2020-03-04 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-03-09 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-02-12 | 2020-04-08 | [5 empty] | A | Girlie O. Bombeo | Purok 2, Lanao, Kidapawan City | Cotabato (North Cotabato) | 125.0841 | 7.029 | Greenfield |  |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 225sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-15 |  |  | 2020-05-15 |  | 2020-04-22 | [16 empty] | 2020-05-13 |  |  | 2020-05-22 | [6 empty] | 2020-06-05 |  |  |  | 2020-06-05 |  |  |  |  | 2020-04-29 |  | 2020-05-09 |  |  | 2020-05-13 |  | 2020-05-16 |  |  | 2020-05-30 |  |  |  | 2020-06-06 |  | DGT-30-280C-2NPT（290KPH/C） |  |  | 2020-06-18 |  | 2020-05-27 | [6 empty] | 2020-06-26 | 2020-07-03 | [20 empty] | 2020-08-02 |  |  |  | 2020-08-05 | [8 empty] | 2020-06-11 |  | 2020-06-14 |  |  | 2020-06-26 |  |  |  | 2020-06-29 |  |  | 2020-07-06 |  |  |  | 2020-07-09 |  |  | 2020-07-24 |  |  |  | 2020-08-05 |  | 2020-08-08
PH1200011 | 125.0854 | 7.0187 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Poblacion | MIN | PH124704032 | 31586 | 30 | Three Legged Tubular Tower | CO66 | 59.9466 | MIN-1200011 | Level 5 | phase3 | phase3 | M15 not 630 | DepEd_3352 | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-03-05 | 2020-01-20 | 2020-03-07 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-24 |  |  |  | 2020-01-24 |  |  |  | 2020-03-12 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-02-24 | 2020-04-11 | [5 empty] | A | Euginio Aguinaldo | Overland Terminal Rd., Poblacion, Kidapawan City | Cotabato (North Cotabato) | 125.0853 | 7.0176 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-18 | 2020-02-28 |  | 2020-05-18 | 2020-03-05 | 2020-04-25 | [16 empty] | 2020-05-16 | ok |  | 2020-05-25 | [6 empty] | 2020-06-08 |  |  |  | 2020-06-08 |  |  |  | Awaiting MOC approval | 2020-05-02 |  | 2020-05-12 |  |  | 2020-05-16 | 2020-03-11 | 2020-05-19 | 2020-03-13 | 2020-03-13 | 2020-06-02 |  |  |  | 2020-06-09 |  | DGT-30-340C-2NPT |  |  | 2020-06-21 |  | 2020-05-30 | [6 empty] | 2020-06-29 | 2020-07-06 | [20 empty] | 2020-08-05 |  |  |  | 2020-08-08 | [8 empty] | 2020-06-14 |  | 2020-06-17 |  |  | 2020-06-29 |  |  |  | 2020-07-02 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-27 |  |  |  | 2020-08-08 |  | 2020-08-11
PH1200012 | 125.0854 | 7.0115 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Poblacion | MIN | PH124704032 | 31586 | 30 | Three Legged Tubular Tower | CO66 | 60.0749 | MIN-1200012 | Level 5 | phase3 | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-20 | 2020-01-24 | 2020-01-20 | 2020-01-26 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-24 |  |  |  | 2020-01-24 |  |  |  | 2020-01-31 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-02-28 | 2020-03-01 | 2020-03-03 |  |  | 2020-03-03 | 2020-03-05 | A | Epifania Balundo | M. Cuenco St., Purok Chico, Poblacion, Kidapawan City | Cotabato (North Cotabato) | 125.0858 | 7.0122 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-08 | 2020-01-30 |  | 2020-04-07 |  | 2020-03-15 | [16 empty] | 2020-04-05 |  |  | 2020-04-14 | [6 empty] | 2020-04-28 |  |  |  | 2020-04-28 |  |  |  |  | 2020-03-22 |  | 2020-04-01 |  |  | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-22 |  |  |  | 2020-04-29 |  | DGT-30-340C-2NPT |  |  | 2020-05-11 |  | 2020-04-19 | [6 empty] | 2020-05-19 | 2020-05-26 | [20 empty] | 2020-06-25 |  |  |  | 2020-06-28 | [8 empty] | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-05-29 |  |  |  | 2020-06-01 |  |  | 2020-06-16 |  |  |  | 2020-06-28 |  | 2020-07-01
PH1200013 | 125.0853 | 7.0042 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Poblacion | MIN | PH124704032 | 31586 | 30 | Three Legged Tubular Tower | CO66 | 60.2138 | MIN-1200013 | Level 5 | phase3 | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-03-08 | 2020-01-20 | 2020-03-10 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-07 |  |  |  | 2020-02-07 |  |  |  | 2020-03-15 | 2020-02-07 |  |  |  | 2020-02-07 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-24 | 2020-04-14 | [5 empty] | A | Greg Naco | Overland Terminal Rd., Poblacion, Kidapawan City | Cotabato (North Cotabato) | 125.0838 | 7.0049 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-21 | 2020-02-28 |  | 2020-05-21 | 2020-03-05 | 2020-04-28 | [16 empty] | 2020-05-19 | ok |  | 2020-05-28 | [6 empty] | 2020-06-11 |  |  |  | 2020-06-11 |  |  |  | Awaiting MOC approval | 2020-05-05 |  | 2020-05-15 |  |  | 2020-05-19 | 2020-03-11 | 2020-05-22 |  |  | 2020-06-05 |  |  |  | 2020-06-12 |  | DGT-30-340C-2NPT |  |  | 2020-06-24 |  | 2020-06-02 | [6 empty] | 2020-07-02 | 2020-07-09 | [20 empty] | 2020-08-08 |  |  |  | 2020-08-11 | [8 empty] | 2020-06-17 |  | 2020-06-20 |  |  | 2020-07-02 |  |  |  | 2020-07-05 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-30 |  |  |  | 2020-08-11 |  | 2020-08-14
PH1200014 | 125.0917 | 7.0223 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Sudapin | MIN | PH124704039 | 10385 | 30 | Monopole Tower | CO66 | 59.202 | MIN-1200014 | Level 5 | phase3 | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-20 | 2020-01-25 | 2020-01-21 | 2020-01-27 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-24 |  |  |  | 2020-01-24 |  |  |  | 2020-02-01 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-02-24 | 2020-03-02 | [5 empty] | A | Alfredo Rabor | San Antonio Village, Brgy. Sudapin, Kidapawan City | Cotabato (North Cotabato) | 125.0906 | 7.023 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-09 | 2020-01-30 |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 | 2020-03-06 | 2020-04-02 |  |  | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-23 |  |  |  | 2020-04-30 |  | DGT-30-340C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1200015 | 125.0916 | 7.0151 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Poblacion | MIN | PH124704032 | 31586 | 30 | Three Legged Tubular Tower | CO66 | 59.3266 | MIN-1200015 | Level 5 | phase2_add | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-03-11 | 2020-01-20 | 2020-03-13 | 2020-01-22 |  |  |  | 2020-01-22 | 2020-01-24 |  |  |  | 2020-01-24 |  |  |  | 2020-03-18 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-01-22 |  |  |  | 2020-01-22 |  | 2020-04-17 | [5 empty] | A |  |  |  | 125.0912 | 7.015 | Greenfield | [15 empty] | 2020-04-24 | 2020-02-28 |  | 2020-05-24 | 2020-03-05 | 2020-05-01 | [16 empty] | 2020-05-22 | ok |  | 2020-05-31 | [6 empty] | 2020-06-14 |  |  |  | 2020-06-14 |  |  |  | Awaiting MOC approval | 2020-05-08 |  | 2020-05-18 |  |  | 2020-05-22 | 2020-03-11 | 2020-05-25 | 2020-03-13 | 2020-03-13 | 2020-06-08 |  |  |  | 2020-06-15 |  | DGT-30-280C-2NPT（290KPH/C） |  |  | 2020-06-27 |  | 2020-06-05 | [6 empty] | 2020-07-05 | 2020-07-12 | [20 empty] | 2020-08-11 |  |  |  | 2020-08-14 | [8 empty] | 2020-06-20 |  | 2020-06-23 |  |  | 2020-07-05 |  |  |  | 2020-07-08 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-08-02 |  |  |  | 2020-08-14 |  | 2020-08-17
PH1200016 | 125.0916 | 7.0078 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Poblacion | MIN | PH124704032 | 31586 | 30 | Monopole Tower | CO66 | 59.4617 | MIN-1200016 | Level 5 | phase2_add | phase3 | 630_M15 | DepEd_3537 | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-20 | 2020-01-26 | 2020-01-20 | 2020-01-28 | 2020-01-23 |  |  |  | 2020-01-23 | 2020-01-25 |  |  |  | 2020-01-25 |  |  |  | 2020-02-02 | 2020-01-25 |  |  |  | 2020-01-25 | 2020-01-23 |  |  |  | 2020-01-23 |  | 2020-03-03 | [5 empty] | A |  |  |  | 125.0924 | 7.0081 | Greenfield | [15 empty] | 2020-03-10 | 2020-02-28 |  | 2020-04-09 | 2020-03-05 | 2020-03-17 | [16 empty] | 2020-04-07 | ok |  | 2020-04-16 | [6 empty] | 2020-04-30 |  |  |  | 2020-04-30 |  |  |  | Awaiting MOC approval | 2020-03-24 | 2020-03-09 | 2020-04-03 |  |  | 2020-04-07 | 2020-03-07 | 2020-04-10 | 2020-03-11 | 2020-03-11 | 2020-04-24 |  |  |  | 2020-05-01 |  | DGT-30-280C-2NPT（290KPH/C） |  |  | 2020-05-13 |  | 2020-04-21 | [6 empty] | 2020-05-21 | 2020-05-28 | [20 empty] | 2020-06-27 |  |  |  | 2020-06-30 | [8 empty] | 2020-05-06 |  | 2020-05-09 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-18 |  |  |  | 2020-06-30 |  | 2020-07-03
PH1200017 | 125.098 | 7.0259 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Sudapin | MIN | PH124704039 | 10385 | 30 | Three Legged Tubular Tower | CO66 | 58.459 | MIN-1200017 | Level 5 | phase2_add | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-20 | 2020-01-27 | 2020-01-15 | 2020-01-29 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-17 |  |  |  | 2020-01-17 |  |  |  | 2020-02-03 | 2020-01-17 |  |  |  | 2020-01-17 | [6 empty] | 2020-03-04 | [5 empty] | A |  |  |  | 125.094 | 7.0271 | [16 empty] | 2020-03-11 |  |  | 2020-04-10 |  | 2020-03-18 | [16 empty] | 2020-04-08 |  |  | 2020-04-17 | [6 empty] | 2020-05-01 |  |  |  | 2020-05-01 |  |  |  |  | 2020-03-25 |  | 2020-04-04 |  |  | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-25 |  |  |  | 2020-05-02 |  | DGT-30-280C-2NPT（290KPH/C） |  |  | 2020-05-14 |  | 2020-04-22 | [6 empty] | 2020-05-22 | 2020-05-29 | [20 empty] | 2020-06-28 |  |  |  | 2020-07-01 | [8 empty] | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-22 |  |  |  | 2020-05-25 |  |  | 2020-06-01 |  |  |  | 2020-06-04 |  |  | 2020-06-19 |  |  |  | 2020-07-01 |  | 2020-07-04
PH1200018 | 125.0979 | 7.0114 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Nuangan | MIN | PH124704032 | 31586 | 30 | Three Legged Tubular Tower | CO66 | 58.7109 | MIN-1200018 | Level 5 | phase3 | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-03-14 | 2020-01-31 | 2020-03-16 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-05 |  |  |  | 2020-02-05 |  |  |  | 2020-03-21 | 2020-02-05 |  |  |  | 2020-02-05 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-24 | 2020-04-20 | [5 empty] | A | Francisco Encarnacion | Datu Ingkal st., Poblacion, Kidapawan City | Cotabato (North Cotabato) | 125.0977 | 7.0115 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-27 | 2020-02-28 |  | 2020-05-27 | 2020-03-06 | 2020-05-04 | [16 empty] | 2020-05-25 | ok |  | 2020-06-03 | [6 empty] | 2020-06-17 |  |  |  | 2020-06-17 |  |  |  | Awaiting MOC approval | 2020-05-11 |  | 2020-05-21 |  |  | 2020-05-25 | 2020-03-12 | 2020-05-28 |  |  | 2020-06-11 |  |  |  | 2020-06-18 |  | DGT-30-340C-2NPT |  |  | 2020-06-30 |  | 2020-06-08 | [6 empty] | 2020-07-08 | 2020-07-15 | [20 empty] | 2020-08-14 |  |  |  | 2020-08-17 | [8 empty] | 2020-06-23 |  | 2020-06-26 |  |  | 2020-07-08 |  |  |  | 2020-07-11 |  |  | 2020-07-18 |  |  |  | 2020-07-21 |  |  | 2020-08-05 |  |  |  | 2020-08-17 |  | 2020-08-20
PH1200019 | 125.1042 | 7.0295 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Manongol | MIN | PH124704039 | 10385 | 30 | Three Legged Tubular Tower | CO66 | 57.7175 | MIN-1200019 | Level 5 | phase3 | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-20 | 2020-01-28 | 2020-01-14 | 2020-01-30 | 2020-01-15 | 2020-01-28 |  |  | 2020-01-15 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-02-04 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-01-15 | 2020-01-28 |  |  | 2020-01-15 |  | 2020-03-05 | [5 empty] | A |  |  |  | 125.1051 | 7.0271 | [16 empty] | 2020-03-12 |  |  | 2020-04-11 |  | 2020-03-19 | [16 empty] | 2020-04-09 | ok |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 |  | 2020-04-05 |  |  | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-26 |  |  |  | 2020-05-03 |  | DGT-30-340C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1200021 | 125.1568 | 6.1361 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Isidro (Lagao 2nd) | MIN | PH126303023 | 52832 | 30 | Monopole Tower | CO67 | 1.2296 | MIN-1200020 | Level 4 (220) | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  |  |  | 2019-11-27 | 2019-12-28 | 2019-12-28 | 2019-12-30 | 2019-12-29 |  |  |  | 2019-12-29 | 2019-12-30 |  |  |  | 2019-12-30 |  |  |  | 2020-01-04 | 2019-12-31 |  |  |  | 2019-12-31 | 2019-12-29 |  |  |  | 2019-12-29 | 2020-02-21 | 2020-02-03 | [5 empty] | A | Anarsely D. Cagas | Quizon Compound, San Isidro, General Santos City | South Cotabato | 125.1559 | 6.1377 | Greenfield |  |  | 15 years | P23,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-10 |  |  | 2020-03-11 |  | 2020-02-17 | [16 empty] | 2020-03-09 |  |  | 2020-03-18 | [6 empty] | 2020-04-01 |  |  |  | 2020-04-01 |  |  |  |  | 2020-02-24 |  | 2020-03-05 |  |  | 2020-03-09 |  | 2020-03-12 |  |  | 2020-03-26 |  |  |  | 2020-04-02 |  | DGT-30-340C-2NPT |  |  | 2020-04-14 |  | 2020-03-23 | [6 empty] | 2020-04-22 | 2020-04-29 | [20 empty] | 2020-05-29 |  |  |  | 2020-06-01 | [8 empty] | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-02 |  |  |  | 2020-05-05 |  |  | 2020-05-20 |  |  |  | 2020-06-01 |  | 2020-06-04
PH1200022 | 125.1631 | 6.1469 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Isidro (Lagao 2nd) | MIN | PH126303023 | 52832 | 30 | Monopole Tower | CO67 | 1.664 | MIN-1200021 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-22 | 2019-12-22 | 2019-12-24 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-23 |  |  |  | 2019-12-23 |  |  |  | 2019-12-29 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-23 |  |  |  | 2019-12-23 | 2019-12-27 | 2020-01-28 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | John Villaferte | Purok Mapailubon, San Isidro, General Santos City | South Cotabato | 125.163 | 6.1485 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-04 |  |  | 2020-03-05 |  | 2020-02-11 | [11 empty] | 0906-6493988 |  |  |  |  | 2020-03-03 |  |  | 2020-03-12 | [6 empty] | 2020-03-26 |  |  |  | 2020-03-26 |  |  |  |  | 2020-02-18 |  | 2020-02-28 |  |  | 2020-03-03 |  | 2020-03-06 |  |  | 2020-03-20 |  |  |  | 2020-03-27 |  | DGT-30-340C-2NPT |  |  | 2020-04-08 |  | 2020-03-17 | [6 empty] | 2020-04-16 | 2020-04-23 |  |  |  | 2020-03-02 |  | 2020-03-02 | [14 empty] | 2020-05-23 |  |  |  | 2020-05-26 | [8 empty] | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-16 |  |  |  | 2020-04-19 |  |  | 2020-04-26 |  |  |  | 2020-04-29 |  |  | 2020-05-14 |  |  |  | 2020-05-26 |  | 2020-05-29
PH1200023 | 125.1631 | 6.1397 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Isidro (Lagao 2nd) | MIN | PH126303023 | 52832 | 30 | Monopole Tower | CO67 | 0.92225 | MIN-1200022 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-23 | 2019-12-23 | 2019-12-25 | 2019-12-26 | 2020-02-01 |  |  | 2019-12-26 |  | 2020-02-05 |  |  | 2020-02-05 |  |  |  | 2019-12-30 |  | 2020-02-05 |  |  | 2020-02-05 | 2019-12-26 | 2020-02-01 |  |  | 2019-12-26 | 2020-02-20 | 2020-01-29 | [5 empty] | B | Romeo Salangsang | Nashville, Brgy. San Pedro, General Santos City | South Cotabato | 125.1641 | 6.1392 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-05 |  |  | 2020-03-06 |  | 2020-02-12 | [16 empty] | 2020-03-04 |  |  | 2020-03-13 | [6 empty] | 2020-03-27 |  |  |  | 2020-03-27 |  |  |  |  | 2020-02-19 |  | 2020-02-29 |  |  | 2020-03-04 |  | 2020-03-07 |  |  | 2020-03-21 |  |  |  | 2020-03-28 |  | DGT-30-340C-2NPT |  |  | 2020-04-09 |  | 2020-03-18 | [6 empty] | 2020-04-17 | 2020-04-24 | [20 empty] | 2020-05-24 |  |  |  | 2020-05-27 | [8 empty] | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-04-27 |  |  |  | 2020-04-30 |  |  | 2020-05-15 |  |  |  | 2020-05-27 |  | 2020-05-30
PH1200024 | 125.1631 | 6.1325 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Isidro (Lagao 2nd) | MIN | PH126303034 | 24014 | 30 | Three Legged Tubular Tower | CO67 | 0.47488 | MIN-1200023 | Level 5 | phase3 | phase3 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | EGB |  |  |  | 2019-12-13 | 2019-12-27 | 2019-12-27 | 2019-12-29 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-01-10 |  |  |  | 2020-01-10 |  |  |  | 2020-01-03 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-01-10 |  |  |  | 2020-01-10 | 2020-02-07 | 2020-02-02 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Pedro Jaime Chanco Jr. | Chal Compound Mabuhay Road, City Heights, Gen. Santos City | South Cotabato | 125.1638 | 6.1328 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-09 |  |  | 2020-03-10 |  | 2020-02-16 | [16 empty] | 2020-03-08 |  |  | 2020-03-17 | [6 empty] | 2020-03-31 |  |  |  | 2020-03-31 |  |  |  |  | 2020-02-23 | 2020-03-04 | 2020-03-04 | 2020-03-12 | 2020-03-12 | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-25 |  |  |  | 2020-04-01 |  | DGT-30-340C-2NPT |  |  | 2020-04-13 |  | 2020-03-22 | [6 empty] | 2020-04-21 | 2020-04-28 |  |  |  | 2020-03-02 |  | 2020-03-02 | [14 empty] | 2020-05-28 |  |  |  | 2020-05-31 | [8 empty] | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-01 |  |  |  | 2020-05-04 |  |  | 2020-05-19 |  |  |  | 2020-05-31 |  | 2020-06-03
PH1200025 | 125.163 | 6.1252 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Isidro (Lagao 2nd) | MIN | PH126303034 | 24014 | 30 | Monopole Tower | CO67 | 0.94543 | MIN-1200024 | Level 4 (220) | phase1_220_20% | phase1_630 | old 630 Scope | DepEd_3513 | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  |  |  | 2019-11-27 | 2020-01-25 | 2020-01-04 | 2020-01-27 | 2020-01-05 | 2020-02-01 |  |  | 2020-01-05 | 2020-01-05 |  |  |  | 2020-01-05 |  |  |  | 2020-02-01 |  | 2020-02-03 |  |  | 2020-02-03 | 2020-01-05 | 2020-02-01 |  |  | 2020-01-05 | 2020-02-24 | 2020-03-02 | 2020-02-26 |  |  | 2020-02-26 | 2020-03-02 | B | Lolita D. Palacios | Romana Estate, Bethel Rd., Brgy. City Heights, General Santos City | South Cotabato | 125.1618 | 6.1243 | Greenfield |  |  | 10 years | P17,000 exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-09 |  |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 |  | 2020-04-02 |  |  | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-23 |  |  |  | 2020-04-30 |  | DGT-30-340C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1200026 | 125.1694 | 6.1433 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Isidro (Lagao 2nd) | MIN | PH126303023 | 52832 | 30 | Three Legged Tubular Tower | CO67 | 1.2123 | MIN-1200025 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | EGB |  |  |  | 2019-12-12 | 2019-12-29 | 2019-12-29 | 2019-12-31 | 2019-12-30 |  |  |  | 2019-12-30 | 2019-12-30 |  |  |  | 2019-12-30 |  |  |  | 2020-01-05 | 2019-12-31 |  |  |  | 2019-12-31 | 2019-12-30 |  |  |  | 2019-12-30 | 2020-01-24 | 2020-02-04 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Eduardo Fermalino | Brgy. San Isidro, General Santos City | South Cotabato | 125.169 | 6.1425 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-11 |  |  | 2020-03-12 |  | 2020-02-18 | [16 empty] | 2020-03-10 |  |  | 2020-03-19 | [6 empty] | 2020-04-02 |  |  |  | 2020-04-02 |  |  |  |  | 2020-02-25 | 2020-03-04 | 2020-03-06 |  |  | 2020-03-10 | 2020-02-20 | 2020-03-13 |  |  | 2020-03-27 |  |  |  | 2020-04-03 |  | DGT-30-340C-2NPT |  |  | 2020-04-15 |  | 2020-03-24 | [6 empty] | 2020-04-23 | 2020-04-30 |  |  |  | 2020-03-02 |  | 2020-03-02 | [14 empty] | 2020-05-30 |  |  |  | 2020-06-02 | [8 empty] | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-21 |  |  |  | 2020-06-02 |  | 2020-06-05
PH1200027 | 125.1693 | 6.136 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Isidro (Lagao 2nd) | MIN | PH126303023 | 52832 | 15 | Pole | CO67 | 0.44506 | MIN-1200026 | Level 4 (220) | phase1_220_20% | phase1_630 | old 630 Scope | Philcom_101 | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | EGB |  | KASBEL |  | 2019-11-27 | 2019-12-06 | 2019-12-06 | 2019-12-08 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-13 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-07 | 2019-12-07 |  |  | 2019-12-07 | 2019-12-23 | 2020-01-12 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | A | Gerolen Cabardo | Purok Malakas, San Isidro, General Santos City | South Cotabato | 125.1691 | 6.1364 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-19 |  |  | 2020-02-18 |  | 2020-01-26 | [16 empty] | 2020-02-16 |  |  | 2020-02-25 | [6 empty] | 2020-03-10 |  |  |  | 2020-03-10 |  |  |  |  | 2020-02-02 |  | 2020-02-12 |  |  | 2020-02-16 |  | 2020-02-19 |  |  | 2020-03-04 |  |  |  | 2020-03-11 |  | DGT-30-340C-2NPT |  |  | 2020-03-23 |  | 2020-03-01 | [6 empty] | 2020-03-31 | 2020-04-07 | [20 empty] | 2020-05-07 |  |  |  | 2020-05-10 | [8 empty] | 2020-03-16 |  | 2020-03-19 |  |  | 2020-03-31 |  |  |  | 2020-04-03 |  |  | 2020-04-10 |  |  |  | 2020-04-13 |  |  | 2020-04-28 |  |  |  | 2020-05-10 |  | 2020-05-13
PH1200028 | 125.1694 | 6.1288 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Isidro (Lagao 2nd) | MIN | PH126303034 | 24014 | 30 | Three Legged Tubular Tower | CO67 | 0.47985 | MIN-1200027 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-02-20 | 2020-01-10 | 2020-02-22 | 2020-01-13 | 2020-02-01 |  |  | 2020-01-13 |  | 2020-02-03 |  |  | 2020-02-03 |  |  |  | 2020-02-27 |  | 2020-02-03 |  |  | 2020-02-03 | 2020-01-13 | 2020-02-01 |  |  | 2020-01-13 | 2020-02-20 | 2020-03-28 | [5 empty] | A | Bernadette Serentas/Claudio Canedo | Adam St., Paradise Subd., City Heights, General Santos City | South Cotabato | 125.169 | 6.1291 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-04 |  |  | 2020-05-04 |  | 2020-04-11 | [16 empty] | 2020-05-02 |  |  | 2020-05-11 | [6 empty] | 2020-05-25 |  |  |  | 2020-05-25 |  |  |  |  | 2020-04-18 |  | 2020-04-28 |  |  | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-19 |  |  |  | 2020-05-26 |  | DGT-30-340C-2NPT |  |  | 2020-06-07 |  | 2020-05-16 | [6 empty] | 2020-06-15 | 2020-06-22 | [20 empty] | 2020-07-22 |  |  |  | 2020-07-25 | [8 empty] | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-06-25 |  |  |  | 2020-06-28 |  |  | 2020-07-13 |  |  |  | 2020-07-25 |  | 2020-07-28
PH1200029 | 125.165 | 6.119 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | City Heights | MIN | PH126303034 | 24014 | 30 | Three Legged Tubular Tower | CO67 | 1.5355 | MIN-1200028 | Level 5 | phase3 | phase2_1231 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2019-12-23 | 2019-12-23 | 2019-12-25 | 2019-12-26 |  |  |  | 2019-12-26 | 2020-12-27 |  |  |  | 2020-12-27 |  |  |  | 2019-12-30 | 2019-12-27 |  |  |  | 2019-12-27 | 2019-12-26 |  |  |  | 2019-12-26 | 2020-02-07 | 2020-01-29 | 2020-02-13 |  |  | 2020-02-14 | 2020-02-19 | A | Remina B. Ponce | 34 Durian St., Brgy. North, General Santos City | South Cotabato | 125.1653 | 6.1182 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-05 |  |  | 2020-03-06 |  | 2020-02-12 | [16 empty] | 2020-03-04 |  |  | 2020-03-13 | [6 empty] | 2020-03-27 |  |  |  | 2020-03-27 |  |  |  |  | 2020-02-19 |  | 2020-02-29 |  |  | 2020-03-04 | 2020-02-20 | 2020-03-07 |  |  | 2020-03-21 |  |  |  | 2020-03-28 |  | DGT-30-340C-2NPT |  |  | 2020-04-09 |  | 2020-03-18 | [6 empty] | 2020-04-17 | 2020-04-24 | [20 empty] | 2020-05-24 |  |  |  | 2020-05-27 | [8 empty] | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-04-27 |  |  |  | 2020-04-30 |  |  | 2020-05-15 |  |  |  | 2020-05-27 |  | 2020-05-30
PH1200030 | 125.1692 | 6.1144 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | City Heights | MIN | PH126303035 | 8056 | 30 | Three Legged Tubular Tower | CO67 | 2.0355 | MIN-1200029 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-02-23 | 2020-01-17 | 2020-02-25 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-21 |  |  |  | 2020-01-21 |  |  |  | 2020-03-01 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-02-20 | 2020-03-31 | [5 empty] | A | Holy Trinity College/ Atty. Josemar Albano | 5F, Macario & Catalina Hall, Holy Trinity College, General Santos City | South Cotabato | 125.1692 | 6.1131 | Rooftop |  | 12m | 10 years | P25,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-17 | n/a |  |  |  | n/a | 2020-04-07 |  |  | 2020-05-07 |  | 2020-04-14 | [16 empty] | 2020-05-05 |  |  | 2020-05-14 | [6 empty] | 2020-05-28 |  |  |  | 2020-05-28 |  |  |  |  | 2020-04-21 |  | 2020-05-01 |  |  | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-22 |  |  |  | 2020-05-29 |  | ZCG-12-340D-1NPT |  |  | 2020-06-10 |  | 2020-05-19 | [6 empty] | 2020-06-18 | 2020-06-25 | [20 empty] | 2020-07-25 |  |  |  | 2020-07-28 | [8 empty] | 2020-06-03 |  | 2020-06-06 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-06-28 |  |  |  | 2020-07-01 |  |  | 2020-07-16 |  |  |  | 2020-07-28 |  | 2020-07-31
PH1200032 | 125.1756 | 6.1324 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Isidro (Lagao 2nd) | MIN | PH126303034 | 24014 | 30 | Three Legged Tubular Tower | CO67 | 0.90907 | MIN-1200030 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-23 | 2019-12-23 | 2019-12-25 | 2019-12-26 |  |  |  | 2019-12-26 | 2019-12-27 |  |  |  | 2019-12-27 |  |  |  | 2019-12-30 | [5 empty] | 2019-12-26 |  |  |  | 2019-12-26 |  | 2020-01-29 | [27 empty] | 2020-02-05 |  |  | 2020-03-06 |  | 2020-02-12 | [16 empty] | 2020-03-04 |  |  | 2020-03-13 | [6 empty] | 2020-03-27 |  |  |  | 2020-03-27 |  |  |  |  | 2020-02-19 |  | 2020-02-29 |  |  | 2020-03-04 |  | 2020-03-07 |  |  | 2020-03-21 |  |  |  | 2020-03-28 |  | JGT-30-340C-2NPT |  |  | 2020-04-09 |  | 2020-03-18 | [6 empty] | 2020-04-17 | 2020-04-24 | [20 empty] | 2020-05-24 |  |  |  | 2020-05-27 | [8 empty] | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-04-27 |  |  |  | 2020-04-30 |  |  | 2020-05-15 |  |  |  | 2020-05-27 |  | 2020-05-30
PH1200033 | 125.1755 | 6.1252 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Lagao (1st & 3rd) | MIN | PH126303034 | 24014 | 30 | Monopole Tower | CO67 | 1.2226 | MIN-1200031 | Level 5 | phase3 | phase3 | PO Issued not 630 | DepEd_3497 | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-23 | 2019-12-23 | 2019-12-25 | 2019-12-26 |  |  |  | 2019-12-26 | 2019-12-27 |  |  |  | 2019-12-27 |  |  |  | 2019-12-30 | 2019-12-28 |  |  |  | 2019-12-28 | 2019-12-26 |  |  |  | 2019-12-26 | 2020-03-06 | 2020-01-29 | 2020-03-10 |  |  | 2020-03-10 | 2020-03-10 | A | Nilo Quimsing | Block 6, Brgy. City Heights, General Santos City | South Cotabato | 125.1763 | 6.1257 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-05 |  |  | 2020-03-06 |  | 2020-02-12 | [16 empty] | 2020-03-04 |  |  | 2020-03-13 | [6 empty] | 2020-03-27 |  |  |  | 2020-03-27 |  |  |  |  | 2020-02-19 |  | 2020-02-29 |  |  | 2020-03-04 |  | 2020-03-07 |  |  | 2020-03-21 |  |  |  | 2020-03-28 |  | DGT-30-340C-2NPT |  |  | 2020-04-09 |  | 2020-03-18 | [6 empty] | 2020-04-17 | 2020-04-24 | [20 empty] | 2020-05-24 |  |  |  | 2020-05-27 | [8 empty] | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-17 |  |  |  | 2020-04-20 |  |  | 2020-04-27 |  |  |  | 2020-04-30 |  |  | 2020-05-15 |  |  |  | 2020-05-27 |  | 2020-05-30
PH1200034 | 125.1755 | 6.1179 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | City Heights | MIN | PH126303007 | 4746 | 30 | Three Legged Tubular Tower | CO67 | 1.8591 | MIN-1200032 | Level 4 (220) | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  |  |  | 2019-11-27 | 2020-01-25 | 2020-01-10 | 2020-01-27 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-01-12 |  |  |  | 2020-01-12 |  |  |  | 2020-02-01 | 2020-01-12 |  |  |  | 2020-01-12 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-03-06 | 2020-03-02 | 2020-03-10 |  |  | 2020-03-10 | 2020-03-10 | A | Annalou Asperga | JP Laurel East, General Santos City | South Cotabato | 125.1748 | 6.1181 | Rooftop |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 250sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-09 |  |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 |  | 2020-04-02 |  |  | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-23 |  |  |  | 2020-04-30 |  | ZCG-12-340D-1NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1200035 | 125.1755 | 6.1107 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | City Heights | MIN | PH126303036 | 6199 | 30 | Three Legged Tubular Tower | CO67 | 2.5907 | MIN-1200033 | Level 4 (220) | phase1_220_20% | phase1_630 | old 630 Scope | DepEd_3498 | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | EGB |  |  |  | 2019-11-27 | 2020-01-26 | 2020-01-16 | 2020-01-28 |  | 2020-01-17 |  |  | 2020-01-17 |  | 2020-01-18 |  |  | 2020-01-18 |  |  |  | 2020-02-02 |  | 2020-01-18 |  |  | 2020-01-18 | 2020-01-16 | 2020-01-17 |  |  | 2020-01-16 | 2020-02-24 | 2020-03-03 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | A | Helen Ly | QUIRINO AVENUE, GENERAL SANTOS CITY | South Cotabato | 125.1762 | 6.1101 | Rooftop |  | 12m | 10 years | P17,000 inclusive of VAT and withholding tax | monthly | 25sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-10 |  |  | 2020-04-09 |  | 2020-03-17 | [16 empty] | 2020-04-07 |  |  | 2020-04-16 | [6 empty] | 2020-04-30 |  |  |  | 2020-04-30 |  |  |  |  | 2020-03-24 |  | 2020-04-03 |  |  | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-24 |  |  |  | 2020-05-01 |  | ZCG-12-340D-1NPT |  |  | 2020-05-13 |  | 2020-04-21 | [6 empty] | 2020-05-21 | 2020-05-28 | [20 empty] | 2020-06-27 |  |  |  | 2020-06-30 | [8 empty] | 2020-05-06 |  | 2020-05-09 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-18 |  |  |  | 2020-06-30 |  | 2020-07-03
PH1200036 | 125.1821 | 6.1361 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Isidro (Lagao 2nd) | MIN | PH126303023 | 52832 | 30 | Three Legged Tubular Tower | CO67 | 1.6791 | MIN-1200034 | Level 5 | phase3 | phase3 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-27 | 2019-12-27 | 2019-12-29 | 2019-12-28 | 2020-02-01 |  |  | 2019-12-28 | 2019-12-29 |  |  |  | 2019-12-29 |  |  |  | 2020-01-03 | [5 empty] | 2019-12-28 | 2020-02-01 |  |  | 2019-12-28 |  | 2020-02-02 | [27 empty] | 2020-02-09 |  |  | 2020-03-10 |  | 2020-02-16 | [16 empty] | 2020-03-08 |  |  | 2020-03-17 | [6 empty] | 2020-03-31 |  |  |  | 2020-03-31 |  |  |  |  | 2020-02-23 |  | 2020-03-04 |  |  | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-25 |  |  |  | 2020-04-01 |  | DGT-30-340C-2NPT |  |  | 2020-04-13 |  | 2020-03-22 | [6 empty] | 2020-04-21 | 2020-04-28 | [20 empty] | 2020-05-28 |  |  |  | 2020-05-31 | [8 empty] | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-01 |  |  |  | 2020-05-04 |  |  | 2020-05-19 |  |  |  | 2020-05-31 |  | 2020-06-03
PH1200038 | 125.1818 | 6.1215 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Lagao (1st & 3rd) | MIN | PH126303011 | 50789 | 30 | Monopole Tower | CO67 | 2.0125 | MIN-1200035 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-02-26 | 2020-01-18 | 2020-02-28 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-21 |  |  |  | 2020-01-21 |  |  |  | 2020-03-04 | [5 empty] | 2020-01-20 |  |  |  | 2020-01-20 |  | 2020-04-03 | [27 empty] | 2020-04-10 |  |  | 2020-05-10 |  | 2020-04-17 | [16 empty] | 2020-05-08 |  |  | 2020-05-17 | [6 empty] | 2020-05-31 |  |  |  | 2020-05-31 |  |  |  |  | 2020-04-24 |  | 2020-05-04 |  |  | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-25 |  |  |  | 2020-06-01 |  | DGT-30-340C-2NPT |  |  | 2020-06-13 |  | 2020-05-22 | [6 empty] | 2020-06-21 | 2020-06-28 | [20 empty] | 2020-07-28 |  |  |  | 2020-07-31 | [8 empty] | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-01 |  |  |  | 2020-07-04 |  |  | 2020-07-19 |  |  |  | 2020-07-31 |  | 2020-08-03
PH1200039 | 125.1817 | 6.1143 | Urban | Rooftop | Rooftop | Y1 | L7+L21+L26 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Lagao (1st & 3rd) | MIN | PH126303011 | 50789 | 12 | Pole | CO67 | 2.5804 | MIN-1200036 | Level 4 (220) | phase1_220_20% | phase2_1231 | PO Issued not 630 | Philcom_102 | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2020-02-29 | 2020-01-10 | 2020-03-02 |  | 2020-01-13 | 2020-02-01 |  | 2020-01-13 |  |  | 2020-02-03 |  | 2020-02-03 |  |  |  | 2020-03-07 |  |  | 2020-02-03 |  | 2020-02-03 | 2020-01-29 | 2020-01-13 | 2020-02-01 |  | 2020-01-13 | 2020-02-20 | 2020-04-06 | 2020-02-26 |  |  | 2020-02-26 | 2020-03-02 | C | Edwin Yap | J CATOLICO SR AVE. , GENERAL SANTOS CITY | South Cotabato | 125.1822 | 6.1134 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 250sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-13 |  |  | 2020-05-13 |  | 2020-04-20 | [16 empty] | 2020-05-11 |  |  | 2020-05-20 | [6 empty] | 2020-06-03 |  |  |  | 2020-06-03 |  |  |  |  | 2020-04-27 |  | 2020-05-07 |  |  | 2020-05-11 |  | 2020-05-14 |  |  | 2020-05-28 |  |  |  | 2020-06-04 |  | DGT-30-340C-2NPT |  |  | 2020-06-16 |  | 2020-05-25 | [6 empty] | 2020-06-24 | 2020-07-01 | [20 empty] | 2020-07-31 |  |  |  | 2020-08-03 | [8 empty] | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-04 |  |  |  | 2020-07-07 |  |  | 2020-07-22 |  |  |  | 2020-08-03 |  | 2020-08-06
PH1200040 | 125.1881 | 6.1324 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Lagao (1st & 3rd) | MIN | PH126303011 | 50789 | 30 | Monopole Tower | CO67 | 2.2925 | MIN-1200037 | Level 4 (220) | phase1_220_20% | phase1_630 | old 630 Scope |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | EGB |  | KASBEL |  | 2019-11-27 | 2019-11-28 | 2019-11-28 | 2019-11-30 | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2019-12-04 | 2019-12-05 | 2019-12-05 | 2019-12-05 |  | 2019-12-05 |  |  |  | 2019-12-05 | 2019-12-18 |  |  |  | 2019-12-18 | 2019-11-28 | 2019-11-28 | 2019-11-28 |  | 2019-11-28 | 2020-03-06 | 2020-01-04 | 2019-12-27 |  |  | 2020-03-06 |  | A | Renato Bayani | NLSA Road, Lagao, General Santos City | South Cotabato | 125.1881 | 6.1324 | Greenfield |  |  | 15 years | P20,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-11 |  |  | 2020-02-10 |  | 2020-01-18 | [16 empty] | 2020-02-08 |  |  | 2020-02-17 | [6 empty] | 2020-03-02 |  |  |  | 2020-03-02 |  |  |  |  | 2020-01-25 | 2020-03-02 | 2020-02-04 |  |  | 2020-02-08 |  | 2020-02-11 |  |  | 2020-02-25 |  |  |  | 2020-03-03 |  | DGT-30-340C-2NPT |  |  | 2020-03-15 |  | 2020-02-22 | [6 empty] | 2020-03-23 | 2020-03-30 |  |  |  | 2020-03-02 |  | 2020-03-02 | [14 empty] | 2020-04-29 |  |  |  | 2020-05-02 | [8 empty] | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-23 |  |  |  | 2020-03-26 |  |  | 2020-04-02 |  |  |  | 2020-04-05 |  |  | 2020-04-20 |  |  |  | 2020-05-02 |  | 2020-05-05
PH1200041 | 125.1881 | 6.1251 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Lagao (1st & 3rd) | MIN | PH126303011 | 50789 | 30 | Three Legged Tubular Tower | CO67 | 2.434 | MIN-1200038 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-03-03 | 2020-01-03 | 2020-03-05 | 2020-01-04 | 2020-01-13 | 2020-02-01 |  | 2020-01-04 | 2020-01-04 |  |  |  | 2020-01-04 |  |  |  | 2020-03-10 |  |  | 2020-02-03 |  | 2020-02-03 | 2020-01-04 | 2020-01-13 | 2020-02-01 |  | 2020-01-04 | 2020-02-24 | 2020-04-09 | [5 empty] | C | Prodencio Jano | Saint Joseph street Lagao, General Santos City | South Cotabato | 125.188 | 6.127 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-04-16 |  |  | 2020-05-16 |  | 2020-04-23 | [16 empty] | 2020-05-14 |  |  | 2020-05-23 | [6 empty] | 2020-06-06 |  |  |  | 2020-06-06 |  |  |  |  | 2020-04-30 |  | 2020-05-10 |  |  | 2020-05-14 |  | 2020-05-17 |  |  | 2020-05-31 |  |  |  | 2020-06-07 |  | DGT-30-340C-2NPT |  |  | 2020-06-19 |  | 2020-05-28 | [6 empty] | 2020-06-27 | 2020-07-04 | [20 empty] | 2020-08-03 |  |  |  | 2020-08-06 | [8 empty] | 2020-06-12 |  | 2020-06-15 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-07 |  |  |  | 2020-07-10 |  |  | 2020-07-25 |  |  |  | 2020-08-06 |  | 2020-08-09
PH1200042 | 125.188 | 6.1179 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Lagao (1st & 3rd) | MIN | PH126303011 | 50789 | 30 | Monopole Tower | CO67 | 2.8082 | MIN-1200039 | Level 4 (220) | phase1_220_20% | phase1_630 | old 630 Scope | Robinsons_17 | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  |  |  | 2019-11-27 | 2020-01-28 | 2020-01-09 | 2020-01-30 | 2020-01-22 |  |  |  | 2020-01-22 | [8 empty] | 2020-02-04 | [5 empty] | 2020-01-22 |  |  |  | 2020-01-22 |  | 2020-03-05 | [27 empty] | 2020-03-12 |  |  | 2020-04-11 |  | 2020-03-19 | [16 empty] | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 |  | 2020-04-05 |  |  | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-26 |  |  |  | 2020-05-03 |  | DGT-30-340C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1200043 | 125.188 | 6.1107 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Lagao (1st & 3rd) | MIN | PH126303005 | 31363 | 30 | Monopole Tower | CO67 | 3.3379 | MIN-1200040 | Level 5 | phase3 | phase3 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2020-03-06 | 2020-01-10 | 2020-03-08 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-01-12 |  |  |  | 2020-01-12 |  |  |  | 2020-03-13 | 2020-01-12 |  |  |  | 2020-01-12 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-03-06 | 2020-04-12 | 2020-01-23 |  |  | 2020-03-06 |  | A | Mary Joy G. Cabrera/ Michael Q. Chiongbian | Honorio Arriola St., Bula-Bugao Rd., General Santos City | South Cotabato | 125.1897 | 6.111 | Greenfield |  |  | 15 years | P12,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-04-19 |  |  | 2020-05-19 |  | 2020-04-26 | [16 empty] | 2020-05-17 |  |  | 2020-05-26 | [6 empty] | 2020-06-09 |  |  |  | 2020-06-09 |  |  |  |  | 2020-05-03 |  | 2020-05-13 |  |  | 2020-05-17 |  | 2020-05-20 |  |  | 2020-06-03 |  |  |  | 2020-06-10 |  | DGT-30-340C-2NPT |  |  | 2020-06-22 |  | 2020-05-31 | [6 empty] | 2020-06-30 | 2020-07-07 | [20 empty] | 2020-08-06 |  |  |  | 2020-08-09 | [8 empty] | 2020-06-15 |  | 2020-06-18 |  |  | 2020-06-30 |  |  |  | 2020-07-03 |  |  | 2020-07-10 |  |  |  | 2020-07-13 |  |  | 2020-07-28 |  |  |  | 2020-08-09 |  | 2020-08-12
PH1200047 | 125.2006 | 6.1251 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Lagao (1st & 3rd) | MIN | PH126303011 | 50789 | 30 | Monopole Tower | CO67 | 3.766 | MIN-1200041 | Level 5 | phase3 | phase3 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-13 | 2019-12-27 | 2019-12-27 | 2019-12-29 | 2019-12-28 | 2020-02-01 |  |  | 2019-12-28 |  | 2020-02-03 |  |  | 2020-02-03 |  |  |  | 2020-01-03 |  | 2020-02-03 |  |  | 2020-02-03 | 2019-12-28 | 2020-02-01 |  |  | 2019-12-28 | 2020-02-21 | 2020-02-02 | [5 empty] | B | Marlene Alcasid | Diaz Subd., Lagao, General Santos City | South Cotabato | 125.2011 | 6.1235 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-09 |  |  | 2020-03-10 |  | 2020-02-16 | [16 empty] | 2020-03-08 |  |  | 2020-03-17 | [6 empty] | 2020-03-31 |  |  |  | 2020-03-31 |  |  |  |  | 2020-02-23 |  | 2020-03-04 |  |  | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-25 |  |  |  | 2020-04-01 |  | DGT-30-340C-2NPT |  |  | 2020-04-13 |  | 2020-03-22 | [6 empty] | 2020-04-21 | 2020-04-28 | [20 empty] | 2020-05-28 |  |  |  | 2020-05-31 | [8 empty] | 2020-04-06 |  | 2020-04-09 |  |  | 2020-04-21 |  |  |  | 2020-04-24 |  |  | 2020-05-01 |  |  |  | 2020-05-04 |  |  | 2020-05-19 |  |  |  | 2020-05-31 |  | 2020-06-03
PH1200086 | 124.668 | 6.6757 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Tacurong City | Upper Katungal | MIN | PH126511010 | 11711 | 40 | Three Legged Tubular Tower | CO68 | 76.3861 | MIN-1200042 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-17 |  | 2020-03-19 | [13 empty] | 2020-03-24 | [11 empty] | 2020-04-23 | [27 empty] | 2020-04-30 |  |  | 2020-05-30 |  | 2020-05-07 | [16 empty] | 2020-05-28 |  |  | 2020-06-06 | [6 empty] | 2020-06-20 |  |  |  | 2020-06-20 |  |  |  |  | 2020-05-14 |  | 2020-05-24 |  |  | 2020-05-28 |  | 2020-05-31 |  |  | 2020-06-14 |  |  |  | 2020-06-21 |  | JGT-36-280C-2NPT |  |  | 2020-07-03 |  | 2020-06-11 | [6 empty] | 2020-07-11 | 2020-07-18 | [20 empty] | 2020-08-17 |  |  |  | 2020-08-20 | [8 empty] | 2020-06-26 |  | 2020-06-29 |  |  | 2020-07-11 |  |  |  | 2020-07-14 |  |  | 2020-07-21 |  |  |  | 2020-07-24 |  |  | 2020-08-08 |  |  |  | 2020-08-20 |  | 2020-08-23
PH1200087 | 124.6778 | 6.6925 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Tacurong City | Poblacion | MIN | PH126511013 | 16199 | 40 | Monopole Tower | CO68 | 75.5786 | MIN-1200043 | Level 6 | phase2_add | phase2_1231 |  | DICT_40 | Cluster M17 | Enovell | [7 empty] | 2020-03-20 |  | 2020-03-22 | [13 empty] | 2020-03-27 | [11 empty] | 2020-04-26 | [27 empty] | 2020-05-03 |  |  | 2020-06-02 |  | 2020-05-10 | [16 empty] | 2020-05-31 |  |  | 2020-06-09 | [6 empty] | 2020-06-23 |  |  |  | 2020-06-23 |  |  |  |  | 2020-05-17 |  | 2020-05-27 |  |  | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-17 |  |  |  | 2020-06-24 |  | JGT-36-280C-2NPT |  |  | 2020-07-06 |  | 2020-06-14 | [6 empty] | 2020-07-14 | 2020-07-21 | [20 empty] | 2020-08-20 |  |  |  | 2020-08-23 | [8 empty] | 2020-06-29 |  | 2020-07-02 |  |  | 2020-07-14 |  |  |  | 2020-07-17 |  |  | 2020-07-24 |  |  |  | 2020-07-27 |  |  | 2020-08-11 |  |  |  | 2020-08-23 |  | 2020-08-26
PH1200093 | 124.7069 | 6.698 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Tacurong City | San Emmanuel | MIN | PH126510026 | 1099 | 40 | Three Legged Tubular Tower | CO68 | 77.1695 | MIN-1200044 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-23 |  | 2020-03-25 | [13 empty] | 2020-03-30 | [11 empty] | 2020-04-29 | [27 empty] | 2020-05-06 |  |  | 2020-06-05 |  | 2020-05-13 | [16 empty] | 2020-06-03 |  |  | 2020-06-12 | [6 empty] | 2020-06-26 |  |  |  | 2020-06-26 |  |  |  |  | 2020-05-20 |  | 2020-05-30 |  |  | 2020-06-03 |  | 2020-06-06 |  |  | 2020-06-20 |  |  |  | 2020-06-27 |  | JGT-36-280C-2NPT |  |  | 2020-07-09 |  | 2020-06-17 | [6 empty] | 2020-07-17 | 2020-07-24 | [20 empty] | 2020-08-23 |  |  |  | 2020-08-26 | [8 empty] | 2020-07-02 |  | 2020-07-05 |  |  | 2020-07-17 |  |  |  | 2020-07-20 |  |  | 2020-07-27 |  |  |  | 2020-07-30 |  |  | 2020-08-14 |  |  |  | 2020-08-26 |  | 2020-08-29
PH1200096 | 124.7371 | 6.7008 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Pres. E. Quirino | Poblacion (Sambulawan) | MIN | PH126510016 | 6502 | 40 | Angular Steel Tower | CO67 | 79.0756 | MIN-1200045 | Level 6 | phase2_add | phase2_1231 |  | DepEd_3481 | Cluster M17 | Enovell | [7 empty] | 2020-03-26 |  | 2020-03-28 | [13 empty] | 2020-04-02 | [11 empty] | 2020-05-02 | [27 empty] | 2020-05-09 |  |  | 2020-06-08 |  | 2020-05-16 | [16 empty] | 2020-06-06 |  |  | 2020-06-15 | [6 empty] | 2020-06-29 |  |  |  | 2020-06-29 |  |  |  |  | 2020-05-23 |  | 2020-06-02 |  |  | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-23 |  |  |  | 2020-06-30 |  | JGT-36-280C-2NPT |  |  | 2020-07-12 |  | 2020-06-20 | [6 empty] | 2020-07-20 | 2020-07-27 | [20 empty] | 2020-08-26 |  |  |  | 2020-08-29 | [8 empty] | 2020-07-05 |  | 2020-07-08 |  |  | 2020-07-20 |  |  |  | 2020-07-23 |  |  | 2020-07-30 |  |  |  | 2020-08-02 |  |  | 2020-08-17 |  |  |  | 2020-08-29 |  | 2020-09-01
PH1200099 | 124.8325 | 6.5013 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | Koronadal City | Caloocan | MIN | PH126306019 | 8833 | 40 | Three Legged Tubular Tower | CO67 | 55.2376 | MIN-1200046 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-02-28 |  | 2020-03-01 | [13 empty] | 2020-03-06 | [11 empty] | 2020-04-05 | [27 empty] | 2020-04-12 |  |  | 2020-05-12 |  | 2020-04-19 | [16 empty] | 2020-05-10 |  |  | 2020-05-19 | [6 empty] | 2020-06-02 |  |  |  | 2020-06-02 |  |  |  |  | 2020-04-26 |  | 2020-05-06 |  |  | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-27 |  |  |  | 2020-06-03 |  | JGT-36-340C-2NPT |  |  | 2020-06-15 |  | 2020-05-24 | [6 empty] | 2020-06-23 | 2020-06-30 | [20 empty] | 2020-07-30 |  |  |  | 2020-08-02 | [8 empty] | 2020-06-08 |  | 2020-06-11 |  |  | 2020-06-23 |  |  |  | 2020-06-26 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-21 |  |  |  | 2020-08-02 |  | 2020-08-05
PH1200102 | 124.8421 | 6.4845 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | Koronadal City | Zone I | MIN | PH126306024 | 13534 | 40 | Three Legged Tubular Tower | CO67 | 53.1346 | MIN-1200047 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-02 |  | 2020-03-04 | [13 empty] | 2020-03-09 | [11 empty] | 2020-04-08 | [27 empty] | 2020-04-15 |  |  | 2020-05-15 |  | 2020-04-22 | [16 empty] | 2020-05-13 |  |  | 2020-05-22 | [6 empty] | 2020-06-05 |  |  |  | 2020-06-05 |  |  |  |  | 2020-04-29 |  | 2020-05-09 |  |  | 2020-05-13 |  | 2020-05-16 |  |  | 2020-05-30 |  |  |  | 2020-06-06 |  | JGT-36-340C-2NPT |  |  | 2020-06-18 |  | 2020-05-27 | [6 empty] | 2020-06-26 | 2020-07-03 | [20 empty] | 2020-08-02 |  |  |  | 2020-08-05 | [8 empty] | 2020-06-11 |  | 2020-06-14 |  |  | 2020-06-26 |  |  |  | 2020-06-29 |  |  | 2020-07-06 |  |  |  | 2020-07-09 |  |  | 2020-07-24 |  |  |  | 2020-08-05 |  | 2020-08-08
PH1200105 | 124.8519 | 6.5013 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | Koronadal City | Caloocan | MIN | PH126306008 | 24612 | 40 | Monopole Tower | CO67 | 53.8175 | MIN-1200048 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-05 | 2020-01-06 | 2020-03-07 | 2020-01-07 |  |  |  | 2020-01-07 | 2020-01-08 |  |  |  | 2020-01-08 |  |  |  | 2020-03-12 | [5 empty] | 2020-01-07 |  |  |  | 2020-01-07 |  | 2020-04-11 | [27 empty] | 2020-04-18 |  |  | 2020-05-18 |  | 2020-04-25 | [16 empty] | 2020-05-16 |  |  | 2020-05-25 | [6 empty] | 2020-06-08 |  |  |  | 2020-06-08 |  |  |  |  | 2020-05-02 |  | 2020-05-12 |  |  | 2020-05-16 |  | 2020-05-19 |  |  | 2020-06-02 |  |  |  | 2020-06-09 |  | JGT-36-340C-2NPT |  |  | 2020-06-21 |  | 2020-05-30 | [6 empty] | 2020-06-29 | 2020-07-06 | [20 empty] | 2020-08-05 |  |  |  | 2020-08-08 | [8 empty] | 2020-06-14 |  | 2020-06-17 |  |  | 2020-06-29 |  |  |  | 2020-07-02 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-27 |  |  |  | 2020-08-08 |  | 2020-08-11
PH1200109 | 124.8712 | 6.4788 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | Koronadal City | Santo Nino (Bo. 2) | MIN | PH126306006 | 4268 | 15 | Pole | CO67 | 50.5284 | MIN-1200049 | Level 6 | phase2_add | phase2_1231 | OA_1231 |  | Cluster M17 | Enovell | [6 empty] | 2020-02-12 | 2020-03-08 |  | 2020-03-10 | [13 empty] | 2020-03-15 | [11 empty] | 2020-04-14 | [27 empty] | 2020-04-21 |  |  | 2020-05-21 |  | 2020-04-28 | [16 empty] | 2020-05-19 |  |  | 2020-05-28 | [6 empty] | 2020-06-11 |  |  |  | 2020-06-11 |  |  |  |  | 2020-05-05 |  | 2020-05-15 |  |  | 2020-05-19 |  | 2020-05-22 |  |  | 2020-06-05 |  |  |  | 2020-06-12 |  | JGT-30-340C-2NPT |  |  | 2020-06-24 |  | 2020-06-02 | [6 empty] | 2020-07-02 | 2020-07-09 | [20 empty] | 2020-08-08 |  |  |  | 2020-08-11 | [8 empty] | 2020-06-17 |  | 2020-06-20 |  |  | 2020-07-02 |  |  |  | 2020-07-05 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-30 |  |  |  | 2020-08-11 |  | 2020-08-14
PH1200112 | 125.1013 | 6.058 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Fatima | MIN | PH126303038 | 66460 | 3 | Camouflage Square Column | CO67 | 11.0493 | MIN-1200050 | Level 5 | phase2_add | phase1_630 | old 630 Scope |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  |  |  | 2019-11-27 | 2020-01-30 | 2020-01-18 | 2020-02-01 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-01-27 |  |  |  | 2020-01-27 |  |  |  | 2020-02-06 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-02-25 | 2020-03-07 | [5 empty] | A | Ebrahim Salem | Purok 13-a, Fatima, General Santos City | South Cotabato | 125.1063 | 6.0718 | Greenfield |  |  | 10 years | P12,000 exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-14 |  |  | 2020-04-13 |  | 2020-03-21 | [16 empty] | 2020-04-11 |  |  | 2020-04-20 | [6 empty] | 2020-05-04 |  |  |  | 2020-05-04 |  |  |  |  | 2020-03-28 |  | 2020-04-07 |  |  | 2020-04-11 |  | 2020-04-14 |  |  | 2020-04-28 |  |  |  | 2020-05-05 |  | JGT-30-340C-2NPT |  |  | 2020-05-17 |  | 2020-04-25 | [6 empty] | 2020-05-25 | 2020-06-01 | [20 empty] | 2020-07-01 |  |  |  | 2020-07-04 | [8 empty] | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-04 |  |  |  | 2020-06-07 |  |  | 2020-06-22 |  |  |  | 2020-07-04 |  | 2020-07-07
PH1200113 | 125.1118 | 6.1183 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Apopong | MIN | PH126303029 | 46384 | 40 | Three Legged Tubular Tower | CO67 | 6.3378 | MIN-1200051 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2020-03-09 | 2020-01-14 | 2020-03-11 | 2020-01-15 |  |  |  | 2020-01-15 | [8 empty] | 2020-03-16 | [11 empty] | 2020-04-15 | [27 empty] | 2020-04-22 |  |  | 2020-05-22 |  | 2020-04-29 | [16 empty] | 2020-05-20 |  |  | 2020-05-29 | [6 empty] | 2020-06-12 |  |  |  | 2020-06-12 |  |  |  |  | 2020-05-06 |  | 2020-05-16 |  |  | 2020-05-20 |  | 2020-05-23 |  |  | 2020-06-06 |  |  |  | 2020-06-13 |  | JGT-36-340C-2NPT |  |  | 2020-06-25 |  | 2020-06-03 | [6 empty] | 2020-07-03 | 2020-07-10 | [20 empty] | 2020-08-09 |  |  |  | 2020-08-12 | [8 empty] | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-13 |  |  |  | 2020-07-16 |  |  | 2020-07-31 |  |  |  | 2020-08-12 |  | 2020-08-15
PH1200119 | 125.122 | 6.0854 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Labangal | MIN | PH126303033 | 75342 | 40 | Angular Steel Tower | CO67 | 7.2538 | MIN-1200052 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | EGB |  | Mobicon |  | 2019-11-27 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-18 |  |  |  | 2019-12-18 |  |  |  | 2019-12-14 | 2019-12-18 |  |  |  | 2019-12-18 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-23 | 2020-01-13 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | A | Felizardo Consigna | Purok Tomasa, Brgy. Calumpang, General Santos City | South Cotabato | 125.122 | 6.0854 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-20 |  |  | 2020-02-19 |  | 2020-01-27 | [16 empty] | 2020-02-17 |  |  | 2020-02-26 | [6 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  |  | 2020-02-03 |  | 2020-02-13 |  |  | 2020-02-17 |  | 2020-02-20 |  |  | 2020-03-05 |  |  |  | 2020-03-12 |  | JGT-36-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 |  |  |  | 2020-03-02 |  | 2020-03-02 | [14 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [8 empty] | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1200122 | 125.1319 | 6.1358 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Sinawal | MIN | PH126303026 | 13285 | 40 | Angular Steel Tower | CO67 | 3.9377 | MIN-1200053 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | EGB |  | STJV |  | 2019-11-27 | 2019-12-09 | 2019-12-09 | 2019-12-11 | 2019-12-10 |  |  |  | 2019-12-10 | 2019-12-10 |  |  |  | 2019-12-10 |  |  |  | 2019-12-16 | 2019-12-10 |  |  |  | 2019-12-10 | 2019-12-10 |  |  |  | 2019-12-10 | 2019-12-23 | 2020-01-15 | 2019-12-27 |  |  |  |  | A | Palgencio Javison | Brgy. Apopong, General Santos City | South Cotabato | 125.1309 | 6.1378 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-22 |  |  | 2020-02-21 |  | 2020-01-29 | [16 empty] | 2020-02-19 |  |  | 2020-02-28 | [6 empty] | 2020-03-13 |  |  |  | 2020-03-13 |  |  |  |  | 2020-02-05 |  | 2020-02-15 |  |  | 2020-02-19 |  | 2020-02-22 |  |  | 2020-03-07 |  |  |  | 2020-03-14 |  | JGT-36-340C-2NPT |  |  | 2020-03-26 |  | 2020-03-04 | [6 empty] | 2020-04-03 | 2020-04-10 | [20 empty] | 2020-05-10 |  |  |  | 2020-05-13 | [8 empty] | 2020-03-19 |  | 2020-03-22 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-05-01 |  |  |  | 2020-05-13 |  | 2020-05-16
PH1200130 | 125.1417 | 6.175 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Mabuhay | MIN | PH126303016 | 28288 | 40 | Angular Steel Tower | CO67 | 5.506 | MIN-1200054 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2019-12-29 | 2019-12-29 | 2019-12-31 | 2019-12-30 |  |  |  | 2019-12-30 | 2019-12-31 |  |  |  | 2019-12-31 |  |  |  | 2020-01-05 | [5 empty] | 2019-12-30 |  |  |  | 2019-12-30 |  | 2020-02-04 | [27 empty] | 2020-02-11 |  |  | 2020-03-12 |  | 2020-02-18 | [16 empty] | 2020-03-10 |  |  | 2020-03-19 | [6 empty] | 2020-04-02 |  |  |  | 2020-04-02 |  |  |  |  | 2020-02-25 |  | 2020-03-06 |  |  | 2020-03-10 |  | 2020-03-13 |  |  | 2020-03-27 |  |  |  | 2020-04-03 |  | JGT-36-340C-2NPT |  |  | 2020-04-15 |  | 2020-03-24 | [6 empty] | 2020-04-23 | 2020-04-30 | [20 empty] | 2020-05-30 |  |  |  | 2020-06-02 | [8 empty] | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-23 |  |  |  | 2020-04-26 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-21 |  |  |  | 2020-06-02 |  | 2020-06-05
PH1200135 | 125.1446 | 6.1198 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Apopong | MIN | PH126303012 | 61713 | 40 | Angular Steel Tower | CO67 | 2.8806 | MIN-1200055 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | EGB |  | STJV |  | 2019-11-27 | 2019-11-28 | 2019-11-28 | 2019-11-30 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-05 | 2019-12-12 |  |  |  | 2019-12-12 | 2019-12-06 |  |  |  | 2019-12-06 | 2020-01-24 | 2020-01-04 | 2019-12-27 |  |  | 2020-01-24 | 2020-02-06 | A | Dionesa C. Panolino | Purok Malipayon, Brgy. Labangal, General Santos City | South Cotabato | 125.1433 | 6.1184 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-11 |  |  | 2020-02-10 |  | 2020-01-18 | [16 empty] | 2020-02-08 |  |  | 2020-02-17 | [6 empty] | 2020-03-02 |  |  |  | 2020-03-02 |  |  |  |  | 2020-01-25 |  | 2020-02-04 |  |  | 2020-02-08 |  | 2020-02-11 |  |  | 2020-02-25 |  |  |  | 2020-03-03 |  | JGT-36-340C-2NPT |  |  | 2020-03-15 |  | 2020-02-22 | [6 empty] | 2020-03-23 | 2020-03-30 |  |  |  | 2020-03-02 |  | 2020-03-02 | [14 empty] | 2020-04-29 |  |  |  | 2020-05-02 | [8 empty] | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-23 |  |  |  | 2020-03-26 |  |  | 2020-04-02 |  |  |  | 2020-04-05 |  |  | 2020-04-20 |  |  |  | 2020-05-02 |  | 2020-05-05
PH1200155 | 125.1611 | 6.1637 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Conel | MIN | PH126303023 | 52832 | 40 | Angular Steel Tower | CO67 | 3.5355 | MIN-1200056 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | EGB |  |  |  | 2019-11-27 | 2019-12-30 | 2019-12-30 | 2020-01-01 | 2019-12-31 |  |  |  | 2019-12-31 | 2019-12-31 |  |  |  | 2019-12-31 |  |  |  | 2020-01-06 | 2019-12-31 |  |  |  | 2019-12-31 | 2019-12-31 |  |  |  | 2019-12-31 | 2020-01-24 | 2020-02-05 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Daniel Escarmoso | Promise Land 2, Mabuhay, General Santos City | South Cotabato | 125.1595 | 6.1633 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-12 |  |  | 2020-03-13 |  | 2020-02-19 | [16 empty] | 2020-03-11 |  |  | 2020-03-20 | [6 empty] | 2020-04-03 |  |  |  | 2020-04-03 |  |  |  |  | 2020-02-26 |  | 2020-03-07 |  |  | 2020-03-11 |  | 2020-03-14 |  |  | 2020-03-28 |  |  |  | 2020-04-04 |  | JGT-36-340C-2NPT |  |  | 2020-04-16 |  | 2020-03-25 | [6 empty] | 2020-04-24 | 2020-05-01 | [20 empty] | 2020-05-31 |  |  |  | 2020-06-03 | [8 empty] | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-04 |  |  |  | 2020-05-07 |  |  | 2020-05-22 |  |  |  | 2020-06-03 |  | 2020-06-06
PH1200156 | 125.1588 | 6.1183 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | City Heights | MIN | PH126303035 | 8056 | 40 | Angular Steel Tower | CO67 | 1.8457 | MIN-1200057 | Level 5 | phase3 | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-01-05 | 2020-01-10 | 2020-01-07 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-01-12 |  |  |  | 2020-01-12 |  |  |  | 2020-01-12 | 2020-01-12 |  |  |  | 2020-01-12 | 2020-01-11 |  |  |  | 2020-01-11 | 2020-01-24 | 2020-02-11 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Almira P. Alea | Dagohoy, Brgy. North, General Santos City | South Cotabato | 125.1579 | 6.1196 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-18 |  |  | 2020-03-19 |  | 2020-02-25 | [16 empty] | 2020-03-17 |  |  | 2020-03-26 | [6 empty] | 2020-04-09 |  |  |  | 2020-04-09 |  |  |  |  | 2020-03-03 |  | 2020-03-13 |  |  | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-03 |  |  |  | 2020-04-10 |  | JGT-36-340C-2NPT |  |  | 2020-04-22 |  | 2020-03-31 | [6 empty] | 2020-04-30 | 2020-05-07 | [20 empty] | 2020-06-06 |  |  |  | 2020-06-09 | [8 empty] | 2020-04-15 |  | 2020-04-18 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-10 |  |  |  | 2020-05-13 |  |  | 2020-05-28 |  |  |  | 2020-06-09 |  | 2020-06-12
PH1200165 | 125.1904 | 6.2029 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Olympog | MIN | PH126303006 | 11164 | 40 | Angular Steel Tower | CO67 | 8.2198 | MIN-1200058 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) |  |  |  |  | 2019-11-27 | 2020-03-11 | 2020-01-18 | 2020-03-13 | 2020-01-16 |  |  |  | 2020-01-16 | 2020-01-17 |  |  |  | 2020-01-17 |  |  |  | 2020-03-18 | [11 empty] | 2020-04-17 | [27 empty] | 2020-04-24 |  |  | 2020-05-24 |  | 2020-05-01 | [16 empty] | 2020-05-22 |  |  | 2020-05-31 | [6 empty] | 2020-06-14 |  |  |  | 2020-06-14 |  |  |  |  | 2020-05-08 |  | 2020-05-18 |  |  | 2020-05-22 |  | 2020-05-25 |  |  | 2020-06-08 |  |  |  | 2020-06-15 |  | JGT-36-340C-2NPT |  |  | 2020-06-27 |  | 2020-06-05 | [6 empty] | 2020-07-05 | 2020-07-12 | [20 empty] | 2020-08-11 |  |  |  | 2020-08-14 | [8 empty] | 2020-06-20 |  | 2020-06-23 |  |  | 2020-07-05 |  |  |  | 2020-07-08 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-08-02 |  |  |  | 2020-08-14 |  | 2020-08-17
PH1200166 | 125.1902 | 6.1692 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Conel | MIN | PH126303009 | 13948 | 40 | Angular Steel Tower | CO67 | 4.7974 | MIN-1200059 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | Enovell |  |  |  | 2019-11-27 | 2020-01-31 | 2020-01-11 | 2020-02-02 | 2020-01-14 |  |  |  | 2020-01-14 | [8 empty] | 2020-02-07 | [5 empty] | 2020-01-29 |  |  |  | 2020-01-29 |  | 2020-03-08 | [27 empty] | 2020-03-15 |  |  | 2020-04-14 |  | 2020-03-22 | [16 empty] | 2020-04-12 |  |  | 2020-04-21 | [6 empty] | 2020-05-05 |  |  |  | 2020-05-05 |  |  |  |  | 2020-03-29 |  | 2020-04-08 |  |  | 2020-04-12 |  | 2020-04-15 |  |  | 2020-04-29 |  |  |  | 2020-05-06 |  | JGT-36-340C-2NPT |  |  | 2020-05-18 |  | 2020-04-26 | [6 empty] | 2020-05-26 | 2020-06-02 | [20 empty] | 2020-07-02 |  |  |  | 2020-07-05 | [8 empty] | 2020-05-11 |  | 2020-05-14 |  |  | 2020-05-26 |  |  |  | 2020-05-29 |  |  | 2020-06-05 |  |  |  | 2020-06-08 |  |  | 2020-06-23 |  |  |  | 2020-07-05 |  | 2020-07-08
PH1200168 | 125.1892 | 6.1404 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Lagao (1st & 3rd) | MIN | PH126303011 | 50789 | 40 | Angular Steel Tower | CO67 | 2.5667 | MIN-1200060 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | EGB |  | KASBEL |  | 2019-11-27 | 2019-11-28 | 2019-11-28 | 2019-11-30 | 2019-12-04 | 2019-12-04 | 2019-12-04 |  | 2019-12-04 | 2019-12-05 | 2019-12-05 | 2019-12-05 |  | 2019-12-05 |  |  |  | 2019-12-05 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-11-28 |  |  |  | 2019-11-28 | 2020-01-24 | 2020-01-04 | 2020-01-09 |  |  | 2020-01-10 | 2020-02-04 | A | Marcelino M. Jucutan | Conel Rd., Lagao, General Santos City | South Cotabato | 125.1891 | 6.1406 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-11 |  |  | 2020-02-10 |  | 2020-01-18 | [16 empty] | 2020-02-08 |  |  | 2020-02-17 | [6 empty] | 2020-03-02 |  |  |  | 2020-03-02 |  |  |  |  | 2020-01-25 | 2020-02-28 | 2020-02-04 |  |  | 2020-02-08 |  | 2020-02-11 |  |  | 2020-02-25 |  |  |  | 2020-03-03 |  | JGT-36-340C-2NPT |  |  | 2020-03-15 |  | 2020-02-22 | [6 empty] | 2020-03-23 | 2020-03-30 | [20 empty] | 2020-04-29 |  |  |  | 2020-05-02 | [8 empty] | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-23 |  |  |  | 2020-03-26 |  |  | 2020-04-02 |  |  |  | 2020-04-05 |  |  | 2020-04-20 |  |  |  | 2020-05-02 |  | 2020-05-05
PH1200177 | 125.2191 | 6.1299 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Baluan | MIN | PH126303003 | 7611 | 40 | Angular Steel Tower | CO67 | 5.7349 | MIN-1200061 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | EGB |  |  |  | 2019-11-27 | 2019-12-28 | 2019-12-28 | 2019-12-30 | 2020-01-07 |  |  |  | 2020-01-07 | 2020-01-08 |  |  |  | 2020-01-08 |  |  |  | 2020-01-04 | 2020-01-08 |  |  |  | 2020-01-08 | 2020-01-07 |  |  |  | 2020-01-07 | 2020-01-24 | 2020-02-03 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Glaisa Gregori | Purok Pantay-Pantay, Brgy. Baluan, General Santos City | South Cotabato | 125.2204 | 6.1292 | Greenfield |  |  | 15 years | P12,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-10 |  |  | 2020-03-11 |  | 2020-02-17 | [16 empty] | 2020-03-09 |  |  | 2020-03-18 | [6 empty] | 2020-04-01 |  |  |  | 2020-04-01 |  |  |  |  | 2020-02-24 | 2020-03-02 | 2020-03-05 |  |  | 2020-03-09 |  | 2020-03-12 |  |  | 2020-03-26 |  |  |  | 2020-04-02 |  | JGT-36-340C-2NPT |  |  | 2020-04-14 |  | 2020-03-23 | [6 empty] | 2020-04-22 | 2020-04-29 |  |  |  | 2020-03-02 |  | 2020-03-02 | [14 empty] | 2020-05-29 |  |  |  | 2020-06-01 | [8 empty] | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-02 |  |  |  | 2020-05-05 |  |  | 2020-05-20 |  |  |  | 2020-06-01 |  | 2020-06-04
PH1200178 | 125.229 | 6.1579 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Ligaya | MIN | PH126303015 | 5298 | 40 | Angular Steel Tower | CO67 | 7.3701 | MIN-1200062 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2019-12-28 | 2019-12-28 | 2019-12-30 | 2020-01-07 |  |  |  | 2020-01-07 | 2020-01-08 |  |  |  | 2020-01-08 |  |  |  | 2020-01-04 | 2020-01-08 |  |  |  | 2020-01-08 | 2020-01-07 |  |  |  | 2020-01-07 | 2020-03-06 | 2020-02-03 | 2020-01-23 |  |  | 2020-03-06 |  | A | Geromille Lim | Purok 3, Ligaya, General Santos City | South Cotabato | 125.229 | 6.1594 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-10 |  |  | 2020-03-11 |  | 2020-02-17 | [16 empty] | 2020-03-09 |  |  | 2020-03-18 | [6 empty] | 2020-04-01 |  |  |  | 2020-04-01 |  |  |  |  | 2020-02-24 |  | 2020-03-05 |  |  | 2020-03-09 |  | 2020-03-12 |  |  | 2020-03-26 |  |  |  | 2020-04-02 |  | JGT-36-340C-2NPT |  |  | 2020-04-14 |  | 2020-03-23 | [6 empty] | 2020-04-22 | 2020-04-29 | [20 empty] | 2020-05-29 |  |  |  | 2020-06-01 | [8 empty] | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-02 |  |  |  | 2020-05-05 |  |  | 2020-05-20 |  |  |  | 2020-06-01 |  | 2020-06-04
PH1200185 | 124.6692 | 6.7132 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Tacurong City | Buenaflor | MIN | PH126511006 | 6537 | 40 | Three Legged Tubular Tower | CO68 | 73.1967 | MIN-1200063 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-29 |  | 2020-03-31 | [13 empty] | 2020-04-05 | [11 empty] | 2020-05-05 | [27 empty] | 2020-05-12 |  |  | 2020-06-11 |  | 2020-05-19 | [16 empty] | 2020-06-09 |  |  | 2020-06-18 | [6 empty] | 2020-07-02 |  |  |  | 2020-07-02 |  |  |  |  | 2020-05-26 |  | 2020-06-05 |  |  | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-26 |  |  |  | 2020-07-03 |  | 4GT-42-340C-2NPT |  |  | 2020-07-15 |  | 2020-06-23 | [6 empty] | 2020-07-23 | 2020-07-30 | [20 empty] | 2020-08-29 |  |  |  | 2020-09-01 | [8 empty] | 2020-07-08 |  | 2020-07-11 |  |  | 2020-07-23 |  |  |  | 2020-07-26 |  |  | 2020-08-02 |  |  |  | 2020-08-05 |  |  | 2020-08-20 |  |  |  | 2020-09-01 |  | 2020-09-04
PH1200186 | 124.668 | 6.6645 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Tacurong City | Lancheta | MIN | PH126511003 | 2498 | 40 | Three Legged Tubular Tower | CO68 | 77.3802 | MIN-1200064 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-01 |  | 2020-04-03 | [13 empty] | 2020-04-08 | [11 empty] | 2020-05-08 | [27 empty] | 2020-05-15 |  |  | 2020-06-14 |  | 2020-05-22 | [16 empty] | 2020-06-12 |  |  | 2020-06-21 | [6 empty] | 2020-07-05 |  |  |  | 2020-07-05 |  |  |  |  | 2020-05-29 |  | 2020-06-08 |  |  | 2020-06-12 |  | 2020-06-15 |  |  | 2020-06-29 |  |  |  | 2020-07-06 |  | 3GT-36-280C-2NPT |  |  | 2020-07-18 |  | 2020-06-26 | [6 empty] | 2020-07-26 | 2020-08-02 | [20 empty] | 2020-09-01 |  |  |  | 2020-09-04 | [8 empty] | 2020-07-11 |  | 2020-07-14 |  |  | 2020-07-26 |  |  |  | 2020-07-29 |  |  | 2020-08-05 |  |  |  | 2020-08-08 |  |  | 2020-08-23 |  |  |  | 2020-09-04 |  | 2020-09-07
PH1200191 | 124.7137 | 6.6824 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Tacurong City | Kalandagan | MIN | PH126511016 | 6472 | 40 | Three Legged Tubular Tower | CO68 | 78.973 | MIN-1200065 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-04 |  | 2020-04-06 | [13 empty] | 2020-04-11 | [11 empty] | 2020-05-11 | [27 empty] | 2020-05-18 |  |  | 2020-06-17 |  | 2020-05-25 | [16 empty] | 2020-06-15 |  |  | 2020-06-24 | [6 empty] | 2020-07-08 |  |  |  | 2020-07-08 |  |  |  |  | 2020-06-01 |  | 2020-06-11 |  |  | 2020-06-15 |  | 2020-06-18 |  |  | 2020-07-02 |  |  |  | 2020-07-09 |  | 3GT-36-280C-2NPT |  |  | 2020-07-21 |  | 2020-06-29 | [6 empty] | 2020-07-29 | 2020-08-05 | [20 empty] | 2020-09-04 |  |  |  | 2020-09-07 | [8 empty] | 2020-07-14 |  | 2020-07-17 |  |  | 2020-07-29 |  |  |  | 2020-08-01 |  |  | 2020-08-08 |  |  |  | 2020-08-11 |  |  | 2020-08-26 |  |  |  | 2020-09-07 |  | 2020-09-10
PH1200200 | 124.8616 | 6.4956 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Koronadal City | General Paulino Santos (Bo. 1) | MIN | PH126306025 | 10770 | 40 | Three Legged Tubular Tower | CO67 | 52.6477 | MIN-1200066 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-14 |  | 2020-03-16 | [13 empty] | 2020-03-21 | [11 empty] | 2020-04-20 | [27 empty] | 2020-04-27 |  |  | 2020-05-27 |  | 2020-05-04 | [16 empty] | 2020-05-25 |  |  | 2020-06-03 | [6 empty] | 2020-06-17 |  |  |  | 2020-06-17 |  |  |  |  | 2020-05-11 |  | 2020-05-21 |  |  | 2020-05-25 |  | 2020-05-28 |  |  | 2020-06-11 |  |  |  | 2020-06-18 |  | 4GT-42-340C-2NPT |  |  | 2020-06-30 |  | 2020-06-08 | [6 empty] | 2020-07-08 | 2020-07-15 | [20 empty] | 2020-08-14 |  |  |  | 2020-08-17 | [8 empty] | 2020-06-23 |  | 2020-06-26 |  |  | 2020-07-08 |  |  |  | 2020-07-11 |  |  | 2020-07-18 |  |  |  | 2020-07-21 |  |  | 2020-08-05 |  |  |  | 2020-08-17 |  | 2020-08-20
PH1200205 | 124.9048 | 6.4705 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Koronadal City | New Pangasinan (Bo. 4) | MIN | PH126306010 | 3169 | 40 | Three Legged Tubular Tower | CO67 | 47.4731 | MIN-1200067 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-17 |  | 2020-03-19 | [13 empty] | 2020-03-24 | [11 empty] | 2020-04-23 | [27 empty] | 2020-04-30 |  |  | 2020-05-30 |  | 2020-05-07 | [16 empty] | 2020-05-28 |  |  | 2020-06-06 | [6 empty] | 2020-06-20 |  |  |  | 2020-06-20 |  |  |  |  | 2020-05-14 |  | 2020-05-24 |  |  | 2020-05-28 |  | 2020-05-31 |  |  | 2020-06-14 |  |  |  | 2020-06-21 |  | 4GT-42-340C-2NPT |  |  | 2020-07-03 |  | 2020-06-11 | [6 empty] | 2020-07-11 | 2020-07-18 | [20 empty] | 2020-08-17 |  |  |  | 2020-08-20 | [8 empty] | 2020-06-26 |  | 2020-06-29 |  |  | 2020-07-11 |  |  |  | 2020-07-14 |  |  | 2020-07-21 |  |  |  | 2020-07-24 |  |  | 2020-08-08 |  |  |  | 2020-08-20 |  | 2020-08-23
PH1200207 | 125.0534 | 7.0057 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Balindog | MIN | PH124704038 | 8041 | 40 | Three Legged Tubular Tower | CO66 | 63.6635 | MIN-1200068 | Level 5 | phase2_add | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  |  |  | 2020-01-20 | 2020-04-07 | 2020-01-08 | 2020-04-09 | 2020-01-28 |  |  |  | 2020-01-28 | 2020-01-29 |  |  |  | 2020-01-29 |  |  |  | 2020-04-14 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-01-28 |  |  |  | 2020-01-28 |  | 2020-05-14 | [5 empty] | A |  |  |  | 125.0552 | 7.0056 | [16 empty] | 2020-05-21 |  |  | 2020-06-20 |  | 2020-05-28 | [16 empty] | 2020-06-18 |  |  | 2020-06-27 | [6 empty] | 2020-07-11 |  |  |  | 2020-07-11 |  |  |  |  | 2020-06-04 |  | 2020-06-14 |  |  | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-05 |  |  |  | 2020-07-12 |  | JGT-36-280C-2NPT（290KPH/D） |  |  | 2020-07-24 |  | 2020-07-02 | [6 empty] | 2020-08-01 | 2020-08-08 | [20 empty] | 2020-09-07 |  |  |  | 2020-09-10 | [8 empty] | 2020-07-17 |  | 2020-07-20 |  |  | 2020-08-01 |  |  |  | 2020-08-04 |  |  | 2020-08-11 |  |  |  | 2020-08-14 |  |  | 2020-08-29 |  |  |  | 2020-09-10 |  | 2020-09-13
PH1200208 | 125.0544 | 7.0378 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Balindog | MIN | PH124704004 | 5756 | 40 | Three Legged Tubular Tower | CO66 | 63.0719 | MIN-1200069 | Level 5 | phase2_add | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-21 | 2020-01-29 | 2020-01-18 | 2020-01-31 | 2020-01-19 |  |  |  | 2020-01-19 | [8 empty] | 2020-02-05 | [5 empty] | 2020-01-19 |  |  |  | 2020-01-19 |  | 2020-03-06 | [27 empty] | 2020-03-13 | 2020-01-27 |  | 2020-04-12 |  | 2020-03-20 | [16 empty] | 2020-04-10 | ok |  | 2020-04-19 | [6 empty] | 2020-05-03 |  |  |  | 2020-05-03 |  |  |  |  | 2020-03-27 |  | 2020-04-06 |  |  | 2020-04-10 |  | 2020-04-13 |  |  | 2020-04-27 |  |  |  | 2020-05-04 |  | JGT-42-280C-2NPT（290KPH/D） |  |  | 2020-05-16 |  | 2020-04-24 | [6 empty] | 2020-05-24 | 2020-05-31 | [20 empty] | 2020-06-30 |  |  |  | 2020-07-03 | [8 empty] | 2020-05-09 |  | 2020-05-12 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-03 |  |  |  | 2020-06-06 |  |  | 2020-06-21 |  |  |  | 2020-07-03 |  | 2020-07-06
PH1200210 | 125.1039 | 6.0954 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Apopong | MIN | PH126303024 | 11333 | 40 | Three Legged Tubular Tower | CO67 | 8.1421 | MIN-1200070 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | EGB |  | Mobicon |  | 2019-12-12 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-14 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-23 | 2020-01-13 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | A | Virgie Datumanay | Diversion Road, Apopong, Purok 13, General Santos City | South Cotabato | 125.1039 | 6.0954 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-20 |  |  | 2020-02-19 |  | 2020-01-27 | [16 empty] | 2020-02-17 |  |  | 2020-02-26 | [6 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  |  | 2020-02-03 | 2020-03-12 | 2020-02-13 | 2020-03-12 | 2020-03-12 | 2020-02-17 |  | 2020-02-20 |  |  | 2020-03-05 |  |  |  | 2020-03-12 |  | 4GT-42-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 | [20 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [8 empty] | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1200212 | 125.1093 | 6.0355 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Tambler | MIN | PH126303027 | 21474 | 40 | Three Legged Tubular Tower | CO67 | 12.5628 | MIN-1200071 | Level 5 | phase3 | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2020-01-27 | 2020-01-16 | 2020-01-29 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-01-18 |  |  |  | 2020-01-18 |  |  |  | 2020-02-03 | [5 empty] | 2020-01-17 |  |  |  | 2020-01-17 |  | 2020-03-04 | [27 empty] | 2020-03-11 | 2020-01-27 |  | 2020-04-10 |  | 2020-03-18 | [16 empty] | 2020-04-08 |  |  | 2020-04-17 | [6 empty] | 2020-05-01 |  |  |  | 2020-05-01 |  |  |  |  | 2020-03-25 |  | 2020-04-04 |  |  | 2020-04-08 |  | 2020-04-11 |  |  | 2020-04-25 |  |  |  | 2020-05-02 |  | 4GT-42-340C-2NPT |  |  | 2020-05-14 |  | 2020-04-22 | [6 empty] | 2020-05-22 | 2020-05-29 | [20 empty] | 2020-06-28 |  |  |  | 2020-07-01 | [8 empty] | 2020-05-07 |  | 2020-05-10 |  |  | 2020-05-22 |  |  |  | 2020-05-25 |  |  | 2020-06-01 |  |  |  | 2020-06-04 |  |  | 2020-06-19 |  |  |  | 2020-07-01 |  | 2020-07-04
PH1200213 | 125.0807 | 6.1442 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Sinawal | MIN | PH126303026 | 13285 | 40 | Three Legged Tubular Tower | CO67 | 9.671 | MIN-1200072 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | EGB |  |  |  | 2019-12-12 | 2020-01-23 | 2020-01-17 | 2020-01-25 | 2020-01-17 | 2020-01-22 |  |  | 2020-01-17 | 2020-01-18 | 2020-01-24 |  |  | 2020-01-18 |  |  |  | 2020-01-30 |  | 2020-01-24 |  |  | 2020-01-24 | 2020-01-16 | 2020-01-22 |  |  | 2020-01-16 |  | 2020-02-29 | [5 empty] | A |  |  |  | 125.125 | 6.1528 | Greenfield | [9 empty] | 2020-01-17 | n/a |  |  |  | n/a | 2020-03-07 |  |  | 2020-04-06 |  | 2020-03-14 | [16 empty] | 2020-04-04 |  |  | 2020-04-13 | [6 empty] | 2020-04-27 |  |  |  | 2020-04-27 |  |  |  |  | 2020-03-21 |  | 2020-03-31 |  |  | 2020-04-04 |  | 2020-04-07 |  |  | 2020-04-21 |  |  |  | 2020-04-28 |  | 4GT-42-340C-2NPT |  |  | 2020-05-10 |  | 2020-04-18 | [6 empty] | 2020-05-18 | 2020-05-25 | [20 empty] | 2020-06-24 |  |  |  | 2020-06-27 | [8 empty] | 2020-05-03 |  | 2020-05-06 |  |  | 2020-05-18 |  |  |  | 2020-05-21 |  |  | 2020-05-28 |  |  |  | 2020-05-31 |  |  | 2020-06-15 |  |  |  | 2020-06-27 |  | 2020-06-30
PH1200214 | 125.1284 | 6.1038 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Labangal | MIN | PH126303029 | 46384 | 40 | Three Legged Tubular Tower | CO67 | 5.3705 | MIN-1200073 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-03-15 | 2020-01-15 | 2020-03-17 | 2020-01-20 | 2020-01-27 |  |  | 2020-01-20 | 2020-01-21 | 2020-01-27 |  |  | 2020-01-21 |  |  |  | 2020-03-22 |  | 2020-01-27 |  |  | 2020-01-27 | 2020-01-20 | 2020-01-27 |  |  | 2020-01-20 | 2020-02-26 | 2020-04-21 | 2020-03-12 |  |  | 2020-03-12 |  | A | Rebecca Simpo | Purok Pandian Gay, Brgy. Labangal, General Santos City | South Cotabato | 125.148 | 6.0944 | Greenfield |  |  | 10 years | P12,000 Exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | 2020-01-17 | n/a |  |  |  | n/a | 2020-04-28 | 2020-01-16 |  | 2020-05-28 |  | 2020-05-05 | [16 empty] | 2020-05-26 |  |  | 2020-06-04 | [6 empty] | 2020-06-18 |  |  |  | 2020-06-18 |  |  |  |  | 2020-05-12 |  | 2020-05-22 |  |  | 2020-05-26 |  | 2020-05-29 |  |  | 2020-06-12 |  |  |  | 2020-06-19 |  | 4GT-42-340C-2NPT |  |  | 2020-07-01 |  | 2020-06-09 | [6 empty] | 2020-07-09 | 2020-07-16 | [20 empty] | 2020-08-15 |  |  |  | 2020-08-18 | [8 empty] | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-19 |  |  |  | 2020-07-22 |  |  | 2020-08-06 |  |  |  | 2020-08-18 |  | 2020-08-21
PH1200215 | 125.1321 | 6.1919 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Mabuhay | MIN | PH126312005 | 3594 | 40 | Three Legged Tubular Tower | CO67 | 7.661 | MIN-1200074 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2019-12-28 | 2019-12-28 | 2019-12-30 | 2019-12-29 | 2020-02-01 |  |  | 2019-12-29 | [8 empty] | 2020-01-04 | [5 empty] | 2019-12-29 | 2020-02-01 |  |  | 2019-12-29 |  | 2020-02-03 | [27 empty] | 2020-02-10 |  |  | 2020-03-11 |  | 2020-02-17 | [16 empty] | 2020-03-09 |  |  | 2020-03-18 | [6 empty] | 2020-04-01 |  |  |  | 2020-04-01 |  |  |  |  | 2020-02-24 |  | 2020-03-05 |  |  | 2020-03-09 |  | 2020-03-12 |  |  | 2020-03-26 |  |  |  | 2020-04-02 |  | JGT-36-340C-2NPT |  |  | 2020-04-14 |  | 2020-03-23 | [6 empty] | 2020-04-22 | 2020-04-29 | [20 empty] | 2020-05-29 |  |  |  | 2020-06-01 | [8 empty] | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-02 |  |  |  | 2020-05-05 |  |  | 2020-05-20 |  |  |  | 2020-06-01 |  | 2020-06-04
PH1200219 | 125.1907 | 6.2155 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Olympog | MIN | PH126303039 | 3352 | 40 | Three Legged Tubular Tower | CO67 | 9.5724 | MIN-1200075 | Level 5 | phase2_add | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2020-01-19 | 2020-01-15 | 2020-01-21 | 2020-01-17 | 2020-01-27 |  |  | 2020-01-17 | [8 empty] | 2020-01-26 | [5 empty] | 2020-01-17 | 2020-01-27 |  |  | 2020-01-17 |  | 2020-02-25 | [27 empty] | 2020-03-03 |  |  | 2020-04-02 |  | 2020-03-10 | [16 empty] | 2020-03-31 |  |  | 2020-04-09 | [6 empty] | 2020-04-23 |  |  |  | 2020-04-23 |  |  |  |  | 2020-03-17 |  | 2020-03-27 |  |  | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-17 |  |  |  | 2020-04-24 |  | 4GT-42-340C-2NPT |  |  | 2020-05-06 |  | 2020-04-14 | [6 empty] | 2020-05-14 | 2020-05-21 | [20 empty] | 2020-06-20 |  |  |  | 2020-06-23 | [8 empty] | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-11 |  |  |  | 2020-06-23 |  | 2020-06-26
PH1200221 | 125.1805 | 6.1749 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Conel | MIN | PH126303006 | 11164 | 40 | Three Legged Tubular Tower | CO67 | 4.9257 | MIN-1200076 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-01-08 | 2020-01-07 | 2020-01-10 | 2020-01-09 |  |  |  | 2020-01-09 | 2020-01-09 |  |  |  | 2020-01-09 |  |  |  | 2020-01-15 | 2020-01-09 |  |  |  | 2020-01-09 | 2020-01-09 |  |  |  | 2020-01-09 | 2020-01-24 | 2020-02-14 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Bobby Biduap | Malinawon, Udagre Conel, General Santos City | South Cotabato | 125.1815 | 6.1742 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-21 |  |  | 2020-03-22 |  | 2020-02-28 | [16 empty] | 2020-03-20 |  |  | 2020-03-29 | [6 empty] | 2020-04-12 |  |  |  | 2020-04-12 |  |  |  |  | 2020-03-06 |  | 2020-03-16 |  |  | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-06 |  |  |  | 2020-04-13 |  | 4GT-42-340C-2NPT |  |  | 2020-04-25 |  | 2020-04-03 | [6 empty] | 2020-05-03 | 2020-05-10 | [20 empty] | 2020-06-09 |  |  |  | 2020-06-12 | [8 empty] | 2020-04-18 |  | 2020-04-21 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-31 |  |  |  | 2020-06-12 |  | 2020-06-15
PH1200227 | 125.2299 | 6.1687 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Katangawan | MIN | PH126303009 | 13948 | 40 | Three Legged Tubular Tower | CO67 | 8.0019 | MIN-1200077 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2020-01-20 | 2020-01-08 | 2020-01-22 | 2020-01-09 | 2020-01-22 |  |  | 2020-01-09 | 2020-01-11 | 2020-01-23 |  |  | 2020-01-11 |  |  |  | 2020-01-27 |  | 2020-01-23 |  |  | 2020-01-23 | 2020-01-09 | 2020-01-22 |  |  | 2020-01-09 | 2020-02-25 | 2020-02-26 | [5 empty] | A | Julito Edang | Purok 3, Brgy. Ligaya, General Santos City | South Cotabato | 125.2298 | 6.1676 | Greenfield |  |  | 10 years | P17,000 exclusive of VAT and withholding tax | quarterly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-04 |  |  | 2020-04-03 |  | 2020-03-11 | [16 empty] | 2020-04-01 |  |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  |  | 2020-03-18 |  | 2020-03-28 |  |  | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-18 |  |  |  | 2020-04-25 |  | 4GT-42-340C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1200228 | 125.2288 | 6.1242 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Buayan | MIN | PH126303003 | 7611 | 40 | Three Legged Tubular Tower | CO67 | 6.8597 | MIN-1200078 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 | AFP_25 | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-03-18 | 2020-01-15 | 2020-03-20 | 2020-01-16 | 2020-01-22 |  |  | 2020-01-16 | 2020-01-17 | 2020-01-23 |  |  | 2020-01-17 |  |  |  | 2020-03-25 |  | 2020-01-23 |  |  | 2020-01-23 | 2020-01-16 | 2020-01-22 |  |  | 2020-01-16 | 2020-02-24 | 2020-04-24 | [5 empty] | A | Gina Redondo | Purok Damayan Baluan, General Santos City | South Cotabato | 125.2277 | 6.1215 | Greenfield |  |  | 10 years | P17,000 exclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-05-01 |  |  | 2020-05-31 |  | 2020-05-08 | [16 empty] | 2020-05-29 |  |  | 2020-06-07 | [6 empty] | 2020-06-21 |  |  |  | 2020-06-21 |  |  |  |  | 2020-05-15 |  | 2020-05-25 |  |  | 2020-05-29 |  | 2020-06-01 |  |  | 2020-06-15 |  |  |  | 2020-06-22 |  | 4GT-42-340C-2NPT |  |  | 2020-07-04 |  | 2020-06-12 | [6 empty] | 2020-07-12 | 2020-07-19 | [20 empty] | 2020-08-18 |  |  |  | 2020-08-21 | [8 empty] | 2020-06-27 |  | 2020-06-30 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-22 |  |  |  | 2020-07-25 |  |  | 2020-08-09 |  |  |  | 2020-08-21 |  | 2020-08-24
PH1200232 | 125.2589 | 6.2581 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Batomelong | MIN | PH128007019 | 15071 | 40 | Three Legged Tubular Tower | CO67 | 17.2368 | MIN-1200079 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2020-01-08 | 2020-01-08 | 2020-01-10 | 2020-01-09 |  |  |  | 2020-01-09 | 2020-01-09 |  |  |  | 2020-01-09 |  |  |  | 2020-01-15 | 2020-01-09 |  |  |  | 2020-01-09 | 2020-01-09 |  |  |  | 2020-01-09 | 2020-01-24 | 2020-02-14 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Terisita B. Pagalangan | Sitio Pula Tana, Malandag, General Santos City | South Cotabato | 125.2589 | 6.258 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-21 |  |  | 2020-03-22 |  | 2020-02-28 | [16 empty] | 2020-03-20 |  |  | 2020-03-29 | [6 empty] | 2020-04-12 |  |  |  | 2020-04-12 |  |  |  |  | 2020-03-06 |  | 2020-03-16 |  |  | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-06 |  |  |  | 2020-04-13 |  | 4GT-42-340C-2NPT |  |  | 2020-04-25 |  | 2020-04-03 | [6 empty] | 2020-05-03 | 2020-05-10 | [20 empty] | 2020-06-09 |  |  |  | 2020-06-12 | [8 empty] | 2020-04-18 |  | 2020-04-21 |  |  | 2020-05-03 |  |  |  | 2020-05-06 |  |  | 2020-05-13 |  |  |  | 2020-05-16 |  |  | 2020-05-31 |  |  |  | 2020-06-12 |  | 2020-06-15
PH1200233 | 125.1183 | 5.9917 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Siguel | MIN | PH126303030 | 12757 | 40 | Three Legged Tubular Tower | CO67 | 16.5779 | MIN-1200080 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-03-21 | 2020-01-13 | 2020-03-23 | 2020-01-20 |  |  |  | 2020-01-20 | [8 empty] | 2020-03-28 | [5 empty] | 2020-01-20 |  |  |  | 2020-01-20 |  | 2020-04-27 | [27 empty] | 2020-05-04 |  |  | 2020-06-03 |  | 2020-05-11 | [16 empty] | 2020-06-01 |  |  | 2020-06-10 | [6 empty] | 2020-06-24 |  |  |  | 2020-06-24 |  |  |  |  | 2020-05-18 |  | 2020-05-28 |  |  | 2020-06-01 |  | 2020-06-04 |  |  | 2020-06-18 |  |  |  | 2020-06-25 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-07-07 |  | 2020-06-15 | [6 empty] | 2020-07-15 | 2020-07-22 | [20 empty] | 2020-08-21 |  |  |  | 2020-08-24 | [8 empty] | 2020-06-30 |  | 2020-07-03 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-07-25 |  |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  |  | 2020-08-24 |  | 2020-08-27
PH1200234 | 125.2356 | 6.2104 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Tinagacan | MIN | PH126303028 | 6322 | 40 | Monopole Tower | CO67 | 11.4891 | MIN-1200081 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_3619 | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | EGB |  | NOVATECH |  | 2019-12-12 | 2019-12-09 | 2019-12-09 | 2019-12-11 | 2019-12-10 |  |  |  | 2019-12-10 | 2019-12-10 |  |  |  | 2019-12-10 |  |  |  | 2019-12-16 | 2019-12-10 |  |  |  | 2019-12-10 | 2019-12-10 |  |  |  | 2019-12-10 | 2020-03-06 | 2020-01-15 | 2020-03-06 |  |  | 2020-03-06 | 2020-03-06 | A | Gilbert Villarbia | Purok 1, Brgy. Tinagacan, General Santos City | South Cotabato | 125.236 | 6.2093 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-22 |  |  | 2020-02-21 |  | 2020-01-29 | [16 empty] | 2020-02-19 |  |  | 2020-02-28 | [6 empty] | 2020-03-13 |  |  |  | 2020-03-13 |  |  |  |  | 2020-02-05 | 2020-02-27 | 2020-02-15 | 2020-03-10 | 2020-03-10 | 2020-02-19 | 2020-03-12 | 2020-02-22 | 2020-03-13 |  | 2020-03-07 |  |  |  | 2020-03-14 |  | 4GT-42-340C-2NPT |  |  | 2020-03-26 |  | 2020-03-04 | [6 empty] | 2020-04-03 | 2020-04-10 |  |  |  | 2020-03-02 |  | 2020-03-02 | [14 empty] | 2020-05-10 |  |  |  | 2020-05-13 | [8 empty] | 2020-03-19 |  | 2020-03-22 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  |  | 2020-04-16 |  |  | 2020-05-01 |  |  |  | 2020-05-13 |  | 2020-05-16
PH1200235 | 125.2939 | 6.0971 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sarangani | Alabel | Spring | MIN | PH128001010 | 18104 | 40 | Three Legged Tubular Tower | CO67 | 14.5431 | MIN-1200082 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019121802PH_WLS | Batch 1 (333) | EGB |  | NOVATECH |  | 2019-11-27 | 2019-11-29 | 2019-11-29 | 2019-12-01 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-06 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-11-28 | 2019-11-28 | 2019-11-28 |  | 2019-11-28 | 2020-02-19 | 2020-01-05 | 2020-01-09 |  |  | 2020-02-26 |  | A | Sabina Dela Cruz Eballe | Lot 149-A-3, Cogonal, Alabel | Sarangani | 125.2944 | 6.0975 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-12 |  |  | 2020-02-11 |  | 2020-01-19 | [16 empty] | 2020-02-09 |  |  | 2020-02-18 | [6 empty] | 2020-03-03 |  |  |  | 2020-03-03 |  |  |  |  | 2020-01-26 |  | 2020-02-05 |  |  | 2020-02-09 |  | 2020-02-12 |  |  | 2020-02-26 |  |  |  | 2020-03-04 |  | 4GT-42-340C-2NPT |  |  | 2020-03-16 |  | 2020-02-23 | [6 empty] | 2020-03-24 | 2020-03-31 | [20 empty] | 2020-04-30 |  |  |  | 2020-05-03 | [8 empty] | 2020-03-09 |  | 2020-03-12 |  |  | 2020-03-24 |  |  |  | 2020-03-27 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-21 |  |  |  | 2020-05-03 |  | 2020-05-06
PH1200241 | 124.7778 | 6.4202 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Banga | Reyes | MIN | PH126302002 | 3149 | 40 | Monopole Tower | CO67 | 53.6364 | MIN-1200083 | Level 6 | phase2_add | phase3 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-20 |  | 2020-03-22 | [13 empty] | 2020-03-27 | [11 empty] | 2020-04-26 | [27 empty] | 2020-05-03 |  |  | 2020-06-02 |  | 2020-05-10 | [16 empty] | 2020-05-31 |  |  | 2020-06-09 | [6 empty] | 2020-06-23 |  |  |  | 2020-06-23 |  |  |  |  | 2020-05-17 |  | 2020-05-27 |  |  | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-17 |  |  |  | 2020-06-24 |  | 4GT-42-340C-2NPT |  |  | 2020-07-06 |  | 2020-06-14 | [6 empty] | 2020-07-14 | 2020-07-21 | [20 empty] | 2020-08-20 |  |  |  | 2020-08-23 | [8 empty] | 2020-06-29 |  | 2020-07-02 |  |  | 2020-07-14 |  |  |  | 2020-07-17 |  |  | 2020-07-24 |  |  |  | 2020-07-27 |  |  | 2020-08-11 |  |  |  | 2020-08-23 |  | 2020-08-26
PH1200243 | 125.0918 | 6.2433 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Polomolok | Polo | MIN | PH126312024 | 23310 | 40 | Three Legged Tubular Tower | CO67 | 14.8833 | MIN-1200084 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2019-12-10 | 2019-12-10 | 2019-12-12 | 2019-12-11 |  |  |  | 2019-12-11 | 2019-12-12 |  |  |  | 2019-12-12 |  |  |  | 2019-12-17 | 2019-12-17 |  |  |  | 2019-12-17 | 2019-12-12 |  |  |  | 2019-12-12 | 2020-01-24 | 2020-01-16 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | DABC | Lot 109 X, Brgy. Cannery, Polomolok, General Santos City | South Cotabato | 125.0919 | 6.2434 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-01-23 |  |  | 2020-02-22 |  | 2020-01-30 | [16 empty] | 2020-02-20 |  |  | 2020-02-29 | [6 empty] | 2020-03-14 |  |  |  | 2020-03-14 |  |  |  |  | 2020-02-06 |  | 2020-02-16 |  |  | 2020-02-20 |  | 2020-02-23 |  |  | 2020-03-08 |  |  |  | 2020-03-15 |  | 4GT-42-340C-2NPT |  |  | 2020-03-27 |  | 2020-03-05 | [6 empty] | 2020-04-04 | 2020-04-11 | [20 empty] | 2020-05-11 |  |  |  | 2020-05-14 | [8 empty] | 2020-03-20 |  | 2020-03-23 |  |  | 2020-04-04 |  |  |  | 2020-04-07 |  |  | 2020-04-14 |  |  |  | 2020-04-17 |  |  | 2020-05-02 |  |  |  | 2020-05-14 |  | 2020-05-17
PH1200245 | 124.7558 | 6.3571 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Surallah | Libertad | MIN | PH126313003 | 10310 | 40 | Three Legged Tubular Tower | CO67 | 51.8913 | MIN-1200085 | Level 6 | phase2_add | phase3 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-23 |  | 2020-03-25 | [13 empty] | 2020-03-30 | [11 empty] | 2020-04-29 | [27 empty] | 2020-05-06 |  |  | 2020-06-05 |  | 2020-05-13 | [16 empty] | 2020-06-03 |  |  | 2020-06-12 | [6 empty] | 2020-06-26 |  |  |  | 2020-06-26 |  |  |  |  | 2020-05-20 |  | 2020-05-30 |  |  | 2020-06-03 |  | 2020-06-06 |  |  | 2020-06-20 |  |  |  | 2020-06-27 |  | 4GT-42-340C-2NPT |  |  | 2020-07-09 |  | 2020-06-17 | [6 empty] | 2020-07-17 | 2020-07-24 | [20 empty] | 2020-08-23 |  |  |  | 2020-08-26 | [8 empty] | 2020-07-02 |  | 2020-07-05 |  |  | 2020-07-17 |  |  |  | 2020-07-20 |  |  | 2020-07-27 |  |  |  | 2020-07-30 |  |  | 2020-08-14 |  |  |  | 2020-08-26 |  | 2020-08-29
PH1200249 | 124.5972 | 6.6137 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Isulan | Kalawag III | MIN | PH126504013 | 6407 | 40 | Three Legged Tubular Tower | CO68 | 77.8429 | MIN-1200086 | Level 6 | phase2_add | phase2_1231 |  | DICT_73 | Cluster M17 | Enovell | [7 empty] | 2020-04-10 |  | 2020-04-12 | [13 empty] | 2020-04-17 | [11 empty] | 2020-05-17 | [27 empty] | 2020-05-24 |  |  | 2020-06-23 |  | 2020-05-31 | [16 empty] | 2020-06-21 |  |  | 2020-06-30 | [6 empty] | 2020-07-14 |  |  |  | 2020-07-14 |  |  |  |  | 2020-06-07 |  | 2020-06-17 |  |  | 2020-06-21 |  | 2020-06-24 |  |  | 2020-07-08 |  |  |  | 2020-07-15 |  | 4GT-42-340C-2NPT |  |  | 2020-07-27 |  | 2020-07-05 | [6 empty] | 2020-08-04 | 2020-08-11 | [20 empty] | 2020-09-10 |  |  |  | 2020-09-13 | [8 empty] | 2020-07-20 |  | 2020-07-23 |  |  | 2020-08-04 |  |  |  | 2020-08-07 |  |  | 2020-08-14 |  |  |  | 2020-08-17 |  |  | 2020-09-01 |  |  |  | 2020-09-13 |  | 2020-09-16
PH1200251 | 124.5857 | 6.6543 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Isulan | Dansuli | MIN | PH126504010 | 2224 | 40 | Three Legged Tubular Tower | CO68 | 73.2953 | MIN-1200087 | Level 6 | phase2_add | phase2_1231 | OA_1231 |  | Cluster M17 | Enovell | [6 empty] | 2020-02-12 | 2020-04-13 |  | 2020-04-15 | [13 empty] | 2020-04-20 | [11 empty] | 2020-05-20 | [27 empty] | 2020-05-27 |  |  | 2020-06-26 |  | 2020-06-03 | [16 empty] | 2020-06-24 |  |  | 2020-07-03 | [6 empty] | 2020-07-17 |  |  |  | 2020-07-17 |  |  |  |  | 2020-06-10 |  | 2020-06-20 |  |  | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-11 |  |  |  | 2020-07-18 |  | 4GT-42-340C-2NPT |  |  | 2020-07-30 |  | 2020-07-08 | [6 empty] | 2020-08-07 | 2020-08-14 | [20 empty] | 2020-09-13 |  |  |  | 2020-09-16 | [8 empty] | 2020-07-23 |  | 2020-07-26 |  |  | 2020-08-07 |  |  |  | 2020-08-10 |  |  | 2020-08-17 |  |  |  | 2020-08-20 |  |  | 2020-09-04 |  |  |  | 2020-09-16 |  | 2020-09-19
PH1200260 | 125.0985 | 6.9507 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Makilala | New Cebu | MIN | PH124707029 | 10645 | 40 | Three Legged Tubular Tower | CO66 | 60.1356 | MIN-1200088 | Level 5 | phase3 | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-21 | 2020-01-20 | 2020-01-05 | 2020-01-22 | 2020-01-14 | 2020-02-01 |  |  | 2020-01-14 |  | 2020-02-03 |  |  | 2020-02-03 |  |  |  | 2020-01-27 |  | 2020-02-03 |  |  | 2020-02-03 | 2020-01-14 | 2020-02-01 |  |  | 2020-01-14 | 2020-02-24 | 2020-02-26 | [5 empty] | A | Lydia Morales | Purok 6, Poblacion Makilala | Cotabato (North Cotabato) | 125.0942 | 6.9588 | Greenfield |  |  | 10 years | P15,000 exclusive of VAT and withholding tax | quarterly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-04 |  |  | 2020-04-03 |  | 2020-03-11 | [11 empty] | 0909-8129207 |  |  |  |  | 2020-04-01 |  |  | 2020-04-10 | [6 empty] | 2020-04-24 |  |  |  | 2020-04-24 |  |  |  |  | 2020-03-18 |  | 2020-03-28 |  |  | 2020-04-01 |  | 2020-04-04 |  |  | 2020-04-18 |  |  |  | 2020-04-25 |  | 4GT-42-340C-2NPT |  |  | 2020-05-07 |  | 2020-04-15 | [6 empty] | 2020-05-15 | 2020-05-22 | [20 empty] | 2020-06-21 |  |  |  | 2020-06-24 | [8 empty] | 2020-04-30 |  | 2020-05-03 |  |  | 2020-05-15 |  |  |  | 2020-05-18 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-12 |  |  |  | 2020-06-24 |  | 2020-06-27
PH1200262 | 125.1437 | 6.9409 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Makilala | Malasila | MIN | PH124707001 | 2557 | 40 | Three Legged Tubular Tower | CO66 | 55.69 | MIN-1200089 | Level 5 | phase3 | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-21 | 2020-01-13 | 2020-01-07 | 2020-01-15 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-01-16 |  |  |  | 2020-01-16 |  |  |  | 2020-01-20 | 2020-01-15 |  |  |  | 2020-01-15 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-01-24 | 2020-02-19 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Lilia E. San Pedro | Purok Nangka, Malasila, Makilala | Cotabato (North Cotabato) | 125.1437 | 6.9408 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-26 | 2020-01-27 |  | 2020-03-27 |  | 2020-03-04 | [16 empty] | 2020-03-25 |  |  | 2020-04-03 | [6 empty] | 2020-04-17 |  |  |  | 2020-04-17 |  |  |  |  | 2020-03-11 | 2020-03-04 | 2020-03-21 |  |  | 2020-03-25 | 2020-03-07 | 2020-03-28 | 2020-03-11 |  | 2020-04-11 |  |  |  | 2020-04-18 |  | 4GT-42-340C-2NPT |  |  | 2020-04-30 |  | 2020-04-08 | [6 empty] | 2020-05-08 | 2020-05-15 | [20 empty] | 2020-06-14 |  |  |  | 2020-06-17 | [8 empty] | 2020-04-23 |  | 2020-04-26 |  |  | 2020-05-08 |  |  |  | 2020-05-11 |  |  | 2020-05-18 |  |  |  | 2020-05-21 |  |  | 2020-06-05 |  |  |  | 2020-06-17 |  | 2020-06-20
PH1200269 | 124.9342 | 6.9012 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | M'Lang | New Janiuay | MIN | PH124710028 | 2327 | 40 | Three Legged Tubular Tower | CO66 | 79.0817 | MIN-1200090 | Level 5 | phase2_add | phase3 | 630_M15 | DepEd_5079 | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  | Enovell |  | 2020-01-21 | 2020-01-14 | 2020-01-11 | 2020-01-16 | 2020-01-14 | 2020-02-01 |  |  | 2020-01-14 | 2020-01-14 |  |  |  | 2020-01-14 |  |  |  | 2020-01-21 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-01-14 | 2020-02-01 |  |  | 2020-01-14 | 2020-03-06 | 2020-02-20 | 2020-03-09 |  |  | 2020-03-09 |  | A | Nemesio /Angeles Porras | Purok Narra, New Rizal, Mlang | Cotabato (North Cotabato) | 124.9338 | 6.9023 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 225sqm | n/a | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-27 | 2020-02-01 |  | 2020-03-28 | 2020-02-20 | 2020-03-05 | [16 empty] | 2020-03-26 | ok |  | 2020-04-04 | [6 empty] | 2020-04-18 |  |  |  | 2020-04-18 |  |  |  | Awaiting NRAF approval | 2020-03-12 | 2020-03-09 | 2020-03-22 |  |  | 2020-03-26 | 2020-03-09 | 2020-03-29 | 2020-03-11 | 2020-03-11 | 2020-04-12 |  |  |  | 2020-04-19 |  | JGT-42-280C-2NPT（290KPH/D） |  |  | 2020-05-01 |  | 2020-04-09 | [6 empty] | 2020-05-09 | 2020-05-16 | [20 empty] | 2020-06-15 |  |  |  | 2020-06-18 | [8 empty] | 2020-04-24 |  | 2020-04-27 |  |  | 2020-05-09 |  |  |  | 2020-05-12 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-06-06 |  |  |  | 2020-06-18 |  | 2020-06-21
PH1200270 | 124.8869 | 6.9478 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | M'Lang | Bialong | MIN | PH124710031 | 5119 | 40 | Three Legged Tubular Tower | CO68 | 76.7168 | MIN-1200091 | Level 5 | phase2_add | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  | 2020-01-21 | 2020-01-14 | 2020-01-11 | 2020-01-16 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-01-14 |  |  |  | 2020-01-14 |  |  |  | 2020-01-21 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-03-06 | 2020-02-20 | 2020-03-06 |  |  | 2020-03-06 | 2020-03-06 | A | Alberta Tejada | Purok Maharlika, Bagontapay, Mlang | Cotabato (North Cotabato) | 124.8863 | 6.9477 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-27 | 2020-02-01 |  | 2020-03-28 | 2020-02-20 | 2020-03-05 | [16 empty] | 2020-03-26 | ok |  | 2020-04-04 | [6 empty] | 2020-04-18 |  |  |  | 2020-04-18 |  |  |  | For RFP submission in DingTalk | 2020-03-12 | 2020-03-10 | 2020-03-22 |  |  | 2020-03-26 | 2020-03-09 | 2020-03-29 |  |  | 2020-04-12 |  |  |  | 2020-04-19 |  | JGT-42-280C-2NPT（290KPH/D） |  |  | 2020-05-01 |  | 2020-04-09 | [6 empty] | 2020-05-09 | 2020-05-16 | [20 empty] | 2020-06-15 |  |  |  | 2020-06-18 | [8 empty] | 2020-04-24 |  | 2020-04-27 |  |  | 2020-05-09 |  |  |  | 2020-05-12 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-06-06 |  |  |  | 2020-06-18 |  | 2020-06-21
PH1200271 | 125.0613 | 6.2167 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Polomolok | Poblacion | MIN | PH126312016 | 12156 | 40 | Three Legged Tubular Tower | CO67 | 15.0012 | MIN-1200092 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DICT_25 | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | Enovell |  |  |  | 2019-12-12 | 2020-01-24 | 2020-01-18 | 2020-01-26 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-01-21 |  |  |  | 2020-01-21 |  |  |  | 2020-01-31 | 2020-01-21 |  |  |  | 2020-01-21 | 2020-01-20 |  |  |  | 2020-01-20 | 2020-02-24 | 2020-03-01 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | A | Lydia Deseo | J. Deseo Subd. Purok Bagtindon Brgy Magsaysay, polomolok | South Cotabato | 125.061 | 6.2158 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-08 |  |  | 2020-04-07 |  | 2020-03-15 | [16 empty] | 2020-04-05 |  |  | 2020-04-14 | [6 empty] | 2020-04-28 |  |  |  | 2020-04-28 |  |  |  |  | 2020-03-22 |  | 2020-04-01 |  |  | 2020-04-05 |  | 2020-04-08 |  |  | 2020-04-22 |  |  |  | 2020-04-29 |  | 4GT-42-340C-2NPT |  |  | 2020-05-11 |  | 2020-04-19 | [6 empty] | 2020-05-19 | 2020-05-26 | [20 empty] | 2020-06-25 |  |  |  | 2020-06-28 | [8 empty] | 2020-05-04 |  | 2020-05-07 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-05-29 |  |  |  | 2020-06-01 |  |  | 2020-06-16 |  |  |  | 2020-06-28 |  | 2020-07-01
PH1200274 | 124.8121 | 6.4812 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Koronadal City | Paraiso | MIN | PH126306015 | 5669 | 40 | Three Legged Tubular Tower | CO67 | 55.1833 | MIN-1200093 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-26 |  | 2020-03-28 | [13 empty] | 2020-04-02 | [11 empty] | 2020-05-02 | [27 empty] | 2020-05-09 |  |  | 2020-06-08 |  | 2020-05-16 | [16 empty] | 2020-06-06 |  |  | 2020-06-15 | [6 empty] | 2020-06-29 |  |  |  | 2020-06-29 |  |  |  |  | 2020-05-23 |  | 2020-06-02 |  |  | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-23 |  |  |  | 2020-06-30 |  | JGT-36-340C-2NPT |  |  | 2020-07-12 |  | 2020-06-20 | [6 empty] | 2020-07-20 | 2020-07-27 | [20 empty] | 2020-08-26 |  |  |  | 2020-08-29 | [8 empty] | 2020-07-05 |  | 2020-07-08 |  |  | 2020-07-20 |  |  |  | 2020-07-23 |  |  | 2020-07-30 |  |  |  | 2020-08-02 |  |  | 2020-08-17 |  |  |  | 2020-08-29 |  | 2020-09-01
PH1200283 | 124.8843 | 6.404 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Koronadal City | Sarabia (Bo. 8) | MIN | PH126306026 | 8935 | 40 | Three Legged Tubular Tower | CO67 | 43.4747 | MIN-1200094 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-03-29 |  | 2020-03-31 | [13 empty] | 2020-04-05 | [11 empty] | 2020-05-05 | [27 empty] | 2020-05-12 |  |  | 2020-06-11 |  | 2020-05-19 | [16 empty] | 2020-06-09 |  |  | 2020-06-18 | [6 empty] | 2020-07-02 |  |  |  | 2020-07-02 |  |  |  |  | 2020-05-26 |  | 2020-06-05 |  |  | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-26 |  |  |  | 2020-07-03 |  | JGT-36-340C-2NPT |  |  | 2020-07-15 |  | 2020-06-23 | [6 empty] | 2020-07-23 | 2020-07-30 | [20 empty] | 2020-08-29 |  |  |  | 2020-09-01 | [8 empty] | 2020-07-08 |  | 2020-07-11 |  |  | 2020-07-23 |  |  |  | 2020-07-26 |  |  | 2020-08-02 |  |  |  | 2020-08-05 |  |  | 2020-08-20 |  |  |  | 2020-09-01 |  | 2020-09-04
PH1200285 | 125.0852 | 6.1952 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Polomolok | Silway 8 | MIN | PH126312019 | 10447 | 40 | Monopole Tower | CO67 | 11.4454 | MIN-1200095 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | EGB |  | KASBEL |  | 2019-12-12 | 2019-11-29 | 2019-11-29 | 2019-12-01 | 2019-12-07 |  |  |  | 2019-12-07 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-06 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-11-28 | 2019-11-28 | 2019-12-06 |  | 2019-11-28 | 2020-01-24 | 2020-01-05 | 2020-01-09 |  |  | 2020-01-10 | 2020-02-04 | A | Brizel Daga-ang | Purok Mabuhay, Silway 8, Polomolok | South Cotabato | 125.0856 | 6.1956 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-12 |  |  | 2020-02-11 |  | 2020-01-19 | [16 empty] | 2020-02-09 |  |  | 2020-02-18 | [6 empty] | 2020-03-03 |  |  |  | 2020-03-03 |  |  |  |  | 2020-01-26 | 2020-02-27 | 2020-02-05 | 2020-03-10 | 2020-03-10 | 2020-02-09 | 2020-03-12 | 2020-02-12 | 2020-03-13 |  | 2020-02-26 |  |  |  | 2020-03-04 |  | JGT-36-340C-2NPT |  |  | 2020-03-16 |  | 2020-02-23 | [6 empty] | 2020-03-24 | 2020-03-31 | [20 empty] | 2020-04-30 |  |  |  | 2020-05-03 | [8 empty] | 2020-03-09 |  | 2020-03-12 |  |  | 2020-03-24 |  |  |  | 2020-03-27 |  |  | 2020-04-03 |  |  |  | 2020-04-06 |  |  | 2020-04-21 |  |  |  | 2020-05-03 |  | 2020-05-06
PH1200290 | 124.7908 | 6.4473 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Banga | San Vicente (Barrio 6) | MIN | PH126302022 | 6092 | 40 | Three Legged Tubular Tower | CO67 | 54.381 | MIN-1200096 | Level 6 | phase2_add | phase3 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-01 |  | 2020-04-03 | [13 empty] | 2020-04-08 | [11 empty] | 2020-05-08 | [27 empty] | 2020-05-15 |  |  | 2020-06-14 |  | 2020-05-22 | [16 empty] | 2020-06-12 |  |  | 2020-06-21 | [6 empty] | 2020-07-05 |  |  |  | 2020-07-05 |  |  |  |  | 2020-05-29 |  | 2020-06-08 |  |  | 2020-06-12 |  | 2020-06-15 |  |  | 2020-06-29 |  |  |  | 2020-07-06 |  | JGT-36-340C-2NPT |  |  | 2020-07-18 |  | 2020-06-26 | [6 empty] | 2020-07-26 | 2020-08-02 | [20 empty] | 2020-09-01 |  |  |  | 2020-09-04 | [8 empty] | 2020-07-11 |  | 2020-07-14 |  |  | 2020-07-26 |  |  |  | 2020-07-29 |  |  | 2020-08-05 |  |  |  | 2020-08-08 |  |  | 2020-08-23 |  |  |  | 2020-09-04 |  | 2020-09-07
PH1200314 | 124.9519 | 6.3331 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Tupi | Linan | MIN | PH126317013 | 15781 | 40 | Monopole Tower | CO67 | 32.6283 | MIN-1200097 | Level 6 | phase3 | phase3 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-04 |  | 2020-04-06 | [13 empty] | 2020-04-11 | [11 empty] | 2020-05-11 | [27 empty] | 2020-05-18 |  |  | 2020-06-17 |  | 2020-05-25 | [16 empty] | 2020-06-15 |  |  | 2020-06-24 | [6 empty] | 2020-07-08 |  |  |  | 2020-07-08 |  |  |  |  | 2020-06-01 |  | 2020-06-11 |  |  | 2020-06-15 |  | 2020-06-18 |  |  | 2020-07-02 |  |  |  | 2020-07-09 |  | JGT-36-340C-2NPT |  |  | 2020-07-21 |  | 2020-06-29 | [6 empty] | 2020-07-29 | 2020-08-05 | [20 empty] | 2020-09-04 |  |  |  | 2020-09-07 | [8 empty] | 2020-07-14 |  | 2020-07-17 |  |  | 2020-07-29 |  |  |  | 2020-08-01 |  |  | 2020-08-08 |  |  |  | 2020-08-11 |  |  | 2020-08-26 |  |  |  | 2020-09-07 |  | 2020-09-10
PH1200319 | 124.9205 | 6.3643 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Tupi | Bololmala | MIN | PH126317005 | 4214 | 40 | Monopole Tower | CO67 | 37.5277 | MIN-1200098 | Level 6 | phase2_add | phase2_1231 | P1_630 | DepEd_3474 | Cluster M17 | Enovell | PO2020011302PH_WLS | PO Batch 3 | Enovell |  |  |  |  | 2019-12-28 | 2019-12-28 | 2019-12-30 | 2019-12-29 |  |  |  | 2019-12-29 | 2019-12-30 |  |  |  | 2019-12-30 |  |  |  | 2020-01-04 | 2019-12-31 |  |  |  | 2019-12-31 | 2019-12-29 |  |  |  | 2019-12-29 | 2020-01-24 | 2020-02-03 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Araceli A. Claudio | Crossing Rubber, Purok 3, Tupi | South Cotabato | 124.9197 | 6.3644 | Greenfield |  |  | 15 years | P17,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-10 |  |  | 2020-03-11 |  | 2020-02-17 | [16 empty] | 2020-03-09 |  |  | 2020-03-18 | [6 empty] | 2020-04-01 |  |  |  | 2020-04-01 |  |  |  |  | 2020-02-24 | 2020-03-05 | 2020-03-05 | 2020-03-12 | 2020-03-12 | 2020-03-09 |  | 2020-03-12 |  |  | 2020-03-26 |  |  |  | 2020-04-02 |  | 4GT-42-340C-2NPT |  |  | 2020-04-14 |  | 2020-03-23 | [6 empty] | 2020-04-22 | 2020-04-29 | [20 empty] | 2020-05-29 |  |  |  | 2020-06-01 | [8 empty] | 2020-04-07 |  | 2020-04-10 |  |  | 2020-04-22 |  |  |  | 2020-04-25 |  |  | 2020-05-02 |  |  |  | 2020-05-05 |  |  | 2020-05-20 |  |  |  | 2020-06-01 |  | 2020-06-04
PH1200332 | 125.0665 | 6.0681 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | San Jose | MIN | PH126303024 | 11333 | 40 | Three Legged Tubular Tower | CO67 | 13.2541 | MIN-1200099 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_3607 | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | EGB |  | Mobicon |  | 2019-12-12 | 2019-12-07 | 2019-12-07 | 2019-12-09 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-09 |  |  |  | 2019-12-09 |  |  |  | 2019-12-14 | 2019-12-09 |  |  |  | 2019-12-09 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-12-27 | 2020-01-13 | 2020-01-03 |  |  | 2020-01-06 | 2020-01-15 | A | Georgie Villoria | Brgy. Shutter San Jose, General Santos City | South Cotabato | 125.0662 | 6.0684 | Greenfield |  |  | 15 years | P10,000 inclusive of VAT and withholding tax | monthly | 300sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-20 |  |  | 2020-02-19 |  | 2020-01-27 | [11 empty] | 0920-3023190 |  |  |  |  | 2020-02-17 |  |  | 2020-02-26 | [6 empty] | 2020-03-11 |  |  |  | 2020-03-11 |  |  |  |  | 2020-02-03 |  | 2020-02-13 |  |  | 2020-02-17 |  | 2020-02-20 |  |  | 2020-03-05 |  |  |  | 2020-03-12 |  | 4GT-42-340C-2NPT |  |  | 2020-03-24 |  | 2020-03-02 | [6 empty] | 2020-04-01 | 2020-04-08 | [20 empty] | 2020-05-08 |  |  |  | 2020-05-11 | [8 empty] | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-01 |  |  |  | 2020-04-04 |  |  | 2020-04-11 |  |  |  | 2020-04-14 |  |  | 2020-04-29 |  |  |  | 2020-05-11 |  | 2020-05-14
PH1200334 | 124.7018 | 6.6559 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Tacurong City | Calean | MIN | PH126511007 | 2439 | 40 | Three Legged Tubular Tower | CO67 | 77.6696 | MIN-1200100 | Level 6 | phase2_add | phase2_1231 |  | DepEd_3528 | Cluster M17 | Enovell | [7 empty] | 2020-04-16 |  | 2020-04-18 | [13 empty] | 2020-04-23 | [11 empty] | 2020-05-23 | [27 empty] | 2020-05-30 |  |  | 2020-06-29 |  | 2020-06-06 | [16 empty] | 2020-06-27 |  |  | 2020-07-06 | [6 empty] | 2020-07-20 |  |  |  | 2020-07-20 |  |  |  |  | 2020-06-13 |  | 2020-06-23 |  |  | 2020-06-27 |  | 2020-06-30 |  |  | 2020-07-14 |  |  |  | 2020-07-21 |  | 3GT-36-280C-2NPT |  |  | 2020-08-02 |  | 2020-07-11 | [6 empty] | 2020-08-10 | 2020-08-17 | [20 empty] | 2020-09-16 |  |  |  | 2020-09-19 | [8 empty] | 2020-07-26 |  | 2020-07-29 |  |  | 2020-08-10 |  |  |  | 2020-08-13 |  |  | 2020-08-20 |  |  |  | 2020-08-23 |  |  | 2020-09-07 |  |  |  | 2020-09-19 |  | 2020-09-22
PH1200340 | 124.8836 | 6.824 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Tulunan | Bual | MIN | PH124714022 | 4131 | 40 | Three Legged Tubular Tower | CO68 | 82.859 | MIN-1200101 | Level 5 | phase2_add | phase3 | M15 not 630 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 |  |  | Enovell |  | 2020-01-21 | 2020-01-09 | 2020-01-06 | 2020-01-11 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-01-14 |  |  |  | 2020-01-14 |  |  |  | 2020-01-16 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-03-06 | 2020-02-15 | 2020-03-06 |  |  | 2020-03-06 | 2020-03-06 | A | Romeo/Jose Pagaran | Purok 7B Sibsib , Tulunan | Cotabato (North Cotabato) | 124.8836 | 6.8237 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-22 | 2020-02-01 |  | 2020-03-23 | 2020-02-20 | 2020-02-29 | [16 empty] | 2020-03-21 | ok |  | 2020-03-30 | [6 empty] | 2020-04-13 |  |  |  | 2020-04-13 |  |  |  | For RFP submission in DingTalk | 2020-03-07 |  | 2020-03-17 |  |  | 2020-03-21 | 2020-03-12 | 2020-03-24 |  |  | 2020-04-07 |  |  |  | 2020-04-14 |  | JGT-42-280C-2NPT（290KPH/D） |  |  | 2020-04-26 |  | 2020-04-04 | [6 empty] | 2020-05-04 | 2020-05-11 | [20 empty] | 2020-06-10 |  |  |  | 2020-06-13 | [8 empty] | 2020-04-19 |  | 2020-04-22 |  |  | 2020-05-04 |  |  |  | 2020-05-07 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-06-01 |  |  |  | 2020-06-13 |  | 2020-06-16
PH1200342 | 124.6622 | 6.5216 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Norala | Poblacion | MIN | PH126311013 | 12592 | 40 | Three Legged Tubular Tower | CO67 | 70.6266 | MIN-1200102 | Level 6 | phase2_add | phase3 |  | DepEd_3622 | Cluster M17 | Enovell | [7 empty] | 2020-04-07 |  | 2020-04-09 | [13 empty] | 2020-04-14 | [11 empty] | 2020-05-14 | [27 empty] | 2020-05-21 |  |  | 2020-06-20 |  | 2020-05-28 | [16 empty] | 2020-06-18 |  |  | 2020-06-27 | [6 empty] | 2020-07-11 |  |  |  | 2020-07-11 |  |  |  |  | 2020-06-04 |  | 2020-06-14 |  |  | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-05 |  |  |  | 2020-07-12 |  | 4GT-42-340C-2NPT |  |  | 2020-07-24 |  | 2020-07-02 | [6 empty] | 2020-08-01 | 2020-08-08 | [20 empty] | 2020-09-07 |  |  |  | 2020-09-10 | [8 empty] | 2020-07-17 |  | 2020-07-20 |  |  | 2020-08-01 |  |  |  | 2020-08-04 |  |  | 2020-08-11 |  |  |  | 2020-08-14 |  |  | 2020-08-29 |  |  |  | 2020-09-10 |  | 2020-09-13
PH1200345 | 124.7993 | 6.5369 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Tantangan | Cabuling | MIN | PH126315008 | 4227 | 40 | Three Legged Tubular Tower | CO67 | 60.6363 | MIN-1200103 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-10 |  | 2020-04-12 | [13 empty] | 2020-04-17 | [11 empty] | 2020-05-17 | [27 empty] | 2020-05-24 |  |  | 2020-06-23 |  | 2020-05-31 | [16 empty] | 2020-06-21 |  |  | 2020-06-30 | [6 empty] | 2020-07-14 |  |  |  | 2020-07-14 |  |  |  |  | 2020-06-07 |  | 2020-06-17 |  |  | 2020-06-21 |  | 2020-06-24 |  |  | 2020-07-08 |  |  |  | 2020-07-15 |  | 4GT-42-340C-2NPT |  |  | 2020-07-27 |  | 2020-07-05 | [6 empty] | 2020-08-04 | 2020-08-11 | [20 empty] | 2020-09-10 |  |  |  | 2020-09-13 | [8 empty] | 2020-07-20 |  | 2020-07-23 |  |  | 2020-08-04 |  |  |  | 2020-08-07 |  |  | 2020-08-14 |  |  |  | 2020-08-17 |  |  | 2020-09-01 |  |  |  | 2020-09-13 |  | 2020-09-16
PH1200347 | 125.2372 | 7.4525 | Rural |  |  | Y4 |  | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Arakan | Anapolon | MIN | PH112402175 | [5 empty] | MIN-1200118 | Level 1 (OA) |  |  | PO Issued not 630 |  | Cluster M06 | EPC | PO2019122103PH_WLS | Batch 2 | [5 empty] | 2020-04-13 |  | 2020-04-15 | [13 empty] | 2020-04-20 | [11 empty] | 2020-05-20 | [27 empty] | 2020-05-27 |  |  | 2020-06-26 |  | 2020-06-03 | [16 empty] | 2020-06-24 |  |  | 2020-07-03 | [6 empty] | 2020-07-17 |  |  |  | 2020-07-17 |  |  |  |  | 2020-06-10 |  | 2020-06-20 |  |  | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-11 |  |  |  | 2020-07-18 |  |  |  |  | 2020-07-30 |  | 2020-07-08 | [6 empty] | 2020-08-07 | 2020-08-14 | [20 empty] | 2020-09-13 |  |  |  | 2020-09-16 | [8 empty] | 2020-07-23 |  | 2020-07-26 |  |  | 2020-08-07 |  |  |  | 2020-08-10 |  |  | 2020-08-17 |  |  |  | 2020-08-20 |  |  | 2020-09-04 |  |  |  | 2020-09-16 |  | 2020-09-19
PH1200350 | 124.9186 | 6.5234 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Koronadal City | San Jose (Bo. 5) | MIN | PH126306009 | 3871 | 40 | Three Legged Tubular Tower | CO67 | 51.4191 | MIN-1200104 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-13 |  | 2020-04-15 | [13 empty] | 2020-04-20 | [11 empty] | 2020-05-20 | [27 empty] | 2020-05-27 |  |  | 2020-06-26 |  | 2020-06-03 | [16 empty] | 2020-06-24 |  |  | 2020-07-03 | [6 empty] | 2020-07-17 |  |  |  | 2020-07-17 |  |  |  |  | 2020-06-10 |  | 2020-06-20 |  |  | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-11 |  |  |  | 2020-07-18 |  | 4GT-42-340C-2NPT |  |  | 2020-07-30 |  | 2020-07-08 | [6 empty] | 2020-08-07 | 2020-08-14 | [20 empty] | 2020-09-13 |  |  |  | 2020-09-16 | [8 empty] | 2020-07-23 |  | 2020-07-26 |  |  | 2020-08-07 |  |  |  | 2020-08-10 |  |  | 2020-08-17 |  |  |  | 2020-08-20 |  |  | 2020-09-04 |  |  |  | 2020-09-16 |  | 2020-09-19
PH1200358 | 124.6173 | 6.6312 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Isulan | Sampao | MIN | PH126504026 | 6076 | 40 | Three Legged Tubular Tower | CO68 | 77.3019 | MIN-1200105 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-19 |  | 2020-04-21 | [13 empty] | 2020-04-26 | [11 empty] | 2020-05-26 | [27 empty] | 2020-06-02 |  |  | 2020-07-02 |  | 2020-06-09 | [16 empty] | 2020-06-30 |  |  | 2020-07-09 | [6 empty] | 2020-07-23 |  |  |  | 2020-07-23 |  |  |  |  | 2020-06-16 |  | 2020-06-26 |  |  | 2020-06-30 |  | 2020-07-03 |  |  | 2020-07-17 |  |  |  | 2020-07-24 |  | 3GT-36-280C-2NPT |  |  | 2020-08-05 |  | 2020-07-14 | [6 empty] | 2020-08-13 | 2020-08-20 | [20 empty] | 2020-09-19 |  |  |  | 2020-09-22 | [8 empty] | 2020-07-29 |  | 2020-08-01 |  |  | 2020-08-13 |  |  |  | 2020-08-16 |  |  | 2020-08-23 |  |  |  | 2020-08-26 |  |  | 2020-09-10 |  |  |  | 2020-09-22 |  | 2020-09-25
PH1200368 | 125.2847 | 6.0619 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sarangani | Alabel | Kawas | MIN | PH128001006 | 6337 | 40 | Three Legged Tubular Tower | CO67 | 15.1667 | MIN-1200106 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-03-24 | 2020-01-13 | 2020-03-26 | 2020-02-09 |  |  |  | 2020-02-09 | 2020-02-11 |  |  |  | 2020-02-11 |  |  |  | 2020-03-31 | 2020-02-11 |  |  |  | 2020-02-11 | 2020-02-09 |  |  |  | 2020-02-09 |  | 2020-04-30 | [5 empty] | A |  |  |  | 125.2819 | 6.0631 | [16 empty] | 2020-05-07 |  |  | 2020-06-06 |  | 2020-05-14 | [16 empty] | 2020-06-04 |  |  | 2020-06-13 | [6 empty] | 2020-06-27 |  |  |  | 2020-06-27 |  |  |  |  | 2020-05-21 |  | 2020-05-31 |  |  | 2020-06-04 |  | 2020-06-07 |  |  | 2020-06-21 |  |  |  | 2020-06-28 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-07-10 |  | 2020-06-18 | [6 empty] | 2020-07-18 | 2020-07-25 | [20 empty] | 2020-08-24 |  |  |  | 2020-08-27 | [8 empty] | 2020-07-03 |  | 2020-07-06 |  |  | 2020-07-18 |  |  |  | 2020-07-21 |  |  | 2020-07-28 |  |  |  | 2020-07-31 |  |  | 2020-08-15 |  |  |  | 2020-08-27 |  | 2020-08-30
PH1200375 | 125.0108 | 6.2693 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Polomolok | Crossing Palkan | MIN | PH126312002 | 1967 | 40 | Three Legged Tubular Tower | CO67 | 23.0303 | MIN-1200107 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M17 | Enovell | PO2019122102PH_WLS | Batch 2 | EGB |  | KASBEL |  |  | 2019-11-28 | 2019-11-28 | 2019-11-30 | 2019-12-06 |  |  |  | 2019-12-06 | 2019-12-08 |  |  |  | 2019-12-08 |  |  |  | 2019-12-05 | 2019-12-08 |  |  |  | 2019-12-08 | 2019-11-28 | 2019-11-28 | 2019-11-28 |  | 2019-11-28 | 2019-12-23 | 2020-01-04 | 2019-12-27 |  |  | 2019-12-27 | 2020-01-15 | A | Camilo B. Cagande | P-2 Crossing Palkan, Polomolok | South Cotabato | 125.0114 | 6.2699 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 400sqm | 1 month | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-01-11 | 2020-02-01 |  | 2020-02-10 | 2020-02-13 | 2020-01-18 | [16 empty] | 2020-02-08 | ok |  | 2020-02-17 | [6 empty] | 2020-03-02 |  | 2020-03-02 | 2020-03-07 | 2020-03-02 | 2020-03-12 | 2020-03-10 | 2020-03-12 | Cheque released | 2020-01-25 | 2020-02-25 | 2020-02-04 | 2020-03-10 | 2020-03-10 | 2020-02-08 | 2020-03-12 | 2020-02-11 | 2020-03-13 | 2020-03-13 | 2020-02-25 |  |  |  | 2020-03-03 |  | 4GT-42-340C-2NPT |  |  | 2020-03-15 |  | 2020-02-22 | [6 empty] | 2020-03-23 | 2020-03-30 |  |  |  | 2020-03-02 |  | 2020-03-02 | [14 empty] | 2020-04-29 |  |  |  | 2020-05-02 | [7 empty] | 2020-02-27 | 2020-03-08 |  | 2020-03-11 |  |  | 2020-03-23 |  |  |  | 2020-03-26 |  |  | 2020-04-02 |  |  |  | 2020-04-05 |  |  | 2020-04-20 |  |  |  | 2020-05-02 |  | 2020-05-05
PH1200376 | 125.0407 | 6.9509 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Makilala | San Vicente | MIN | PH124707032 | 5973 | 40 | Three Legged Tubular Tower | CO66 | 66.2858 | MIN-1200108 | Level 5 | phase3 | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  |  | 2020-01-14 | 2020-01-06 | 2020-01-16 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-01-14 |  |  |  | 2020-01-14 |  |  |  | 2020-01-21 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-01-14 |  |  |  | 2020-01-14 | 2020-02-24 | 2020-02-20 | 2020-03-02 |  |  | 2020-03-02 | 2020-03-03 | A | Josefina Bautista | Purok 8, San Vicente, Makilala | Cotabato (North Cotabato) | 125.0393 | 6.9504 | Greenfield |  |  | 15 years | P12,000 inclusive of VAT and withholding tax | monthly | 225sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-27 |  |  | 2020-03-28 |  | 2020-03-05 | [16 empty] | 2020-03-26 |  |  | 2020-04-04 | [6 empty] | 2020-04-18 |  |  |  | 2020-04-18 |  |  |  |  | 2020-03-12 | 2020-03-06 | 2020-03-22 |  |  | 2020-03-26 |  | 2020-03-29 |  |  | 2020-04-12 |  |  |  | 2020-04-19 |  | 4GT-42-340C-2NPT |  |  | 2020-05-01 |  | 2020-04-09 | [6 empty] | 2020-05-09 | 2020-05-16 | [20 empty] | 2020-06-15 |  |  |  | 2020-06-18 | [8 empty] | 2020-04-24 |  | 2020-04-27 |  |  | 2020-05-09 |  |  |  | 2020-05-12 |  |  | 2020-05-19 |  |  |  | 2020-05-22 |  |  | 2020-06-06 |  |  |  | 2020-06-18 |  | 2020-06-21
PH1200382 | 125.1235 | 6.2219 | Rural | Rooftop | Rooftop | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Polomolok | Upper Klinan | MIN | PH126312022 | 3872 | 6 | Wall Mounted Pole | CO67 | 11.0561 | MIN-1200109 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) | EGB |  |  |  | 2019-12-12 | 2020-01-05 | 2020-01-04 | 2020-01-07 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-06 |  |  |  | 2020-01-06 |  |  |  | 2020-01-12 | 2020-01-06 |  |  |  | 2020-01-06 | 2020-01-05 |  |  |  | 2020-01-05 | 2020-01-24 | 2020-02-11 | 2020-01-23 |  |  | 2020-01-24 | 2020-02-06 | A | Alejo Z. Bercero, Sr. | Purok Makugihon, Upper Klinan, Polomolok | South Cotabato | 125.1235 | 6.2219 | Greenfield |  |  | 15 years | P15,000 inclusive of VAT and withholding tax | monthly | 300sqm | 3 months | n/a | 4.5% increase on the 4th year | [6 empty] | 2020-02-18 | 2020-02-28 |  | 2020-03-19 | 2020-03-09 | 2020-02-25 | [16 empty] | 2020-03-17 |  |  | 2020-03-26 | [6 empty] | 2020-04-09 |  |  |  | 2020-04-09 |  |  |  | Awaiting Lessor ID | 2020-03-03 | 2020-03-04 | 2020-03-13 |  |  | 2020-03-17 |  | 2020-03-20 |  |  | 2020-04-03 |  |  |  | 2020-04-10 |  | JGT-36-340C-2NPT |  |  | 2020-04-22 |  | 2020-03-31 | [6 empty] | 2020-04-30 | 2020-05-07 | [20 empty] | 2020-06-06 |  |  |  | 2020-06-09 | [8 empty] | 2020-04-15 |  | 2020-04-18 |  |  | 2020-04-30 |  |  |  | 2020-05-03 |  |  | 2020-05-10 |  |  |  | 2020-05-13 |  |  | 2020-05-28 |  |  |  | 2020-06-09 |  | 2020-06-12
PH1200386 | 124.8579 | 6.5609 | Rural | Rooftop | Rooftop | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Lutayan | Antong | MIN | PH126507010 | 8824 | 6 | Wall Mounted Pole | CO67 | 58.636 | MIN-1200110 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-16 |  | 2020-04-18 | [13 empty] | 2020-04-23 | [11 empty] | 2020-05-23 | [27 empty] | 2020-05-30 |  |  | 2020-06-29 |  | 2020-06-06 | [16 empty] | 2020-06-27 |  |  | 2020-07-06 | [6 empty] | 2020-07-20 |  |  |  | 2020-07-20 |  |  |  |  | 2020-06-13 |  | 2020-06-23 |  |  | 2020-06-27 |  | 2020-06-30 |  |  | 2020-07-14 |  |  |  | 2020-07-21 |  | 4GT-42-340C-2NPT |  |  | 2020-08-02 |  | 2020-07-11 | [6 empty] | 2020-08-10 | 2020-08-17 | [20 empty] | 2020-09-16 |  |  |  | 2020-09-19 | [8 empty] | 2020-07-26 |  | 2020-07-29 |  |  | 2020-08-10 |  |  |  | 2020-08-13 |  |  | 2020-08-20 |  |  |  | 2020-08-23 |  |  | 2020-09-07 |  |  |  | 2020-09-19 |  | 2020-09-22
PH1200388 | 124.9822 | 6.2979 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Tupi | Acmonan | MIN | PH126317014 | 6759 | 40 | Three Legged Tubular Tower | CO67 | 27.507 | MIN-1200111 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DICT_77 | Cluster M17 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  |  | 2019-12-30 | 2019-12-30 | 2020-01-01 | 2020-01-02 |  |  |  | 2020-01-02 | 2020-01-02 |  |  |  | 2020-01-02 |  |  |  | 2020-01-06 | [5 empty] | 2020-01-02 |  |  |  | 2020-01-02 |  | 2020-02-05 | [27 empty] | 2020-02-12 |  |  | 2020-03-13 |  | 2020-02-19 | [16 empty] | 2020-03-11 |  |  | 2020-03-20 | [6 empty] | 2020-04-03 |  |  |  | 2020-04-03 |  |  |  |  | 2020-02-26 |  | 2020-03-07 |  |  | 2020-03-11 |  | 2020-03-14 |  |  | 2020-03-28 |  |  |  | 2020-04-04 |  | 4GT-42-340C-2NPT |  |  | 2020-04-16 |  | 2020-03-25 | [6 empty] | 2020-04-24 | 2020-05-01 | [20 empty] | 2020-05-31 |  |  |  | 2020-06-03 | [8 empty] | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-24 |  |  |  | 2020-04-27 |  |  | 2020-05-04 |  |  |  | 2020-05-07 |  |  | 2020-05-22 |  |  |  | 2020-06-03 |  | 2020-06-06
PH1200410 | 124.7481 | 6.6206 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Tantangan | New Cuyapo | MIN | PH126315010 | 8040 | 40 | Three Legged Tubular Tower | CO67 | 71.3533 | MIN-1200112 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-22 |  | 2020-04-24 | [13 empty] | 2020-04-29 | [11 empty] | 2020-05-29 | [27 empty] | 2020-06-05 |  |  | 2020-07-05 |  | 2020-06-12 | [16 empty] | 2020-07-03 |  |  | 2020-07-12 | [6 empty] | 2020-07-26 |  |  |  | 2020-07-26 |  |  |  |  | 2020-06-19 |  | 2020-06-29 |  |  | 2020-07-03 |  | 2020-07-06 |  |  | 2020-07-20 |  |  |  | 2020-07-27 |  | 4GT-42-340C-2NPT |  |  | 2020-08-08 |  | 2020-07-17 | [6 empty] | 2020-08-16 | 2020-08-23 | [20 empty] | 2020-09-22 |  |  |  | 2020-09-25 | [8 empty] | 2020-08-01 |  | 2020-08-04 |  |  | 2020-08-16 |  |  |  | 2020-08-19 |  |  | 2020-08-26 |  |  |  | 2020-08-29 |  |  | 2020-09-13 |  |  |  | 2020-09-25 |  | 2020-09-28
PH1200419 | 124.8593 | 6.4387 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Koronadal City | San Isidro | MIN | PH126306001 | 2025 | 45 | Three Legged Tubular Tower | CO67 | 48.1502 | MIN-1200113 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-19 |  | 2020-04-21 | [13 empty] | 2020-04-26 | [11 empty] | 2020-05-26 | [27 empty] | 2020-06-02 |  |  | 2020-07-02 |  | 2020-06-09 | [16 empty] | 2020-06-30 |  |  | 2020-07-09 | [6 empty] | 2020-07-23 |  |  |  | 2020-07-23 |  |  |  |  | 2020-06-16 |  | 2020-06-26 |  |  | 2020-06-30 |  | 2020-07-03 |  |  | 2020-07-17 |  |  |  | 2020-07-24 |  | 4GT-42-340C-2NPT |  |  | 2020-08-05 |  | 2020-07-14 | [6 empty] | 2020-08-13 | 2020-08-20 | [20 empty] | 2020-09-19 |  |  |  | 2020-09-22 | [8 empty] | 2020-07-29 |  | 2020-08-01 |  |  | 2020-08-13 |  |  |  | 2020-08-16 |  |  | 2020-08-23 |  |  |  | 2020-08-26 |  |  | 2020-09-10 |  |  |  | 2020-09-22 |  | 2020-09-25
PH1200450 | 124.6135 | 6.4814 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Sultan Kudarat | Bagumbayan | Kinayao | MIN | PH126501006 | 2614 | 45 | Three Legged Tubular Tower | CO67 | 72.4737 | MIN-1200114 | Level 6 | phase2_add | phase3 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-22 |  | 2020-04-24 | [13 empty] | 2020-04-29 | [11 empty] | 2020-05-29 | [27 empty] | 2020-06-05 |  |  | 2020-07-05 |  | 2020-06-12 | [16 empty] | 2020-07-03 |  |  | 2020-07-12 | [6 empty] | 2020-07-26 |  |  |  | 2020-07-26 |  |  |  |  | 2020-06-19 |  | 2020-06-29 |  |  | 2020-07-03 |  | 2020-07-06 |  |  | 2020-07-20 |  |  |  | 2020-07-27 |  | 4GT-42-340C-2NPT |  |  | 2020-08-08 |  | 2020-07-17 | [6 empty] | 2020-08-16 | 2020-08-23 | [20 empty] | 2020-09-22 |  |  |  | 2020-09-25 | [8 empty] | 2020-08-01 |  | 2020-08-04 |  |  | 2020-08-16 |  |  |  | 2020-08-19 |  |  | 2020-08-26 |  |  |  | 2020-08-29 |  |  | 2020-09-13 |  |  |  | 2020-09-25 |  | 2020-09-28
PH1200453 | 125.1817 | 6.2639 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | General Santos City | Conel | MIN | PH126303006 | 11164 | 45 | Three Legged Tubular Tower | CO67 | 14.6866 | MIN-1200115 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M16 | Enovell | PO2019122102PH_WLS | Batch 2 (333) |  |  |  |  | 2019-12-12 | 2020-04-25 | 2020-01-13 | 2020-04-27 | [13 empty] | 2020-05-02 | [11 empty] | 2020-06-01 | [27 empty] | 2020-06-08 |  |  | 2020-07-08 |  | 2020-06-15 | [16 empty] | 2020-07-06 |  |  | 2020-07-15 | [6 empty] | 2020-07-29 |  |  |  | 2020-07-29 |  |  |  |  | 2020-06-22 |  | 2020-07-02 |  |  | 2020-07-06 |  | 2020-07-09 |  |  | 2020-07-23 |  |  |  | 2020-07-30 |  | 4GT-42-340C-2NPT |  |  | 2020-08-11 |  | 2020-07-20 | [6 empty] | 2020-08-19 | 2020-08-26 | [20 empty] | 2020-09-25 |  |  |  | 2020-09-28 | [8 empty] | 2020-08-04 |  | 2020-08-07 |  |  | 2020-08-19 |  |  |  | 2020-08-22 |  |  | 2020-08-29 |  |  |  | 2020-09-01 |  |  | 2020-09-16 |  |  |  | 2020-09-28 |  | 2020-10-01
PH1200477 | 124.8169 | 6.3685 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | South Cotabato | Banga | San Jose (Barrio 7) | MIN | PH126302021 | 4077 | 45 | Three Legged Tubular Tower | CO67 | 46.7796 | MIN-1200116 | Level 6 | phase2_add | phase3 |  |  | Cluster M17 | Enovell | [7 empty] | 2020-04-28 |  | 2020-04-30 | [13 empty] | 2020-05-05 | [11 empty] | 2020-06-04 | [27 empty] | 2020-06-11 |  |  | 2020-07-11 |  | 2020-06-18 | [16 empty] | 2020-07-09 |  |  | 2020-07-18 | [6 empty] | 2020-08-01 |  |  |  | 2020-08-01 |  |  |  |  | 2020-06-25 |  | 2020-07-05 |  |  | 2020-07-09 |  | 2020-07-12 |  |  | 2020-07-26 |  |  |  | 2020-08-02 |  | 4GT-42-340C-2NPT |  |  | 2020-08-14 |  | 2020-07-23 | [6 empty] | 2020-08-22 | 2020-08-29 | [20 empty] | 2020-09-28 |  |  |  | 2020-10-01 | [8 empty] | 2020-08-07 |  | 2020-08-10 |  |  | 2020-08-22 |  |  |  | 2020-08-25 |  |  | 2020-09-01 |  |  |  | 2020-09-04 |  |  | 2020-09-19 |  |  |  | 2020-10-01 |  | 2020-10-04
PH1200513 | 124.9982 | 6.9884 | Rural | Greenfield | Greenfield | Y1 | L7 | SOCCSKSARGEN (Region XII) | Cotabato (North Cotabato) | Kidapawan City | Junction | MIN | PH124704011 | 1457 | 45 | Three Legged Tubular Tower | CO66 | 69.9952 | MIN-1200117 | Level 5 | phase3 | phase3 | 630_M15 |  | Cluster M15 | Enovell | PO2019122102PH_WLS | Batch 2 | Enovell |  |  |  |  | 2020-01-21 | 2020-01-05 | 2020-01-23 | 2020-01-23 |  |  |  | 2020-01-23 | 2020-02-26 |  |  |  | 2020-02-26 |  |  |  | 2020-01-28 | 2020-02-26 |  |  |  | 2020-02-26 | 2020-01-23 |  |  |  | 2020-01-23 |  | 2020-02-27 | [9 empty] | 124.8215 | 7.1122 | [16 empty] | 2020-03-05 |  |  | 2020-04-04 |  | 2020-03-12 | [16 empty] | 2020-04-02 | ok |  | 2020-04-11 | [6 empty] | 2020-04-25 |  |  |  | 2020-04-25 |  |  |  |  | 2020-03-19 |  | 2020-03-29 |  |  | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-19 |  |  |  | 2020-04-26 |  | 4GT-42-340C-2NPT |  |  | 2020-05-08 |  | 2020-04-16 | [6 empty] | 2020-05-16 | 2020-05-23 | [20 empty] | 2020-06-22 |  |  |  | 2020-06-25 | [8 empty] | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-16 |  |  |  | 2020-05-19 |  |  | 2020-05-26 |  |  |  | 2020-05-29 |  |  | 2020-06-13 |  |  |  | 2020-06-25 |  | 2020-06-28
PH1500002 | 121.9753 | 6.7056 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Basilan | Isabela City | Seaside | MIN | PH099701044 | 951 | 30 | Three Legged Tubular Tower | CO69 | 26.7656 | MIN-1500001 | Level 6 | phase3 | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-03-05 |  | 2020-03-07 | [13 empty] | 2020-03-12 | [11 empty] | 2020-04-11 | [27 empty] | 2020-04-18 |  |  | 2020-05-18 |  | 2020-04-25 | [16 empty] | 2020-05-16 |  |  | 2020-05-25 | [6 empty] | 2020-06-08 |  |  |  | 2020-06-08 |  |  |  |  | 2020-05-02 |  | 2020-05-12 |  |  | 2020-05-16 |  | 2020-05-19 |  |  | 2020-06-02 |  |  |  | 2020-06-09 |  | ZCG-12-280C-1NPT |  |  | 2020-06-21 |  | 2020-05-30 | [6 empty] | 2020-06-29 | 2020-07-06 | [20 empty] | 2020-08-05 |  |  |  | 2020-08-08 | [8 empty] | 2020-06-14 |  | 2020-06-17 |  |  | 2020-06-29 |  |  |  | 2020-07-02 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-27 |  |  |  | 2020-08-08 |  | 2020-08-11
PH1500003 | 124.2331 | 7.2026 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Cotabato City | Rosary Heights IX | MIN | PH129804029 | 15732 | 15 | Pole | CO68 | 2.8382 | MIN-1500002 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-03-25 |  | 2020-03-27 | [13 empty] | 2020-04-01 | [11 empty] | 2020-05-01 | [27 empty] | 2020-05-08 |  |  | 2020-06-07 |  | 2020-05-15 | [16 empty] | 2020-06-05 |  |  | 2020-06-14 | [6 empty] | 2020-06-28 |  |  |  | 2020-06-28 |  |  |  |  | 2020-05-22 |  | 2020-06-01 |  |  | 2020-06-05 |  | 2020-06-08 |  |  | 2020-06-22 |  |  |  | 2020-06-29 |  | ZCG-12-280C-1NPT |  |  | 2020-07-11 |  | 2020-06-19 | [6 empty] | 2020-07-19 | 2020-07-26 | [20 empty] | 2020-08-25 |  |  |  | 2020-08-28 | [8 empty] | 2020-07-04 |  | 2020-07-07 |  |  | 2020-07-19 |  |  |  | 2020-07-22 |  |  | 2020-07-29 |  |  |  | 2020-08-01 |  |  | 2020-08-16 |  |  |  | 2020-08-28 |  | 2020-08-31
PH1500008 | 124.2457 | 7.2098 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Cotabato City | Rosary Heights III | MIN | PH129804004 | 13943 | 30 | Monopole Tower | CO68 | 1.4688 | MIN-1500003 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 | DepEd_3751 | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-03-28 |  | 2020-03-30 | [13 empty] | 2020-04-04 | [11 empty] | 2020-05-04 | [27 empty] | 2020-05-11 |  |  | 2020-06-10 |  | 2020-05-18 | [16 empty] | 2020-06-08 |  |  | 2020-06-17 | [6 empty] | 2020-07-01 |  |  |  | 2020-07-01 |  |  |  |  | 2020-05-25 |  | 2020-06-04 |  |  | 2020-06-08 |  | 2020-06-11 |  |  | 2020-06-25 |  |  |  | 2020-07-02 |  | 3GT-30-280C-2NPT |  |  | 2020-07-14 |  | 2020-06-22 | [6 empty] | 2020-07-22 | 2020-07-29 | [20 empty] | 2020-08-28 |  |  |  | 2020-08-31 | [8 empty] | 2020-07-07 |  | 2020-07-10 |  |  | 2020-07-22 |  |  |  | 2020-07-25 |  |  | 2020-08-01 |  |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  |  | 2020-08-31 |  | 2020-09-03
PH1500010 | 124.2457 | 7.1953 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Cotabato City | Tamontaka III | MIN | PH129804026 | 9257 | 15 | Pole | CO68 | 3.0515 | MIN-1500004 | Level 5 | phase2_add | phase3 | PO Issued not 630 |  | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-03-31 |  | 2020-04-02 | [13 empty] | 2020-04-07 | [11 empty] | 2020-05-07 | [27 empty] | 2020-05-14 |  |  | 2020-06-13 |  | 2020-05-21 | [16 empty] | 2020-06-11 |  |  | 2020-06-20 | [6 empty] | 2020-07-04 |  |  |  | 2020-07-04 |  |  |  |  | 2020-05-28 |  | 2020-06-07 |  |  | 2020-06-11 |  | 2020-06-14 |  |  | 2020-06-28 |  |  |  | 2020-07-05 |  | ZCG-12-280C-1NPT |  |  | 2020-07-17 |  | 2020-06-25 | [6 empty] | 2020-07-25 | 2020-08-01 | [20 empty] | 2020-08-31 |  |  |  | 2020-09-03 | [8 empty] | 2020-07-10 |  | 2020-07-13 |  |  | 2020-07-25 |  |  |  | 2020-07-28 |  |  | 2020-08-04 |  |  |  | 2020-08-07 |  |  | 2020-08-22 |  |  |  | 2020-09-03 |  | 2020-09-06
PH1500011 | 124.252 | 7.2206 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Cotabato City | Kalanganan | MIN | PH129804014 | 6456 | 30 | Monopole Tower | CO68 | 0.37737 | MIN-1500005 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-04-03 |  | 2020-04-05 | [13 empty] | 2020-04-10 | [11 empty] | 2020-05-10 | [27 empty] | 2020-05-17 |  |  | 2020-06-16 |  | 2020-05-24 | [16 empty] | 2020-06-14 |  |  | 2020-06-23 | [6 empty] | 2020-07-07 |  |  |  | 2020-07-07 |  |  |  |  | 2020-05-31 |  | 2020-06-10 |  |  | 2020-06-14 |  | 2020-06-17 |  |  | 2020-07-01 |  |  |  | 2020-07-08 |  | 3GT-30-280C-2NPT |  |  | 2020-07-20 |  | 2020-06-28 | [6 empty] | 2020-07-28 | 2020-08-04 | [20 empty] | 2020-09-03 |  |  |  | 2020-09-06 | [8 empty] | 2020-07-13 |  | 2020-07-16 |  |  | 2020-07-28 |  |  |  | 2020-07-31 |  |  | 2020-08-07 |  |  |  | 2020-08-10 |  |  | 2020-08-25 |  |  |  | 2020-09-06 |  | 2020-09-09
PH1500022 | 121.9575 | 6.6942 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Basilan | Isabela City | Tabuk | MIN | PH099701047 | 6529 | 40 | Three Legged Tubular Tower | CO69 | 28.7841 | MIN-1500006 | Level 6 | phase3 | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-03-08 |  | 2020-03-10 | [13 empty] | 2020-03-15 | [11 empty] | 2020-04-14 | [27 empty] | 2020-04-21 |  |  | 2020-05-21 |  | 2020-04-28 | [16 empty] | 2020-05-19 |  |  | 2020-05-28 | [6 empty] | 2020-06-11 |  |  |  | 2020-06-11 |  |  |  |  | 2020-05-05 |  | 2020-05-15 |  |  | 2020-05-19 |  | 2020-05-22 |  |  | 2020-06-05 |  |  |  | 2020-06-12 |  | JGT-36-280C-2NPT |  |  | 2020-06-24 |  | 2020-06-02 | [6 empty] | 2020-07-02 | 2020-07-09 | [20 empty] | 2020-08-08 |  |  |  | 2020-08-11 | [8 empty] | 2020-06-17 |  | 2020-06-20 |  |  | 2020-07-02 |  |  |  | 2020-07-05 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-30 |  |  |  | 2020-08-11 |  | 2020-08-14
PH1500024 | 122.1326 | 6.6516 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Basilan | Lamitan City | Limo-Ok | MIN | PH150702068 | 2169 | 40 | Three Legged Tubular Tower | CO69 | 30.6861 | MIN-1500007 | Level 6 | phase3 | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-03-11 |  | 2020-03-13 | [13 empty] | 2020-03-18 | [11 empty] | 2020-04-17 | [27 empty] | 2020-04-24 |  |  | 2020-05-24 |  | 2020-05-01 | [16 empty] | 2020-05-22 |  |  | 2020-05-31 | [6 empty] | 2020-06-14 |  |  |  | 2020-06-14 |  |  |  |  | 2020-05-08 |  | 2020-05-18 |  |  | 2020-05-22 |  | 2020-05-25 |  |  | 2020-06-08 |  |  |  | 2020-06-15 |  | JGT-36-280C-2NPT |  |  | 2020-06-27 |  | 2020-06-05 | [6 empty] | 2020-07-05 | 2020-07-12 | [20 empty] | 2020-08-11 |  |  |  | 2020-08-14 | [8 empty] | 2020-06-20 |  | 2020-06-23 |  |  | 2020-07-05 |  |  |  | 2020-07-08 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-08-02 |  |  |  | 2020-08-14 |  | 2020-08-17
PH1500025 | 122.1377 | 6.6613 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Basilan | Lamitan City | Malakas | MIN | PH150702066 | 2676 | 40 | Monopole Tower | CO69 | 29.7403 | MIN-1500008 | Level 6 | phase3 | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-03-14 |  | 2020-03-16 | [13 empty] | 2020-03-21 | [11 empty] | 2020-04-20 | [27 empty] | 2020-04-27 |  |  | 2020-05-27 |  | 2020-05-04 | [16 empty] | 2020-05-25 |  |  | 2020-06-03 | [6 empty] | 2020-06-17 |  |  |  | 2020-06-17 |  |  |  |  | 2020-05-11 |  | 2020-05-21 |  |  | 2020-05-25 |  | 2020-05-28 |  |  | 2020-06-11 |  |  |  | 2020-06-18 |  | JGT-36-280C-2NPT |  |  | 2020-06-30 |  | 2020-06-08 | [6 empty] | 2020-07-08 | 2020-07-15 | [20 empty] | 2020-08-14 |  |  |  | 2020-08-17 | [8 empty] | 2020-06-23 |  | 2020-06-26 |  |  | 2020-07-08 |  |  |  | 2020-07-11 |  |  | 2020-07-18 |  |  |  | 2020-07-21 |  |  | 2020-08-05 |  |  |  | 2020-08-17 |  | 2020-08-20
PH1500029 | 124.2239 | 7.1841 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Cotabato City | Rosary Heights XIII | MIN | PH129804005 | 12027 | 40 | Three Legged Tubular Tower | CO68 | 5.1072 | MIN-1500009 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-04-06 |  | 2020-04-08 | [13 empty] | 2020-04-13 | [11 empty] | 2020-05-13 | [27 empty] | 2020-05-20 |  |  | 2020-06-19 |  | 2020-05-27 | [16 empty] | 2020-06-17 |  |  | 2020-06-26 | [6 empty] | 2020-07-10 |  |  |  | 2020-07-10 |  |  |  |  | 2020-06-03 |  | 2020-06-13 |  |  | 2020-06-17 |  | 2020-06-20 |  |  | 2020-07-04 |  |  |  | 2020-07-11 |  | JGT-36-280C-2NPT |  |  | 2020-07-23 |  | 2020-07-01 | [6 empty] | 2020-07-31 | 2020-08-07 | [20 empty] | 2020-09-06 |  |  |  | 2020-09-09 | [8 empty] | 2020-07-16 |  | 2020-07-19 |  |  | 2020-07-31 |  |  |  | 2020-08-03 |  |  | 2020-08-10 |  |  |  | 2020-08-13 |  |  | 2020-08-28 |  |  |  | 2020-09-09 |  | 2020-09-12
PH1500032 | 124.2323 | 7.2209 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Cotabato City | Poblacion II | MIN | PH129804006 | 9206 | 40 | Three Legged Tubular Tower | CO68 | 1.8664 | MIN-1500010 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-04-09 |  | 2020-04-11 | [13 empty] | 2020-04-16 | [11 empty] | 2020-05-16 | [27 empty] | 2020-05-23 |  |  | 2020-06-22 |  | 2020-05-30 | [16 empty] | 2020-06-20 |  |  | 2020-06-29 | [6 empty] | 2020-07-13 |  |  |  | 2020-07-13 |  |  |  |  | 2020-06-06 |  | 2020-06-16 |  |  | 2020-06-20 |  | 2020-06-23 |  |  | 2020-07-07 |  |  |  | 2020-07-14 |  | JGT-36-280C-2NPT |  |  | 2020-07-26 |  | 2020-07-04 | [6 empty] | 2020-08-03 | 2020-08-10 | [20 empty] | 2020-09-09 |  |  |  | 2020-09-12 | [8 empty] | 2020-07-19 |  | 2020-07-22 |  |  | 2020-08-03 |  |  |  | 2020-08-06 |  |  | 2020-08-13 |  |  |  | 2020-08-16 |  |  | 2020-08-31 |  |  |  | 2020-09-12 |  | 2020-09-15
PH1500035 | 124.2421 | 7.2265 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Cotabato City | Poblacion I | MIN | PH129804001 | 18137 | 40 | Three Legged Tubular Tower | CO68 | 0.89473 | MIN-1500011 | Level 5 | phase2_add | phase3 | PO Issued not 630 |  | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-04-12 |  | 2020-04-14 | [13 empty] | 2020-04-19 | [11 empty] | 2020-05-19 | [27 empty] | 2020-05-26 |  |  | 2020-06-25 |  | 2020-06-02 | [16 empty] | 2020-06-23 |  |  | 2020-07-02 | [6 empty] | 2020-07-16 |  |  |  | 2020-07-16 |  |  |  |  | 2020-06-09 |  | 2020-06-19 |  |  | 2020-06-23 |  | 2020-06-26 |  |  | 2020-07-10 |  |  |  | 2020-07-17 |  | JGT-36-280C-2NPT |  |  | 2020-07-29 |  | 2020-07-07 | [6 empty] | 2020-08-06 | 2020-08-13 | [20 empty] | 2020-09-12 |  |  |  | 2020-09-15 | [8 empty] | 2020-07-22 |  | 2020-07-25 |  |  | 2020-08-06 |  |  |  | 2020-08-09 |  |  | 2020-08-16 |  |  |  | 2020-08-19 |  |  | 2020-09-03 |  |  |  | 2020-09-15 |  | 2020-09-18
PH1500036 | 124.254 | 7.9946 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Lanao Del Sur | Marawi City | Poona Marantao | MIN | PH153617039 | 6516 | 40 | Monopole Tower | CO68 | 85.8478 | MIN-1500012 | Level 6 | phase2_add | phase3 |  |  | Cluster M26 | Enovell | [7 empty] | 2020-03-12 |  | 2020-03-14 | [13 empty] | 2020-03-19 | [11 empty] | 2020-04-18 | [27 empty] | 2020-04-25 |  |  | 2020-05-25 |  | 2020-05-02 | [16 empty] | 2020-05-23 |  |  | 2020-06-01 | [6 empty] | 2020-06-15 |  |  |  | 2020-06-15 |  |  |  |  | 2020-05-09 |  | 2020-05-19 |  |  | 2020-05-23 |  | 2020-05-26 |  |  | 2020-06-09 |  |  |  | 2020-06-16 |  | JGT-36-280C-2NPT |  |  | 2020-06-28 |  | 2020-06-06 | [6 empty] | 2020-07-06 | 2020-07-13 | [20 empty] | 2020-08-12 |  |  |  | 2020-08-15 | [8 empty] | 2020-06-21 |  | 2020-06-24 |  |  | 2020-07-06 |  |  |  | 2020-07-09 |  |  | 2020-07-16 |  |  |  | 2020-07-19 |  |  | 2020-08-03 |  |  |  | 2020-08-15 |  | 2020-08-18
PH1500039 | 124.2633 | 7.2378 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Sultan Kudarat (Nuling) | Salimbao | MIN | PH153812006 | 7503 | 40 | Monopole Tower | CO68 | 2.3006 | MIN-1500013 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-04-15 |  | 2020-04-17 | [13 empty] | 2020-04-22 | [11 empty] | 2020-05-22 | [27 empty] | 2020-05-29 |  |  | 2020-06-28 |  | 2020-06-05 | [16 empty] | 2020-06-26 |  |  | 2020-07-05 | [6 empty] | 2020-07-19 |  |  |  | 2020-07-19 |  |  |  |  | 2020-06-12 |  | 2020-06-22 |  |  | 2020-06-26 |  | 2020-06-29 |  |  | 2020-07-13 |  |  |  | 2020-07-20 |  | JGT-36-280C-2NPT |  |  | 2020-08-01 |  | 2020-07-10 | [6 empty] | 2020-08-09 | 2020-08-16 | [20 empty] | 2020-09-15 |  |  |  | 2020-09-18 | [8 empty] | 2020-07-25 |  | 2020-07-28 |  |  | 2020-08-09 |  |  |  | 2020-08-12 |  |  | 2020-08-19 |  |  |  | 2020-08-22 |  |  | 2020-09-06 |  |  |  | 2020-09-18 |  | 2020-09-21
PH1500041 | 124.2739 | 8.003 | Suburban | Rooftop | Rooftop | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Lanao Del Sur | Lake | Lake | MIN | PH153617066 | 2827 | 15 | Pole | CO68 | 86.827 | MIN-1500014 | Level 6 | phase2_add | phase3 |  |  | Cluster M26 | Enovell | [7 empty] | 2020-03-15 |  | 2020-03-17 | [13 empty] | 2020-03-22 | [11 empty] | 2020-04-21 | [27 empty] | 2020-04-28 |  |  | 2020-05-28 |  | 2020-05-05 | [16 empty] | 2020-05-26 |  |  | 2020-06-04 | [6 empty] | 2020-06-18 |  |  |  | 2020-06-18 |  |  |  |  | 2020-05-12 |  | 2020-05-22 |  |  | 2020-05-26 |  | 2020-05-29 |  |  | 2020-06-12 |  |  |  | 2020-06-19 |  | ZCG-9-340D-1NPT |  |  | 2020-07-01 |  | 2020-06-09 | [6 empty] | 2020-07-09 | 2020-07-16 | [20 empty] | 2020-08-15 |  |  |  | 2020-08-18 | [8 empty] | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-19 |  |  |  | 2020-07-22 |  |  | 2020-08-06 |  |  |  | 2020-08-18 |  | 2020-08-21
PH1500042 | 124.2833 | 8.0113 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Lanao Del Sur | Marawi City | Norhaya Village | MIN | PH153617072 | 3508 | 40 | Three Legged Tubular Tower | CO68 | 87.7871 | MIN-1500015 | Level 6 | phase2_add | phase3 |  | AFP_2 | Cluster M26 | Enovell | [7 empty] | 2020-03-18 |  | 2020-03-20 | [13 empty] | 2020-03-25 | [11 empty] | 2020-04-24 | [27 empty] | 2020-05-01 |  |  | 2020-05-31 |  | 2020-05-08 | [16 empty] | 2020-05-29 |  |  | 2020-06-07 | [6 empty] | 2020-06-21 |  |  |  | 2020-06-21 |  |  |  |  | 2020-05-15 |  | 2020-05-25 |  |  | 2020-05-29 |  | 2020-06-01 |  |  | 2020-06-15 |  |  |  | 2020-06-22 |  | JGT-36-280C-2NPT |  |  | 2020-07-04 |  | 2020-06-12 | [6 empty] | 2020-07-12 | 2020-07-19 | [20 empty] | 2020-08-18 |  |  |  | 2020-08-21 | [8 empty] | 2020-06-27 |  | 2020-06-30 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-22 |  |  |  | 2020-07-25 |  |  | 2020-08-09 |  |  |  | 2020-08-21 |  | 2020-08-24
PH1500046 | 124.3028 | 8.0113 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Lanao Del Sur | Marawi City | Bubonga Cadayonan | MIN | PH153617097 | 1862 | 40 | Three Legged Tubular Tower | CO68 | 87.8985 | MIN-1500016 | Level 6 | phase2_add | phase3 |  |  | Cluster M26 | Enovell | [7 empty] | 2020-03-21 |  | 2020-03-23 | [13 empty] | 2020-03-28 | [11 empty] | 2020-04-27 | [27 empty] | 2020-05-04 |  |  | 2020-06-03 |  | 2020-05-11 | [16 empty] | 2020-06-01 |  |  | 2020-06-10 | [6 empty] | 2020-06-24 |  |  |  | 2020-06-24 |  |  |  |  | 2020-05-18 |  | 2020-05-28 |  |  | 2020-06-01 |  | 2020-06-04 |  |  | 2020-06-18 |  |  |  | 2020-06-25 |  | JGT-36-280C-2NPT |  |  | 2020-07-07 |  | 2020-06-15 | [6 empty] | 2020-07-15 | 2020-07-22 | [20 empty] | 2020-08-21 |  |  |  | 2020-08-24 | [8 empty] | 2020-06-30 |  | 2020-07-03 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-07-25 |  |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  |  | 2020-08-24 |  | 2020-08-27
PH1500047 | 124.3028 | 8 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Autonomous Region of Muslim Mindanao (ARMM) | Lanao Del Sur | Lake | Lake | MIN | PH153617051 | 2438 | 40 | Three Legged Tubular Tower | CO68 | 86.6543 | MIN-1500017 | Level 6 | phase2_add | phase3 |  |  | Cluster M26 | Enovell | [7 empty] | 2020-03-24 |  | 2020-03-26 | [13 empty] | 2020-03-31 | [11 empty] | 2020-04-30 | [27 empty] | 2020-05-07 |  |  | 2020-06-06 |  | 2020-05-14 | [16 empty] | 2020-06-04 |  |  | 2020-06-13 | [6 empty] | 2020-06-27 |  |  |  | 2020-06-27 |  |  |  |  | 2020-05-21 |  | 2020-05-31 |  |  | 2020-06-04 |  | 2020-06-07 |  |  | 2020-06-21 |  |  |  | 2020-06-28 |  | JGT-36-280C-2NPT |  |  | 2020-07-10 |  | 2020-06-18 | [6 empty] | 2020-07-18 | 2020-07-25 | [20 empty] | 2020-08-24 |  |  |  | 2020-08-27 | [8 empty] | 2020-07-03 |  | 2020-07-06 |  |  | 2020-07-18 |  |  |  | 2020-07-21 |  |  | 2020-07-28 |  |  |  | 2020-07-31 |  |  | 2020-08-15 |  |  |  | 2020-08-27 |  | 2020-08-30
PH1500054 | 122.1072 | 6.6586 | Rural | Greenfield | Greenfield | Y1 | L7 | Autonomous Region of Muslim Mindanao (ARMM) | Basilan | Lamitan City | Ubit | MIN | PH150702050 | 1648 | 40 | Three Legged Tubular Tower | CO69 | 29.5064 | MIN-1500018 | Level 6 | phase3 | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-03-17 |  | 2020-03-19 | [13 empty] | 2020-03-24 | [11 empty] | 2020-04-23 | [27 empty] | 2020-04-30 |  |  | 2020-05-30 |  | 2020-05-07 | [16 empty] | 2020-05-28 |  |  | 2020-06-06 | [6 empty] | 2020-06-20 |  |  |  | 2020-06-20 |  |  |  |  | 2020-05-14 |  | 2020-05-24 |  |  | 2020-05-28 |  | 2020-05-31 |  |  | 2020-06-14 |  |  |  | 2020-06-21 |  | JGT-42-280C-2NPT |  |  | 2020-07-03 |  | 2020-06-11 | [6 empty] | 2020-07-11 | 2020-07-18 | [20 empty] | 2020-08-17 |  |  |  | 2020-08-20 | [8 empty] | 2020-06-26 |  | 2020-06-29 |  |  | 2020-07-11 |  |  |  | 2020-07-14 |  |  | 2020-07-21 |  |  |  | 2020-07-24 |  |  | 2020-08-08 |  |  |  | 2020-08-20 |  | 2020-08-23
PH1500061 | 124.2142 | 7.2435 | Rural | Greenfield | Greenfield | Y1 | L7 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Cotabato City | Poblacion V | MIN | PH129804002 | 15019 | 40 | Three Legged Tubular Tower | CO68 | 4.5056 | MIN-1500019 | Level 5 | phase2_add | phase3 | PO Issued not 630 |  | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-04-18 |  | 2020-04-20 | [13 empty] | 2020-04-25 | [11 empty] | 2020-05-25 | [27 empty] | 2020-06-01 |  |  | 2020-07-01 |  | 2020-06-08 | [16 empty] | 2020-06-29 |  |  | 2020-07-08 | [6 empty] | 2020-07-22 |  |  |  | 2020-07-22 |  |  |  |  | 2020-06-15 |  | 2020-06-25 |  |  | 2020-06-29 |  | 2020-07-02 |  |  | 2020-07-16 |  |  |  | 2020-07-23 |  | 3GT-36-280C-2NPT |  |  | 2020-08-04 |  | 2020-07-13 | [6 empty] | 2020-08-12 | 2020-08-19 | [20 empty] | 2020-09-18 |  |  |  | 2020-09-21 | [8 empty] | 2020-07-28 |  | 2020-07-31 |  |  | 2020-08-12 |  |  |  | 2020-08-15 |  |  | 2020-08-22 |  |  |  | 2020-08-25 |  |  | 2020-09-09 |  |  |  | 2020-09-21 |  | 2020-09-24
PH1500067 | 124.2433 | 7.184 | Rural | Greenfield | Greenfield | Y1 | L7 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Cotabato City | Tamontaka II | MIN | PH129804034 | 4184 | 40 | Three Legged Tubular Tower | CO68 | 4.3309 | MIN-1500020 | Level 5 | phase2_add | phase2_1231 | PO Issued not 630 |  | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-04-21 |  | 2020-04-23 | [13 empty] | 2020-04-28 | [11 empty] | 2020-05-28 | [27 empty] | 2020-06-04 |  |  | 2020-07-04 |  | 2020-06-11 | [16 empty] | 2020-07-02 |  |  | 2020-07-11 | [6 empty] | 2020-07-25 |  |  |  | 2020-07-25 |  |  |  |  | 2020-06-18 |  | 2020-06-28 |  |  | 2020-07-02 |  | 2020-07-05 |  |  | 2020-07-19 |  |  |  | 2020-07-26 |  | 4GT-42-340C-2NPT |  |  | 2020-08-07 |  | 2020-07-16 | [6 empty] | 2020-08-15 | 2020-08-22 | [20 empty] | 2020-09-21 |  |  |  | 2020-09-24 | [8 empty] | 2020-07-31 |  | 2020-08-03 |  |  | 2020-08-15 |  |  |  | 2020-08-18 |  |  | 2020-08-25 |  |  |  | 2020-08-28 |  |  | 2020-09-12 |  |  |  | 2020-09-24 |  | 2020-09-27
PH1500069 | 124.2541 | 8.0058 | Rural | Greenfield | Greenfield | Y1 | L7 | Autonomous Region of Muslim Mindanao (ARMM) | Lanao Del Sur | Marawi City | Basak Malutlut | MIN | PH153617025 | 4222 | 40 | Three Legged Tubular Tower | CO68 | 87.0946 | MIN-1500021 | Level 6 | phase2_add | phase3 |  |  | Cluster M26 | Enovell | [7 empty] | 2020-03-27 |  | 2020-03-29 | [13 empty] | 2020-04-03 | [11 empty] | 2020-05-03 | [27 empty] | 2020-05-10 |  |  | 2020-06-09 |  | 2020-05-17 | [16 empty] | 2020-06-07 |  |  | 2020-06-16 | [6 empty] | 2020-06-30 |  |  |  | 2020-06-30 |  |  |  |  | 2020-05-24 |  | 2020-06-03 |  |  | 2020-06-07 |  | 2020-06-10 |  |  | 2020-06-24 |  |  |  | 2020-07-01 |  | JGT-42-280C-2NPT |  |  | 2020-07-13 |  | 2020-06-21 | [6 empty] | 2020-07-21 | 2020-07-28 | [20 empty] | 2020-08-27 |  |  |  | 2020-08-30 | [8 empty] | 2020-07-06 |  | 2020-07-09 |  |  | 2020-07-21 |  |  |  | 2020-07-24 |  |  | 2020-07-31 |  |  |  | 2020-08-03 |  |  | 2020-08-18 |  |  |  | 2020-08-30 |  | 2020-09-02
PH1500077 | 124.3028 | 8.0225 | Rural | Greenfield | Greenfield | Y1 | L7 | Autonomous Region of Muslim Mindanao (ARMM) | Lanao Del Sur | Marawi City | Boganga | MIN | PH153617143 | 2027 | 40 | Three Legged Tubular Tower | CO68 | 89.143 | MIN-1500022 | Level 6 | phase2_add | phase3 |  |  | Cluster M26 | Enovell | [7 empty] | 2020-03-30 |  | 2020-04-01 | [13 empty] | 2020-04-06 | [11 empty] | 2020-05-06 | [27 empty] | 2020-05-13 |  |  | 2020-06-12 |  | 2020-05-20 | [16 empty] | 2020-06-10 |  |  | 2020-06-19 | [6 empty] | 2020-07-03 |  |  |  | 2020-07-03 |  |  |  |  | 2020-05-27 | 2020-02-28 | 2020-06-06 |  |  | 2020-06-10 |  | 2020-06-13 |  |  | 2020-06-27 |  |  |  | 2020-07-04 |  | JGT-42-280C-2NPT |  |  | 2020-07-16 |  | 2020-06-24 | [6 empty] | 2020-07-24 | 2020-07-31 | [20 empty] | 2020-08-30 |  |  |  | 2020-09-02 | [8 empty] | 2020-07-09 |  | 2020-07-12 |  |  | 2020-07-24 |  |  |  | 2020-07-27 |  |  | 2020-08-03 |  |  |  | 2020-08-06 |  |  | 2020-08-21 |  |  |  | 2020-09-02 |  | 2020-09-05
PH1500099 | 122.0004 | 6.7044 | Rural | Greenfield | Greenfield | Y1 | L7 | Autonomous Region of Muslim Mindanao (ARMM) | Basilan | Isabela City | Tabiawan | MIN | PH099701050 | 1535 | 40 | Three Legged Tubular Tower | CO69 | 25.8147 | MIN-1500023 | Level 6 | phase3 | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-03-20 |  | 2020-03-22 | [13 empty] | 2020-03-27 | [11 empty] | 2020-04-26 | [27 empty] | 2020-05-03 |  |  | 2020-06-02 |  | 2020-05-10 | [16 empty] | 2020-05-31 |  |  | 2020-06-09 | [6 empty] | 2020-06-23 |  |  |  | 2020-06-23 |  |  |  |  | 2020-05-17 |  | 2020-05-27 |  |  | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-17 |  |  |  | 2020-06-24 |  | 3GT-36-280C-2NPT |  |  | 2020-07-06 |  | 2020-06-14 | [6 empty] | 2020-07-14 | 2020-07-21 | [20 empty] | 2020-08-20 |  |  |  | 2020-08-23 | [8 empty] | 2020-06-29 |  | 2020-07-02 |  |  | 2020-07-14 |  |  |  | 2020-07-17 |  |  | 2020-07-24 |  |  |  | 2020-07-27 |  |  | 2020-08-11 |  |  |  | 2020-08-23 |  | 2020-08-26
PH1500100 | 121.9895 | 6.724 | Rural | Greenfield | Greenfield | Y1 | L7 | Autonomous Region of Muslim Mindanao (ARMM) | Basilan | Isabela City | Marketsite | MIN | PH099701050 | 1535 | 40 | Three Legged Tubular Tower | CO69 | 24.2508 | MIN-1500024 | Level 6 | phase3 | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-03-23 |  | 2020-03-25 | [13 empty] | 2020-03-30 | [11 empty] | 2020-04-29 | [27 empty] | 2020-05-06 |  |  | 2020-06-05 |  | 2020-05-13 | [16 empty] | 2020-06-03 |  |  | 2020-06-12 | [6 empty] | 2020-06-26 |  |  |  | 2020-06-26 |  |  |  |  | 2020-05-20 |  | 2020-05-30 |  |  | 2020-06-03 |  | 2020-06-06 |  |  | 2020-06-20 |  |  |  | 2020-06-27 |  | 4GT-42-340C-2NPT |  |  | 2020-07-09 |  | 2020-06-17 | [6 empty] | 2020-07-17 | 2020-07-24 | [20 empty] | 2020-08-23 |  |  |  | 2020-08-26 | [8 empty] | 2020-07-02 |  | 2020-07-05 |  |  | 2020-07-17 |  |  |  | 2020-07-20 |  |  | 2020-07-27 |  |  |  | 2020-07-30 |  |  | 2020-08-14 |  |  |  | 2020-08-26 |  | 2020-08-29
PH1500102 | 122.0638 | 6.6791 | Rural | Greenfield | Greenfield | Y1 | L7 | Autonomous Region of Muslim Mindanao (ARMM) | Basilan | Lamitan City | Santa Clara | MIN | PH150702045 | 5360 | 40 | Three Legged Tubular Tower | CO69 | 27.1387 | MIN-1500025 | Level 6 | phase3 | phase3 |  |  | Cluster M27 | Richworld | [7 empty] | 2020-03-26 |  | 2020-03-28 | [13 empty] | 2020-04-02 | [11 empty] | 2020-05-02 | [27 empty] | 2020-05-09 |  |  | 2020-06-08 |  | 2020-05-16 | [16 empty] | 2020-06-06 |  |  | 2020-06-15 | [6 empty] | 2020-06-29 |  |  |  | 2020-06-29 |  |  |  |  | 2020-05-23 |  | 2020-06-02 |  |  | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-23 |  |  |  | 2020-06-30 |  | JGT-42-280C-2NPT |  |  | 2020-07-12 |  | 2020-06-20 | [6 empty] | 2020-07-20 | 2020-07-27 | [20 empty] | 2020-08-26 |  |  |  | 2020-08-29 | [8 empty] | 2020-07-05 |  | 2020-07-08 |  |  | 2020-07-20 |  |  |  | 2020-07-23 |  |  | 2020-07-30 |  |  |  | 2020-08-02 |  |  | 2020-08-17 |  |  |  | 2020-08-29 |  | 2020-09-01
PH1500104 | 124.2038 | 7.2132 | Rural | Greenfield | Greenfield | Y1 | L7 | Autonomous Region of Muslim Mindanao (ARMM) | Maguindanao | Cotabato City | Poblacion VII | MIN | PH129804010 | 5999 | 40 | Three Legged Tubular Tower | CO68 | 5.1093 | MIN-1500026 | Level 5 | phase2_add | phase3 | PO Issued not 630 |  | Cluster M24 | TBD |  | Batch 2 | [5 empty] | 2020-04-24 |  | 2020-04-26 | [13 empty] | 2020-05-01 | [11 empty] | 2020-05-31 | [27 empty] | 2020-06-07 |  |  | 2020-07-07 |  | 2020-06-14 | [16 empty] | 2020-07-05 |  |  | 2020-07-14 | [6 empty] | 2020-07-28 |  |  |  | 2020-07-28 |  |  |  |  | 2020-06-21 |  | 2020-07-01 |  |  | 2020-07-05 |  | 2020-07-08 |  |  | 2020-07-22 |  |  |  | 2020-07-29 |  | 3GT-36-280C-2NPT |  |  | 2020-08-10 |  | 2020-07-19 | [6 empty] | 2020-08-18 | 2020-08-25 | [20 empty] | 2020-09-24 |  |  |  | 2020-09-27 | [8 empty] | 2020-08-03 |  | 2020-08-06 |  |  | 2020-08-18 |  |  |  | 2020-08-21 |  |  | 2020-08-28 |  |  |  | 2020-08-31 |  |  | 2020-09-15 |  |  |  | 2020-09-27 |  | 2020-09-30
PH1500170 | 124.0721 | 7.5916 | [20 empty] | OA_1231_no BTS | [102 empty] | 1900-01-11
PH1600001 | 125.492 | 9.7895 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Caraga (Region XIII) | Surigao Del Norte | Surigao City | Taft | MIN | PH166724068 | 18900 | 30 | Monopole Tower | CO64 | 92.9343 | MIN-1600001 | Level 6 | phase3 | phase3 |  |  | Cluster M11 | Marrox | [7 empty] | 2020-02-02 |  | 2020-02-04 | [13 empty] | 2020-02-09 | [11 empty] | 2020-03-10 | [27 empty] | 2020-03-17 |  |  | 2020-04-16 |  | 2020-03-24 | [16 empty] | 2020-04-14 |  |  | 2020-04-23 | [6 empty] | 2020-05-07 |  |  |  | 2020-05-07 |  |  |  |  | 2020-03-31 |  | 2020-04-10 |  |  | 2020-04-14 |  | 2020-04-17 |  |  | 2020-05-01 |  |  |  | 2020-05-08 |  | ZCG-12-340D-1NPT |  |  | 2020-05-20 |  | 2020-04-28 | [6 empty] | 2020-05-28 | 2020-06-04 | [20 empty] | 2020-07-04 |  |  |  | 2020-07-07 | [8 empty] | 2020-05-13 |  | 2020-05-16 |  |  | 2020-05-28 |  |  |  | 2020-05-31 |  |  | 2020-06-07 |  |  |  | 2020-06-10 |  |  | 2020-06-25 |  |  |  | 2020-07-07 |  | 2020-07-10
PH1600002 | 125.5046 | 8.9578 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Libertad | MIN | PH160202004 | 12656 | 30 | Three Legged Tubular Tower | CO64 | 3.925 | MIN-1600002 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-03-07 |  | 2020-03-09 | [13 empty] | 2020-03-14 | [11 empty] | 2020-04-13 | [27 empty] | 2020-04-20 |  |  | 2020-05-20 |  | 2020-04-27 | [16 empty] | 2020-05-18 |  |  | 2020-05-27 | [6 empty] | 2020-06-10 |  |  |  | 2020-06-10 |  |  |  |  | 2020-05-04 |  | 2020-05-14 |  |  | 2020-05-18 |  | 2020-05-21 |  |  | 2020-06-04 |  |  |  | 2020-06-11 |  | DGT-30-340C-2NPT |  |  | 2020-06-23 |  | 2020-06-01 | [6 empty] | 2020-07-01 | 2020-07-08 | [20 empty] | 2020-08-07 |  |  |  | 2020-08-10 | [8 empty] | 2020-06-16 |  | 2020-06-19 |  |  | 2020-07-01 |  |  |  | 2020-07-04 |  |  | 2020-07-11 |  |  |  | 2020-07-14 |  |  | 2020-07-29 |  |  |  | 2020-08-10 |  | 2020-08-13
PH1600003 | 125.5046 | 8.9506 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Libertad | MIN | PH160202054 | 21703 | 30 | Monopole Tower | CO64 | 3.9506 | MIN-1600003 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-03-10 |  | 2020-03-12 | [13 empty] | 2020-03-17 | [11 empty] | 2020-04-16 | [27 empty] | 2020-04-23 |  |  | 2020-05-23 |  | 2020-04-30 | [16 empty] | 2020-05-21 |  |  | 2020-05-30 | [6 empty] | 2020-06-13 |  |  |  | 2020-06-13 |  |  |  |  | 2020-05-07 |  | 2020-05-17 |  |  | 2020-05-21 |  | 2020-05-24 |  |  | 2020-06-07 |  |  |  | 2020-06-14 |  | DGT-30-340C-2NPT |  |  | 2020-06-26 |  | 2020-06-04 | [6 empty] | 2020-07-04 | 2020-07-11 | [20 empty] | 2020-08-10 |  |  |  | 2020-08-13 | [8 empty] | 2020-06-19 |  | 2020-06-22 |  |  | 2020-07-04 |  |  |  | 2020-07-07 |  |  | 2020-07-14 |  |  |  | 2020-07-17 |  |  | 2020-08-01 |  |  |  | 2020-08-13 |  | 2020-08-16
PH1600004 | 125.5109 | 8.9614 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Libertad | MIN | PH160202004 | 12656 | 30 | Three Legged Tubular Tower | CO64 | 3.2942 | MIN-1600004 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-03-13 |  | 2020-03-15 | [13 empty] | 2020-03-20 | [11 empty] | 2020-04-19 | [27 empty] | 2020-04-26 |  |  | 2020-05-26 |  | 2020-05-03 | [16 empty] | 2020-05-24 |  |  | 2020-06-02 | [6 empty] | 2020-06-16 |  |  |  | 2020-06-16 |  |  |  |  | 2020-05-10 |  | 2020-05-20 |  |  | 2020-05-24 |  | 2020-05-27 |  |  | 2020-06-10 |  |  |  | 2020-06-17 |  | DGT-30-340C-2NPT |  |  | 2020-06-29 |  | 2020-06-07 | [6 empty] | 2020-07-07 | 2020-07-14 | [20 empty] | 2020-08-13 |  |  |  | 2020-08-16 | [8 empty] | 2020-06-22 |  | 2020-06-25 |  |  | 2020-07-07 |  |  |  | 2020-07-10 |  |  | 2020-07-17 |  |  |  | 2020-07-20 |  |  | 2020-08-04 |  |  |  | 2020-08-16 |  | 2020-08-19
PH1600006 | 125.5108 | 8.947 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Libertad | MIN | PH160202054 | 21703 | 30 | Three Legged Tubular Tower | CO64 | 3.3549 | MIN-1600005 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-16 | 2020-01-17 | 2020-01-18 | [13 empty] | 2020-01-23 | [11 empty] | 2020-02-22 | [27 empty] | 2020-02-29 |  |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 |  | 2020-03-24 |  |  | 2020-03-28 |  | 2020-03-31 |  |  | 2020-04-14 |  |  |  | 2020-04-21 |  | JGT-30-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1600011 | 125.5171 | 8.9433 | Urban | Rooftop | Rooftop | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Bonbon | MIN | PH160202054 | 21703 | 12 | Pole | CO64 | 2.8606 | MIN-1600006 | Level 6 | phase3 | phase3 |  | Robinsons_5 | Cluster M21 | Marrox | [7 empty] | 2020-03-16 | 2020-01-16 | 2020-03-18 | [13 empty] | 2020-03-23 | [11 empty] | 2020-04-22 | [27 empty] | 2020-04-29 |  |  | 2020-05-29 |  | 2020-05-06 | [16 empty] | 2020-05-27 |  |  | 2020-06-05 | [6 empty] | 2020-06-19 |  |  |  | 2020-06-19 |  |  |  |  | 2020-05-13 |  | 2020-05-23 |  |  | 2020-05-27 |  | 2020-05-30 |  |  | 2020-06-13 |  |  |  | 2020-06-20 |  | DGT-30-340C-2NPT |  |  | 2020-07-02 |  | 2020-06-10 | [6 empty] | 2020-07-10 | 2020-07-17 | [20 empty] | 2020-08-16 |  |  |  | 2020-08-19 | [8 empty] | 2020-06-25 |  | 2020-06-28 |  |  | 2020-07-10 |  |  |  | 2020-07-13 |  |  | 2020-07-20 |  |  |  | 2020-07-23 |  |  | 2020-08-07 |  |  |  | 2020-08-19 |  | 2020-08-22
PH1600012 | 125.5236 | 8.9686 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Babag | MIN | PH160202039 | 13728 | 30 | Three Legged Tubular Tower | CO64 | 2.3631 | MIN-1600007 | Level 6 | phase3 | phase2_1231 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-03-19 |  | 2020-03-21 | [13 empty] | 2020-03-26 | [11 empty] | 2020-04-25 | [27 empty] | 2020-05-02 |  |  | 2020-06-01 |  | 2020-05-09 | [16 empty] | 2020-05-30 |  |  | 2020-06-08 | [6 empty] | 2020-06-22 |  |  |  | 2020-06-22 |  |  |  |  | 2020-05-16 |  | 2020-05-26 |  |  | 2020-05-30 |  | 2020-06-02 |  |  | 2020-06-16 |  |  |  | 2020-06-23 |  | DGT-30-340C-2NPT |  |  | 2020-07-05 |  | 2020-06-13 | [6 empty] | 2020-07-13 | 2020-07-20 | [20 empty] | 2020-08-19 |  |  |  | 2020-08-22 | [8 empty] | 2020-06-28 |  | 2020-07-01 |  |  | 2020-07-13 |  |  |  | 2020-07-16 |  |  | 2020-07-23 |  |  |  | 2020-07-26 |  |  | 2020-08-10 |  |  |  | 2020-08-22 |  | 2020-08-25
PH1600013 | 125.5235 | 8.9613 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Libertad | MIN | PH160202039 | 13728 | 30 | Three Legged Tubular Tower | CO64 | 1.9615 | MIN-1600008 | Level 6 | phase3 | phase2_1231 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-03-22 |  | 2020-03-24 | [13 empty] | 2020-03-29 | [11 empty] | 2020-04-28 | [27 empty] | 2020-05-05 |  |  | 2020-06-04 |  | 2020-05-12 | [16 empty] | 2020-06-02 |  |  | 2020-06-11 | [6 empty] | 2020-06-25 |  |  |  | 2020-06-25 |  |  |  |  | 2020-05-19 |  | 2020-05-29 |  |  | 2020-06-02 |  | 2020-06-05 |  |  | 2020-06-19 |  |  |  | 2020-06-26 |  | DGT-30-340C-2NPT |  |  | 2020-07-08 |  | 2020-06-16 | [6 empty] | 2020-07-16 | 2020-07-23 | [20 empty] | 2020-08-22 |  |  |  | 2020-08-25 | [8 empty] | 2020-07-01 |  | 2020-07-04 |  |  | 2020-07-16 |  |  |  | 2020-07-19 |  |  | 2020-07-26 |  |  |  | 2020-07-29 |  |  | 2020-08-13 |  |  |  | 2020-08-25 |  | 2020-08-28
PH1600015 | 125.5234 | 8.9469 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Bonbon | MIN | PH160202020 | 4599 | 30 | Three Legged Tubular Tower | CO64 | 2.0618 | MIN-1600009 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-03-25 |  | 2020-03-27 | [13 empty] | 2020-04-01 | [11 empty] | 2020-05-01 | [27 empty] | 2020-05-08 |  |  | 2020-06-07 |  | 2020-05-15 | [16 empty] | 2020-06-05 |  |  | 2020-06-14 | [6 empty] | 2020-06-28 |  |  |  | 2020-06-28 |  |  |  |  | 2020-05-22 |  | 2020-06-01 |  |  | 2020-06-05 |  | 2020-06-08 |  |  | 2020-06-22 |  |  |  | 2020-06-29 |  | DGT-30-340C-2NPT |  |  | 2020-07-11 |  | 2020-06-19 | [6 empty] | 2020-07-19 | 2020-07-26 | [20 empty] | 2020-08-25 |  |  |  | 2020-08-28 | [8 empty] | 2020-07-04 |  | 2020-07-07 |  |  | 2020-07-19 |  |  |  | 2020-07-22 |  |  | 2020-07-29 |  |  |  | 2020-08-01 |  |  | 2020-08-16 |  |  |  | 2020-08-28 |  | 2020-08-31
PH1600016 | 125.5298 | 8.9649 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Doongan | MIN | PH160202039 | 13728 | 30 | Three Legged Tubular Tower | CO64 | 1.5769 | MIN-1600010 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-03-28 |  | 2020-03-30 | [13 empty] | 2020-04-04 | [11 empty] | 2020-05-04 | [27 empty] | 2020-05-11 |  |  | 2020-06-10 |  | 2020-05-18 | [16 empty] | 2020-06-08 |  |  | 2020-06-17 | [6 empty] | 2020-07-01 |  |  |  | 2020-07-01 |  |  |  |  | 2020-05-25 |  | 2020-06-04 |  |  | 2020-06-08 |  | 2020-06-11 |  |  | 2020-06-25 |  |  |  | 2020-07-02 |  | JGT-30-340C-2NPT |  |  | 2020-07-14 |  | 2020-06-22 | [6 empty] | 2020-07-22 | 2020-07-29 | [20 empty] | 2020-08-28 |  |  |  | 2020-08-31 | [8 empty] | 2020-07-07 |  | 2020-07-10 |  |  | 2020-07-22 |  |  |  | 2020-07-25 |  |  | 2020-08-01 |  |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  |  | 2020-08-31 |  | 2020-09-03
PH1600017 | 125.5298 | 8.9577 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Doongan | MIN | PH160202047 | 7267 | 30 | Three Legged Tubular Tower | CO64 | 1.1815 | MIN-1600011 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-03-31 |  | 2020-04-02 | [13 empty] | 2020-04-07 | [11 empty] | 2020-05-07 | [27 empty] | 2020-05-14 |  |  | 2020-06-13 |  | 2020-05-21 | [16 empty] | 2020-06-11 |  |  | 2020-06-20 | [6 empty] | 2020-07-04 |  |  |  | 2020-07-04 |  |  |  |  | 2020-05-28 |  | 2020-06-07 |  |  | 2020-06-11 |  | 2020-06-14 |  |  | 2020-06-28 |  |  |  | 2020-07-05 |  | DGT-30-340C-2NPT |  |  | 2020-07-17 |  | 2020-06-25 | [6 empty] | 2020-07-25 | 2020-08-01 | [20 empty] | 2020-08-31 |  |  |  | 2020-09-03 | [8 empty] | 2020-07-10 |  | 2020-07-13 |  |  | 2020-07-25 |  |  |  | 2020-07-28 |  |  | 2020-08-04 |  |  |  | 2020-08-07 |  |  | 2020-08-22 |  |  |  | 2020-09-03 |  | 2020-09-06
PH1600018 | 125.5297 | 8.9504 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Doongan | MIN | PH160202039 | 13728 | 30 | Monopole Tower | CO64 | 1.2641 | MIN-1600012 | Level 6 | phase3 | phase3 |  | DICT_4 | Cluster M21 | Marrox | [7 empty] | 2020-04-03 | 2020-01-16 | 2020-04-05 | [13 empty] | 2020-04-10 | [11 empty] | 2020-05-10 | [27 empty] | 2020-05-17 |  |  | 2020-06-16 |  | 2020-05-24 | [16 empty] | 2020-06-14 |  |  | 2020-06-23 | [6 empty] | 2020-07-07 |  |  |  | 2020-07-07 |  |  |  |  | 2020-05-31 |  | 2020-06-10 |  |  | 2020-06-14 |  | 2020-06-17 |  |  | 2020-07-01 |  |  |  | 2020-07-08 |  | DGT-30-340C-2NPT |  |  | 2020-07-20 |  | 2020-06-28 | [6 empty] | 2020-07-28 | 2020-08-04 | [20 empty] | 2020-09-03 |  |  |  | 2020-09-06 | [8 empty] | 2020-07-13 |  | 2020-07-16 |  |  | 2020-07-28 |  |  |  | 2020-07-31 |  |  | 2020-08-07 |  |  |  | 2020-08-10 |  |  | 2020-08-25 |  |  |  | 2020-09-06 |  | 2020-09-09
PH1600019 | 125.5297 | 8.9432 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Bonbon | MIN | PH160202037 | 1954 | 30 | Monopole Tower | CO64 | 1.7584 | MIN-1600013 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-04-06 |  | 2020-04-08 | [13 empty] | 2020-04-13 | [11 empty] | 2020-05-13 | [27 empty] | 2020-05-20 |  |  | 2020-06-19 |  | 2020-05-27 | [16 empty] | 2020-06-17 |  |  | 2020-06-26 | [6 empty] | 2020-07-10 |  |  |  | 2020-07-10 |  |  |  |  | 2020-06-03 |  | 2020-06-13 |  |  | 2020-06-17 |  | 2020-06-20 |  |  | 2020-07-04 |  |  |  | 2020-07-11 |  | DGT-30-340C-2NPT |  |  | 2020-07-23 |  | 2020-07-01 | [6 empty] | 2020-07-31 | 2020-08-07 | [20 empty] | 2020-09-06 |  |  |  | 2020-09-09 | [8 empty] | 2020-07-16 |  | 2020-07-19 |  |  | 2020-07-31 |  |  |  | 2020-08-03 |  |  | 2020-08-10 |  |  |  | 2020-08-13 |  |  | 2020-08-28 |  |  |  | 2020-09-09 |  | 2020-09-12
PH1600020 | 125.5296 | 8.936 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Bonbon | MIN | PH160202090 | 11173 | 30 | Monopole Tower | CO64 | 2.4246 | MIN-1600014 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-19 |  | 2020-01-21 | [13 empty] | 2020-01-26 | [11 empty] | 2020-02-25 | [27 empty] | 2020-03-03 |  |  | 2020-04-02 |  | 2020-03-10 | [16 empty] | 2020-03-31 |  |  | 2020-04-09 | [6 empty] | 2020-04-23 |  |  |  | 2020-04-23 |  |  |  |  | 2020-03-17 |  | 2020-03-27 |  |  | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-17 |  |  |  | 2020-04-24 |  | DGT-30-340C-2NPT |  |  | 2020-05-06 |  | 2020-04-14 | [6 empty] | 2020-05-14 | 2020-05-21 | [20 empty] | 2020-06-20 |  |  |  | 2020-06-23 | [8 empty] | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-11 |  |  |  | 2020-06-23 |  | 2020-06-26
PH1600021 | 125.5372 | 9.1203 | Urban | Greenfield | Rooftop | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Cabadbaran City | Kauswagan | MIN | PH160203022 | 364 | 30 | Monopole Tower | CO64 | 18.3684 | MIN-1600015 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-04-09 |  | 2020-04-11 | [13 empty] | 2020-04-16 | [11 empty] | 2020-05-16 | [27 empty] | 2020-05-23 |  |  | 2020-06-22 |  | 2020-05-30 | [16 empty] | 2020-06-20 |  |  | 2020-06-29 | [6 empty] | 2020-07-13 |  |  |  | 2020-07-13 |  |  |  |  | 2020-06-06 |  | 2020-06-16 |  |  | 2020-06-20 |  | 2020-06-23 |  |  | 2020-07-07 |  |  |  | 2020-07-14 |  | JGT-30-340C-2NPT |  |  | 2020-07-26 |  | 2020-07-04 | [6 empty] | 2020-08-03 | 2020-08-10 | [20 empty] | 2020-09-09 |  |  |  | 2020-09-12 | [8 empty] | 2020-07-19 |  | 2020-07-22 |  |  | 2020-08-03 |  |  |  | 2020-08-06 |  |  | 2020-08-13 |  |  |  | 2020-08-16 |  |  | 2020-08-31 |  |  |  | 2020-09-12 |  | 2020-09-15
PH1600022 | 125.5361 | 8.9612 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Doongan | MIN | PH160202091 | 9774 | 30 | Monopole Tower | CO64 | 0.81798 | MIN-1600016 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-04-12 |  | 2020-04-14 | [13 empty] | 2020-04-19 | [11 empty] | 2020-05-19 | [27 empty] | 2020-05-26 |  |  | 2020-06-25 |  | 2020-06-02 | [16 empty] | 2020-06-23 |  |  | 2020-07-02 | [6 empty] | 2020-07-16 |  |  |  | 2020-07-16 |  |  |  |  | 2020-06-09 |  | 2020-06-19 |  |  | 2020-06-23 |  | 2020-06-26 |  |  | 2020-07-10 |  |  |  | 2020-07-17 |  | DGT-30-340C-2NPT |  |  | 2020-07-29 |  | 2020-07-07 | [6 empty] | 2020-08-06 | 2020-08-13 | [20 empty] | 2020-09-12 |  |  |  | 2020-09-15 | [8 empty] | 2020-07-22 |  | 2020-07-25 |  |  | 2020-08-06 |  |  |  | 2020-08-09 |  |  | 2020-08-16 |  |  |  | 2020-08-19 |  |  | 2020-09-03 |  |  |  | 2020-09-15 |  | 2020-09-18
PH1600023 | 125.5361 | 8.954 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Bayanihan Pob. (Bgy. 27) | MIN | PH160202055 | 6301 | 30 | Monopole Tower | CO64 | 0.47411 | MIN-1600017 | Level 6 | phase3 | phase2_1231 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-04-15 |  | 2020-04-17 | [13 empty] | 2020-04-22 | [11 empty] | 2020-05-22 | [27 empty] | 2020-05-29 |  |  | 2020-06-28 |  | 2020-06-05 | [16 empty] | 2020-06-26 |  |  | 2020-07-05 | [6 empty] | 2020-07-19 |  |  |  | 2020-07-19 |  |  |  |  | 2020-06-12 |  | 2020-06-22 |  |  | 2020-06-26 |  | 2020-06-29 |  |  | 2020-07-13 |  |  |  | 2020-07-20 |  | DGT-30-340C-2NPT |  |  | 2020-08-01 |  | 2020-07-10 | [6 empty] | 2020-08-09 | 2020-08-16 | [20 empty] | 2020-09-15 |  |  |  | 2020-09-18 | [8 empty] | 2020-07-25 |  | 2020-07-28 |  |  | 2020-08-09 |  |  |  | 2020-08-12 |  |  | 2020-08-19 |  |  |  | 2020-08-22 |  |  | 2020-09-06 |  |  |  | 2020-09-18 |  | 2020-09-21
PH1600024 | 125.536 | 8.9468 | Urban | Greenfield | Rooftop | Y1 | L7+L21+L26 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Villa Kananga | MIN | PH160202051 | 1135 | 30 | Monopole Tower | CO64 | 1.0358 | MIN-1600018 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-21 | 2020-01-16 | 2020-01-23 | [13 empty] | 2020-01-28 | [11 empty] | 2020-02-27 | [27 empty] | 2020-03-05 |  |  | 2020-04-04 |  | 2020-03-12 | [16 empty] | 2020-04-02 |  |  | 2020-04-11 | [6 empty] | 2020-04-25 |  |  |  | 2020-04-25 |  |  |  |  | 2020-03-19 |  | 2020-03-29 |  |  | 2020-04-02 |  | 2020-04-05 |  |  | 2020-04-19 |  |  |  | 2020-04-26 |  | JGT-30-340C-2NPT |  |  | 2020-05-08 |  | 2020-04-16 | [6 empty] | 2020-05-16 | 2020-05-23 | [20 empty] | 2020-06-22 |  |  |  | 2020-06-25 | [8 empty] | 2020-05-01 |  | 2020-05-04 |  |  | 2020-05-16 |  |  |  | 2020-05-19 |  |  | 2020-05-26 |  |  |  | 2020-05-29 |  |  | 2020-06-13 |  |  |  | 2020-06-25 |  | 2020-06-28
PH1600025 | 125.536 | 8.9396 | Urban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Villa Kananga | MIN | PH160202045 | 5036 | 30 | Monopole Tower | CO64 | 1.7925 | MIN-1600019 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-04-18 |  | 2020-04-20 | [13 empty] | 2020-04-25 | [11 empty] | 2020-05-25 | [27 empty] | 2020-06-01 |  |  | 2020-07-01 |  | 2020-06-08 | [16 empty] | 2020-06-29 |  |  | 2020-07-08 | [6 empty] | 2020-07-22 |  |  |  | 2020-07-22 |  |  |  |  | 2020-06-15 |  | 2020-06-25 |  |  | 2020-06-29 |  | 2020-07-02 |  |  | 2020-07-16 |  |  |  | 2020-07-23 |  | DGT-30-340C-2NPT |  |  | 2020-08-04 |  | 2020-07-13 | [6 empty] | 2020-08-12 | 2020-08-19 | [20 empty] | 2020-09-18 |  |  |  | 2020-09-21 | [8 empty] | 2020-07-28 |  | 2020-07-31 |  |  | 2020-08-12 |  |  |  | 2020-08-15 |  |  | 2020-08-22 |  |  |  | 2020-08-25 |  |  | 2020-09-09 |  |  |  | 2020-09-21 |  | 2020-09-24
PH1600050 | 125.4704 | 9.7754 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Surigao Del Norte | Surigao City | Togbongon | MIN | PH166724037 | 6659 | 40 | Angular Steel Tower | CO64 | 91.5304 | MIN-1600020 | Level 6 | phase3 | phase3 |  |  | Cluster M11 | Marrox | [7 empty] | 2020-02-05 |  | 2020-02-07 | [13 empty] | 2020-02-12 | [11 empty] | 2020-03-13 | [27 empty] | 2020-03-20 |  |  | 2020-04-19 |  | 2020-03-27 | [16 empty] | 2020-04-17 |  |  | 2020-04-26 | [6 empty] | 2020-05-10 |  |  |  | 2020-05-10 |  |  |  |  | 2020-04-03 |  | 2020-04-13 |  |  | 2020-04-17 |  | 2020-04-20 |  |  | 2020-05-04 |  |  |  | 2020-05-11 |  | JGT-36-340C-2NPT |  |  | 2020-05-23 |  | 2020-05-01 | [6 empty] | 2020-05-31 | 2020-06-07 | [20 empty] | 2020-07-07 |  |  |  | 2020-07-10 | [8 empty] | 2020-05-16 |  | 2020-05-19 |  |  | 2020-05-31 |  |  |  | 2020-06-03 |  |  | 2020-06-10 |  |  |  | 2020-06-13 |  |  | 2020-06-28 |  |  |  | 2020-07-10 |  | 2020-07-13
PH1600055 | 125.4933 | 9.7819 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Surigao Del Norte | Surigao City | Taft | MIN | PH166724048 | 18571 | 40 | Angular Steel Tower | CO64 | 92.0773 | MIN-1600021 | Level 6 | phase3 | phase3 |  |  | Cluster M11 | Marrox | [7 empty] | 2020-02-08 |  | 2020-02-10 | [13 empty] | 2020-02-15 | [11 empty] | 2020-03-16 | [27 empty] | 2020-03-23 |  |  | 2020-04-22 |  | 2020-03-30 | [16 empty] | 2020-04-20 |  |  | 2020-04-29 | [6 empty] | 2020-05-13 |  |  |  | 2020-05-13 |  |  |  |  | 2020-04-06 |  | 2020-04-16 |  |  | 2020-04-20 |  | 2020-04-23 |  |  | 2020-05-07 |  |  |  | 2020-05-14 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-05-26 |  | 2020-05-04 | [6 empty] | 2020-06-03 | 2020-06-10 | [20 empty] | 2020-07-10 |  |  |  | 2020-07-13 | [8 empty] | 2020-05-19 |  | 2020-05-22 |  |  | 2020-06-03 |  |  |  | 2020-06-06 |  |  | 2020-06-13 |  |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  |  | 2020-07-13 |  | 2020-07-16
PH1600058 | 125.5185 | 9.0255 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Magallanes | Poblacion | MIN | PH160208009 | 3639 | 40 | Three Legged Tubular Tower | CO64 | 8.1791 | MIN-1600022 | Level 6 | phase3 | phase3 |  | DICT_45 | Cluster M21 | Marrox | [7 empty] | 2020-04-21 | 2020-01-16 | 2020-04-23 | [13 empty] | 2020-04-28 | [11 empty] | 2020-05-28 | [27 empty] | 2020-06-04 |  |  | 2020-07-04 |  | 2020-06-11 | [16 empty] | 2020-07-02 |  |  | 2020-07-11 | [6 empty] | 2020-07-25 |  |  |  | 2020-07-25 |  |  |  |  | 2020-06-18 |  | 2020-06-28 |  |  | 2020-07-02 |  | 2020-07-05 |  |  | 2020-07-19 |  |  |  | 2020-07-26 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-08-07 |  | 2020-07-16 | [6 empty] | 2020-08-15 | 2020-08-22 | [20 empty] | 2020-09-21 |  |  |  | 2020-09-24 | [8 empty] | 2020-07-31 |  | 2020-08-03 |  |  | 2020-08-15 |  |  |  | 2020-08-18 |  |  | 2020-08-25 |  |  |  | 2020-08-28 |  |  | 2020-09-12 |  |  |  | 2020-09-24 |  | 2020-09-27
PH1600065 | 125.5459 | 8.9523 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Imadejas Pob. (Bgy. 24) | MIN | PH160202033 | 5376 | 40 | Three Legged Tubular Tower | CO64 | 0.69736 | MIN-1600023 | Level 6 | phase2_add | phase2_1231 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-04-24 |  | 2020-04-26 | [13 empty] | 2020-05-01 | [11 empty] | 2020-05-31 | [27 empty] | 2020-06-07 |  |  | 2020-07-07 |  | 2020-06-14 | [16 empty] | 2020-07-05 |  |  | 2020-07-14 | [6 empty] | 2020-07-28 |  |  |  | 2020-07-28 |  |  |  |  | 2020-06-21 |  | 2020-07-01 |  |  | 2020-07-05 |  | 2020-07-08 |  |  | 2020-07-22 |  |  |  | 2020-07-29 |  | JGT-36-340C-2NPT |  |  | 2020-08-10 |  | 2020-07-19 | [6 empty] | 2020-08-18 | 2020-08-25 | [20 empty] | 2020-09-24 |  |  |  | 2020-09-27 | [8 empty] | 2020-08-03 |  | 2020-08-06 |  |  | 2020-08-18 |  |  |  | 2020-08-21 |  |  | 2020-08-28 |  |  |  | 2020-08-31 |  |  | 2020-09-15 |  |  |  | 2020-09-27 |  | 2020-09-30
PH1600066 | 125.5458 | 8.9299 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Kinamlutan | MIN | PH160202098 | 2630 | 40 | Monopole Tower | CO64 | 2.8677 | MIN-1600024 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-04-27 |  | 2020-04-29 | [13 empty] | 2020-05-04 | [11 empty] | 2020-06-03 | [27 empty] | 2020-06-10 |  |  | 2020-07-10 |  | 2020-06-17 | [16 empty] | 2020-07-08 |  |  | 2020-07-17 | [6 empty] | 2020-07-31 |  |  |  | 2020-07-31 |  |  |  |  | 2020-06-24 |  | 2020-07-04 |  |  | 2020-07-08 |  | 2020-07-11 |  |  | 2020-07-25 |  |  |  | 2020-08-01 |  | JGT-36-340C-2NPT |  |  | 2020-08-13 |  | 2020-07-22 | [6 empty] | 2020-08-21 | 2020-08-28 | [20 empty] | 2020-09-27 |  |  |  | 2020-09-30 | [8 empty] | 2020-08-06 |  | 2020-08-09 |  |  | 2020-08-21 |  |  |  | 2020-08-24 |  |  | 2020-08-31 |  |  |  | 2020-09-03 |  |  | 2020-09-18 |  |  |  | 2020-09-30 |  | 2020-10-03
PH1600068 | 125.5644 | 9.1002 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Cabadbaran City | Mabini | MIN | PH160203038 | 1979 | 40 | Three Legged Tubular Tower | CO64 | 16.3432 | MIN-1600025 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-04-30 |  | 2020-05-02 | [13 empty] | 2020-05-07 | [11 empty] | 2020-06-06 | [27 empty] | 2020-06-13 |  |  | 2020-07-13 |  | 2020-06-20 | [16 empty] | 2020-07-11 |  |  | 2020-07-20 | [6 empty] | 2020-08-03 |  |  |  | 2020-08-03 |  |  |  |  | 2020-06-27 |  | 2020-07-07 |  |  | 2020-07-11 |  | 2020-07-14 |  |  | 2020-07-28 |  |  |  | 2020-08-04 |  | JGT-36-340C-2NPT |  |  | 2020-08-16 |  | 2020-07-25 | [6 empty] | 2020-08-24 | 2020-08-31 | [20 empty] | 2020-09-30 |  |  |  | 2020-10-03 | [8 empty] | 2020-08-09 |  | 2020-08-12 |  |  | 2020-08-24 |  |  |  | 2020-08-27 |  |  | 2020-09-03 |  |  |  | 2020-09-06 |  |  | 2020-09-21 |  |  |  | 2020-10-03 |  | 2020-10-06
PH1600072 | 125.5948 | 8.9576 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Baan Km 3 | MIN | PH160202007 | 12720 | 45 | Three Legged Tubular Tower | CO64 | 5.9944 | MIN-1600026 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-16 | 2020-01-18 | 2020-01-18 | 2020-01-30 | 2020-02-04 | 2020-02-05 |  | 2020-01-30 | 2020-01-20 |  | 2020-02-21 |  | 2020-01-20 |  |  |  | 2020-01-23 |  |  | 2020-02-21 |  | 2020-02-21 | 2020-01-30 | 2020-02-04 | 2020-02-05 |  | 2020-01-30 |  | 2020-02-22 | [5 empty] | C |  |  |  | 125.6012 | 8.9645 | [16 empty] | 2020-02-29 | 2020-02-27 |  | 2020-03-30 |  | 2020-03-07 | [16 empty] | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 | 2020-02-27 | 2020-03-24 | 2020-03-09 | 2020-03-09 | 2020-03-28 | 2020-03-05 | 2020-03-31 | 2020-03-07 | 2020-03-08 | 2020-04-14 | 2020-03-09 | 2020-03-09 | 2020-03-09 | 2020-04-21 | 2020-03-09 | JGT-36-340C-2NPT |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1600074 | 125.7491 | 8.7212 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Sur | Bayugan City | Taglatawan | MIN | PH160301016 | 16010 | 45 | Three Legged Tubular Tower | CO64 | 34.6905 | MIN-1600027 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-02-11 |  | 2020-02-13 | [13 empty] | 2020-02-18 | [11 empty] | 2020-03-19 | [27 empty] | 2020-03-26 |  |  | 2020-04-25 |  | 2020-04-02 | [16 empty] | 2020-04-23 |  |  | 2020-05-02 | [6 empty] | 2020-05-16 |  |  |  | 2020-05-16 |  |  |  |  | 2020-04-09 |  | 2020-04-19 |  |  | 2020-04-23 |  | 2020-04-26 |  |  | 2020-05-10 |  |  |  | 2020-05-17 |  | JGT-36-340C-2NPT |  |  | 2020-05-29 |  | 2020-05-07 | [6 empty] | 2020-06-06 | 2020-06-13 | [20 empty] | 2020-07-13 |  |  |  | 2020-07-16 | [8 empty] | 2020-05-22 |  | 2020-05-25 |  |  | 2020-06-06 |  |  |  | 2020-06-09 |  |  | 2020-06-16 |  |  |  | 2020-06-19 |  |  | 2020-07-04 |  |  |  | 2020-07-16 |  | 2020-07-19
PH1600077 | 125.7688 | 8.7112 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Agusan del Sur | Bayugan City | Santa Teresita | MIN | PH160301003 | 2949 | 30 | Three Legged Tubular Tower | CO64 | 36.9682 | MIN-1600028 | Level 6 | phase3 | phase3 | OA_630 |  | Cluster M21 | Marrox | PO2020011304PH_WLS | PO Batch 3 | JXD-2 |  | EPC |  |  | 2020-01-16 | 2020-01-16 | 2020-01-18 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-01-18 |  |  |  | 2020-01-18 |  |  |  | 2020-01-23 | 2020-01-18 |  |  |  | 2020-01-18 | 2020-01-17 |  |  |  | 2020-01-17 | 2020-02-24 | 2020-02-22 | [5 empty] | A | Edgar M. Rondez | Purok 1, Fili, Bayugan City | Agusan del Sur | 125.7681 | 8.711 | Greenfield | 52m |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-02-29 | 2020-02-13 |  | 2020-03-30 |  | 2020-03-07 | [11 empty] | 0910-7959071 0907-7795618 |  |  |  |  | 2020-03-28 |  |  | 2020-04-06 | [6 empty] | 2020-04-20 |  |  |  | 2020-04-20 |  |  |  |  | 2020-03-14 | 2020-02-28 | 2020-03-24 | 2020-03-06 | 2020-03-06 | 2020-03-28 | 2020-02-19 | 2020-03-31 | 2020-02-21 | 2020-02-25 | 2020-04-14 | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-04-21 | 2020-03-11 | JGT-30-340C-2NPT（340KPH/D） |  |  | 2020-05-03 |  | 2020-04-11 | [6 empty] | 2020-05-11 | 2020-05-18 | [20 empty] | 2020-06-17 |  |  |  | 2020-06-20 | [8 empty] | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-11 |  |  |  | 2020-05-14 |  |  | 2020-05-21 |  |  |  | 2020-05-24 |  |  | 2020-06-08 |  |  |  | 2020-06-20 |  | 2020-06-23
PH1600078 | 126.1812 | 9.0762 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Surigao Del Sur | Tandag City | San Agustin Norte | MIN | PH166819018 | 5485 | 45 | Three Legged Tubular Tower | CO64 | 71.669 | MIN-1600029 | Level 6 | phase3 | phase3 |  |  | Cluster M22 | Marrox | [7 empty] | 2020-02-14 |  | 2020-02-16 | [13 empty] | 2020-02-21 | [11 empty] | 2020-03-22 | [27 empty] | 2020-03-29 |  |  | 2020-04-28 |  | 2020-04-05 | [16 empty] | 2020-04-26 |  |  | 2020-05-05 | [6 empty] | 2020-05-19 |  |  |  | 2020-05-19 |  |  |  |  | 2020-04-12 |  | 2020-04-22 |  |  | 2020-04-26 |  | 2020-04-29 |  |  | 2020-05-13 |  |  |  | 2020-05-20 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-06-01 |  | 2020-05-10 | [6 empty] | 2020-06-09 | 2020-06-16 | [20 empty] | 2020-07-16 |  |  |  | 2020-07-19 | [8 empty] | 2020-05-25 |  | 2020-05-28 |  |  | 2020-06-09 |  |  |  | 2020-06-12 |  |  | 2020-06-19 |  |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  |  | 2020-07-19 |  | 2020-07-22
PH1600079 | 126.1914 | 9.0699 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Surigao Del Sur | Tandag City | Telaje | MIN | PH166819022 | 8771 | 45 | Three Legged Tubular Tower | CO64 | 72.6429 | MIN-1600030 | Level 6 | phase3 | phase3 |  |  | Cluster M22 | Marrox | [7 empty] | 2020-02-17 |  | 2020-02-19 | [13 empty] | 2020-02-24 | [11 empty] | 2020-03-25 | [27 empty] | 2020-04-01 |  |  | 2020-05-01 |  | 2020-04-08 | [16 empty] | 2020-04-29 |  |  | 2020-05-08 | [6 empty] | 2020-05-22 |  |  |  | 2020-05-22 |  |  |  |  | 2020-04-15 |  | 2020-04-25 |  |  | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-16 |  |  |  | 2020-05-23 |  | JGT-36-340C-2NPT |  |  | 2020-06-04 |  | 2020-05-13 | [6 empty] | 2020-06-12 | 2020-06-19 | [20 empty] | 2020-07-19 |  |  |  | 2020-07-22 | [8 empty] | 2020-05-28 |  | 2020-05-31 |  |  | 2020-06-12 |  |  |  | 2020-06-15 |  |  | 2020-06-22 |  |  |  | 2020-06-25 |  |  | 2020-07-10 |  |  |  | 2020-07-22 |  | 2020-07-25
PH1600082 | 126.2102 | 9.048 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Surigao Del Sur | Tandag City | Rosario | MIN | PH166819015 | 3262 | 45 | Three Legged Tubular Tower | CO64 | 74.3036 | MIN-1600031 | Level 6 | phase3 | phase3 |  | DepEd_3701 | Cluster M22 | Marrox | [7 empty] | 2020-02-20 |  | 2020-02-22 | [13 empty] | 2020-02-27 | [11 empty] | 2020-03-28 | [27 empty] | 2020-04-04 |  |  | 2020-05-04 |  | 2020-04-11 | [16 empty] | 2020-05-02 |  |  | 2020-05-11 | [6 empty] | 2020-05-25 |  |  |  | 2020-05-25 |  |  |  |  | 2020-04-18 |  | 2020-04-28 |  |  | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-19 |  |  |  | 2020-05-26 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-06-07 |  | 2020-05-16 | [6 empty] | 2020-06-15 | 2020-06-22 | [20 empty] | 2020-07-22 |  |  |  | 2020-07-25 | [8 empty] | 2020-05-31 |  | 2020-06-03 |  |  | 2020-06-15 |  |  |  | 2020-06-18 |  |  | 2020-06-25 |  |  |  | 2020-06-28 |  |  | 2020-07-13 |  |  |  | 2020-07-25 |  | 2020-07-28
PH1600085 | 126.3221 | 8.209 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Surigao Del Sur | Bislig City | Poblacion | MIN | PH166803012 | 9477 | 30 | Three Legged Tubular Tower | CO65 | 102.1334 | MIN-1600032 | Level 6 | phase3 | phase3 |  |  | Cluster M23 | Marrox | [7 empty] | 2020-02-23 |  | 2020-02-25 | [13 empty] | 2020-03-01 | [11 empty] | 2020-03-31 | [27 empty] | 2020-04-07 |  |  | 2020-05-07 |  | 2020-04-14 | [16 empty] | 2020-05-05 |  |  | 2020-05-14 | [6 empty] | 2020-05-28 |  |  |  | 2020-05-28 |  |  |  |  | 2020-04-21 |  | 2020-05-01 |  |  | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-22 |  |  |  | 2020-05-29 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-06-10 |  | 2020-05-19 | [6 empty] | 2020-06-18 | 2020-06-25 | [20 empty] | 2020-07-25 |  |  |  | 2020-07-28 | [8 empty] | 2020-06-03 |  | 2020-06-06 |  |  | 2020-06-18 |  |  |  | 2020-06-21 |  |  | 2020-06-28 |  |  |  | 2020-07-01 |  |  | 2020-07-16 |  |  |  | 2020-07-28 |  | 2020-07-31
PH1600087 | 126.3391 | 8.1841 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Surigao Del Sur | Bislig City | Mangagoy | MIN | PH166803025 | 3472 | 30 | Three Legged Tubular Tower | CO65 | 100.916 | MIN-1600033 | Level 6 | phase3 | phase3 |  |  | Cluster M23 | Marrox | [7 empty] | 2020-02-26 |  | 2020-02-28 | [13 empty] | 2020-03-04 | [11 empty] | 2020-04-03 | [27 empty] | 2020-04-10 |  |  | 2020-05-10 |  | 2020-04-17 | [16 empty] | 2020-05-08 |  |  | 2020-05-17 | [6 empty] | 2020-05-31 |  |  |  | 2020-05-31 |  |  |  |  | 2020-04-24 |  | 2020-05-04 |  |  | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-25 |  |  |  | 2020-06-01 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-06-13 |  | 2020-05-22 | [6 empty] | 2020-06-21 | 2020-06-28 | [20 empty] | 2020-07-28 |  |  |  | 2020-07-31 | [8 empty] | 2020-06-06 |  | 2020-06-09 |  |  | 2020-06-21 |  |  |  | 2020-06-24 |  |  | 2020-07-01 |  |  |  | 2020-07-04 |  |  | 2020-07-19 |  |  |  | 2020-07-31 |  | 2020-08-03
PH1600088 | 126.353 | 8.1853 | Suburban | Greenfield | Greenfield | Y1 | L7+L21 | Caraga (Region XIII) | Surigao Del Sur | Bislig City | Mangagoy | MIN | PH166803009 | 32464 | 30 | Three Legged Tubular Tower | CO65 | 101.9205 | MIN-1600034 | Level 6 | phase3 | phase3 |  | DepEd_3684 | Cluster M23 | Marrox | [7 empty] | 2020-02-29 | 2020-02-25 | 2020-03-02 | 2020-02-26 |  |  |  | 2020-02-26 | [8 empty] | 2020-03-07 | [11 empty] | 2020-04-06 | [27 empty] | 2020-04-13 |  |  | 2020-05-13 |  | 2020-04-20 | [16 empty] | 2020-05-11 |  |  | 2020-05-20 | [6 empty] | 2020-06-03 |  |  |  | 2020-06-03 |  |  |  |  | 2020-04-27 |  | 2020-05-07 |  |  | 2020-05-11 |  | 2020-05-14 |  |  | 2020-05-28 |  |  |  | 2020-06-04 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-06-16 |  | 2020-05-25 | [6 empty] | 2020-06-24 | 2020-07-01 | [20 empty] | 2020-07-31 |  |  |  | 2020-08-03 | [8 empty] | 2020-06-09 |  | 2020-06-12 |  |  | 2020-06-24 |  |  |  | 2020-06-27 |  |  | 2020-07-04 |  |  |  | 2020-07-07 |  |  | 2020-07-22 |  |  |  | 2020-08-03 |  | 2020-08-06
PH1600096 | 125.5248 | 8.9284 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Bonbon | MIN | PH160202090 | 11173 | 40 | Three Legged Tubular Tower | CO64 | 3.4206 | MIN-1600035 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-22 | 2020-01-17 | 2020-01-24 | 2020-01-18 | 2020-02-05 |  |  | 2020-01-18 | 2020-01-19 | 2020-02-09 |  |  | 2020-01-19 |  |  |  | 2020-01-29 |  | 2020-02-09 |  |  | 2020-02-09 | 2020-01-18 | 2020-02-05 |  |  | 2020-01-18 | 2020-02-25 | 2020-02-28 | [5 empty] | B | Dominique Albay | Purok 5, Villa Kananga, Butuan City | Agusan del Norte | 125.5348 | 8.9298 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-06 | 2020-02-13 |  | 2020-04-05 |  | 2020-03-13 | [11 empty] | 0912-7181749 |  |  |  |  | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 | 2020-02-26 | 2020-03-30 | 2020-02-29 | 2020-02-29 | 2020-04-03 | 2020-03-03 | 2020-04-06 | 2020-03-04 | 2020-03-04 | 2020-04-20 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-04-27 | 2020-03-04 | JGT-36-340C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1600098 | 125.5398 | 9.0957 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Cabadbaran City | Tolosa | MIN | PH160203018 | 6530 | 40 | Three Legged Tubular Tower | CO64 | 15.6266 | MIN-1600036 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-05-03 |  | 2020-05-05 | [13 empty] | 2020-05-10 | [11 empty] | 2020-06-09 | [27 empty] | 2020-06-16 |  |  | 2020-07-16 |  | 2020-06-23 | [16 empty] | 2020-07-14 |  |  | 2020-07-23 | [6 empty] | 2020-08-06 |  |  |  | 2020-08-06 |  |  |  |  | 2020-06-30 |  | 2020-07-10 |  |  | 2020-07-14 |  | 2020-07-17 |  |  | 2020-07-31 |  |  |  | 2020-08-07 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-08-19 |  | 2020-07-28 | [6 empty] | 2020-08-27 | 2020-09-03 | [20 empty] | 2020-10-03 |  |  |  | 2020-10-06 | [8 empty] | 2020-08-12 |  | 2020-08-15 |  |  | 2020-08-27 |  |  |  | 2020-08-30 |  |  | 2020-09-06 |  |  |  | 2020-09-09 |  |  | 2020-09-24 |  |  |  | 2020-10-06 |  | 2020-10-09
PH1600104 | 125.5444 | 8.8942 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Amparo | MIN | PH160202022 | 3166 | 40 | Three Legged Tubular Tower | CO64 | 6.7937 | MIN-1600037 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 | DepEd_3634 | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-19 | 2020-01-21 | 2020-01-21 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-02 |  |  |  | 2020-02-02 |  |  |  | 2020-01-26 | 2020-02-02 |  |  |  | 2020-02-02 | 2020-02-01 |  |  |  | 2020-02-01 | 2020-02-19 | 2020-02-25 | [5 empty] | A | Pio Sumampong | Purok 15, Upper Mandacpan, San Vicente Butuan City | Agusan del Norte | 125.5477 | 8.9026 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-03 | 2020-02-12 |  | 2020-04-02 | 2020-03-10 | 2020-03-10 | [16 empty] | 2020-03-31 |  |  | 2020-04-09 | [6 empty] | 2020-04-23 |  |  |  | 2020-04-23 |  |  |  | Awaiting MOC approval | 2020-03-17 | 2020-02-26 | 2020-03-27 | 2020-02-29 | 2020-02-29 | 2020-03-31 | 2020-03-03 | 2020-04-03 | 2020-03-04 | 2020-03-06 | 2020-04-17 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-04-24 | 2020-03-04 | JGT-36-340C-2NPT |  |  | 2020-05-06 |  | 2020-04-14 | [6 empty] | 2020-05-14 | 2020-05-21 | [20 empty] | 2020-06-20 |  |  |  | 2020-06-23 | [8 empty] | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-11 |  |  |  | 2020-06-23 |  | 2020-06-26
PH1600107 | 125.5557 | 8.9579 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Golden Ribbon Pob. (Bgy. 2) | MIN | PH160202012 | 11308 | 40 | Three Legged Tubular Tower | CO64 | 1.7275 | MIN-1600038 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-19 | 2020-01-18 | 2020-01-21 | 2020-02-14 | 2020-02-26 |  |  | 2020-02-14 | 2020-02-23 |  |  |  | 2020-02-23 |  |  |  | 2020-01-26 | 2020-02-23 |  |  |  | 2020-02-23 | 2020-03-03 |  |  |  | 2020-03-03 | 2020-03-04 | 2020-02-25 | 2020-03-04 |  |  | 2020-03-05 | 2020-03-05 |  | Cheryl Medrano | Purok 4, Baan Kub, Butuan City | Agusan del Norte | 125.5668 | 8.9475 | Greenfield |  |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-03 | 2020-02-24 |  | 2020-04-02 |  | 2020-03-10 | [16 empty] | 2020-03-31 |  |  | 2020-04-09 | [6 empty] | 2020-04-23 |  |  |  | 2020-04-23 |  |  |  |  | 2020-03-17 |  | 2020-03-27 |  |  | 2020-03-31 |  | 2020-04-03 |  |  | 2020-04-17 |  |  |  | 2020-04-24 |  | JGT-36-340C-2NPT |  |  | 2020-05-06 |  | 2020-04-14 | [6 empty] | 2020-05-14 | 2020-05-21 | [20 empty] | 2020-06-20 |  |  |  | 2020-06-23 | [8 empty] | 2020-04-29 |  | 2020-05-02 |  |  | 2020-05-14 |  |  |  | 2020-05-17 |  |  | 2020-05-24 |  |  |  | 2020-05-27 |  |  | 2020-06-11 |  |  |  | 2020-06-23 |  | 2020-06-26
PH1600116 | 125.7588 | 8.7043 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Sur | Bayugan City | Marcelina | MIN | PH160301029 | 3918 | 40 | Three Legged Tubular Tower | CO64 | 36.8005 | MIN-1600039 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-03-03 |  | 2020-03-05 | [13 empty] | 2020-03-10 | [11 empty] | 2020-04-09 | [27 empty] | 2020-04-16 |  |  | 2020-05-16 |  | 2020-04-23 | [16 empty] | 2020-05-14 |  |  | 2020-05-23 | [6 empty] | 2020-06-06 |  |  |  | 2020-06-06 |  |  |  |  | 2020-04-30 |  | 2020-05-10 |  |  | 2020-05-14 |  | 2020-05-17 |  |  | 2020-05-31 |  |  |  | 2020-06-07 |  | JGT-36-340C-2NPT |  |  | 2020-06-19 |  | 2020-05-28 | [6 empty] | 2020-06-27 | 2020-07-04 | [20 empty] | 2020-08-03 |  |  |  | 2020-08-06 | [8 empty] | 2020-06-12 |  | 2020-06-15 |  |  | 2020-06-27 |  |  |  | 2020-06-30 |  |  | 2020-07-07 |  |  |  | 2020-07-10 |  |  | 2020-07-25 |  |  |  | 2020-08-06 |  | 2020-08-09
PH1600117 | 126.1971 | 9.054 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Sur | Tandag City | Telaje | MIN | PH166819008 | 6271 | 40 | Three Legged Tubular Tower | CO64 | 72.9677 | MIN-1600040 | Level 6 | phase3 | phase3 |  |  | Cluster M22 | Marrox | [7 empty] | 2020-03-06 |  | 2020-03-08 | [13 empty] | 2020-03-13 | [11 empty] | 2020-04-12 | [27 empty] | 2020-04-19 |  |  | 2020-05-19 |  | 2020-04-26 | [16 empty] | 2020-05-17 |  |  | 2020-05-26 | [6 empty] | 2020-06-09 |  |  |  | 2020-06-09 |  |  |  |  | 2020-05-03 |  | 2020-05-13 |  |  | 2020-05-17 |  | 2020-05-20 |  |  | 2020-06-03 |  |  |  | 2020-06-10 |  | 4GT-42-340C-2NPT |  |  | 2020-06-22 |  | 2020-05-31 | [6 empty] | 2020-06-30 | 2020-07-07 | [20 empty] | 2020-08-06 |  |  |  | 2020-08-09 | [8 empty] | 2020-06-15 |  | 2020-06-18 |  |  | 2020-06-30 |  |  |  | 2020-07-03 |  |  | 2020-07-10 |  |  |  | 2020-07-13 |  |  | 2020-07-28 |  |  |  | 2020-08-09 |  | 2020-08-12
PH1600120 | 126.3111 | 8.2142 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Sur | Bislig City | Poblacion | MIN | PH166803012 | 9477 | 40 | Three Legged Tubular Tower | CO65 | 101.9534 | MIN-1600041 | Level 6 | phase3 | phase3 |  |  | Cluster M23 | Marrox | [7 empty] | 2020-03-09 |  | 2020-03-11 | [13 empty] | 2020-03-16 | [11 empty] | 2020-04-15 | [27 empty] | 2020-04-22 |  |  | 2020-05-22 |  | 2020-04-29 | [16 empty] | 2020-05-20 |  |  | 2020-05-29 | [6 empty] | 2020-06-12 |  |  |  | 2020-06-12 |  |  |  |  | 2020-05-06 |  | 2020-05-16 |  |  | 2020-05-20 |  | 2020-05-23 |  |  | 2020-06-06 |  |  |  | 2020-06-13 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-06-25 |  | 2020-06-03 | [6 empty] | 2020-07-03 | 2020-07-10 | [20 empty] | 2020-08-09 |  |  |  | 2020-08-12 | [8 empty] | 2020-06-18 |  | 2020-06-21 |  |  | 2020-07-03 |  |  |  | 2020-07-06 |  |  | 2020-07-13 |  |  |  | 2020-07-16 |  |  | 2020-07-31 |  |  |  | 2020-08-12 |  | 2020-08-15
PH1600121 | 126.3598 | 8.1787 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Sur | Bislig City | Mangagoy | MIN | PH166803020 | 13015 | 40 | Three Legged Tubular Tower | CO65 | 101.7689 | MIN-1600042 | Level 6 | phase3 | phase3 |  |  | Cluster M23 | Marrox | [7 empty] | 2020-03-12 |  | 2020-03-14 | [13 empty] | 2020-03-19 | [11 empty] | 2020-04-18 | [27 empty] | 2020-04-25 |  |  | 2020-05-25 |  | 2020-05-02 | [16 empty] | 2020-05-23 |  |  | 2020-06-01 | [6 empty] | 2020-06-15 |  |  |  | 2020-06-15 |  |  |  |  | 2020-05-09 |  | 2020-05-19 |  |  | 2020-05-23 |  | 2020-05-26 |  |  | 2020-06-09 |  |  |  | 2020-06-16 |  | 4GT-42-340C-2NPT |  |  | 2020-06-28 |  | 2020-06-06 | [6 empty] | 2020-07-06 | 2020-07-13 | [20 empty] | 2020-08-12 |  |  |  | 2020-08-15 | [8 empty] | 2020-06-21 |  | 2020-06-24 |  |  | 2020-07-06 |  |  |  | 2020-07-09 |  |  | 2020-07-16 |  |  |  | 2020-07-19 |  |  | 2020-08-03 |  |  |  | 2020-08-15 |  | 2020-08-18
PH1600125 | 125.4871 | 8.9969 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Masao | MIN | PH160202067 | 1786 | 40 | Three Legged Tubular Tower | CO64 | 7.4609 | MIN-1600043 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-25 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-01-27 |  |  |  | 2020-01-27 |  |  |  | 2020-02-01 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-01-24 |  |  |  | 2020-01-24 | 2020-03-06 | 2020-03-02 | 2020-03-09 |  |  | 2020-03-09 |  | A | Alex Dimata | Purok 3, Masao, Butuan City | Agusan del Norte | 125.486 | 8.9971 | Greenfield |  |  | 10 years | P20,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-09 | 2020-02-24 |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 | 2020-02-27 | 2020-04-02 | 2020-03-09 | 2020-03-09 | 2020-04-06 | 2020-03-05 | 2020-04-09 | 2020-03-06 | 2020-03-08 | 2020-04-23 | 2020-03-09 | 2020-03-09 | 2020-03-09 | 2020-04-30 | 2020-03-09 | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1600126 | 125.6117 | 8.9929 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Ampayon | MIN | PH160202080 | 4989 | 40 | Three Legged Tubular Tower | CO64 | 8.9037 | MIN-1600044 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-22 | 2020-01-18 | 2020-01-24 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-01-30 |  |  |  | 2020-01-30 |  |  |  | 2020-01-29 | 2020-01-30 |  |  |  | 2020-01-30 | 2020-01-29 |  |  |  | 2020-01-29 | 2020-02-19 | 2020-02-28 | [5 empty] | A | Leonila Arconada | Purok 1, Sumihilon, Butuan City | Agusan del Norte | 125.6148 | 8.9841 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-06 | 2020-02-12 |  | 2020-04-05 | 2020-03-10 | 2020-03-13 | [16 empty] | 2020-04-03 | ok |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  | Awaiting MOC approval | 2020-03-20 | 2020-02-26 | 2020-03-30 | 2020-02-29 | 2020-02-29 | 2020-04-03 | 2020-03-05 | 2020-04-06 | 2020-03-06 | 2020-03-06 | 2020-04-20 | 2020-03-06 | 2020-03-06 | 2020-03-06 | 2020-04-27 | 2020-03-06 | JGT-36-340C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1600127 | 125.6351 | 8.9354 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Basag | MIN | PH160202084 | 4100 | 40 | Three Legged Tubular Tower | CO64 | 10.6466 | MIN-1600045 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-05-06 |  | 2020-05-08 | [13 empty] | 2020-05-13 | [11 empty] | 2020-06-12 | [27 empty] | 2020-06-19 |  |  | 2020-07-19 |  | 2020-06-26 | [16 empty] | 2020-07-17 |  |  | 2020-07-26 | [6 empty] | 2020-08-09 |  |  |  | 2020-08-09 |  |  |  |  | 2020-07-03 |  | 2020-07-13 |  |  | 2020-07-17 |  | 2020-07-20 |  |  | 2020-08-03 |  |  |  | 2020-08-10 |  | 4GT-42-340C-2NPT |  |  | 2020-08-22 |  | 2020-07-31 | [6 empty] | 2020-08-30 | 2020-09-06 | [20 empty] | 2020-10-06 |  |  |  | 2020-10-09 | [8 empty] | 2020-08-15 |  | 2020-08-18 |  |  | 2020-08-30 |  |  |  | 2020-09-02 |  |  | 2020-09-09 |  |  |  | 2020-09-12 |  |  | 2020-09-27 |  |  |  | 2020-10-09 |  | 2020-10-12
PH1600131 | 125.4597 | 9.7571 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Norte | Surigao City | San Roque | MIN | PH166724019 | 593 | 40 | Three Legged Tubular Tower | CO64 | 89.6172 | MIN-1600046 | Level 6 | phase3 | phase3 |  |  | Cluster M11 | Marrox | [7 empty] | 2020-03-15 |  | 2020-03-17 | [13 empty] | 2020-03-22 | [11 empty] | 2020-04-21 | [27 empty] | 2020-04-28 |  |  | 2020-05-28 |  | 2020-05-05 | [16 empty] | 2020-05-26 |  |  | 2020-06-04 | [6 empty] | 2020-06-18 |  |  |  | 2020-06-18 |  |  |  |  | 2020-05-12 |  | 2020-05-22 |  |  | 2020-05-26 |  | 2020-05-29 |  |  | 2020-06-12 |  |  |  | 2020-06-19 |  | 4GT-42-340C-2NPT |  |  | 2020-07-01 |  | 2020-06-09 | [6 empty] | 2020-07-09 | 2020-07-16 | [20 empty] | 2020-08-15 |  |  |  | 2020-08-18 | [8 empty] | 2020-06-24 |  | 2020-06-27 |  |  | 2020-07-09 |  |  |  | 2020-07-12 |  |  | 2020-07-19 |  |  |  | 2020-07-22 |  |  | 2020-08-06 |  |  |  | 2020-08-18 |  | 2020-08-21
PH1600132 | 125.4461 | 9.7947 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Norte | Surigao City | Ipil | MIN | PH166724022 | 4323 | 40 | Three Legged Tubular Tower | CO64 | 93.9297 | MIN-1600047 | Level 6 | phase3 | phase3 |  |  | Cluster M11 | Marrox | [7 empty] | 2020-03-18 |  | 2020-03-20 | [13 empty] | 2020-03-25 | [11 empty] | 2020-04-24 | [27 empty] | 2020-05-01 |  |  | 2020-05-31 |  | 2020-05-08 | [16 empty] | 2020-05-29 |  |  | 2020-06-07 | [6 empty] | 2020-06-21 |  |  |  | 2020-06-21 |  |  |  |  | 2020-05-15 |  | 2020-05-25 |  |  | 2020-05-29 |  | 2020-06-01 |  |  | 2020-06-15 |  |  |  | 2020-06-22 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-07-04 |  | 2020-06-12 | [6 empty] | 2020-07-12 | 2020-07-19 | [20 empty] | 2020-08-18 |  |  |  | 2020-08-21 | [8 empty] | 2020-06-27 |  | 2020-06-30 |  |  | 2020-07-12 |  |  |  | 2020-07-15 |  |  | 2020-07-22 |  |  |  | 2020-07-25 |  |  | 2020-08-09 |  |  |  | 2020-08-21 |  | 2020-08-24
PH1600133 | 126.2891 | 8.238 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Sur | Bislig City | San Roque (Cadanglasan) | MIN | PH166803023 | 1162 | 40 | Three Legged Tubular Tower | CO65 | 102.9097 | MIN-1600048 | Level 6 | phase3 | phase3 |  |  | Cluster M23 | Marrox | [7 empty] | 2020-03-21 |  | 2020-03-23 | [13 empty] | 2020-03-28 | [11 empty] | 2020-04-27 | [27 empty] | 2020-05-04 |  |  | 2020-06-03 |  | 2020-05-11 | [16 empty] | 2020-06-01 |  |  | 2020-06-10 | [6 empty] | 2020-06-24 |  |  |  | 2020-06-24 |  |  |  |  | 2020-05-18 |  | 2020-05-28 |  |  | 2020-06-01 |  | 2020-06-04 |  |  | 2020-06-18 |  |  |  | 2020-06-25 |  | 4GT-42-340C-2NPT |  |  | 2020-07-07 |  | 2020-06-15 | [6 empty] | 2020-07-15 | 2020-07-22 | [20 empty] | 2020-08-21 |  |  |  | 2020-08-24 | [8 empty] | 2020-06-30 |  | 2020-07-03 |  |  | 2020-07-15 |  |  |  | 2020-07-18 |  |  | 2020-07-25 |  |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  |  | 2020-08-24 |  | 2020-08-27
PH1600142 | 125.4059 | 8.9699 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Buenavista | Poblacion 5 | MIN | PH160201014 | 1435 | 40 | Three Legged Tubular Tower | CO64 | 14.8512 | MIN-1600049 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-05-09 |  | 2020-05-11 | [13 empty] | 2020-05-16 | [11 empty] | 2020-06-15 | [27 empty] | 2020-06-22 |  |  | 2020-07-22 |  | 2020-06-29 | [16 empty] | 2020-07-20 |  |  | 2020-07-29 | [6 empty] | 2020-08-12 |  |  |  | 2020-08-12 |  |  |  |  | 2020-07-06 |  | 2020-07-16 |  |  | 2020-07-20 |  | 2020-07-23 |  |  | 2020-08-06 |  |  |  | 2020-08-13 |  | JGT-36-340C-2NPT |  |  | 2020-08-25 |  | 2020-08-03 | [6 empty] | 2020-09-02 | 2020-09-09 | [20 empty] | 2020-10-09 |  |  |  | 2020-10-12 | [8 empty] | 2020-08-18 |  | 2020-08-21 |  |  | 2020-09-02 |  |  |  | 2020-09-05 |  |  | 2020-09-12 |  |  |  | 2020-09-15 |  |  | 2020-09-30 |  |  |  | 2020-10-12 |  | 2020-10-15
PH1600146 | 125.5997 | 9.0293 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Baobaoan | MIN | PH160202100 | 2658 | 40 | Three Legged Tubular Tower | CO64 | 10.5205 | MIN-1600050 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-25 | 2020-01-24 | 2020-01-27 |  |  | 2020-01-29 |  | 2020-01-29 | 2020-01-30 |  |  |  | 2020-01-30 |  |  |  | 2020-02-01 |  |  | 2020-01-30 |  | 2020-01-30 |  |  | 2020-01-29 |  | 2020-01-29 | 2020-02-19 | 2020-03-02 | 2020-03-13 |  |  | 2020-03-12 | 2020-03-13 | C | Ray Yuson | Purok 12, Los Angeles, Butuan City | Agusan del Norte | 125.6094 | 9.0151 | Greenfield |  |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-09 | 2020-02-12 |  | 2020-04-08 | 2020-03-09 | 2020-03-16 | [16 empty] | 2020-04-06 | ok |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  | For RFP submission in DingTalk | 2020-03-23 | 2020-02-26 | 2020-04-02 | 2020-02-29 | 2020-02-29 | 2020-04-06 | 2020-03-05 | 2020-04-09 | 2020-03-06 | 2020-03-06 | 2020-04-23 | 2020-03-08 | 2020-03-08 | 2020-03-08 | 2020-04-30 | 2020-03-08 | JGT-36-340C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1600151 | 126.0014 | 8.3838 | Rural |  |  | Y3 |  | Caraga (Region XIII) | Agusan del Sur | Rosario | Poblacion | MIN | PH160307006 | [5 empty] | MIN-1600071 | Level 1 (OA) |  |  | Site Cancel |  | Cluster M23 | Marrox | PO2020010202PH_WLS | Batch 2 (additional) | [5 empty] | 2020-03-24 | 2020-01-23 | 2020-03-26 | 2020-01-24 |  |  |  | 2020-01-24 | [8 empty] | 2020-03-31 | [5 empty] | 2020-01-24 |  |  |  | 2020-01-24 |  | 2020-04-30 | [27 empty] | 2020-05-07 |  |  | 2020-06-06 |  | 2020-05-14 | [16 empty] | 2020-06-04 |  |  | 2020-06-13 | [6 empty] | 2020-06-27 |  |  |  | 2020-06-27 |  |  |  |  | 2020-05-21 |  | 2020-05-31 |  |  | 2020-06-04 |  | 2020-06-07 |  |  | 2020-06-21 |  |  |  | 2020-06-28 |  |  |  |  | 2020-07-10 |  | 2020-06-18 | [6 empty] | 2020-07-18 | 2020-07-25 | [20 empty] | 2020-08-24 |  |  |  | 2020-08-27 | [8 empty] | 2020-07-03 |  | 2020-07-06 |  |  | 2020-07-18 |  |  |  | 2020-07-21 |  |  | 2020-07-28 |  |  |  | 2020-07-31 |  |  | 2020-08-15 |  |  |  | 2020-08-27 |  | 2020-08-30
PH1600164 | 125.4796 | 9.7237 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Norte | Surigao City | Mat-I | MIN | PH166724031 | 5722 | 40 | Three Legged Tubular Tower | CO64 | 85.7203 | MIN-1600051 | Level 6 | phase3 | phase3 |  |  | Cluster M11 | Marrox | [7 empty] | 2020-03-27 |  | 2020-03-29 | [13 empty] | 2020-04-03 | [11 empty] | 2020-05-03 | [27 empty] | 2020-05-10 |  |  | 2020-06-09 |  | 2020-05-17 | [16 empty] | 2020-06-07 |  |  | 2020-06-16 | [6 empty] | 2020-06-30 |  |  |  | 2020-06-30 |  |  |  |  | 2020-05-24 |  | 2020-06-03 |  |  | 2020-06-07 |  | 2020-06-10 |  |  | 2020-06-24 |  |  |  | 2020-07-01 |  | JGT-36-340C-2NPT |  |  | 2020-07-13 |  | 2020-06-21 | [6 empty] | 2020-07-21 | 2020-07-28 | [20 empty] | 2020-08-27 |  |  |  | 2020-08-30 | [8 empty] | 2020-07-06 |  | 2020-07-09 |  |  | 2020-07-21 |  |  |  | 2020-07-24 |  |  | 2020-07-31 |  |  |  | 2020-08-03 |  |  | 2020-08-18 |  |  |  | 2020-08-30 |  | 2020-09-02
PH1600171 | 125.4314 | 8.9523 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Buenavista | Talo-Ao | MIN | PH160201026 | 1825 | 40 | Three Legged Tubular Tower | CO64 | 11.9564 | MIN-1600052 | Level 6 | phase3 | phase2_1231 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-05-12 |  | 2020-05-14 | [13 empty] | 2020-05-19 | [11 empty] | 2020-06-18 | [27 empty] | 2020-06-25 |  |  | 2020-07-25 |  | 2020-07-02 | [16 empty] | 2020-07-23 |  |  | 2020-08-01 | [6 empty] | 2020-08-15 |  |  |  | 2020-08-15 |  |  |  |  | 2020-07-09 |  | 2020-07-19 |  |  | 2020-07-23 |  | 2020-07-26 |  |  | 2020-08-09 |  |  |  | 2020-08-16 |  | JGT-36-340C-2NPT |  |  | 2020-08-28 |  | 2020-08-06 | [6 empty] | 2020-09-05 | 2020-09-12 | [20 empty] | 2020-10-12 |  |  |  | 2020-10-15 | [8 empty] | 2020-08-21 |  | 2020-08-24 |  |  | 2020-09-05 |  |  |  | 2020-09-08 |  |  | 2020-09-15 |  |  |  | 2020-09-18 |  |  | 2020-10-03 |  |  |  | 2020-10-15 |  | 2020-10-18
PH1600236 | 125.5061 | 8.9124 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Bit-Os | MIN | PH160202025 | 5446 | 40 | Three Legged Tubular Tower | CO64 | 6.0547 | MIN-1600053 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-28 | 2020-01-16 | 2020-01-30 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-01-28 |  |  |  | 2020-01-28 |  |  |  | 2020-02-04 | 2020-01-28 |  |  |  | 2020-01-28 | 2020-01-27 |  |  |  | 2020-01-27 | 2020-02-19 | 2020-03-05 | [5 empty] | A | Rommel A. Endozo | Purok 4, Bonbon, Butuan City | Agusan del Norte | 125.5047 | 8.9322 | Greenfield | 19m |  | 10 years | P20,000 exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-12 | 2020-02-12 |  | 2020-04-11 |  | 2020-03-19 | [16 empty] | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 | 2020-02-27 | 2020-04-05 | 2020-03-09 | 2020-03-09 | 2020-04-09 | 2020-03-03 | 2020-04-12 | 2020-03-05 | 2020-03-05 | 2020-04-26 | 2020-03-09 | 2020-03-09 | 2020-03-09 | 2020-05-03 | 2020-03-09 | JGT-36-340C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1600242 | 125.3457 | 8.9847 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Nasipit | Punta | MIN | PH160209015 | 1319 | 40 | Three Legged Tubular Tower | CO64 | 21.6165 | MIN-1600054 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-05-15 |  | 2020-05-17 | [13 empty] | 2020-05-22 | [11 empty] | 2020-06-21 | [27 empty] | 2020-06-28 |  |  | 2020-07-28 |  | 2020-07-05 | [16 empty] | 2020-07-26 |  |  | 2020-08-04 | [6 empty] | 2020-08-18 |  |  |  | 2020-08-18 |  |  |  |  | 2020-07-12 |  | 2020-07-22 |  |  | 2020-07-26 |  | 2020-07-29 |  |  | 2020-08-12 |  |  |  | 2020-08-19 |  | 4GT-42-340C-2NPT（340KPH/D） |  |  | 2020-08-31 |  | 2020-08-09 | [6 empty] | 2020-09-08 | 2020-09-15 | [20 empty] | 2020-10-15 |  |  |  | 2020-10-18 | [8 empty] | 2020-08-24 |  | 2020-08-27 |  |  | 2020-09-08 |  |  |  | 2020-09-11 |  |  | 2020-09-18 |  |  |  | 2020-09-21 |  |  | 2020-10-06 |  |  |  | 2020-10-18 |  | 2020-10-21
PH1600264 | 126.064 | 8.0452 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Sur | Trento | Poblacion | MIN | PH160312006 | 18139 | 40 | Monopole Tower | CO65 | 72.4967 | MIN-1600055 | Level 1 (OA) | phase3 | phase3 | OA_630 |  | Cluster M23 | Marrox | PO2020010202PH_WLS | Batch 2 (additional) | JXD-2 |  | Enovell |  |  | 2020-01-30 | 2020-01-17 | 2020-02-01 | 2020-01-18 | 2020-01-24 | 2020-01-24 |  | 2020-01-18 | 2020-01-19 | 2020-01-24 |  |  | 2020-01-19 |  |  |  | 2020-02-06 |  | 2020-01-24 |  |  | 2020-01-24 | 2020-01-18 | 2020-01-24 | 2020-01-24 |  | 2020-01-18 | 2020-03-05 | 2020-03-07 | 2020-03-06 |  |  | 2020-03-05 | 2020-03-06 | A | Emmia Haddley | Purok 8-A, Poblacion, Trento | Agusan del Sur | 126.057 | 8.0441 | Greenfield | 44m |  | 10 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-14 | 2020-02-24 |  | 2020-04-13 |  | 2020-03-21 | [16 empty] | 2020-04-11 |  |  | 2020-04-20 | [6 empty] | 2020-05-04 |  |  |  | 2020-05-04 |  |  |  |  | 2020-03-28 | 2020-02-28 | 2020-04-07 | 2020-03-06 | 2020-03-06 | 2020-04-11 | 2020-02-20 | 2020-04-14 | 2020-02-20 | 2020-02-21 | 2020-04-28 | 2020-02-20 |  |  | 2020-05-05 |  | JGT-36-340C-2NPT |  |  | 2020-05-17 |  | 2020-04-25 | [6 empty] | 2020-05-25 | 2020-06-01 | [20 empty] | 2020-07-01 |  |  |  | 2020-07-04 | [8 empty] | 2020-05-10 |  | 2020-05-13 |  |  | 2020-05-25 |  |  |  | 2020-05-28 |  |  | 2020-06-04 |  |  |  | 2020-06-07 |  |  | 2020-06-22 |  |  |  | 2020-07-04 |  | 2020-07-07
PH1600269 | 125.538 | 9.7539 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Norte | Surigao City | Capalayan | MIN | PH166724067 | 1114 | 40 | Three Legged Tubular Tower | CO64 | 88.8196 | MIN-1600056 | Level 6 | phase3 | phase3 |  |  | Cluster M11 | Marrox | [7 empty] | 2020-03-30 |  | 2020-04-01 | [13 empty] | 2020-04-06 | [11 empty] | 2020-05-06 | [27 empty] | 2020-05-13 |  |  | 2020-06-12 |  | 2020-05-20 | [16 empty] | 2020-06-10 |  |  | 2020-06-19 | [6 empty] | 2020-07-03 |  |  |  | 2020-07-03 |  |  |  |  | 2020-05-27 |  | 2020-06-06 |  |  | 2020-06-10 |  | 2020-06-13 |  |  | 2020-06-27 |  |  |  | 2020-07-04 |  | JGT-36-340C-2NPT |  |  | 2020-07-16 |  | 2020-06-24 | [6 empty] | 2020-07-24 | 2020-07-31 | [20 empty] | 2020-08-30 |  |  |  | 2020-09-02 | [8 empty] | 2020-07-09 |  | 2020-07-12 |  |  | 2020-07-24 |  |  |  | 2020-07-27 |  |  | 2020-08-03 |  |  |  | 2020-08-06 |  |  | 2020-08-21 |  |  |  | 2020-09-02 |  | 2020-09-05
PH1600272 | 125.6032 | 8.8835 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Don Francisco | MIN | PH160202099 | 1580 | 45 | Three Legged Tubular Tower | CO64 | 10.5483 | MIN-1600057 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-22 | 2020-01-21 | 2020-01-24 | 2020-01-22 | 2020-01-22 | 2020-01-31 | 2020-01-31 | 2020-01-22 | 2020-01-25 |  | 2020-02-02 |  | 2020-01-25 |  |  |  | 2020-01-29 |  |  | 2020-02-02 |  | 2020-02-02 | 2020-01-22 | 2020-01-22 | 2020-01-31 | 2020-01-31 | 2020-01-22 | 2020-03-06 | 2020-02-28 | 2020-03-07 |  |  | 2020-03-06 | 2020-03-07 | D | Warlito Compesino | Purok 6A, Tagabaca, Butuan City | Agusan del Norte | 125.5744 | 8.8988 | Greenfield |  |  | 10 years | P20,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-06 | 2020-02-12 |  | 2020-04-05 |  | 2020-03-13 | [16 empty] | 2020-04-03 |  |  | 2020-04-12 | [6 empty] | 2020-04-26 |  |  |  | 2020-04-26 |  |  |  |  | 2020-03-20 | 2020-02-26 | 2020-03-30 | 2020-02-29 | 2020-02-29 | 2020-04-03 | 2020-03-03 | 2020-04-06 | 2020-03-04 | 2020-03-04 | 2020-04-20 | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-04-27 | 2020-03-04 | 4GT-42-340C-2NPT |  |  | 2020-05-09 |  | 2020-04-17 | [6 empty] | 2020-05-17 | 2020-05-24 | [20 empty] | 2020-06-23 |  |  |  | 2020-06-26 | [8 empty] | 2020-05-02 |  | 2020-05-05 |  |  | 2020-05-17 |  |  |  | 2020-05-20 |  |  | 2020-05-27 |  |  |  | 2020-05-30 |  |  | 2020-06-14 |  |  |  | 2020-06-26 |  | 2020-06-29
PH1600273 | 125.5974 | 8.9174 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Pigdaulan | MIN | PH160202031 | 1258 | 45 | Three Legged Tubular Tower | CO64 | 7.5467 | MIN-1600058 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-25 | 2020-01-23 | 2020-01-27 | 2020-01-24 | 2020-01-24 | 2020-02-03 | 2020-02-03 | 2020-01-24 |  |  | 2020-02-06 |  | 2020-02-06 |  |  |  | 2020-02-01 |  |  | 2020-02-06 |  | 2020-02-06 | 2020-01-24 | 2020-01-24 | 2020-02-03 | 2020-02-03 | 2020-01-24 | 2020-03-06 | 2020-03-02 | 2020-03-07 |  |  | 2020-03-06 | 2020-03-07 | A | Estrella Aray | Purok 1B, Pigdaulan, Butuan City | Agusan del Norte | 125.5852 | 8.9149 | Greenfield |  |  | 10 years | P20,000 Exclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-09 | 2020-02-24 |  | 2020-04-08 |  | 2020-03-16 | [16 empty] | 2020-04-06 |  |  | 2020-04-15 | [6 empty] | 2020-04-29 |  |  |  | 2020-04-29 |  |  |  |  | 2020-03-23 | 2020-02-27 | 2020-04-02 | 2020-03-03 | 2020-03-03 | 2020-04-06 | 2020-03-03 | 2020-04-09 | 2020-03-05 | 2020-03-05 | 2020-04-23 | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-04-30 | 2020-03-12 | JGT-36-340C-2NPT |  |  | 2020-05-12 |  | 2020-04-20 | [6 empty] | 2020-05-20 | 2020-05-27 | [20 empty] | 2020-06-26 |  |  |  | 2020-06-29 | [8 empty] | 2020-05-05 |  | 2020-05-08 |  |  | 2020-05-20 |  |  |  | 2020-05-23 |  |  | 2020-05-30 |  |  |  | 2020-06-02 |  |  | 2020-06-17 |  |  |  | 2020-06-29 |  | 2020-07-02
PH1600275 | 125.4841 | 8.8744 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Nong-Nong | MIN | PH160202096 | 1594 | 45 | Three Legged Tubular Tower | CO64 | 10.8918 | MIN-1600059 | Level 6 | phase3 | phase3 |  | DICT_5 | Cluster M21 | Marrox | [7 empty] | 2020-05-18 |  | 2020-05-20 | [13 empty] | 2020-05-25 | [11 empty] | 2020-06-24 | [27 empty] | 2020-07-01 |  |  | 2020-07-31 |  | 2020-07-08 | [16 empty] | 2020-07-29 |  |  | 2020-08-07 | [6 empty] | 2020-08-21 |  |  |  | 2020-08-21 |  |  |  |  | 2020-07-15 |  | 2020-07-25 |  |  | 2020-07-29 |  | 2020-08-01 |  |  | 2020-08-15 |  |  |  | 2020-08-22 |  | 4GT-42-340C-2NPT |  |  | 2020-09-03 |  | 2020-08-12 | [6 empty] | 2020-09-11 | 2020-09-18 | [20 empty] | 2020-10-18 |  |  |  | 2020-10-21 | [8 empty] | 2020-08-27 |  | 2020-08-30 |  |  | 2020-09-11 |  |  |  | 2020-09-14 |  |  | 2020-09-21 |  |  |  | 2020-09-24 |  |  | 2020-10-09 |  |  |  | 2020-10-21 |  | 2020-10-24
PH1600279 | 125.6989 | 9.0052 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Pianing | MIN | PH160202008 | 3864 | 45 | Three Legged Tubular Tower | CO64 | 18.2951 | MIN-1600060 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-05-21 |  | 2020-05-23 | [13 empty] | 2020-05-28 | [11 empty] | 2020-06-27 | [27 empty] | 2020-07-04 |  |  | 2020-08-03 |  | 2020-07-11 | [16 empty] | 2020-08-01 |  |  | 2020-08-10 | [6 empty] | 2020-08-24 |  |  |  | 2020-08-24 |  |  |  |  | 2020-07-18 |  | 2020-07-28 |  |  | 2020-08-01 |  | 2020-08-04 |  |  | 2020-08-18 |  |  |  | 2020-08-25 |  | 4GT-42-340C-2NPT |  |  | 2020-09-06 |  | 2020-08-15 | [6 empty] | 2020-09-14 | 2020-09-21 | [20 empty] | 2020-10-21 |  |  |  | 2020-10-24 | [8 empty] | 2020-08-30 |  | 2020-09-02 |  |  | 2020-09-14 |  |  |  | 2020-09-17 |  |  | 2020-09-24 |  |  |  | 2020-09-27 |  |  | 2020-10-12 |  |  |  | 2020-10-24 |  | 2020-10-27
PH1600286 | 126.163 | 9.0601 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Sur | Tandag City | Quezon | MIN | PH166819014 | 1468 | 45 | Three Legged Tubular Tower | CO64 | 69.3826 | MIN-1600061 | Level 6 | phase3 | phase3 |  |  | Cluster M22 | Marrox | [7 empty] | 2020-04-02 |  | 2020-04-04 | [13 empty] | 2020-04-09 | [11 empty] | 2020-05-09 | [27 empty] | 2020-05-16 |  |  | 2020-06-15 |  | 2020-05-23 | [16 empty] | 2020-06-13 |  |  | 2020-06-22 | [6 empty] | 2020-07-06 |  |  |  | 2020-07-06 |  |  |  |  | 2020-05-30 |  | 2020-06-09 |  |  | 2020-06-13 |  | 2020-06-16 |  |  | 2020-06-30 |  |  |  | 2020-07-07 |  | 4GT-42-340C-2NPT |  |  | 2020-07-19 |  | 2020-06-27 | [6 empty] | 2020-07-27 | 2020-08-03 | [20 empty] | 2020-09-02 |  |  |  | 2020-09-05 | [8 empty] | 2020-07-12 |  | 2020-07-15 |  |  | 2020-07-27 |  |  |  | 2020-07-30 |  |  | 2020-08-06 |  |  |  | 2020-08-09 |  |  | 2020-08-24 |  |  |  | 2020-09-05 |  | 2020-09-08
PH1600291 | 126.2912 | 8.2852 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Sur | Bislig City | San Vicente | MIN | PH166803017 | 2490 | 45 | Three Legged Tubular Tower | CO65 | 107.558 | MIN-1600062 | Level 6 | phase3 | phase3 |  |  | Cluster M23 | Marrox | [7 empty] | 2020-04-05 |  | 2020-04-07 | [13 empty] | 2020-04-12 | [11 empty] | 2020-05-12 | [27 empty] | 2020-05-19 |  |  | 2020-06-18 |  | 2020-05-26 | [16 empty] | 2020-06-16 |  |  | 2020-06-25 | [6 empty] | 2020-07-09 |  |  |  | 2020-07-09 |  |  |  |  | 2020-06-02 |  | 2020-06-12 |  |  | 2020-06-16 |  | 2020-06-19 |  |  | 2020-07-03 |  |  |  | 2020-07-10 |  | 4GT-42-340C-2NPT |  |  | 2020-07-22 |  | 2020-06-30 | [6 empty] | 2020-07-30 | 2020-08-06 | [20 empty] | 2020-09-05 |  |  |  | 2020-09-08 | [8 empty] | 2020-07-15 |  | 2020-07-18 |  |  | 2020-07-30 |  |  |  | 2020-08-02 |  |  | 2020-08-09 |  |  |  | 2020-08-12 |  |  | 2020-08-27 |  |  |  | 2020-09-08 |  | 2020-09-11
PH1600293 | 125.7302 | 8.7293 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Sur | Bayugan City | Santa Irene | MIN | PH160301010 | 4818 | 40 | Three Legged Tubular Tower | CO64 | 32.6551 | MIN-1600063 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-04-08 |  | 2020-04-10 | [13 empty] | 2020-04-15 | [11 empty] | 2020-05-15 | [27 empty] | 2020-05-22 |  |  | 2020-06-21 |  | 2020-05-29 | [16 empty] | 2020-06-19 |  |  | 2020-06-28 | [6 empty] | 2020-07-12 |  |  |  | 2020-07-12 |  |  |  |  | 2020-06-05 |  | 2020-06-15 |  |  | 2020-06-19 |  | 2020-06-22 |  |  | 2020-07-06 |  |  |  | 2020-07-13 |  | JGT-36-340C-2NPT |  |  | 2020-07-25 |  | 2020-07-03 | [6 empty] | 2020-08-02 | 2020-08-09 | [20 empty] | 2020-09-08 |  |  |  | 2020-09-11 | [8 empty] | 2020-07-18 |  | 2020-07-21 |  |  | 2020-08-02 |  |  |  | 2020-08-05 |  |  | 2020-08-12 |  |  |  | 2020-08-15 |  |  | 2020-08-30 |  |  |  | 2020-09-11 |  | 2020-09-14
PH1600294 | 125.7141 | 8.6854 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Sur | Bayugan City | Gamao | MIN | PH160301019 | 5886 | 40 | Three Legged Tubular Tower | CO64 | 35.5588 | MIN-1600064 | Level 6 | phase3 | phase3 |  | DepEd_5126 | Cluster M21 | Marrox | [7 empty] | 2020-04-11 |  | 2020-04-13 | [13 empty] | 2020-04-18 | [11 empty] | 2020-05-18 | [27 empty] | 2020-05-25 |  |  | 2020-06-24 |  | 2020-06-01 | [16 empty] | 2020-06-22 |  |  | 2020-07-01 | [6 empty] | 2020-07-15 |  |  |  | 2020-07-15 |  |  |  |  | 2020-06-08 |  | 2020-06-18 |  |  | 2020-06-22 |  | 2020-06-25 |  |  | 2020-07-09 |  |  |  | 2020-07-16 |  | 4GT-42-340C-2NPT |  |  | 2020-07-28 |  | 2020-07-06 | [6 empty] | 2020-08-05 | 2020-08-12 | [20 empty] | 2020-09-11 |  |  |  | 2020-09-14 | [8 empty] | 2020-07-21 |  | 2020-07-24 |  |  | 2020-08-05 |  |  |  | 2020-08-08 |  |  | 2020-08-15 |  |  |  | 2020-08-18 |  |  | 2020-09-02 |  |  |  | 2020-09-14 |  | 2020-09-17
PH1600296 | 125.7743 | 8.753 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Sur | Bayugan City | Calaitan | MIN | PH160301023 | 3651 | 45 | Three Legged Tubular Tower | CO64 | 34.1525 | MIN-1600065 | Level 6 | phase3 | phase3 |  |  | Cluster M21 | Marrox | [7 empty] | 2020-04-14 |  | 2020-04-16 | [13 empty] | 2020-04-21 | [11 empty] | 2020-05-21 | [27 empty] | 2020-05-28 |  |  | 2020-06-27 |  | 2020-06-04 | [16 empty] | 2020-06-25 |  |  | 2020-07-04 | [6 empty] | 2020-07-18 |  |  |  | 2020-07-18 |  |  |  |  | 2020-06-11 |  | 2020-06-21 |  |  | 2020-06-25 |  | 2020-06-28 |  |  | 2020-07-12 |  |  |  | 2020-07-19 |  | 4GT-42-340C-2NPT |  |  | 2020-07-31 |  | 2020-07-09 | [6 empty] | 2020-08-08 | 2020-08-15 | [20 empty] | 2020-09-14 |  |  |  | 2020-09-17 | [8 empty] | 2020-07-24 |  | 2020-07-27 |  |  | 2020-08-08 |  |  |  | 2020-08-11 |  |  | 2020-08-18 |  |  |  | 2020-08-21 |  |  | 2020-09-05 |  |  |  | 2020-09-17 |  | 2020-09-20
PH1600300 | 125.5639 | 8.8644 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Amparo | MIN | PH160202010 | 1660 | 45 | Three Legged Tubular Tower | CO64 | 10.4212 | MIN-1600066 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-28 | 2020-01-21 | 2020-01-30 | 2020-01-22 | 2020-01-22 | 2020-02-03 | 2020-02-03 | 2020-01-22 | 2020-03-06 |  |  |  | 2020-03-06 |  |  |  | 2020-02-04 | 2020-03-06 |  |  |  | 2020-03-06 | 2020-01-22 | 2020-01-22 | 2020-02-03 | 2020-02-03 | 2020-01-22 |  | 2020-03-05 | [5 empty] | A |  |  |  | 125.5573 | 8.8641 | [16 empty] | 2020-03-12 |  |  | 2020-04-11 |  | 2020-03-19 | [11 empty] | 0933-8686128 |  |  |  |  | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 |  | 2020-04-05 |  |  | 2020-04-09 |  | 2020-04-12 |  |  | 2020-04-26 |  |  |  | 2020-05-03 |  | 4GT-42-340C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1600302 | 125.5463 | 8.9945 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Norte | Butuan City | Maug | MIN | PH160202017 | 4235 | 45 | Three Legged Tubular Tower | CO64 | 4.4236 | MIN-1600067 | Level 4 (220) | phase1_220_20% | phase1_630 | P1_630 |  | Cluster M21 | Marrox | PO2020010202PH_WLS | Batch 2 | JXD-2 |  |  |  | 2020-01-21 | 2020-01-28 | 2020-01-18 | 2020-01-30 | 2020-01-27 | 2020-01-27 |  |  | 2020-01-27 | 2020-01-28 |  |  |  | 2020-01-28 |  |  |  | 2020-02-04 |  | 2020-01-28 |  |  | 2020-01-28 | 2020-01-27 | 2020-01-27 |  |  | 2020-01-27 | 2020-02-13 | 2020-03-05 | [5 empty] | A | Remegio Buyan | Mabungahon Prk 1, Pagatpatan, Butuan City | Agusan del Norte | 125.5227 | 8.9854 | Greenfield |  |  | 15 years | P20,000 inclusive of VAT and withholding tax | quarterly | 144sqm | 3 months | 3 months | 4.5% increase on the 4th year | [6 empty] | 2020-03-12 | 2020-02-17 |  | 2020-04-11 |  | 2020-03-19 | [16 empty] | 2020-04-09 |  |  | 2020-04-18 | [6 empty] | 2020-05-02 |  |  |  | 2020-05-02 |  |  |  |  | 2020-03-26 | 2020-02-27 | 2020-04-05 | 2020-03-03 | 2020-03-03 | 2020-04-09 | 2020-03-03 | 2020-04-12 | 2020-03-05 | 2020-03-05 | 2020-04-26 | 2020-03-07 | 2020-03-07 | 2020-03-07 | 2020-05-03 | 2020-03-07 | 4GT-42-340C-2NPT |  |  | 2020-05-15 |  | 2020-04-23 | [6 empty] | 2020-05-23 | 2020-05-30 | [20 empty] | 2020-06-29 |  |  |  | 2020-07-02 | [8 empty] | 2020-05-08 |  | 2020-05-11 |  |  | 2020-05-23 |  |  |  | 2020-05-26 |  |  | 2020-06-02 |  |  |  | 2020-06-05 |  |  | 2020-06-20 |  |  |  | 2020-07-02 |  | 2020-07-05
PH1600304 | 126.2204 | 8.2379 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Agusan del Sur | Bunawan | Bunawan Brook | MIN | PH166803004 | 6040 | 45 | Three Legged Tubular Tower | CO65 | 99.2192 | MIN-1600068 | Level 6 | phase3 | phase3 |  |  | Cluster M23 | Marrox | [7 empty] | 2020-04-17 |  | 2020-04-19 | [13 empty] | 2020-04-24 | [11 empty] | 2020-05-24 | [27 empty] | 2020-05-31 |  |  | 2020-06-30 |  | 2020-06-07 | [16 empty] | 2020-06-28 |  |  | 2020-07-07 | [6 empty] | 2020-07-21 |  |  |  | 2020-07-21 |  |  |  |  | 2020-06-14 |  | 2020-06-24 |  |  | 2020-06-28 |  | 2020-07-01 |  |  | 2020-07-15 |  |  |  | 2020-07-22 |  | 4GT-42-340C-2NPT |  |  | 2020-08-03 |  | 2020-07-12 | [6 empty] | 2020-08-11 | 2020-08-18 | [20 empty] | 2020-09-17 |  |  |  | 2020-09-20 | [8 empty] | 2020-07-27 |  | 2020-07-30 |  |  | 2020-08-11 |  |  |  | 2020-08-14 |  |  | 2020-08-21 |  |  |  | 2020-08-24 |  |  | 2020-09-08 |  |  |  | 2020-09-20 |  | 2020-09-23
PH1600340 | 125.4928 | 9.7597 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Norte | Surigao City | Cagniog | MIN | PH166724026 | 10425 | 45 | Three Legged Tubular Tower | CO64 | 89.6129 | MIN-1600069 | Level 6 | phase3 | phase3 |  |  | Cluster M11 | Marrox | [7 empty] | 2020-04-20 |  | 2020-04-22 | [13 empty] | 2020-04-27 | [11 empty] | 2020-05-27 | [27 empty] | 2020-06-03 |  |  | 2020-07-03 |  | 2020-06-10 | [16 empty] | 2020-07-01 |  |  | 2020-07-10 | [6 empty] | 2020-07-24 |  |  |  | 2020-07-24 |  |  |  |  | 2020-06-17 |  | 2020-06-27 |  |  | 2020-07-01 |  | 2020-07-04 |  |  | 2020-07-18 |  |  |  | 2020-07-25 |  | 4GT-42-340C-2NPT |  |  | 2020-08-06 |  | 2020-07-15 | [6 empty] | 2020-08-14 | 2020-08-21 | [20 empty] | 2020-09-20 |  |  |  | 2020-09-23 | [8 empty] | 2020-07-30 |  | 2020-08-02 |  |  | 2020-08-14 |  |  |  | 2020-08-17 |  |  | 2020-08-24 |  |  |  | 2020-08-27 |  |  | 2020-09-11 |  |  |  | 2020-09-23 |  | 2020-09-26
PH1600342 | 125.5179 | 9.7588 | Rural | Greenfield | Greenfield | Y1 | L7 | Caraga (Region XIII) | Surigao Del Norte | Surigao City | Silop | MIN | PH166724014 | 5225 | 45 | Three Legged Tubular Tower | CO64 | 89.3955 | MIN-1600070 | Level 6 | phase3 | phase3 |  |  | Cluster M11 | Marrox | [7 empty] | 2020-04-23 |  | 2020-04-25 | [13 empty] | 2020-04-30 | [11 empty] | 2020-05-30 | [27 empty] | 2020-06-06 |  |  | 2020-07-06 |  | 2020-06-13 | [16 empty] | 2020-07-04 |  |  | 2020-07-13 | [6 empty] | 2020-07-27 |  |  |  | 2020-07-27 |  |  |  |  | 2020-06-20 |  | 2020-06-30 |  |  | 2020-07-04 |  | 2020-07-07 |  |  | 2020-07-21 |  |  |  | 2020-07-28 |  | JGT-36-340C-2NPT（340KPH/D） |  |  | 2020-08-09 |  | 2020-07-18 | [6 empty] | 2020-08-17 | 2020-08-24 | [20 empty] | 2020-09-23 |  |  |  | 2020-09-26 | [8 empty] | 2020-08-02 |  | 2020-08-05 |  |  | 2020-08-17 |  |  |  | 2020-08-20 |  |  | 2020-08-27 |  |  |  | 2020-08-30 |  |  | 2020-09-14 |  |  |  | 2020-09-26 |  | 2020-09-29
Formulas:
Submitted Plan = [Survey Done Plan]+2
Submitted Actual = MIN([Submitted Option A]:[Submitted Option D])
Approved Plan = [Submitted Plan]+5
BrgyClearance Plan = [MOC Approved Plan]+7
BrgyResolution Applied = [BrgyClearance Plan]+30
BrgyResolution Actual = [MOC Approved Plan]+14
Lease Package Plan = [BrgyResolution Actual]+21
Draft COL Plan = [BrgyResolution Actual]+30
COL Signed Plan = [Draft COL Plan]+14
Rental Paid Plan = [BrgyResolution Applied]+21
SBT/SI Done Plan = [MOC Approved Plan]+21
SBT/SI Report Plan = [SBT/SI Done Plan]+10
TSS Done Plan = [SBT/SI Report Plan]+4
TSSR Submitted Plan = [TSS Done Plan]+3
DDD Submitted Plan = [TSSR Submitted Plan]+14
DDD Approved Plan = [DDD Submitted Plan]+7
Tower Delivery on Site_Plan = [FSIC Applied]+7
ATO/CAAP Acquired = [ATO/CAAP Applied]+7
Sanitary Permit Secured = [ATO/CAAP Acquired]+30
BOM = [Sanitary Permit Secured]+3
FSIC Applied = [DDD Approved Plan]+5
SKOM Actual = [FSIC Applied]+3
Excavation Plan = [SKOM Actual]+12
Rebar Installation = [Excavation Plan]+3
Concrete Plan = [Rebar Installation]+7
Back Filling Actual = [Concrete Plan]+3
Electrical Grounding Plan = [Back Filling Actual]+15
Tower Erection Completed = [Electrical Grounding Plan]+12
Site Dev Works Completed (RFI) = [Electrical Grounding Plan]+15
Reviewed Actual = MIN([Reviewed Option A]:[Reviewed Option D])
Approved Actual = MIN([Approved Option A]:[Approved Option D])
MOC Signed Actual = MIN([MOC Signed Option A]:[MOC Signed Option D])
Note on GU4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: fka "Rebar Shattering Started"
Note on AA231: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA233: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA239: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AM241: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Done by JXD.
Note on BF241: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Done by JXD.
Note on AA243: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA246: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA247: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA248: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA250: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on BU251: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on actual TSSR
Note on BV251: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on actual TSSR
Note on AA252: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA253: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA254: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA255: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA257: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA264: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA271: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA276: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA287: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA295: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA296: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA300: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA302: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA303: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA304: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA305: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA306: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA315: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA333: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA334: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA341: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA345: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA348: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA349: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA350: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA351: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA352: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA363: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA367: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA375: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA384: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA400: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA406: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on BU459: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on actual TSSR
Note on BV459: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on actual TSSR
Note on BG463: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sent by JXD
Note on AA473: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on BU495: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on actual TSSR
Note on BV495: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on actual TSSR
Note on AA509: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on BU518: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on actual TSSR
Note on BV518: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on actual TSSR
Note on AA530: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld
Note on AA543: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previously awarded to Richworld